## TIDP_Sheet
TASK INFORMATION DELIVERY PLAN (TIDP)
CLIENT | Qiddiya | #VALUE!
PROJECT | Qiddiya Performing Arts Center (QPAC)
ORGANISATION | Nesma & Partners
DISCIPLINE | Electrical
APPROVER | BSBG
DATE CREATED
DATE LAST UPDATED
REVISION NUMBER | 00
DOCUMENT REFERENCE | QF01012-NES-C04518-TDP-ELE-00-000000-000001
This document shall be populated and kept up-to-date by the task team | [10 empty] | REFER TO THE FILE NAMING CONVENTION IN THE BIM EXECUTION PLAN | [10 empty] | DATA EXCHANGE #01 | [5 empty] | DATA EXCHANGE #02
[11 empty] | DOC REFERENCE GENERATOR | [10 empty] | STAGE: | CONSTRUCTION |  |  |  |  | STAGE: | HAND OVER
[22 empty] | PROGRAMME REF: | [5 empty] | PROGRAMME REF:
[5 empty] | EXCHANGE FORMATS | [5 empty] | FIELD 01 | FIELD 02 | FIELD 03 | FIELD 04 | FIELD 05 | FIELD 06 | FIELD 07 | FIELD 08 |  |  |  |  | LEVEL OF INFORMATION NEED | [5 empty] | LEVEL OF INFORMATION NEED
DOCUMENT NUMBER | DOCUMENT TITLE | EXTRACTED FROM MODEL | SCOPE AREA | AUTHORING SOFTWARE | EXCHANGE FORMAT | SCALE | DELIVERY MILESTONE | PACKAGE NAME | ACTIVITY ID | CLASSIFICATION CODE | PROJECT | ORIGINATOR | CONTRACT | DOCUMENT TYPE | DISCIPLINE | AREA/ZONE | VENUE/BUILDING | DRAWING TYPE | LEVEL | SEQUENCE NUMBER | CORPORATE DISCIPLINE | 01-AUTHOR | 01-GEOMETRICAL | 01-NON GEOMETRICAL | 01-DURATION (DAYS) | 01-PREDECESSOR | 01-EXCHANGE DATE | 02-AUTHOR | 02-GEOMETRICAL | 02-NON GEOMETRICAL | 02-DURATION (DAYS) | 02-PREDECESSOR | 02-EXCHANGE DATE
QF01012-NES-C04518-CAL-ELE-00-Z00000-000001 | B3 Supporting System Load Calculation |  | MEP Engineering | Revit | .rvt,.nwc,.ifc | AS INDICATED | 2026-04-15 | Power | QP.E.ME.MBL.GEN.1350 | FI_60_53 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-CAL-ELE-00-Z00000-000002 | BOH LIGHTING LUX CALCULATION REPORT | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2027-02-15 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELE-00-Z00000-000003 | BOH EMERGENCY LIGHTING LUX CALCULATION REPORT | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2027-02-15 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELE-00-Z00000-000004 | CENTRAL BATTERY SYSTEM SIZING CALCULATIONS | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2027-01-15 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELE-00-Z00000-000005 | CABLE CALCULATION - ETAP STUDY | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2027-02-15 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELE-00-Z00000-000006 | SEC MRMU ROOM LIGHTING LUX CALCULATION | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2027-01-15 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELP-00-Z00000-000001 | Calculation for Earthing and Lightning protection system | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2026-01-29 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELP | 00 | Z00000 | 0 | 00 | 001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELP-00-Z00000-000002 | Calculation for Lightning Protection Risk Assessment | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2026-07-27 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELP | 00 | Z00000 | 0 | 00 | 002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ICT-00-Z00000-000001 | FIBER OPTIC CABLE LOSS CALCULATION | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | MicrosoftWord | .dwg,.pdf | NTS | 2027-04-22 | ICT | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ICT | 00 | Z00000 | 0 | 00 | 001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-SEC-00-Z00000-000001 | CCTV COVERAGE AND STORAGE CALCULATION REPORT | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | MicrosoftWord | .dwg,.pdf | NTS | 2027-04-22 | SECURITY | QP.E.ME.CBR.GEN.1044 | FI_40_10 | QF01012 | NES | C04518 | CAL | SEC | 00 | Z00000 | 0 | 00 | 001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV REVIT MODEL |  | MEP Engineering | Revit | .rvt,.nwc,.ifc | AS INDICATED |  | AV REVIT 3D MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | AVL | 00 | Z00000 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS REVIT MODEL |  | MEP Engineering | Revit | .rvt,.nwc,.ifc | AS INDICATED |  | BMS REVIT 3D MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | BMS | 00 | Z00000 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | ELECTRICAL BUILDER WORK 2D REVIT MODEL |  | MEP Engineering | Revit | .rvt | AS INDICATED |  | ELECTRICAL REVIT 3D MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | EBW | 00 | Z00000 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | ELECTRICAL CONTAINMENT REVIT MODEL |  | MEP Engineering | Revit | .rvt,.nwc,.ifc | AS INDICATED |  | ELECTRICAL REVIT 3D MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ELC | 00 | Z00000 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-ELC-00-Z00000-0000002 | ELECTRICAL SUPPORT SYSTEM REVIT MODEL |  | MEP Engineering | Revit | .rvt,.nwc,.ifc | AS INDICATED |  | ELECTRICAL SUPPORT REVIT 3D MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ELC | 00 | Z00000 | 0 | 00 | 0002 | Electrical | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | ELECTRICAL POWER REVIT MODEL |  | MEP Engineering | Revit | .rvt,.nwc,.ifc | AS INDICATED |  | ELECTRICAL REVIT 3D MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ELE | 00 | Z00000 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | ICT REVIT MODEL |  | MEP Engineering | Revit | .rvt,.nwc,.ifc | AS INDICATED |  | ICT REVIT 3D MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ICT | 00 | Z00000 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | SECURITY REVIT MODEL |  | MEP Engineering | Revit | .rvt,.nwc,.ifc | AS INDICATED |  | SECURITY REVIT 3D MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | SEC | 00 | Z00000 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400
QF01012-NES-C04518-REP-BMS-00-Z00000-000001 | BMS - SEQUENCE OF OPERATION | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | MicrosoftWord | .pdf | NTS | 2027-04-08 | BMS | QP.E.ME.CBR.GEN.1044 | FI_90_72 | QF01012 | NES | C04518 | REP | BMS | 00 | Z00000 | 0 | 00 | 001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-REP-BMS-00-Z00000-000002 | BMS - DDC PANEL WIRING DIAGRAM DRAWINGS | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | MicrosoftWord | .pdf | NTS | 2027-04-08 | BMS | QP.E.ME.CBR.GEN.1044 | FI_90_72 | QF01012 | NES | C04518 | REP | BMS | 00 | Z00000 | 0 | 00 | 002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-REP-BMS-00-Z00000-000003 | BMS - DDC PANEL GA DRAWINGS | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | MicrosoftWord | .pdf | NTS | 2027-04-08 | BMS | QP.E.ME.CBR.GEN.1044 | FI_90_72 | QF01012 | NES | C04518 | REP | BMS | 00 | Z00000 | 0 | 00 | 003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-AUV-00-BLAD01-0000004 | AUDIO VISUAL SINGLE LINE DIAGRAM FOR BLADE-01 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | AUDIO VISUAL | QP.E.ME.BL1.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD01 | 0 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AUV-00-BLAD01-2000001 | AUDIO VISUAL SYSTEM PLAN - BLADE-01 (+870.5 M​, +876.2 5 M​ & +882 M​) - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.ME.BL1.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AUV-00-BLAD01-2000002 | AUDIO VISUAL SYSTEM PLAN - BLADE-01 (+887.75 M​, +893.5 M& +899.25 M) - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.ME.BL1.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AUV-00-BLAD01-2000003 | AUDIO VISUAL SYSTEM PLAN - BLADE-01 (+905 M, +910.75 M​​​ & +917.5 M​) - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.ME.BL1.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AUV-00-BLAD01-2000004 | AUDIO VISUAL SYSTEM PLAN - BLADE-01 (+922.25 M​, +928 M & +935.85 M) - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.ME.BL1.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AUV-00-BLAD01-2000005 | AUDIO VISUAL SYSTEM PLAN - BLADE-01 (+941.6M​, ROOF BLADE 1​ & +958.45​ M) - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.ME.BL1.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AUV-00-BLAD01-2000006 | AUDIO VISUAL SYSTEM PLAN - BLADE-01 (+962.2 M, +972.48M​​ & +989 M) - SHEET 6 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.ME.BL1.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AUV-00-BLAD02-0000004 | AUDIO VISUAL SINGLE LINE DIAGRAM FOR BLADE-02 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | AUDIO VISUAL | QP.E.ME.BL2.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD02 | 0 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AUV-00-BLAD02-2000001 | AUDIO VISUAL SYSTEM PLAN - BLADE-02 (+876.25 M​, +882.0​ M & +887.75 M​) - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | AUDIO VISUAL | QP.E.ME.BL2.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AUV-00-BLAD02-2000002 | AUDIO VISUAL SYSTEM PLAN - BLADE-02 (+893.5 M​, +899.25 M & +905 M) - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | AUDIO VISUAL | QP.E.ME.BL2.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AUV-00-BLAD02-2000003 | AUDIO VISUAL SYSTEM PLAN - BLADE-02 (+910.75M, +916.5M & +922.25M) - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | AUDIO VISUAL | QP.E.ME.BL2.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AUV-00-BLAD02-2000004 | AUDIO VISUAL SYSTEM PLAN - BLADE-02 (+928 M, +935.85 M & +941.60 M) - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | AUDIO VISUAL | QP.E.ME.BL2.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AUV-00-BLAD02-2000005 | AUDIO VISUAL SYSTEM PLAN - BLADE-02 (+948.28 M​ & +951.40 M ) - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | AUDIO VISUAL | QP.E.ME.BL2.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AUV-00-BLAD03-0000004 | AUDIO VISUAL SINGLE LINE DIAGRAM FOR BLADE-03 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | AUDIO VISUAL | QP.E.ME.BL3.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD03 | 0 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AUV-00-BLAD03-2000001 | AUDIO VISUAL SYSTEM PLAN - BLADE-03 (+847.5, +853.25, +859) - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | AUDIO VISUAL | QP.E.ME.BL3.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AUV-00-BLAD03-2000002 | AUDIO VISUAL SYSTEM PLAN - BLADE-03 (+867.62, +876.25, +882) - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | AUDIO VISUAL | QP.E.ME.BL3.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AUV-00-BLAD03-2000003 | AUDIO VISUAL SYSTEM PLAN - BLADE-03 (+887.75, +893.5, +899.25) - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | AUDIO VISUAL | QP.E.ME.BL3.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AUV-00-BLAD03-2000004 | AUDIO VISUAL SYSTEM PLAN - BLADE-03 (+905, +910.75, +916.5) - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | AUDIO VISUAL | QP.E.ME.BL3.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AUV-00-BLAD03-2000005 | AUDIO VISUAL SYSTEM PLAN - BLADE-03(+921 , +928 , +935.85 ) - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | AUDIO VISUAL | QP.E.ME.BL3.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AUV-00-BLAD04-0000004 | AUDIO VISUAL SINGLE LINE DIAGRAM FOR BLADE-04 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | AUDIO VISUAL | QP.E.ME.BL4.GEN.5930 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD04 | 0 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-AUV-00-BLAD04-2000001 | AUDIO VISUAL SYSTEM PLAN - BLADE-04 (+863.85, +870.5, +876.25) - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | AUDIO VISUAL | QP.E.ME.BL4.GEN.5930 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-AUV-00-BLAD04-2000002 | AUDIO VISUAL SYSTEM PLAN - BLADE-04 (+882, +887.75, +893.5) - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | AUDIO VISUAL | QP.E.ME.BL4.GEN.5930 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-AUV-00-BLAD04-2000003 | AUDIO VISUAL SYSTEM PLAN - BLADE-04 (+899.25, +910.75, +916.5) - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | AUDIO VISUAL | QP.E.ME.BL4.GEN.5930 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-AUV-00-BLAD04-2000004 | AUDIO VISUAL SYSTEM PLAN - BLADE-04 (+922.25, +928, +935.85) - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | AUDIO VISUAL | QP.E.ME.BL4.GEN.5930 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-AUV-00-BLAD04-2000005 | AUDIO VISUAL SYSTEM PLAN - BLADE-04 (+941.60, +947.35, +954) - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | AUDIO VISUAL | QP.E.ME.BL4.GEN.5930 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-AUV-00-BLAD04-2000006 | AUDIO VISUAL SYSTEM PLAN - BLADE-04 (+959, +968.30 ,+975.82) - SHEET 6 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | AUDIO VISUAL | QP.E.ME.BL4.GEN.5930 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-AUV-00-BLAD05-0000004 | AUDIO VISUAL SINGLE LINE DIAGRAM FOR BLADE-05 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | AUDIO VISUAL | QP.E.ME.BL5.GEN.2900 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD05 | 0 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-16
QF01012-NES-C04518-SDW-AUV-00-BLAD05-2000001 | AUDIO VISUAL SYSTEM PLAN - BLADE-05 (+894.5, +899.5, +905) - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | AUDIO VISUAL | QP.E.ME.BL5.GEN.2900 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-16
QF01012-NES-C04518-SDW-AUV-00-BLAD05-2000002 | AUDIO VISUAL SYSTEM PLAN - BLADE-05 (+910.75, +917.5, +922.25) - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | AUDIO VISUAL | QP.E.ME.BL5.GEN.2900 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-16
QF01012-NES-C04518-SDW-AUV-00-BLAD05-2000003 | AUDIO VISUAL SYSTEM PLAN - BLADE-05 (+928, +935.85, +941.60) - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | AUDIO VISUAL | QP.E.ME.BL5.GEN.2900 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-16
QF01012-NES-C04518-SDW-AUV-00-BLAD05-2000004 | AUDIO VISUAL SYSTEM PLAN - BLADE-05 (+948.10, +954, +957.35) - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | AUDIO VISUAL | QP.E.ME.BL5.GEN.2900 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-16
QF01012-NES-C04518-SDW-AUV-00-BLAD05-2000005 | AUDIO VISUAL SYSTEM PLAN - BLADE-05 (+969.30, +960.09) - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | AUDIO VISUAL | QP.E.ME.BL5.GEN.2900 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-16
QF01012-NES-C04518-SDW-AUV-00-CENT01-0ZZ0000 | AUDIO VISUAL SINGLE LINE DIAGRAM FOR MAIN BUILDING - OVER ALL | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 0 | ZZ | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-0ZZ0001 | AUDIO VISUAL SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-01 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 0 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-0ZZ0002 | AUDIO VISUAL SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-02 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 0 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-0ZZ0003 | AUDIO VISUAL SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-03 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 0 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-0ZZ0004 | AUDIO VISUAL SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-04 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 0 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2B10000 | AUDIO VISUAL SYSTEM OVERALL PLAN - B1 SERVICE & PARKING +900.5M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2026-12-10 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | B1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2B20000 | AUDIO VISUAL SYSTEM OVERALL PLAN - B2 SERVICE +893.5M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2026-12-03 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | B2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2B30000 | AUDIO VISUAL SYSTEM OVERALL PLAN - B3 PROMENADE +887.750M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | B3 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2L10000 | AUDIO VISUAL SYSTEM OVERALL PLAN - L1- LOBBY LEVEL +905M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2026-12-17 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | L1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2L20000 | AUDIO VISUAL SYSTEM OVERALL PLAN - L2- THEATRE STALLS +913M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-01-07 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | L2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2L30000 | AUDIO VISUAL SYSTEM OVERALL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-01-14 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | L3 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2L40000 | AUDIO VISUAL SYSTEM OVERALL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-01-21 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | L4 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2L50000 | AUDIO VISUAL SYSTEM OVERALL PLAN - L5- SECOND CIRCLE & LOFT +928M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-01-28 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | L5 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2L60000 | AUDIO VISUAL SYSTEM OVERALL PLAN - L6- SKY GARDEN +935.85M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-02-11 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | L6 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2L80001 | AUDIO VISUAL SYSTEM OVERALL PLAN - L8 ROYAL MAJLIS +948.28M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2M10000 | AUDIO VISUAL SYSTEM OVERALL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2026-12-24 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | M1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2M20000 | AUDIO VISUAL SYSTEM OVERALL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-02-04 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | M2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-CENT01-2RL0001 | AUDIO VISUAL SYSTEM OVERALL PLAN - Roof & Above | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-00-PARK01-2B10000 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B1 PARKING +900.5M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-02-25 | AUDIO VISUAL | QP.E.ME.PAR.GEN.1319 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | PARK01 | 2 | B1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-AUV-00-Z00000-0ZZ0001 | AUDIO VISUAL SINGLE LINE DIAGRAM FOR SITE | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 0 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-00-Z00000-0ZZ0101 | AUDIO VISUAL INSTALLATION DETAILS - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 0 | ZZ | 0101 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-00-Z00000-0ZZ0102 | AUDIO VISUAL INSTALLATION DETAILS - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 0 | ZZ | 0102 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-00-Z00000-0ZZ0103 | AUDIO VISUAL INSTALLATION DETAILS - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 0 | ZZ | 0103 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-00-Z00000-0ZZ0104 | AUDIO VISUAL INSTALLATION DETAILS - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 0 | ZZ | 0104 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-00-Z00000-0ZZ0105 | AUDIO VISUAL INSTALLATION DETAILS - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 0 | ZZ | 0105 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-00-Z00000-2ZZ0000 | AUDIO VISUAL OVERALL SITE PLAN | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:500 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 2 | ZZ | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-01-CENT01-2B10001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 01 - (1 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-01-CENT01-2B20001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 01 - (1 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-01-CENT01-2B30001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 01 - (1 OF 4) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-01-CENT01-2L10001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | CENT01 | 2 | L1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-01-CENT01-2L20001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-01-CENT01-2L30001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-01-CENT01-2L40001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-01-CENT01-2L50001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-01-CENT01-2L60001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-01-CENT01-2M10001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-01-CENT01-2M20001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-01-PARK01-2B10001 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 01 - (1 OF 3) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | AUDIO VISUAL | QP.E.ME.PAR.GEN.1319 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-AUV-01-Z00000-2ZZ0001 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 01 - (1 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 01 | Z00000 | 2 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-02-CENT01-2B10002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 02 - (2 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-02-CENT01-2B20002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 02 - (2 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-02-CENT01-2B30002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 02 - (2 OF 4) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-02-CENT01-2L10002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-02-CENT01-2L20002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-02-CENT01-2L30002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-02-CENT01-2L40002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-02-CENT01-2L50002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-02-CENT01-2L60002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-02-CENT01-2M10002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-02-CENT01-2M20002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-02-PARK01-2B10002 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 02 - (2 OF 3) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | AUDIO VISUAL | QP.E.ME.PAR.GEN.1319 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-AUV-02-Z00000-2ZZ0002 | AUDIO VISUALPARTIAL SITE PLAN - SHEET 02 - (2 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 02 | Z00000 | 2 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-03-CENT01-2L20003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 03 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-03-CENT01-2L30003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 03 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-03-CENT01-2L40003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 03 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-03-CENT01-2L50003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 03 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-03-CENT01-2L60003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 03 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-03-CENT01-2M10003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 03 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-03-CENT01-2M20003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 03 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-03-PARK01-2B10003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 03 - (3 OF 3) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | AUDIO VISUAL | QP.E.ME.PAR.GEN.1319 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 03 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-AUV-03-Z00000-2ZZ0003 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 03 - (3 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 03 | Z00000 | 2 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-04-CENT01-2B10003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 04 - (3 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 04 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-04-CENT01-2B20003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 04 - (3 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 04 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-04-CENT01-2L10003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 04 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 04 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-04-CENT01-2L20004 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 04 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-04-CENT01-2L30004 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 04 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-04-CENT01-2L40004 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 04 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-04-CENT01-2L50004 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 04 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-04-CENT01-2L60004 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 04 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-04-CENT01-2M10004 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 04 | CENT01 | 2 | M1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-04-CENT01-2M20004 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 04 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-04-Z00000-2ZZ0004 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 04 - (4 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 04 | Z00000 | 2 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-05-CENT01-2B10004 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 05 - (4 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | CENT01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-05-CENT01-2B20004 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 05 - (4 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-05-CENT01-2B30003 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 05 - (3 OF 4) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-05-CENT01-2L10004 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 05 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-05-CENT01-2L20005 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-05-CENT01-2L30005 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-05-CENT01-2L40005 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-05-CENT01-2L50005 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-05-CENT01-2L60005 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-05-CENT01-2M10005 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-05-CENT01-2M20005 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-05-Z00000-2ZZ0005 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 05 - (5 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 05 | Z00000 | 2 | ZZ | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-06-CENT01-2L20006 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 06 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-06-CENT01-2L30006 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 06 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-06-CENT01-2L40006 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 06 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-06-CENT01-2L50006 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 06 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-06-CENT01-2L60006 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 06 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-06-CENT01-2M10006 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 06 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-06-CENT01-2M20006 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 06 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-06-Z00000-2ZZ0006 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 06 - (6 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 06 | Z00000 | 2 | ZZ | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-07-CENT01-2B10005 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 07 - (5 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 07 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-07-Z00000-2ZZ0007 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 07 - (7 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 07 | Z00000 | 2 | ZZ | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-08-CENT01-2B10006 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 08 - (6 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 08 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-08-CENT01-2B20005 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 08 - (5 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 08 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-08-Z00000-2ZZ0008 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 08 - (8 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 08 | Z00000 | 2 | ZZ | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-09-CENT01-2B10007 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 09 - (7 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 09 | CENT01 | 2 | B1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-09-CENT01-2B20006 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 09 - (6 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 09 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-09-Z00000-2ZZ0009 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 09 - (9 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 09 | Z00000 | 2 | ZZ | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-10-Z00000-2ZZ0010 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 10 - (10 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 10 | Z00000 | 2 | ZZ | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-11-CENT01-2B20007 | AUDIO VISUAL SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 11 - (7 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 11 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-11-CENT01-2B30004 | AUDIO VISUALSYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 11 - (4 OF 4) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 11 | CENT01 | 2 | B3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-11-CENT01-2L10005 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 11 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 11 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-11-Z00000-2ZZ0011 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 11 - (11 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 11 | Z00000 | 2 | ZZ | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-12-CENT01-2L10006 | AUDIO VISUAL SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 12 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | AUDIO VISUAL | QP.E.ME.MBL.GEN.7300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 12 | CENT01 | 2 | L1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AUV-12-Z00000-2ZZ0012 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 12 - (12 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 12 | Z00000 | 2 | ZZ | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-13-Z00000-2ZZ0013 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 16 - (13 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 13 | Z00000 | 2 | ZZ | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-14-Z00000-2ZZ0014 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 17 - (14 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 14 | Z00000 | 2 | ZZ | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-15-Z00000-2ZZ0015 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 18 - (15 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 15 | Z00000 | 2 | ZZ | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-16-Z00000-2ZZ0016 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 19 - (16 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 16 | Z00000 | 2 | ZZ | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-17-Z00000-2ZZ0017 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 20 - (17 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 17 | Z00000 | 2 | ZZ | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-18-Z00000-2ZZ0018 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 21 - (18 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 18 | Z00000 | 2 | ZZ | 0018 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-19-Z00000-2ZZ0019 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 22 - (19 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 19 | Z00000 | 2 | ZZ | 0019 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-20-Z00000-2ZZ0020 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 23 - (20 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 20 | Z00000 | 2 | ZZ | 0020 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-21-Z00000-2ZZ0021 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 24 - (21 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 21 | Z00000 | 2 | ZZ | 0021 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-22-Z00000-2ZZ0022 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 25 - (22 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 22 | Z00000 | 2 | ZZ | 0022 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-23-Z00000-2ZZ0023 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 26 - (23 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 23 | Z00000 | 2 | ZZ | 0023 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-24-Z00000-2ZZ0024 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 27 - (24 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 24 | Z00000 | 2 | ZZ | 0024 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-25-Z00000-2ZZ0025 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 28 - (25 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 25 | Z00000 | 2 | ZZ | 0025 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-26-Z00000-2ZZ0026 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 29 - (26 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 26 | Z00000 | 2 | ZZ | 0026 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-27-Z00000-2ZZ0027 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 30 - (27 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 27 | Z00000 | 2 | ZZ | 0027 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-28-Z00000-2ZZ0028 | AUDIO VISUAL PARTIAL SITE PLAN - SHEET 31 - (28 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 28 | Z00000 | 2 | ZZ | 0028 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-BLAD01-0000005 | BACKGROUND MUSIC SINGLE LINE DIAGRAM FOR BLADE-01 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | BACKGROUND MUSIC | QP.E.ME.BL1.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD01 | 0 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AVL-00-BLAD01-2000001 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-01 (+870.5 M​, +876.2 5 M​ & +882 M​) - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | BACKGROUND MUSIC | QP.E.ME.BL1.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AVL-00-BLAD01-2000002 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-01 (+887.75 M​, +893.5 M& +899.25 M) - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | BACKGROUND MUSIC | QP.E.ME.BL1.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AVL-00-BLAD01-2000003 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-01 (+905 M, +910.75 M​​​ & +917.5 M​) - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | BACKGROUND MUSIC | QP.E.ME.BL1.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AVL-00-BLAD01-2000004 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-01 (+922.25 M​, +928 M & +935.85 M) - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | BACKGROUND MUSIC | QP.E.ME.BL1.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AVL-00-BLAD01-2000005 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-01 (+941.6M​, ROOF BLADE 1​ & +958.45​ M) - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | BACKGROUND MUSIC | QP.E.ME.BL1.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AVL-00-BLAD01-2000006 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-01 (+962.2 M, +972.48M​​ & +989 M) - SHEET 6 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | BACKGROUND MUSIC | QP.E.ME.BL1.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-AVL-00-BLAD02-0000005 | BACKGROUND MUSIC SINGLE LINE DIAGRAM FOR BLADE-02 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | BACKGROUND MUSIC | QP.E.ME.BL2.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD02 | 0 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AVL-00-BLAD02-2000001 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-02 (+876.25 M​, +882.0​ M & +887.75 M​) - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.ME.BL2.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AVL-00-BLAD02-2000002 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-02 (+893.5 M​, +899.25 M & +905 M) - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.ME.BL2.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AVL-00-BLAD02-2000003 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-02 (+910.75M, +916.5M & +922.25M) - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.ME.BL2.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AVL-00-BLAD02-2000004 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-02 (+928 M, +935.85 M & +941.60 M) - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.ME.BL2.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AVL-00-BLAD02-2000005 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-02 (+948.28 M​ & +951.40 M ) - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.ME.BL2.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-15
QF01012-NES-C04518-SDW-AVL-00-BLAD03-0000005 | BACKGROUND MUSIC SINGLE LINE DIAGRAM FOR BLADE-03 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | BACKGROUND MUSIC | QP.E.ME.BL3.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD03 | 0 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AVL-00-BLAD03-2000001 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-03 (+847.5, +853.25, +859) - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | BACKGROUND MUSIC | QP.E.ME.BL3.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AVL-00-BLAD03-2000002 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-03 (+867.62, +876.25, +882) - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | BACKGROUND MUSIC | QP.E.ME.BL3.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AVL-00-BLAD03-2000003 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-03 (+887.75, +893.5, +899.25) - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | BACKGROUND MUSIC | QP.E.ME.BL3.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AVL-00-BLAD03-2000004 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-03 (+905, +910.75, +916.5) - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | BACKGROUND MUSIC | QP.E.ME.BL3.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AVL-00-BLAD03-2000005 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-03(+921 , +928 , +935.85 ) - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | BACKGROUND MUSIC | QP.E.ME.BL3.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-27
QF01012-NES-C04518-SDW-AVL-00-BLAD04-0000005 | BACKGROUND MUSIC SINGLE LINE DIAGRAM FOR BLADE-04 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | BACKGROUND MUSIC | QP.E.ME.BL4.GEN.5950 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD04 | 0 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-28
QF01012-NES-C04518-SDW-AVL-00-BLAD04-2000001 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-04 (+863.85, +870.5, +876.25) - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | BACKGROUND MUSIC | QP.E.ME.BL4.GEN.5950 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-28
QF01012-NES-C04518-SDW-AVL-00-BLAD04-2000002 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-04 (+882, +887.75, +893.5) - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | BACKGROUND MUSIC | QP.E.ME.BL4.GEN.5950 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-28
QF01012-NES-C04518-SDW-AVL-00-BLAD04-2000003 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-04 (+899.25, +910.75, +916.5) - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | BACKGROUND MUSIC | QP.E.ME.BL4.GEN.5950 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-28
QF01012-NES-C04518-SDW-AVL-00-BLAD04-2000004 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-04 (+922.25, +928, +935.85) - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | BACKGROUND MUSIC | QP.E.ME.BL4.GEN.5950 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-28
QF01012-NES-C04518-SDW-AVL-00-BLAD04-2000005 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-04 (+941.60, +947.35, +954) - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | BACKGROUND MUSIC | QP.E.ME.BL4.GEN.5950 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-28
QF01012-NES-C04518-SDW-AVL-00-BLAD04-2000006 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-04 (+959, +968.30 ,+975.82) - SHEET 6 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | BACKGROUND MUSIC | QP.E.ME.BL4.GEN.5950 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-28
QF01012-NES-C04518-SDW-AVL-00-BLAD05-0000005 | BACKGROUND MUSIC SINGLE LINE DIAGRAM FOR BLADE-05 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | BACKGROUND MUSIC | QP.E.ME.BL5.GEN.2920 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD05 | 0 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-AVL-00-BLAD05-2000001 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-05 (+894.5, +899.5, +905) - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | BACKGROUND MUSIC | QP.E.ME.BL5.GEN.2920 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-AVL-00-BLAD05-2000002 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-05 (+910.75, +917.5, +922.25) - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | BACKGROUND MUSIC | QP.E.ME.BL5.GEN.2920 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-AVL-00-BLAD05-2000003 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-05 (+928, +935.85, +941.60) - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | BACKGROUND MUSIC | QP.E.ME.BL5.GEN.2920 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-AVL-00-BLAD05-2000004 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-05 (+948.10, +954, +957.35) - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | BACKGROUND MUSIC | QP.E.ME.BL5.GEN.2920 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-AVL-00-BLAD05-2000005 | BACKGROUND MUSIC SYSTEM PLAN - BLADE-05 (+969.30, +960.09) - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | BACKGROUND MUSIC | QP.E.ME.BL5.GEN.2920 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-AVL-00-CENT01-0ZZ0000 | BACKGROUND MUSIC SINGLE LINE DIAGRAM FOR MAIN BUILDING - OVER ALL | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 0 | ZZ | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-0ZZ0001 | BACKGROUND MUSIC SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-01 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 0 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-0ZZ0002 | BACKGROUND MUSIC SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-02 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 0 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-0ZZ0003 | BACKGROUND MUSIC SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-03 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 0 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-0ZZ0004 | BACKGROUND MUSIC SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-04 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 0 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-0ZZ0007 | DIGITAL SIGNAGE SCHEMATIC DIAGRAM - OVERALL | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-29 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 0 | ZZ | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-AVL-00-CENT01-2B10000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - B1 SERVICE & PARKING +900.5M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2026-12-10 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | B1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2B20000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - B2 SERVICE +893.5M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2026-12-03 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | B2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2B30000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - B3 PROMENADE +887.750M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | B3 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2L10000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - L1- LOBBY LEVEL +905M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2026-12-17 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | L1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2L20000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - L2- THEATRE STALLS +913M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-01-07 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | L2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2L30000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-01-14 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | L3 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2L40000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-01-21 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | L4 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2L50000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - L5- SECOND CIRCLE & LOFT +928M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-01-28 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | L5 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2L60000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - L6- SKY GARDEN +935.85M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-02-11 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | L6 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2L80000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - L8 ROYAL MAJLIS +948.28M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | L8 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2M10000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2026-12-24 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | M1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2M20000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-02-04 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | M2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-CENT01-2RL0000 | BACKGROUND MUSIC SYSTEM OVERALL PLAN - Roof & Above | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | CENT01 | 2 | RL | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-00-PARK01-2B10000 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B1 PARKING +900.5M | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:300 | 2027-02-25 | BACKGROUND MUSIC | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | PARK01 | 2 | B1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-AVL-00-Z00000-0ZZ0001 | BACKGROUND MUSIC SINGLE LINE DIAGRAM FOR SITE | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2027-04-22 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 0 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-Z00000-0ZZ0101 | BACKGROUND MUSIC INSTALLATION DETAILS - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 0 | ZZ | 0101 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-Z00000-0ZZ0102 | BACKGROUND MUSIC INSTALLATION DETAILS - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 0 | ZZ | 0102 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-Z00000-0ZZ0103 | BACKGROUND MUSIC INSTALLATION DETAILS - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 0 | ZZ | 0103 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-Z00000-0ZZ0104 | BACKGROUND MUSIC INSTALLATION DETAILS - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 0 | ZZ | 0104 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-Z00000-0ZZ0105 | BACKGROUND MUSIC INSTALLATION DETAILS - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 0 | ZZ | 0105 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ0000 | BACKGROUND MUSIC OVERALL SITE PLAN | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:500 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-01-CENT01-2B10001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 01 - (1 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-01-CENT01-2B20001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 01 - (1 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-01-CENT01-2B30001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 01 - (1 OF 4) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-01-CENT01-2L10001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | CENT01 | 2 | L1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-01-CENT01-2L20001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-01-CENT01-2L30001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-01-CENT01-2L40001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-01-CENT01-2L50001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-01-CENT01-2L60001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-01-CENT01-2M10001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-01-CENT01-2M20001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-01-PARK01-2B10001 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 01 - (1 OF 3) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | BACKGROUND MUSIC | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-AVL-01-Z00000-2ZZ0001 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 01 - (1 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 01 | Z00000 | 2 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-02-CENT01-2B10002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 02 - (2 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-02-CENT01-2B20002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 02 - (2 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-02-CENT01-2B30002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 02 - (2 OF 4) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-02-CENT01-2L10002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-02-CENT01-2L20002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-02-CENT01-2L30002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-02-CENT01-2L40002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-02-CENT01-2L50002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-02-CENT01-2L60002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-02-CENT01-2M10002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-02-CENT01-2M20002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-02-PARK01-2B10002 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 02 - (2 OF 3) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | BACKGROUND MUSIC | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-AVL-02-Z00000-2ZZ0002 | BACKGROUND MUSICPARTIAL SITE PLAN - SHEET 02 - (2 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 02 | Z00000 | 2 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-03-CENT01-2L20003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 03 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-03-CENT01-2L30003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 03 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-03-CENT01-2L40003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 03 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-03-CENT01-2L50003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 03 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-03-CENT01-2L60003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 03 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-03-CENT01-2M10003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 03 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-03-CENT01-2M20003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 03 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-03-PARK01-2B10003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 03 - (3 OF 3) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | BACKGROUND MUSIC | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 03 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-AVL-03-Z00000-2ZZ0003 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 03 - (3 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 03 | Z00000 | 2 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-04-CENT01-2B10003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 04 - (3 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 04 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-04-CENT01-2B20003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 04 - (3 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 04 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-04-CENT01-2L10003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 04 - (3 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 04 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-04-CENT01-2L20004 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 04 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-04-CENT01-2L30004 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 04 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-04-CENT01-2L40004 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 04 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-04-CENT01-2L50004 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 04 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-04-CENT01-2L60004 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 04 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-04-CENT01-2M10004 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 04 | CENT01 | 2 | M1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-04-CENT01-2M20004 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 04 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-04-Z00000-2ZZ0004 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 04 - (4 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 04 | Z00000 | 2 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-05-CENT01-2B10004 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 05 - (4 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | CENT01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-05-CENT01-2B20004 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 05 - (4 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-05-CENT01-2B30003 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 05 - (3 OF 4) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-05-CENT01-2L10004 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 05 - (4 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-05-CENT01-2L20005 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-05-CENT01-2L30005 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-05-CENT01-2L40005 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-05-CENT01-2L50005 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-05-CENT01-2L60005 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-05-CENT01-2M10005 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-05-CENT01-2M20005 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-05-Z00000-2ZZ0005 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 05 - (5 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 05 | Z00000 | 2 | ZZ | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-06-CENT01-2L20006 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 06 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-06-CENT01-2L30006 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 06 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-06-CENT01-2L40006 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 06 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-06-CENT01-2L50006 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 06 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-06-CENT01-2L60006 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 06 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-06-CENT01-2M10006 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 06 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-06-CENT01-2M20006 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 06 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-06-Z00000-2ZZ0006 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 06 - (6 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 06 | Z00000 | 2 | ZZ | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-07-CENT01-2B10005 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 07 - (5 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 07 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-07-Z00000-2ZZ0007 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 07 - (7 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 07 | Z00000 | 2 | ZZ | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-08-CENT01-2B10006 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 08 - (6 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 08 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-08-CENT01-2B20005 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 08 - (5 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 08 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-08-Z00000-2ZZ0008 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 08 - (8 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 08 | Z00000 | 2 | ZZ | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-09-CENT01-2B10007 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 09 - (7 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 09 | CENT01 | 2 | B1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-09-CENT01-2B20006 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 09 - (6 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 09 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-09-Z00000-2ZZ0009 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 09 - (9 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 09 | Z00000 | 2 | ZZ | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-10-Z00000-2ZZ0010 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 10 - (10 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 10 | Z00000 | 2 | ZZ | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-11-CENT01-2B20007 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 11 - (7 OF 7) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 11 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-11-CENT01-2B30004 | BACKGROUND MUSICSYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 11 - (4 OF 4) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 11 | CENT01 | 2 | B3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-11-CENT01-2L10005 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 11 - (5 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 11 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-11-Z00000-2ZZ0011 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 11 - (11 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 11 | Z00000 | 2 | ZZ | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-12-CENT01-2L10006 | BACKGROUND MUSIC SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 12 - (6 OF 6) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | BACKGROUND MUSIC | QP.E.ME.MBL.GEN.7320 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 12 | CENT01 | 2 | L1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-AVL-12-Z00000-2ZZ0012 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 12 - (12 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 12 | Z00000 | 2 | ZZ | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-13-Z00000-2ZZ0013 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 16 - (13 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 13 | Z00000 | 2 | ZZ | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-14-Z00000-2ZZ0014 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 17 - (14 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 14 | Z00000 | 2 | ZZ | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-15-Z00000-2ZZ0015 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 18 - (15 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 15 | Z00000 | 2 | ZZ | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-16-Z00000-2ZZ0016 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 19 - (16 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 16 | Z00000 | 2 | ZZ | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-17-Z00000-2ZZ0017 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 20 - (17 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 17 | Z00000 | 2 | ZZ | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-18-Z00000-2ZZ0018 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 21 - (18 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 18 | Z00000 | 2 | ZZ | 0018 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-19-Z00000-2ZZ0019 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 22 - (19 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 19 | Z00000 | 2 | ZZ | 0019 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-20-Z00000-2ZZ0020 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 23 - (20 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 20 | Z00000 | 2 | ZZ | 0020 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-21-Z00000-2ZZ0021 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 24 - (21 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 21 | Z00000 | 2 | ZZ | 0021 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-22-Z00000-2ZZ0022 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 25 - (22 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 22 | Z00000 | 2 | ZZ | 0022 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-23-Z00000-2ZZ0023 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 26 - (23 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 23 | Z00000 | 2 | ZZ | 0023 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-24-Z00000-2ZZ0024 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 27 - (24 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 24 | Z00000 | 2 | ZZ | 0024 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-25-Z00000-2ZZ0025 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 28 - (25 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 25 | Z00000 | 2 | ZZ | 0025 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-26-Z00000-2ZZ0026 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 29 - (26 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 26 | Z00000 | 2 | ZZ | 0026 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-27-Z00000-2ZZ0027 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 30 - (27 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 27 | Z00000 | 2 | ZZ | 0027 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-28-Z00000-2ZZ0028 | BACKGROUND MUSIC PARTIAL SITE PLAN - SHEET 31 - (28 OF 28) | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 28 | Z00000 | 2 | ZZ | 0028 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-BMS-00-BLAD01-0000007 | BMS - BLADE-01 - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2027-01-07 | BMS | QP.E.ME.BL1.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD01 | 0 | 00 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-BMS-00-BLAD01-6000008 | BMS - BLADE-01 - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-08 | BMS | QP.E.ME.BL1.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD01 | 6 | 00 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-BMS-00-BLAD01-6000009 | BMS - BLADE-01 - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2027-01-07 | BMS | QP.E.ME.BL1.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD01 | 6 | 00 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-BMS-00-BLAD02-0000006 | BMS - BLADE-02 - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-31 | BMS | QP.E.ME.BL2.GEN.3320 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD02 | 0 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-23
QF01012-NES-C04518-SDW-BMS-00-BLAD02-6000007 | BMS - BLADE-02 - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-17 | BMS | QP.E.ME.BL2.GEN.3320 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD02 | 6 | 00 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-23
QF01012-NES-C04518-SDW-BMS-00-BLAD02-6000008 | BMS - BLADE-02 - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-31 | BMS | QP.E.ME.BL2.GEN.3320 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD02 | 6 | 00 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-23
QF01012-NES-C04518-SDW-BMS-00-BLAD03-0000006 | BMS - BLADE-03 - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-17 | BMS | QP.E.ME.BL3.GEN.3600 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD03 | 0 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-BMS-00-BLAD03-6000007 | BMS - BLADE-03 - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-24 | BMS | QP.E.ME.BL3.GEN.3600 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD03 | 6 | 00 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-BMS-00-BLAD03-6000008 | BMS - BLADE-03 - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-17 | BMS | QP.E.ME.BL3.GEN.3600 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD03 | 6 | 00 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-BMS-00-BLAD04-0000007 | BMS - BLADE-04 - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-19 | BMS | QP.E.ME.BL4.GEN.5970 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD04 | 0 | 00 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-BMS-00-BLAD04-6000008 | BMS - BLADE-04 - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-03 | BMS | QP.E.ME.BL4.GEN.5970 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD04 | 6 | 00 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-BMS-00-BLAD04-6000009 | BMS - BLADE-04 - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-19 | BMS | QP.E.ME.BL4.GEN.5970 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD04 | 6 | 00 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-BMS-00-BLAD05-0000006 | BMS - BLADE-05 - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-29 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD05 | 0 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-BLAD05-6000007 | BMS - BLADE-05 - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-13 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD05 | 6 | 00 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-BLAD05-6000008 | BMS - BLADE-05 - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-29 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD05 | 6 | 00 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-BLAD05-6000009 | BMS - BLADE-05 - FCU & DAMPERS SCHEDULES | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-13 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | BLAD05 | 6 | 00 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-CENT01-0B10009 | BMS - B1 SERVICE +900.5M - RISER DIAGRAM 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | B1 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0B10010 | BMS - B1 SERVICE +900.5M - RISER DIAGRAM 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | B1 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0B20009 | BMS - B2 SERVICE +893.5M - RISER DIAGRAM 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | B2 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0B20010 | BMS - B2 SERVICE +893.5M - RISER DIAGRAM 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | B2 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0B20011 | BMS - B2 SERVICE +893.5M - RISER DIAGRAM 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | B2 | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0B20012 | BMS - B2 SERVICE +893.5M - RISER DIAGRAM 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | B2 | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0B30006 | BMS - B3 PROMENADE +887.750M - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-07-16 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | B3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0L10008 | BMS - L1 LOBBY LEVEL +905M - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | L1 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0L20008 | BMS - L2 THEATRE STALLS +913M - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-22 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | L2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0L30008 | BMS - L3 STALLES MEZZ & AD THEATRE +917.5M - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | L3 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0L40008 | BMS - L4 FIRST CIRCLE & AD THEATER +921.0M - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-19 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | L4 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0L50008 | BMS - L5 SECOND CIRCLE & LOFT +928M - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | L5 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0L60008 | BMS - L6 SKY GARDEN +935.85M - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | L6 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0L80002 | BMS - L8 ROYAL MAJLIS +948.28M - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-03 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | L8 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0M10008 | BMS - M1 MEZ UPPER LOBBY +909M - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-01 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | M1 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-0M20008 | BMS - M2 MEZ LOFT MEP +931.1M - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 0 | M2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-2B10001 | BMS - B1 SERVICE +900.5M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-2B20001 | BMS - B2 SERVICE +893.5M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-2B30001 | BMS - B3 PROMENADE +887.750M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-07-16 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-2L10001 | BMS - L1 LOBBY LEVEL +905M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 2 | L1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-2L20001 | BMS - L2 THEATRE STALLS +913M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-2L30001 | BMS - L3 STALLES MEZZ & AD THEATRE +917.5M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-2L40001 | BMS - L4 FIRST CIRCLE & AD THEATER +921.0M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-2L50001 | BMS - L5 SECOND CIRCLE & LOFT +928M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-2L60001 | BMS - L6 SKY GARDEN +935.85M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-2M10001 | BMS - M1 MEZ UPPER LOBBY +909M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-10-01 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-2M20001 | BMS - M2 MEZ LOFT MEP +931.1M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B10011 | BMS - B1 SERVICE +900.5M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B1 | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B10012 | BMS - B1 SERVICE +900.5M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B1 | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B10013 | BMS - B1 SERVICE +900.5M - I/O POINT SCHEDULE 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B1 | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B10014 | BMS - B1 SERVICE +900.5M - I/O POINT SCHEDULE 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B1 | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B10015 | BMS - B1 SERVICE +900.5M - FCU IO LIST & SCHEDULE | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B1 | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B10016 | BMS - B1 SERVICE +900.5M - DAMPERS SCHEDULE | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B1 | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B10017 | BMS - B1 SERVICE +900.5M - FILLING RATIO | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B1 | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20013 | BMS - B2 SERVICE +893.5M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20014 | BMS - B2 SERVICE +893.5M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20015 | BMS - B2 SERVICE +893.5M - I/O POINT SCHEDULE 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20016 | BMS - B2 SERVICE +893.5M - I/O POINT SCHEDULE 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20017 | BMS - B2 SERVICE +893.5M - I/O POINT SCHEDULE 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20018 | BMS - B2 SERVICE +893.5M - I/O POINT SCHEDULE 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0018 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20019 | BMS - B2 SERVICE +893.5M - I/O POINT SCHEDULE 07 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0019 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20020 | BMS - B2 SERVICE +893.5M - I/O POINT SCHEDULE 08 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0020 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20021 | BMS - B2 SERVICE +893.5M - I/O POINT SCHEDULE 09 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0021 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20022 | BMS - B2 SERVICE +893.5M - I/O POINT SCHEDULE 10 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0022 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20023 | BMS - B2 SERVICE +893.5M - I/O POINT SCHEDULE 11 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0023 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20024 | BMS - B2 SERVICE +893.5M - DAMPERS SCHEDULE | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0024 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20025 | BMS - B2 SERVICE +893.5M - FCU SCHEDULE | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0025 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B20026 | BMS - B2 SERVICE +893.5M - FILLING RATIO | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B2 | 0026 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B30007 | BMS - B3 PROMENADE +887.750M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-07-16 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B3 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B30008 | BMS - B3 PROMENADE +887.750M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-07-16 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B3 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6B30009 | BMS - B3 PROMENADE +887.750M - SCHEDULES & FILLING RATIO | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-07-16 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | B3 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L10009 | BMS - L1 LOBBY LEVEL +905M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L1 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L10010 | BMS - L1 LOBBY LEVEL +905M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L1 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L20009 | BMS - L2 THEATRE STALLS +913M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-22 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L2 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L20010 | BMS - L2 THEATRE STALLS +913M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-22 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L2 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L30009 | BMS - L3 STALLES MEZZ & AD THEATRE +917.5M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L3 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L30010 | BMS - L3 STALLES MEZZ & AD THEATRE +917.5M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L3 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L40009 | BMS - L4 FIRST CIRCLE & AD THEATER +921.0M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-19 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L4 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L40010 | BMS - L4 FIRST CIRCLE & AD THEATER +921.0M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-19 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L4 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L40011 | BMS - L4 FIRST CIRCLE & AD THEATER +921.0M - SCHEDULES & FILLING RATIO | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-19 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L4 | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L50009 | BMS - L5 SECOND CIRCLE & LOFT +928M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L5 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L50010 | BMS - L5 SECOND CIRCLE & LOFT +928M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L5 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L60009 | BMS - L6 SKY GARDEN +935.85M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L6 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L60010 | BMS - L6 SKY GARDEN +935.85M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L6 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L80003 | BMS - L8 ROYAL MAJLIS +948.28M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-03 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L8 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6L80004 | BMS - L8 ROYAL MAJLIS +948.28M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-03 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | L8 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6M10009 | BMS - M1 MEZ UPPER LOBBY +909M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-01 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | M1 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6M10010 | BMS - M1 MEZ UPPER LOBBY +909M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-01 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | M1 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6M20009 | BMS - M2 MEZ LOFT MEP +931.1M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | M2 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-CENT01-6M20010 | BMS - M2 MEZ LOFT MEP +931.1M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | CENT01 | 6 | M2 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-00-PARK01-0B10005 | BMS - B1 PARKING +900.5M - RISER DIAGRAM | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-15 | BMS | QP.E.ME.PAR.GEN.1339 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | PARK01 | 0 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-BMS-00-PARK01-2B10001 | BMS - B1 PARKING +900.5M - OVERALL | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | BMS | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 00 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-BMS-00-PARK01-6B10006 | BMS - B1 PARKING +900.5M - I/O POINT SCHEDULE 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-15 | BMS | QP.E.ME.PAR.GEN.1339 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | PARK01 | 6 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-BMS-00-PARK01-6B10007 | BMS - B1 PARKING +900.5M - I/O POINT SCHEDULE 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-15 | BMS | QP.E.ME.PAR.GEN.1339 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | PARK01 | 6 | B1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0001 | BMS - CONTROL SCHEMATIC SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-10 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0002 | BMS - CONTROL SCHEMATIC SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-10 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0003 | BMS - CONTROL SCHEMATIC SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-10 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0004 | BMS - CONTROL SCHEMATIC SHEET 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-10 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0005 | BMS - CONTROL SCHEMATIC SHEET 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-10 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0006 | BMS - SYSTEM ARCHITECTURE SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-24 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0007 | BMS - SYSTEM ARCHITECTURE SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-24 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0008 | BMS - SYSTEM ARCHITECTURE SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-12-24 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0009 | BMS - INSTALLATION DETAILS SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2027-04-08 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0010 | BMS - INSTALLATION DETAILS SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2027-04-08 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0011 | BMS - INSTALLATION DETAILS SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2027-04-08 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0012 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-13 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0013 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-13 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0014 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-13 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0015 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-13 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0016 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-13 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0017 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-03 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0018 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 07 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-03 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0018 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0019 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 08 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-03 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0019 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0020 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 09 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-03 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0020 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0021 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 10 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-03 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0021 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0022 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 11 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-10 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0022 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0023 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 12 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-10 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0023 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0024 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 13 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-10 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0024 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0025 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 14 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-10 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0025 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0026 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 15 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-09-10 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0026 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0027 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 16 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-08 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0027 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0028 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 17 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-08 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0028 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0029 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 18 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-08 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0029 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0030 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 19 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-08 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0030 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0031 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 20 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-10-08 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0031 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-00-Z00000-0ZZ0032 | BMS - TYPICAL IO LIST, CONTROL SCHEMATIC AND SEQUENCE OF OPERATION SHEET 21 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | NTS | 2026-08-13 | BMS | QP.E.ME.BL5.GEN.2940 | FI_90_75 | QF01012 | NES | C04518 | SDW | BMS | 00 | Z00000 | 0 | ZZ | 0032 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-01-BLAD01-2000001 | BMS - BLADE-01 (+870.5, +876.25, +882) - SHEET 01 OF 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | BMS | QP.E.ME.BL1.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-BMS-01-BLAD02-2000001 | BMS - BLADE-02 (+876.25, +882, +887.75) - SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.BL2.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-23
QF01012-NES-C04518-SDW-BMS-01-BLAD03-2000001 | BMS - BLADE-03 (+847.5, +853.25, +859) - SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BMS | QP.E.ME.BL3.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-BMS-01-BLAD04-2000001 | BMS - BLADE-04 (+863.85, +870.5, +876.25) - SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | BMS | QP.E.ME.BL4.GEN.5970 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-BMS-01-BLAD05-2000001 | BMS - BLADE-05 (+894.5, +899.5, +905) - SHEET 01 OF 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | BMS | QP.E.ME.BL5.GEN.2940 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-01-CENT01-2B10002 | BMS - B1 SERVICE +900.5M - SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-01-CENT01-2B20002 | BMS - B2 SERVICE +893.5M - SHEET 01 (1 OF 7) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-01-CENT01-2B30002 | BMS - B3 PROMENADE +887.750M - SHEET 01 (1 OF 2) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-01-CENT01-2L10002 | BMS - L1 LOBBY LEVEL +905M - SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-01-CENT01-2L20002 | BMS - L2 THEATRE STALLS +913M - SHEET 01 (1 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-01-CENT01-2L30002 | BMS - L3 STALLES MEZZ & AD THEATRE +917.5M - SHEET 01 (1 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-01-CENT01-2L40002 | BMS - L4 FIRST CIRCLE & AD THEATER +921.0M - SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-01-CENT01-2L50002 | BMS - L5 SECOND CIRCLE & LOFT +928M - SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-01-CENT01-2L60002 | BMS - L6 SKY GARDEN +935.85M - SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-01-CENT01-2M10002 | BMS - M1 MEZ UPPER LOBBY +909M - SHEET 01 (01 OF 04) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-01-CENT01-2M20002 | BMS - M2 MEZ LOFT MEP +931.1M - SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-01-PARK01-2B10002 | BMS - B1 PARKING +900.5M - SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | BMS | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 01 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-BMS-02-BLAD01-2000002 | BMS - BLADE-01 (+887.75, +893.5, +899.25) - SHEET 02 OF 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | BMS | QP.E.ME.BL1.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-BMS-02-BLAD02-2000002 | BMS - BLADE-02 (+893.5, +899.25, +905) - SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.BL2.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-23
QF01012-NES-C04518-SDW-BMS-02-BLAD03-2000002 | BMS - BLADE-03 (+867.62, +876.25, +882) - SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BMS | QP.E.ME.BL3.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-BMS-02-BLAD04-2000002 | BMS - BLADE-04 (+882, +887.75, +893.5) - SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | BMS | QP.E.ME.BL4.GEN.5970 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-BMS-02-BLAD05-2000002 | BMS - BLADE-05 (+910.75, +917.5, +922.25) - SHEET 02 OF 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | BMS | QP.E.ME.BL5.GEN.2940 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-02-CENT01-2B10003 | BMS - B1 SERVICE +900.5M - SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-02-CENT01-2B20003 | BMS - B2 SERVICE +893.5M - SHEET 02 (2 OF 7) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-02-CENT01-2B30003 | BMS - B3 PROMENADE +887.750M - SHEET 02 (2 OF 2) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-02-CENT01-2L10003 | BMS - L1 LOBBY LEVEL +905M - SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-02-CENT01-2L20003 | BMS - L2 THEATRE STALLS +913M - SHEET 02 (2 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-02-CENT01-2L30003 | BMS - L3 STALLES MEZZ & AD THEATRE +917.5M - SHEET 02 (2 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-02-CENT01-2L40003 | BMS - L4 FIRST CIRCLE & AD THEATER +921.0M - SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-02-CENT01-2L50003 | BMS - L5 SECOND CIRCLE & LOFT +928M - SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-02-CENT01-2L60003 | BMS - L6 SKY GARDEN +935.85M - SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-02-CENT01-2M10003 | BMS - M1 MEZ UPPER LOBBY +909M - SHEET 02 (02 OF 04) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-02-CENT01-2M20003 | BMS - M2 MEZ LOFT MEP +931.1M - SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-02-PARK01-2B10003 | BMS - B1 PARKING +900.5M - SHEET 02 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | BMS | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 02 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-BMS-03-BLAD01-2000003 | BMS - BLADE-01 (+905, +910.75, +917.5) - SHEET 03 OF 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | BMS | QP.E.ME.BL1.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-BMS-03-BLAD02-2000003 | BMS - BLADE-02 (+910.75, +916.5, +922.25) - SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.BL2.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-23
QF01012-NES-C04518-SDW-BMS-03-BLAD03-2000003 | BMS - BLADE-03 (+887.75, +893.5, +899.25) - SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BMS | QP.E.ME.BL3.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-BMS-03-BLAD04-2000003 | BMS - BLADE-04 (+899.25, +910.75, +916.5) - SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | BMS | QP.E.ME.BL4.GEN.5970 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-BMS-03-BLAD05-2000003 | BMS - BLADE-05 (+928, +935.85, +941.60) - SHEET 03 OF 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | BMS | QP.E.ME.BL5.GEN.2940 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-03-CENT01-2L20004 | BMS - L2 THEATRE STALLS +913M - SHEET 03 (3 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-03-CENT01-2L30004 | BMS - L3 STALLES MEZZ & AD THEATRE +917.5M - SHEET 03 (3 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-03-CENT01-2L40004 | BMS - L4 FIRST CIRCLE & AD THEATER +921.0M - SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-03-CENT01-2L50004 | BMS - L5 SECOND CIRCLE & LOFT +928M - SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-03-CENT01-2L60004 | BMS - L6 SKY GARDEN +935.85M - SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-03-CENT01-2M20004 | BMS - M2 MEZ LOFT MEP +931.1M - SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-03-PARK01-2B10004 | BMS - B1 PARKING +900.5M - SHEET 03 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | BMS | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 03 | PARK01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-BMS-04-BLAD01-2000004 | BMS - BLADE-01 (+922.25, +928, +935.85) - SHEET 04 OF 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | BMS | QP.E.ME.BL1.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-BMS-04-BLAD02-2000004 | BMS - BLADE-02 (+928, +935.85, +941.6) - SHEET 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | BMS | QP.E.ME.BL2.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-23
QF01012-NES-C04518-SDW-BMS-04-BLAD03-2000004 | BMS - BLADE-03 (+905, +910.75, +916.5) - SHEET 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | BMS | QP.E.ME.BL3.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-BMS-04-BLAD04-2000004 | BMS - BLADE-04 (+922.25, +928, +935.85) - SHEET 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | BMS | QP.E.ME.BL4.GEN.5970 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-BMS-04-BLAD05-2000004 | BMS - BLADE-05 (+948.10, +954, +957.35) - SHEET 04 OF 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | BMS | QP.E.ME.BL5.GEN.2940 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-04-CENT01-2B10004 | BMS - B1 SERVICE +900.5M - SHEET 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | CENT01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-04-CENT01-2B20004 | BMS - B2 SERVICE +893.5M - SHEET 04 (3 OF 7) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-04-CENT01-2L10004 | BMS - L1 LOBBY LEVEL +905M - SHEET 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-04-CENT01-2L20005 | BMS - L2 THEATRE STALLS +913M - SHEET 04 (4 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-04-CENT01-2L30005 | BMS - L3 STALLES MEZZ & AD THEATRE +917.5M - SHEET 04 (4 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-04-CENT01-2L40005 | BMS - L4 FIRST CIRCLE & AD THEATER +921.0M - SHEET 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-04-CENT01-2L50005 | BMS - L5 SECOND CIRCLE & LOFT +928M - SHEET 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-04-CENT01-2L60005 | BMS - L6 SKY GARDEN +935.85M - SHEET 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-04-CENT01-2M10005 | BMS - M1 MEZ UPPER LOBBY +909M - SHEET 04 (03 OF 04) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-04-CENT01-2M20005 | BMS - M2 MEZ LOFT MEP +931.1M - SHEET 04 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 04 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-05-BLAD01-2000005 | BMS - BLADE-01 (+941.6, ROOF, +958.45) - SHEET 05 OF 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | BMS | QP.E.ME.BL1.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-BMS-05-BLAD02-2000005 | BMS - BLADE-02 (+948.28, +951.4) - SHEET 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | BMS | QP.E.ME.BL2.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-23
QF01012-NES-C04518-SDW-BMS-05-BLAD03-2000005 | BMS - BLADE-03 (+921, +928, +935.85) - SHEET 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | BMS | QP.E.ME.BL3.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-BMS-05-BLAD04-2000005 | BMS - BLADE-04 (+941.60, +947.35, +954) - SHEET 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | BMS | QP.E.ME.BL4.GEN.5970 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-BMS-05-BLAD05-2000005 | BMS - BLADE-05 (+969.30, +960.09) - SHEET 05 OF 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | BMS | QP.E.ME.BL5.GEN.2940 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-BMS-05-CENT01-2B10005 | BMS - B1 SERVICE +900.5M - SHEET 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-05-CENT01-2B20005 | BMS - B2 SERVICE +893.5M - SHEET 05 (4 OF 7) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-05-CENT01-2L10005 | BMS - L1 LOBBY LEVEL +905M - SHEET 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-05-CENT01-2L20006 | BMS - L2 THEATRE STALLS +913M - SHEET 05 (5 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-05-CENT01-2L30006 | BMS - L3 STALLES MEZZ & AD THEATRE +917.5M - SHEET 05 (5 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-05-CENT01-2L40006 | BMS - L4 FIRST CIRCLE & AD THEATER +921.0M - SHEET 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-05-CENT01-2L50006 | BMS - L5 SECOND CIRCLE & LOFT +928M - SHEET 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-05-CENT01-2L60006 | BMS - L6 SKY GARDEN +935.85M - SHEET 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-05-CENT01-2M10006 | BMS - M1 MEZ UPPER LOBBY +909M - SHEET 05 (04 OF 04) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-05-CENT01-2M20006 | BMS - M2 MEZ LOFT MEP +931.1M - SHEET 05 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 05 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-06-BLAD01-2000006 | BMS - BLADE-01 (+962.2, +972.48, +989) - SHEET 06 OF 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | BMS | QP.E.ME.BL1.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 06 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-BMS-06-BLAD04-2000006 | BMS - BLADE-04 (+959 , +968.30, +975.82) - SHEET 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | BMS | QP.E.ME.BL4.GEN.5970 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 06 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-BMS-06-CENT01-2L20007 | BMS - L2 THEATRE STALLS +913M - SHEET 06 (6 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 06 | CENT01 | 2 | L2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-06-CENT01-2L30007 | BMS - L3 STALLES MEZZ & AD THEATRE +917.5M - SHEET 06 (6 OF 6) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 06 | CENT01 | 2 | L3 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-06-CENT01-2L40007 | BMS - L4 FIRST CIRCLE & AD THEATER +921.0M - SHEET 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 06 | CENT01 | 2 | L4 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-06-CENT01-2L50007 | BMS - L5 SECOND CIRCLE & LOFT +928M - SHEET 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 06 | CENT01 | 2 | L5 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-06-CENT01-2L60007 | BMS - L6 SKY GARDEN +935.85M - SHEET 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 06 | CENT01 | 2 | L6 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-06-CENT01-2L80001 | BMS - L8 ROYAL MAJLIS +948.28M - SHEET 01 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 06 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-06-CENT01-2M20007 | BMS - M2 MEZ LOFT MEP +931.1M - SHEET 06 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 06 | CENT01 | 2 | M2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-08-CENT01-2B10007 | BMS - B1 SERVICE +900.5M - SHEET 08 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 08 | CENT01 | 2 | B1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-08-CENT01-2B20006 | BMS - B2 SERVICE +893.5M - SHEET 08 (5 OF 7) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-09-CENT01-2B10008 | BMS - B1 SERVICE +900.5M - SHEET 09 | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 09 | CENT01 | 2 | B1 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-09-CENT01-2B20007 | BMS - B2 SERVICE +893.5M - SHEET 09 (6 OF 7) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 09 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-BMS-11-CENT01-2B20008 | BMS - B2 SERVICE +893.5M - SHEET 07 (7 OF 7) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | BMS & Access Control | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | BMS | QP.E.ME.MBL.GEN.7340 | FI_60_25 | QF01012 | NES | C04518 | SDW | BMS | 11 | CENT01 | 2 | B2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-CTV-00-BLAD01-0000003 | CCTV SINGLE LINE DIAGRAM FOR BLADE-01 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD01 | 0 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-CTV-00-BLAD01-2000001 | CCTV SYSTEM PLAN - BLADE-01 (+870.5 M​, +876.2 5 M​ & +882 M​) - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-CTV-00-BLAD01-2000002 | CCTV SYSTEM PLAN - BLADE-01 (+887.75 M​, +893.5 M& +899.25 M) - SHEET 2 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-CTV-00-BLAD01-2000003 | CCTV SYSTEM PLAN - BLADE-01 (+905 M, +910.75 M​​​ & +917.5 M​) - SHEET 3 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-CTV-00-BLAD01-2000004 | CCTV SYSTEM PLAN - BLADE-01 (+922.25 M​, +928 M & +935.85 M) - SHEET 4 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-CTV-00-BLAD01-2000005 | CCTV SYSTEM PLAN - BLADE-01 (+941.6M​, ROOF BLADE 1​ & +958.45​ M) - SHEET 5 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-CTV-00-BLAD01-2000006 | CCTV SYSTEM PLAN - BLADE-01 (+962.2 M, +972.48M​​ & +989 M) - SHEET 6 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-CTV-00-BLAD02-0000003 | CCTV SINGLE LINE DIAGRAM FOR BLADE-02 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD02 | 0 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-CTV-00-BLAD02-2000001 | CCTV SYSTEM PLAN - BLADE-02 (+876.25 M​, +882.0​ M & +887.75 M​) - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-CTV-00-BLAD02-2000002 | CCTV SYSTEM PLAN - BLADE-02 (+893.5 M​, +899.25 M & +905 M) - SHEET 2 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-CTV-00-BLAD02-2000003 | CCTV SYSTEM PLAN - BLADE-02 (+910.75M, +916.5M & +922.25M) - SHEET 3 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-CTV-00-BLAD02-2000004 | CCTV SYSTEM PLAN - BLADE-02 (+928 M, +935.85 M & +941.60 M) - SHEET 4 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-CTV-00-BLAD02-2000005 | CCTV SYSTEM PLAN - BLADE-02 (+948.28 M​ & +951.40 M ) - SHEET 5 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-CTV-00-BLAD03-0000003 | CCTV SINGLE LINE DIAGRAM FOR BLADE-03 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD03 | 0 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-CTV-00-BLAD03-2000001 | CCTV SYSTEM PLAN - BLADE-03 (+847.5, +853.25, +859) - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-CTV-00-BLAD03-2000002 | CCTV SYSTEM PLAN - BLADE-03 (+867.62, +876.25, +882) - SHEET 2 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-CTV-00-BLAD03-2000003 | CCTV SYSTEM PLAN - BLADE-03 (+887.75, +893.5, +899.25) - SHEET 3 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-CTV-00-BLAD03-2000004 | CCTV SYSTEM PLAN - BLADE-03 (+905, +910.75, +916.5) - SHEET 4 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-CTV-00-BLAD03-2000005 | CCTV SYSTEM PLAN - BLADE-03(+921 , +928 , +935.85 ) - SHEET 5 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-CTV-00-BLAD04-0000003 | CCTV SINGLE LINE DIAGRAM FOR BLADE-04 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD04 | 0 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-CTV-00-BLAD04-2000001 | CCTV SYSTEM PLAN - BLADE-04 (+863.85, +870.5, +876.25) - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-CTV-00-BLAD04-2000002 | CCTV SYSTEM PLAN - BLADE-04 (+882, +887.75, +893.5) - SHEET 2 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-CTV-00-BLAD04-2000003 | CCTV SYSTEM PLAN - BLADE-04 (+899.25, +910.75, +916.5) - SHEET 3 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-CTV-00-BLAD04-2000004 | CCTV SYSTEM PLAN - BLADE-04 (+922.25, +928, +935.85) - SHEET 4 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-CTV-00-BLAD04-2000005 | CCTV SYSTEM PLAN - BLADE-04 (+941.60, +947.35, +954) - SHEET 5 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-CTV-00-BLAD04-2000006 | CCTV SYSTEM PLAN - BLADE-04 (+959, +968.30 ,+975.82) - SHEET 6 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-CTV-00-BLAD05-0000003 | CCTV SINGLE LINE DIAGRAM FOR BLADE-05 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD05 | 0 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-CTV-00-BLAD05-2000001 | CCTV SYSTEM PLAN - BLADE-05 (+894.5, +899.5, +905) - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-CTV-00-BLAD05-2000002 | CCTV SYSTEM PLAN - BLADE-05 (+910.75, +917.5, +922.25) - SHEET 2 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-CTV-00-BLAD05-2000003 | CCTV SYSTEM PLAN - BLADE-05 (+928, +935.85, +941.60) - SHEET 3 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-CTV-00-BLAD05-2000004 | CCTV SYSTEM PLAN - BLADE-05 (+948.10, +954, +957.35) - SHEET 4 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-CTV-00-BLAD05-2000005 | CCTV SYSTEM PLAN - BLADE-05 (+969.30, +960.09) - SHEET 5 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-CTV-00-CENT01-0ZZ0000 | CCTV SINGLE LINE DIAGRAM FOR MAIN BUILDING - OVER ALL | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 0 | ZZ | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-0ZZ0001 | CCTV SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-01 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 0 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-0ZZ0002 | CCTV SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-02 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 0 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-0ZZ0003 | CCTV SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-03 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 0 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-0ZZ0004 | CCTV SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-04 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 0 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2B10000 | CCTV SYSTEM OVERALL PLAN - B1 SERVICE & PARKING +900.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | B1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2B20000 | CCTV SYSTEM OVERALL PLAN - B2 SERVICE +893.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | B2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2B30000 | CCTV SYSTEM OVERALL PLAN - B3 PROMENADE +887.750M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-07-23 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | B3 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2L10000 | CCTV SYSTEM OVERALL PLAN - L1- LOBBY LEVEL +905M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-08-13 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | L1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2L20000 | CCTV SYSTEM OVERALL PLAN - L2- THEATRE STALLS +913M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | L2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-01-CENT01-2L20001 | CCTV SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-02-CENT01-2L20002 | CCTV SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-03-CENT01-2L20003 | CCTV SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 03 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2L60000 | CCTV SYSTEM OVERALL PLAN - L6- SKY GARDEN +935.85M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | L6 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2L80001 | CCTV SYSTEM OVERALL PLAN - L8 ROYAL MAJLIS +948.28M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2M10000 | CCTV SYSTEM OVERALL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-08-20 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | M1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-04-CENT01-2L20004 | CCTV SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 04 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2RL0001 | CCTV SYSTEM OVERALL PLAN - Roof & Above | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-PARK01-2B10000 | CCTV SYSTEM PARTIAL PLAN - B1 PARKING +900.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | SECURITY | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | PARK01 | 2 | B1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-CTV-00-Z00000-0ZZ0001 | CCTV SINGLE LINE DIAGRAM FOR SITE | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | Z00000 | 0 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-00-Z00000-0ZZ0101 | STANDARD INSTALLATION DETAILS - CCTV SYSTEM - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | Z00000 | 0 | ZZ | 0101 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-00-Z00000-0ZZ0111 | STANDARD INSTALLATION DETAILS - VEHICLE ACCESS CONTROL TOTEM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | Z00000 | 0 | ZZ | 0111 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-00-Z00000-2ZZ0000 | SECURITY OVERALL SITE PLAN | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:500 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | Z00000 | 2 | ZZ | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-01-CENT01-2B10001 | CCTV SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 01 - (1 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-01-CENT01-2B20001 | CCTV SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 01 - (1 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-01-CENT01-2B30001 | CCTV SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 01 - (1 OF 5) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-01-CENT01-2L10001 | CCTV SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 01 - (1 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | CENT01 | 2 | L1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-05-CENT01-2L20005 | CCTV SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-06-CENT01-2L20006 | CCTV SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 06 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2L20000 | SECURITY SYSTEM OVERALL PLAN - L2- THEATRE STALLS +913M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | L2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-01-CENT01-2L20001 | SECURITY SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-01-CENT01-2L60001 | CCTV SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-01-CENT01-2M10001 | CCTV SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (1 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-02-CENT01-2L20002 | SECURITY SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-01-PARK01-2B10001 | CCTV SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 01 - (1 OF 3) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | SECURITY | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-CTV-01-Z00000-2ZZ0001 | CCTV PARTIAL SITE PLAN - SHEET 01 - (1 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | Z00000 | 2 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-02-CENT01-2B10002 | CCTV SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 02 - (2 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-02-CENT01-2B20002 | CCTV SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 02 - (2 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-02-CENT01-2B30002 | CCTV SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 02 - (2 OF 5) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-02-CENT01-2L10002 | CCTV SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 02 - (2 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-03-CENT01-2L20003 | SECURITY SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 03 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-04-CENT01-2L20004 | SECURITY SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 04 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-05-CENT01-2L20005 | SECURITY SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-06-CENT01-2L20006 | SECURITY SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 06 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-02-CENT01-2L60002 | CCTV SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-02-CENT01-2M10002 | CCTV SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (2 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2L30000 | CCTV SYSTEM OVERALL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | L3 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-02-PARK01-2B10002 | CCTV SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 02 - (2 OF 3) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | SECURITY | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-CTV-02-Z00000-2ZZ0002 | CCTVPARTIAL SITE PLAN - SHEET 02 - (2 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | Z00000 | 2 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-01-CENT01-2L30001 | CCTV SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-02-CENT01-2L30002 | CCTV SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-03-CENT01-2L30003 | CCTV SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 03 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-04-CENT01-2L30004 | CCTV SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 04 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-03-CENT01-2L60003 | CCTV SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 03 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-05-CENT01-2L30005 | CCTV SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-03-PARK01-2B10003 | CCTV SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 03 - (3 OF 3) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | SECURITY | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 03 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-CTV-03-Z00000-2ZZ0003 | CCTV PARTIAL SITE PLAN - SHEET 03 - (3 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 03 | Z00000 | 2 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-04-CENT01-2B10003 | CCTV SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 04 - (3 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 04 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-04-CENT01-2B20003 | CCTV SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 04 - (3 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 04 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-04-CENT01-2L10003 | CCTV SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 04 - (3 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 04 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-06-CENT01-2L30006 | CCTV SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 06 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2L30000 | SECURITY SYSTEM OVERALL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | L3 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-01-CENT01-2L30001 | SECURITY SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-02-CENT01-2L30002 | SECURITY SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-04-CENT01-2L60004 | CCTV SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 04 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-04-CENT01-2M10003 | CCTV SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (3 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 04 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-03-CENT01-2L30003 | SECURITY SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 03 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-04-Z00000-2ZZ0004 | CCTV PARTIAL SITE PLAN - SHEET 04 - (4 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 04 | Z00000 | 2 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-05-CENT01-2B10004 | CCTV SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 05 - (4 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | CENT01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-05-CENT01-2B20004 | CCTV SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 05 - (4 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-05-CENT01-2B30003 | CCTV SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 05 - (3 OF 5) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-05-CENT01-2L10004 | CCTV SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 05 - (4 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-04-CENT01-2L30004 | SECURITY SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 04 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-05-CENT01-2L30005 | SECURITY SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-06-CENT01-2L30006 | SECURITY SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 06 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2L40000 | CCTV SYSTEM OVERALL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | L4 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-05-CENT01-2L60005 | CCTV SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-05-CENT01-2M10004 | CCTV SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (4 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | CENT01 | 2 | M1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-01-CENT01-2L40001 | CCTV SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-05-Z00000-2ZZ0005 | CCTV PARTIAL SITE PLAN - SHEET 05 - (5 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | Z00000 | 2 | ZZ | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-06-CENT01-2B30004 | CCTVSYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 06 - (4 OF 5) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 06 | CENT01 | 2 | B3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-02-CENT01-2L40002 | CCTV SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-03-CENT01-2L40003 | CCTV SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 03 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-04-CENT01-2L40004 | CCTV SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 04 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-05-CENT01-2L40005 | CCTV SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-06-CENT01-2L60006 | CCTV SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 06 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-06-CENT01-2L40006 | CCTV SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 06 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-06-Z00000-2ZZ0006 | CCTV PARTIAL SITE PLAN - SHEET 06 - (6 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 06 | Z00000 | 2 | ZZ | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-07-CENT01-2B10005 | CCTV SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 07 - (5 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 07 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-07-CENT01-2B20005 | CCTV SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 07 - (5 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 07 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-07-Z00000-2ZZ0007 | CCTV PARTIAL SITE PLAN - SHEET 07 - (7 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 07 | Z00000 | 2 | ZZ | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-08-CENT01-2B10006 | CCTV SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 08 - (6 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 08 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-08-CENT01-2B20006 | CCTV SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 08 - (6 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-08-CENT01-2B30005 | CCTVSYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 08 - (5 OF 5) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 08 | CENT01 | 2 | B3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-08-Z00000-2ZZ0008 | CCTV PARTIAL SITE PLAN - SHEET 08 - (8 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 08 | Z00000 | 2 | ZZ | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-09-CENT01-2B10007 | CCTV SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 09 - (7 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 09 | CENT01 | 2 | B1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-09-CENT01-2B20007 | CCTV SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 09 - (7 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 09 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-09-Z00000-2ZZ0009 | CCTV PARTIAL SITE PLAN - SHEET 09 - (9 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 09 | Z00000 | 2 | ZZ | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-10-Z00000-2ZZ0010 | CCTV PARTIAL SITE PLAN - SHEET 10 - (10 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 10 | Z00000 | 2 | ZZ | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-11-Z00000-2ZZ0011 | CCTV PARTIAL SITE PLAN - SHEET 11 - (11 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 11 | Z00000 | 2 | ZZ | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-12-Z00000-2ZZ0012 | CCTV PARTIAL SITE PLAN - SHEET 12 - (12 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 12 | Z00000 | 2 | ZZ | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-13-Z00000-2ZZ0013 | CCTV PARTIAL SITE PLAN - SHEET 16 - (13 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 13 | Z00000 | 2 | ZZ | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-14-Z00000-2ZZ0014 | CCTV PARTIAL SITE PLAN - SHEET 17 - (14 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 14 | Z00000 | 2 | ZZ | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-15-Z00000-2ZZ0015 | CCTV PARTIAL SITE PLAN - SHEET 18 - (15 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 15 | Z00000 | 2 | ZZ | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-16-Z00000-2ZZ0016 | CCTV PARTIAL SITE PLAN - SHEET 19 - (16 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 16 | Z00000 | 2 | ZZ | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-17-Z00000-2ZZ0017 | CCTV PARTIAL SITE PLAN - SHEET 20 - (17 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 17 | Z00000 | 2 | ZZ | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-18-Z00000-2ZZ0018 | CCTV PARTIAL SITE PLAN - SHEET 21 - (18 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 18 | Z00000 | 2 | ZZ | 0018 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-19-GARD01-2ZZ0001 | CCTV SYSTEM PLAN - GUARD ROOM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-01-17 | SECURITY | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 19 | GARD01 | 2 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-CTV-19-Z00000-2ZZ0019 | CCTV PARTIAL SITE PLAN - SHEET 22 - (19 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 19 | Z00000 | 2 | ZZ | 0019 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-20-Z00000-2ZZ0020 | CCTV PARTIAL SITE PLAN - SHEET 23 - (20 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 20 | Z00000 | 2 | ZZ | 0020 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-21-Z00000-2ZZ0021 | CCTV PARTIAL SITE PLAN - SHEET 24 - (21 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 21 | Z00000 | 2 | ZZ | 0021 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-22-Z00000-2ZZ0022 | CCTV PARTIAL SITE PLAN - SHEET 25 - (22 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 22 | Z00000 | 2 | ZZ | 0022 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-23-Z00000-2ZZ0023 | CCTV PARTIAL SITE PLAN - SHEET 26 - (23 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 23 | Z00000 | 2 | ZZ | 0023 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-24-Z00000-2ZZ0024 | CCTV PARTIAL SITE PLAN - SHEET 27 - (24 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 24 | Z00000 | 2 | ZZ | 0024 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-25-Z00000-2ZZ0025 | CCTV PARTIAL SITE PLAN - SHEET 28 - (25 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 25 | Z00000 | 2 | ZZ | 0025 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-26-Z00000-2ZZ0026 | CCTV PARTIAL SITE PLAN - SHEET 29 - (26 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 26 | Z00000 | 2 | ZZ | 0026 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-27-Z00000-2ZZ0027 | CCTV PARTIAL SITE PLAN - SHEET 30 - (27 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 27 | Z00000 | 2 | ZZ | 0027 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-28-Z00000-2ZZ0028 | CCTV PARTIAL SITE PLAN - SHEET 31 - (28 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 28 | Z00000 | 2 | ZZ | 0028 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-EBC-00-CENT01-2B10001 | BUSWAY - B1 SERVICE +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-29 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 00 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-00-CENT01-2B20001 | BUSWAY - B2 SERVICE +893.5M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-15 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 00 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-00-CENT01-2L10005 | BUSWAY - L1- LOBBY LEVEL +905M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 00 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-00-CENT01-2L20001 | BUSWAY - L2- THEATRE STALLS +913M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 00 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-00-CENT01-2L30001 | BUSWAY - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2027-01-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 00 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-00-CENT01-2L40001 | BUSWAY - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2027-01-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 00 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-00-CENT01-2L50001 | BUSWAY - L5- SECOND CIRCLE & LOFT +928M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2027-01-31 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 00 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-00-CENT01-2M10001 | BUSWAY - L1-UPPER LOBBY MEZZANINE +909M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 00 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-00-CENT01-2M20001 | BUSWAY - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2027-02-10 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 00 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-00-PARK01-2B10001 | BUSWAY - B1 PARKING +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-29 | Busway | QP.E.ME.PAR.GEN.1399 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 00 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-25
QF01012-NES-C04518-SDW-EBC-01-CENT01-2B10002 | BUSWAY - B1 SERVICE +900.5M - SHEET 01 - (01 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-29 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 01 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-01-CENT01-2B20002 | BUSWAY - B2 SERVICE +893.5M - SHEET 01 - (01 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-15 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 01 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-01-CENT01-2L10002 | BUSWAY - L1- LOBBY LEVEL +905M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 01 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-01-CENT01-2L20002 | BUSWAY - L2- THEATRE STALLS +913M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 01 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-01-CENT01-2L30002 | BUSWAY - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 01 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-01-CENT01-2L40002 | BUSWAY - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 01 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-01-CENT01-2L50002 | BUSWAY - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-31 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 01 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-01-CENT01-2M10002 | BUSWAY - L1-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 01 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-01-CENT01-2M20002 | BUSWAY - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-02-10 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 01 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-01-PARK01-2B10002 | BUSWAY - B1 PARKING +900.5M - SHEET 01 - (01 OF 03) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-29 | Busway | QP.E.ME.PAR.GEN.1399 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 01 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-25
QF01012-NES-C04518-SDW-EBC-02-CENT01-2B10003 | BUSWAY - B1 SERVICE +900.5M - SHEET 02 - (02 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-29 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 02 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-02-CENT01-2B20003 | BUSWAY - B2 SERVICE +893.5M - SHEET 02 - (02 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-15 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 02 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-02-CENT01-2L10003 | BUSWAY - L1- LOBBY LEVEL +905M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 02 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-02-CENT01-2L20003 | BUSWAY - L2- THEATRE STALLS +913M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 02 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-02-CENT01-2L30003 | BUSWAY - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 02 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-02-CENT01-2L40003 | BUSWAY - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 02 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-02-CENT01-2L50003 | BUSWAY - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-31 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 02 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-02-CENT01-2M10003 | BUSWAY - L1-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 02 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-02-CENT01-2M20003 | BUSWAY - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-02-10 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 02 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-02-PARK01-2B10003 | BUSWAY - B1 PARKING +900.5M - SHEET 02 - (02 OF 03) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-29 | Busway | QP.E.ME.PAR.GEN.1399 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 02 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-25
QF01012-NES-C04518-SDW-EBC-03-CENT01-2B10004 | BUSWAY - B1 SERVICE +900.5M - SHEET 04 - (03 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-29 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 03 | CENT01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-03-CENT01-2L10004 | BUSWAY - L1- LOBBY LEVEL +905M - SHEET 04 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 03 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-03-CENT01-2L20004 | BUSWAY - L2- THEATRE STALLS +913M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 03 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-03-CENT01-2L30004 | BUSWAY - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 03 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-03-CENT01-2L40004 | BUSWAY - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 03 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-03-CENT01-2L50004 | BUSWAY - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-31 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 03 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-03-CENT01-2M10004 | BUSWAY - L1-UPPER LOBBY MEZZANINE +909M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 03 | CENT01 | 2 | M1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-03-CENT01-2M20004 | BUSWAY - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-02-10 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 03 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-03-PARK01-2B10004 | BUSWAY - B1 PARKING +900.5M - SHEET 03 - (03 OF 03) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-29 | Busway | QP.E.ME.PAR.GEN.1399 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 03 | PARK01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-25
QF01012-NES-C04518-SDW-EBC-04-CENT01-2B10005 | BUSWAY - B1 SERVICE +900.5M - SHEET 05 - (04 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-29 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 04 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-04-CENT01-2B20004 | BUSWAY - B2 SERVICE +893.5M - SHEET 04 - (03 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-15 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 04 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-04-CENT01-2L10005 | BUSWAY - L1- LOBBY LEVEL +905M - SHEET 05 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 04 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-04-CENT01-2L20005 | BUSWAY - L2- THEATRE STALLS +913M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 04 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-04-CENT01-2L30005 | BUSWAY - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 04 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-04-CENT01-2L40005 | BUSWAY - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 04 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-04-CENT01-2L50005 | BUSWAY - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-31 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 04 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-04-CENT01-2M10005 | BUSWAY - L1-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 04 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-04-CENT01-2M20005 | BUSWAY - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-02-10 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 04 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-05-CENT01-2B10006 | BUSWAY - B1 SERVICE +900.5M - SHEET 07 - (05 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-29 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 05 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-05-CENT01-2B20005 | BUSWAY - B2 SERVICE +893.5M - SHEET 05 - (04 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-15 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 05 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-05-CENT01-2L10006 | BUSWAY - L1- LOBBY LEVEL +905M - SHEET 10 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 05 | CENT01 | 2 | L1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-05-CENT01-2L20006 | BUSWAY - L2- THEATRE STALLS +913M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 05 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-05-CENT01-2L30006 | BUSWAY - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 05 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-05-CENT01-2L40006 | BUSWAY - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 05 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-05-CENT01-2L50006 | BUSWAY - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-31 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 05 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-05-CENT01-2M10006 | BUSWAY - L1-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 05 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-05-CENT01-2M20006 | BUSWAY - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-02-10 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 05 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-06-CENT01-2B10007 | BUSWAY - B1 SERVICE +900.5M - SHEET 08 - (06 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-29 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 06 | CENT01 | 2 | B1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-06-CENT01-2L10007 | BUSWAY - L1- LOBBY LEVEL +905M - SHEET 11 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 06 | CENT01 | 2 | L1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-06-CENT01-2L20007 | BUSWAY - L2- THEATRE STALLS +913M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 06 | CENT01 | 2 | L2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-06-CENT01-2L30007 | BUSWAY - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-10 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 06 | CENT01 | 2 | L3 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-06-CENT01-2L40007 | BUSWAY - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 06 | CENT01 | 2 | L4 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-06-CENT01-2L50007 | BUSWAY - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-31 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 06 | CENT01 | 2 | L5 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-06-CENT01-2M10007 | BUSWAY - L1-UPPER LOBBY MEZZANINE +909M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-20 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 06 | CENT01 | 2 | M1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-06-CENT01-2M20007 | BUSWAY - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-02-10 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 06 | CENT01 | 2 | M2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-07-CENT01-2B10008 | BUSWAY - B1 SERVICE +900.5M - SHEET 09 - (07 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-29 | Busway | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 07 | CENT01 | 2 | B1 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-08-CENT01-2B20006 | BUSWAY - B2 SERVICE +893.5M - SHEET 08 - (05 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-15 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-09-CENT01-2B20007 | BUSWAY - B2 SERVICE +893.5M - SHEET 09 - (06 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-15 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 09 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBC-11-CENT01-2B20008 | BUSWAY - B2 SERVICE +893.5M - SHEET 11 - (07 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-15 | BusWay | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBC | 11 | CENT01 | 2 | B2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-EBW-00-CENT01-2B10001 | ELECTRICAL BUILDER WORK - B1 SERVICE +900.5M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | Electrical Builder Work | QP.E.ME.MBL.GEN.6870 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-EBW-00-CENT01-2B20001 | ELECTRICAL BUILDER WORK - B2 SERVICE +893.5M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | Electrical Builder work | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-EBW-00-CENT01-2B30001 | ELECTRICAL BUILDER WORK - B3 PROMENADE +887.750M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-07-16 | Electrical Builder Work | QP.E.ME.MBL.GEN.6800 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-01-13
QF01012-NES-C04518-SDW-ELC-01-BLAD02-2000001 | CONTAINMENT - BLADE-02 (+876.25, +882, +887.75)- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.BL2.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-28
QF01012-NES-C04518-SDW-EBW-00-CENT01-2L20001 | ELECTRICAL BUILDER WORK - L2- THEATRE STALLS +913M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | Electrical Builder Work | QP.E.ME.MBL.GEN.6990 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-EBW-00-CENT01-2L30001 | ELECTRICAL BUILDER WORK - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7030 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-EBW-00-CENT01-2L40001 | ELECTRICAL BUILDER WORK - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | Electrical Builder Work | QP.E.ME.MBL.GEN.7070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-ELC-01-BLAD02-2000006 | CONTAINMENT - BLADE-02 (+876.25, +882, +887.75)- SHEET 1 - DETAILS | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.BL2.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | BLAD02 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-28
QF01012-NES-C04518-SDW-EBW-00-CENT01-2L60001 | ELECTRICAL BUILDER WORK - L6- SKY GARDEN +935.85M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-00-CENT01-2M10001 | ELECTRICAL BUILDER WORK - L1-UPPER LOBBY MEZZANINE +909M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-01 | Electrical Builder Work | QP.E.ME.MBL.GEN.6950 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-11
QF01012-NES-C04518-SDW-ELC-02-BLAD02-2000002 | CONTAINMENT - BLADE-02 (+893.5, +899.25, +905)- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.BL2.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-28
QF01012-NES-C04518-SDW-EBW-00-CENT01-3B10009 | ELECTRICAL BUILDER WORK - B1 SERVICE +900.5M - SECTIONS | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-27 | Electrical Builder Work | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 3 | B1 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-EBW-00-CENT01-3B20009 | ELECTRICAL BUILDER WORK - B2 SERVICE +893.5M - SECTIONS | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-06 | Electrical Builder work | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 3 | B2 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-EBW-00-CENT01-3B30006 | ELECTRICAL BUILDER WORK - B3 PROMENADE +887.750M - SECTIONS | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-07-16 | Electrical Builder Work | QP.E.ME.MBL.GEN.6800 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 3 | B3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-01-13
QF01012-NES-C04518-SDW-EBW-00-CENT01-3L30008 | ELECTRICAL BUILDER WORK - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SECTIONS | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-05 | Electrical Builder work | QP.E.ME.MBL.GEN.7030 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 3 | L3 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-EBW-00-CENT01-3L40008 | ELECTRICAL BUILDER WORK - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SECTIONS | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-19 | Electrical Builder Work | QP.E.ME.MBL.GEN.7070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 3 | L4 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-ELC-03-BLAD02-2000003 | CONTAINMENT - BLADE-02 (+910.75, +916.5, +922.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.BL2.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-27
QF01012-NES-C04518-SDW-EBW-00-CENT01-3L60008 | ELECTRICAL BUILDER WORK - L6- SKY GARDEN +935.85M - SECTIONS | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 3 | L6 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELC-00-BLAD03-7000006 | CONTAINMENT - BLADE-03 (+847.5, +853.25, +859)- DETAIL - 01 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Electrical Containment | QP.E.ME.BL3.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | BLAD03 | 7 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-22
QF01012-NES-C04518-SDW-EBW-00-GARD01-2000001 | ELECTRICAL BUILDER WORK - GUARD ROOM | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-17 | Electrical Builder Work | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | GARD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-EBW-00-PARK01-2B10001 | ELECTRICAL BUILDER WORK - B1 PARKING +900.5M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | Electrical Builder Work | QP.E.ME.PAR.GEN.1479 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-EBW-00-PARK01-3B10005 | ELECTRICAL BUILDER WORK - B1 PARKING +900.5M - SECTIONS | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-15 | Electrical Builder Work | QP.E.ME.PAR.GEN.1479 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | PARK01 | 3 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-EBW-00-SECE01-2000001 | ELECTRICAL BUILDER WORK -SEC ROOM | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-17 | Electrical Builder Work | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | SECE01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-EBW-01-BLAD01-2000001 | ELECTRICAL BUILDER WORK - BLADE-01 (+870.5, +876.25, +882)- SHEET 1 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Electrical Builder Work | QP.E.ME.BL1.GEN.3740 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-26
QF01012-NES-C04518-SDW-EBW-01-BLAD01-2ZZ0001 | ELECTRICAL BUILDER WORK - BLADE-01-STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-15 | Electrical Builder Work | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD01 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-EBW-01-BLAD01-2ZZ0002 | ELECTRICAL BUILDER WORK - BLADE-01-STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-15 | Electrical Builder Work | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD01 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-EBW-01-BLAD01-2ZZ0003 | ELECTRICAL BUILDER WORK - BLADE-01-STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | Electrical Builder Work | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD01 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-EBW-01-BLAD01-2ZZ0004 | ELECTRICAL BUILDER WORK - BLADE-01-STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | Electrical Builder Work | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD01 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-ELC-00-BLAD03-7000007 | CONTAINMENT - BLADE-03 (+847.5, +853.25, +859)- DETAIL - 02 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Electrical Containment | QP.E.ME.BL3.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | BLAD03 | 7 | 00 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-22
QF01012-NES-C04518-SDW-EBW-01-BLAD02-2ZZ0001 | ELECTRICAL BUILDER WORK - BLADE-02-STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-15 | Electrical Builder Work | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD02 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-EBW-01-BLAD02-2ZZ0002 | ELECTRICAL BUILDER WORK - BLADE-02-STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-15 | Electrical Builder Work | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD02 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-EBW-01-BLAD02-2ZZ0003 | ELECTRICAL BUILDER WORK - BLADE-02-STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | Electrical Builder Work | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD02 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-EBW-01-BLAD02-2ZZ0004 | ELECTRICAL BUILDER WORK - BLADE-02-STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | Electrical Builder Work | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD02 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-ELC-01-BLAD03-2000001 | CONTAINMENT - BLADE-03 (+847.5, +853.25, +859)- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Electrical Containment | QP.E.ME.BL3.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-22
QF01012-NES-C04518-SDW-EBW-01-BLAD03-2ZZ0001 | ELECTRICAL BUILDER WORK - BLADE-03-STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-15 | Electrical Builder Work | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD03 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-EBW-01-BLAD03-2ZZ0002 | ELECTRICAL BUILDER WORK - BLADE-03-STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-15 | Electrical Builder Work | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD03 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-EBW-01-BLAD03-2ZZ0003 | ELECTRICAL BUILDER WORK - BLADE-03-STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | Electrical Builder Work | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD03 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-EBW-01-BLAD03-2ZZ0004 | ELECTRICAL BUILDER WORK - BLADE-03-STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | Electrical Builder Work | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD03 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-ELC-02-BLAD03-2000002 | CONTAINMENT - BLADE-03 (+867.62, +876.25, +882)- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Electrical Containment | QP.E.ME.BL3.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-22
QF01012-NES-C04518-SDW-EBW-01-BLAD04-2ZZ0001 | ELECTRICAL BUILDER WORK - BLADE-04-STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-15 | Electrical Builder Work | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD04 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-EBW-01-BLAD04-2ZZ0002 | ELECTRICAL BUILDER WORK - BLADE-04-STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-15 | Electrical Builder Work | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD04 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-EBW-01-BLAD04-2ZZ0003 | ELECTRICAL BUILDER WORK - BLADE-04-STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | Electrical Builder Work | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD04 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-EBW-01-BLAD04-2ZZ0004 | ELECTRICAL BUILDER WORK - BLADE-04-STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | Electrical Builder Work | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD04 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-EBW-01-BLAD05-2000001 | ELECTRICAL BUILDER WORK - BLADE-05 (+894.5, +899.5, +905)- SHEET 1 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Electrical Builder Work | QP.E.ME.BL5.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-13
QF01012-NES-C04518-SDW-EBW-01-BLAD05-2ZZ0001 | ELECTRICAL BUILDER WORK - BLADE-05-STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-03-15 | Electrical Builder Work | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD05 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-EBW-01-BLAD05-2ZZ0002 | ELECTRICAL BUILDER WORK - BLADE-05-STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-03-15 | Electrical Builder Work | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD05 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-EBW-01-BLAD05-2ZZ0003 | ELECTRICAL BUILDER WORK - BLADE-05-STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-03-30 | Electrical Builder Work | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD05 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-EBW-01-BLAD05-2ZZ0004 | ELECTRICAL BUILDER WORK - BLADE-05-STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-03-30 | Electrical Builder Work | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD05 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-EBW-01-CENT01-2B10002 | ELECTRICAL BUILDER WORK - B1 SERVICE +900.5M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Electrical Builder Work | QP.E.ME.MBL.GEN.6870 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-EBW-01-CENT01-2B20002 | ELECTRICAL BUILDER WORK - B2 SERVICE +893.5M - SHEET 01 - (01 OF 07) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Builder work | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-EBW-01-CENT01-2B30002 | ELECTRICAL BUILDER WORK - B3 PROMENADE +887.750M - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | Electrical Builder Work | QP.E.ME.MBL.GEN.6800 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-01-13
QF01012-NES-C04518-SDW-ELC-03-BLAD03-2000003 | CONTAINMENT - BLADE-03 (+887.75, +893.5, +899.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Electrical Containment | QP.E.ME.BL3.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-22
QF01012-NES-C04518-SDW-EBW-01-CENT01-2L20002 | ELECTRICAL BUILDER WORK - L2- THEATRE STALLS +913M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Builder Work | QP.E.ME.MBL.GEN.6990 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-EBW-01-CENT01-2L30002 | ELECTRICAL BUILDER WORK - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7030 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-EBW-01-CENT01-2L40002 | ELECTRICAL BUILDER WORK - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Builder Work | QP.E.ME.MBL.GEN.7070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-ELC-04-BLAD03-2000004 | CONTAINMENT - BLADE-03 (+905, +910.75, +916.5)- SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Electrical Containment | QP.E.ME.BL3.GEN.1820 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-11
QF01012-NES-C04518-SDW-EBW-01-CENT01-2L60002 | ELECTRICAL BUILDER WORK - L6- SKY GARDEN +935.85M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-01-CENT01-2L80001 | ELECTRICAL BUILDER WORK - L8 ROYAL MAJLIS +948.28M - SHEET 01 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2M10002 | ELECTRICAL BUILDER WORK - L1-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Electrical Builder Work | QP.E.ME.MBL.GEN.6950 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-11
QF01012-NES-C04518-SDW-ELC-00-BLAD04-7000007 | CONTAINMENT - BLADE-04 (+863.85, +870.5, +876.25)- DETAIL - 01 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Electrical Containment | QP.E.ME.BL4.GEN.2840 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | BLAD04 | 7 | 00 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-EBW-01-CENT01-2RL0001 | ELECTRICAL BUILDER WORK - RL ROOF & ABOVE - SHEET 01 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ELC-00-BLAD04-7000008 | CONTAINMENT - BLADE-04 (+863.85, +870.5, +876.25)- DETAIL - 02 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Electrical Containment | QP.E.ME.BL4.GEN.2840 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | BLAD04 | 7 | 00 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELC-01-BLAD04-2000001 | CONTAINMENT - BLADE-04 (+863.85, +870.5, +876.25)- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Electrical Containment | QP.E.ME.BL4.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-19
QF01012-NES-C04518-SDW-ELC-02-BLAD04-2000002 | CONTAINMENT - BLADE-04 (+882, +887.75, +893.5)- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Electrical Containment | QP.E.ME.BL4.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-19
QF01012-NES-C04518-SDW-ELC-03-BLAD04-2000003 | CONTAINMENT - BLADE-04 (+899.25, +905, +910.75)- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Electrical Containment | QP.E.ME.BL4.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-19
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0005 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 3 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-15 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0006 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 3 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-15 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0007 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 4 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0008 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 4 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-PARK01-2B10002 | ELECTRICAL BUILDER WORK - B1 PARKING +900.5M - SHEET 01 - (01 OF 03) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Electrical Builder Work | QP.E.ME.PAR.GEN.1479 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-EBW-02-BLAD01-2000002 | ELECTRICAL BUILDER WORK - BLADE-01 (+887.75, +893.5, +899.25)- SHEET 2 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Electrical Builder Work | QP.E.ME.BL1.GEN.3740 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-26
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L10008 | CONTAINMENT - L1- LOBBY LEVEL +905M - DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L1 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L10009 | CONTAINMENT - L1- LOBBY LEVEL +905M - DETAILS - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L1 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ELC-00-CENT01-2L10001 | CONTAINMENT - L1- LOBBY LEVEL +905M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 2 | L1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-EBW-02-BLAD05-2000002 | ELECTRICAL BUILDER WORK - BLADE-05 (+910.75, +917.5, +922.25)- SHEET 2 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Electrical Builder Work | QP.E.ME.BL5.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-13
QF01012-NES-C04518-SDW-EBW-02-CENT01-2B10003 | ELECTRICAL BUILDER WORK - B1 SERVICE +900.5M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Electrical Builder Work | QP.E.ME.MBL.GEN.6870 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-EBW-02-CENT01-2B20003 | ELECTRICAL BUILDER WORK - B2 SERVICE +893.5M - SHEET 02 - (02 OF 07) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Builder work | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-EBW-02-CENT01-2B30003 | ELECTRICAL BUILDER WORK - B3 PROMENADE +887.750M - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | Electrical Builder Work | QP.E.ME.MBL.GEN.6800 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-01-13
QF01012-NES-C04518-SDW-ELC-01-CENT01-2L10002 | CONTAINMENT - L1- LOBBY LEVEL +905M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-EBW-02-CENT01-2L20003 | ELECTRICAL BUILDER WORK - L2- THEATRE STALLS +913M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Builder Work | QP.E.ME.MBL.GEN.6990 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-EBW-02-CENT01-2L30003 | ELECTRICAL BUILDER WORK - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7030 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-EBW-02-CENT01-2L40003 | ELECTRICAL BUILDER WORK - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Builder Work | QP.E.ME.MBL.GEN.7070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-ELC-02-CENT01-2L10003 | CONTAINMENT - L1- LOBBY LEVEL +905M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-EBW-02-CENT01-2L60003 | ELECTRICAL BUILDER WORK - L6- SKY GARDEN +935.85M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-02-CENT01-2M10003 | ELECTRICAL BUILDER WORK - L1-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Electrical Builder Work | QP.E.ME.MBL.GEN.6950 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-11
QF01012-NES-C04518-SDW-ELC-04-CENT01-2L10005 | CONTAINMENT - L1- LOBBY LEVEL +905M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-EBW-02-PARK01-2B10003 | ELECTRICAL BUILDER WORK - B1 PARKING +900.5M - SHEET 02 - (02 OF 03) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Electrical Builder Work | QP.E.ME.PAR.GEN.1479 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-EBW-03-BLAD01-2000003 | ELECTRICAL BUILDER WORK - BLADE-01 (+905, +910.75, +917.5)- SHEET 3 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Electrical Builder Work | QP.E.ME.BL1.GEN.3780 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-30
QF01012-NES-C04518-SDW-ELC-05-CENT01-2L10006 | CONTAINMENT - L1- LOBBY LEVEL +905M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | CENT01 | 2 | L1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L50008 | CONTAINMENT - L5- SECOND CIRCLE & LOFT +928M - DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L5 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L50009 | CONTAINMENT - L5- SECOND CIRCLE & LOFT +928M - DETAILS - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L5 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-EBW-03-BLAD05-2000003 | ELECTRICAL BUILDER WORK - BLADE-05 (+928, +935.85, +941.60)- SHEET 3 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Electrical Builder Work | QP.E.ME.BL5.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-ELC-00-CENT01-2L50001 | CONTAINMENT - L5- SECOND CIRCLE & LOFT +928M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-EBW-03-CENT01-2L20004 | ELECTRICAL BUILDER WORK - L2- THEATRE STALLS +913M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Builder Work | QP.E.ME.MBL.GEN.6990 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-EBW-03-CENT01-2L30004 | ELECTRICAL BUILDER WORK - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7030 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-EBW-03-CENT01-2L40004 | ELECTRICAL BUILDER WORK - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Builder Work | QP.E.ME.MBL.GEN.7070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-ELC-01-CENT01-2L50002 | CONTAINMENT - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-EBW-03-CENT01-2L60004 | ELECTRICAL BUILDER WORK - L6- SKY GARDEN +935.85M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELC-02-CENT01-2L50003 | CONTAINMENT - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-EBW-03-PARK01-2B10004 | ELECTRICAL BUILDER WORK - B1 PARKING +900.5M - SHEET 03 - (03 OF 03) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Electrical Builder Work | QP.E.ME.PAR.GEN.1479 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | PARK01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-EBW-04-BLAD01-2000004 | ELECTRICAL BUILDER WORK - BLADE-01 (+922.25, +928, & +935.85)- SHEET 4 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Electrical Builder Work | QP.E.ME.BL1.GEN.3780 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-30
QF01012-NES-C04518-SDW-EBW-04-BLAD02-2000004 | ELECTRICAL BUILDER WORK - BLADE-02 (+928, +935.85, +941.6)- SHEET 4 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Electrical Builder Work | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-ELC-03-CENT01-2L50004 | CONTAINMENT - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-EBW-04-BLAD04-2000004 | ELECTRICAL BUILDER WORK - BLADE-04 (+922.25, +928, +935.85)- SHEET 4 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Builder Work | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-EBW-04-BLAD05-2000004 | ELECTRICAL BUILDER WORK - BLADE-05 (+948.10, +954, +957.35)- SHEET 4 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Electrical Builder Work | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-EBW-04-CENT01-2B10005 | ELECTRICAL BUILDER WORK - B1 SERVICE +900.5M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Electrical Builder Work | QP.E.ME.MBL.GEN.6870 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-EBW-04-CENT01-2B20004 | ELECTRICAL BUILDER WORK - B2 SERVICE +893.5M - SHEET 04 - (03 OF 07) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Builder work | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-ELC-04-CENT01-2L50005 | CONTAINMENT - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-EBW-04-CENT01-2L20005 | ELECTRICAL BUILDER WORK - L2- THEATRE STALLS +913M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Builder Work | QP.E.ME.MBL.GEN.6990 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-EBW-04-CENT01-2L30005 | ELECTRICAL BUILDER WORK - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7030 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-EBW-04-CENT01-2L40005 | ELECTRICAL BUILDER WORK - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Builder Work | QP.E.ME.MBL.GEN.7070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-ELC-05-CENT01-2L50006 | CONTAINMENT - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-EBW-04-CENT01-2L60005 | ELECTRICAL BUILDER WORK - L6- SKY GARDEN +935.85M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-04-CENT01-2M10005 | ELECTRICAL BUILDER WORK - L1-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Electrical Builder Work | QP.E.ME.MBL.GEN.6950 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-11
QF01012-NES-C04518-SDW-ELC-06-CENT01-2L50007 | CONTAINMENT - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 06 | CENT01 | 2 | L5 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-EBW-05-BLAD01-2000005 | ELECTRICAL BUILDER WORK - BLADE-01 (+941.6, ROOF, & +958.45)- SHEET 5 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Electrical Builder Work | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-EBW-05-BLAD02-2000005 | ELECTRICAL BUILDER WORK - BLADE-02 (+948.28 , +951.4)- SHEET 5 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Electrical Builder Work | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-EBW-05-BLAD03-2000005 | ELECTRICAL BUILDER WORK - BLADE-03 (+921 , +928 , +935.85 )- SHEET 5 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Electrical Builder Work | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-EBW-05-BLAD04-2000005 | ELECTRICAL BUILDER WORK - BLADE-04 (+941.60, +947.35, +954)- SHEET 5 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Builder Work | QP.E.ME.BL4.GEN.6110 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-EBW-05-BLAD04-2000006 | ELECTRICAL BUILDER WORK - BLADE-04 (+959, +968.30 ,+975.82)- SHEET 6 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Builder Work | QP.E.ME.BL4.GEN.6110 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-EBW-05-BLAD05-2000005 | ELECTRICAL BUILDER WORK - BLADE-05 (+969.30 , +960.09)- SHEET 5 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Electrical Builder Work | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-EBW-05-CENT01-2B10006 | ELECTRICAL BUILDER WORK - B1 SERVICE +900.5M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Electrical Builder Work | QP.E.ME.MBL.GEN.6870 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-EBW-05-CENT01-2B20005 | ELECTRICAL BUILDER WORK - B2 SERVICE +893.5M - SHEET 05 - (04 OF 07) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Builder work | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-EBW-05-CENT01-2L20006 | ELECTRICAL BUILDER WORK - L2- THEATRE STALLS +913M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Builder Work | QP.E.ME.MBL.GEN.6990 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-EBW-05-CENT01-2L30006 | ELECTRICAL BUILDER WORK - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7030 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-EBW-05-CENT01-2L40006 | ELECTRICAL BUILDER WORK - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Builder Work | QP.E.ME.MBL.GEN.7070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-ELC-00-CENT01-7M20008 | CONTAINMENT - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | M2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-EBW-05-CENT01-2L60006 | ELECTRICAL BUILDER WORK - L6- SKY GARDEN +935.85M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-05-CENT01-2M10006 | ELECTRICAL BUILDER WORK - L1-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Electrical Builder Work | QP.E.ME.MBL.GEN.6950 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-11
QF01012-NES-C04518-SDW-ELC-00-CENT01-7M20009 | CONTAINMENT - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - DETAILS - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | M2 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-EBW-06-BLAD01-2000006 | ELECTRICAL BUILDER WORK - BLADE-01 (+962.2, +972.48, & +989)- SHEET 6 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Electrical Builder Work | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 06 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-EBW-06-CENT01-2L20007 | ELECTRICAL BUILDER WORK - L2- THEATRE STALLS +913M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Builder Work | QP.E.ME.MBL.GEN.6990 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 06 | CENT01 | 2 | L2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-EBW-06-CENT01-2L30007 | ELECTRICAL BUILDER WORK - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7030 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 06 | CENT01 | 2 | L3 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-EBW-06-CENT01-2L40007 | ELECTRICAL BUILDER WORK - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Builder Work | QP.E.ME.MBL.GEN.7070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 06 | CENT01 | 2 | L4 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-ELC-00-CENT01-2M20001 | CONTAINMENT - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-EBW-06-CENT01-2L60007 | ELECTRICAL BUILDER WORK - L6- SKY GARDEN +935.85M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Builder Work | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 06 | CENT01 | 2 | L6 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELC-01-CENT01-2M20002 | CONTAINMENT - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-EBW-08-CENT01-2B20006 | ELECTRICAL BUILDER WORK - B2 SERVICE +893.5M - SHEET 08 - (05 OF 07) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Builder work | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-EBW-08-CENT01-2B20010 | ELECTRICAL BUILDER WORK - B2 SERVICE +899M - SHEET 08 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Builder work | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 08 | CENT01 | 2 | B2 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-EBW-09-CENT01-2B20007 | ELECTRICAL BUILDER WORK - B2 SERVICE +893.5M - SHEET 09 - (06 OF 07) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Builder work | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 09 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-EBW-11-CENT01-2B20008 | ELECTRICAL BUILDER WORK - B2 SERVICE +893.5M - SHEET 11 - (07 OF 07) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Builder work | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 11 | CENT01 | 2 | B2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-EFL-00-BLAD01-7000001 | FAÇADE LIGHTING - BLADE-01 - SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-04-15 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD01 | 7 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD01-7000002 | FAÇADE LIGHTING - BLADE-01 - SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-04-15 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD01 | 7 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD01-7000003 | FAÇADE LIGHTING - BLADE-01 - SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-04-15 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD01 | 7 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD02-7000001 | FAÇADE LIGHTING - BLADE-02 - SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-04-08 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD02 | 7 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD02-7000002 | FAÇADE LIGHTING - BLADE-02 - SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-04-08 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD02 | 7 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD02-7000003 | FAÇADE LIGHTING - BLADE-02 - SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-04-08 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD02 | 7 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD03-7000001 | FAÇADE LIGHTING - BLADE-03 - SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-03-31 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD03 | 7 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD03-7000002 | FAÇADE LIGHTING - BLADE-03 - SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-03-31 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD03 | 7 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD03-7000003 | FAÇADE LIGHTING - BLADE-03 - SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-03-31 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD03 | 7 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD04-7000001 | FAÇADE LIGHTING - BLADE-04 - SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-03-25 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD04 | 7 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD04-7000002 | FAÇADE LIGHTING - BLADE-04 - SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-03-25 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD04 | 7 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD04-7000003 | FAÇADE LIGHTING - BLADE-04 - SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-03-25 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD04 | 7 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD05-7000001 | FAÇADE LIGHTING - BLADE-05 - SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-03-18 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD05 | 7 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD05-7000002 | FAÇADE LIGHTING - BLADE-05 - SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-03-18 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD05 | 7 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-EFL-00-BLAD05-7000003 | FAÇADE LIGHTING - BLADE-05 - SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-03-18 | FAÇADE LIGHTING | QP.E.FA.GEN.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | EFL | 00 | BLAD05 | 7 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ELC-02-CENT01-2M20003 | CONTAINMENT - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-03-CENT01-2M20004 | CONTAINMENT - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-04-CENT01-2M20005 | CONTAINMENT - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-05-CENT01-2M20006 | CONTAINMENT - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-00-CENT01-2B10001 | CONTAINMENT - B1 SERVICE +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | Electrical Containment | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELC-00-CENT01-2B20001 | CONTAINMENT - B2 SERVICE +893.5M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-00-CENT01-2B30001 | CONTAINMENT - B3 PROMENADE +887.750M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-07-23 | Electrical Containment | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELC-06-CENT01-2M20007 | CONTAINMENT - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Containment | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 06 | CENT01 | 2 | M2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-00-CENT01-2L20001 | CONTAINMENT - L2- THEATRE STALLS +913M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | Electrical Containment | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELC-00-CENT01-2L30001 | CONTAINMENT - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELC-00-CENT01-2L40001 | CONTAINMENT - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | Electrical Containment | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELP-01-BLAD02-2000001 | EARTHING & LIGHTNING - BLADE-02 (+876.25, +882, +887.75)- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.BL2.GEN.3420 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-29
QF01012-NES-C04518-SDW-ELC-00-CENT01-2L60001 | CONTAINMENT - L6- SKY GARDEN +935.85M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-00-CENT01-2M10001 | CONTAINMENT - L1-UPPER LOBBY MEZZANINE +909M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Electrical Containment | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELP-02-BLAD02-2000002 | EARTHING & LIGHTNING - BLADE-02 (+893.5, +899.25, +905)- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.BL2.GEN.3420 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-29
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B10009 | CONTAINMENT - B1 SERVICE +900.5M - DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-08-27 | Electrical Containment | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B1 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B10010 | CONTAINMENT - B1 SERVICE +900.5M - DETAILS - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-08-27 | Electrical Containment | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B1 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B20009 | CONTAINMENT - B2 SERVICE +893.5M - DETAILS - (01 OF 08) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B2 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B20010 | CONTAINMENT - B2 SERVICE +893.5M - DETAILS - (02 OF 08) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B2 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B20011 | CONTAINMENT - B2 SERVICE +893.5M - DETAILS - (03 OF 08) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B2 | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B20012 | CONTAINMENT - B2 SERVICE +893.5M - DETAILS - (04 OF 08) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B2 | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B20014 | CONTAINMENT - B2 SERVICE +893.5M - DETAILS - (05 OF 08) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B2 | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B20015 | CONTAINMENT - B2 SERVICE +893.5M - DETAILS - (06 OF 08) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B2 | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B20016 | CONTAINMENT - B2 SERVICE +893.5M - DETAILS - (07 OF 08) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B2 | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B20017 | CONTAINMENT - B2 SERVICE +893.5M - DETAILS - (08 OF 08) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B2 | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B30009 | CONTAINMENT - B3 PROMENADE +887.750M - DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-07-23 | Electrical Containment | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B3 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELC-00-CENT01-7B30010 | CONTAINMENT - B3 PROMENADE +887.750M - DETAILS - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-07-23 | Electrical Containment | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | B3 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELP-03-BLAD02-2000003 | EARTHING & LIGHTNING - BLADE-02 (+910.75, +916.5, +922.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.BL2.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 03 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-ELP-01-BLAD03-2000001 | EARTHING & LIGHTNING - BLADE-03 (+847.5, +853.25, +859)- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Earthing & Lightning | QP.E.ME.BL3.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-07
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L20008 | CONTAINMENT - L2- THEATRE STALLS +913M - OVERALL- DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-22 | Electrical Containment | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L20009 | CONTAINMENT - L2- THEATRE STALLS +913M - OVERALL- DETAILS - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-22 | Electrical Containment | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L2 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L30008 | CONTAINMENT - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L3 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L30009 | CONTAINMENT - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - DETAILS - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L3 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L40008 | CONTAINMENT - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-19 | Electrical Containment | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L4 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L40009 | CONTAINMENT - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - DETAILS - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-19 | Electrical Containment | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L4 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELP-02-BLAD03-2000002 | EARTHING & LIGHTNING - BLADE-03 (+867.62, +876.25, +882)- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Earthing & Lightning | QP.E.ME.BL3.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-07
QF01012-NES-C04518-SDW-ELP-03-BLAD03-2000003 | EARTHING & LIGHTNING - BLADE-03 (+887.75, +893.5, +899.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Earthing & Lightning | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 03 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L60008 | CONTAINMENT - L6- SKY GARDEN +935.85M - DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L6 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L60009 | CONTAINMENT - L6- SKY GARDEN +935.85M - DETAILS - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L6 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-00-CENT01-7L80002 | CONTAINMENT - L8 ROYAL MAJLIS +948.28M - DETAILS | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-12-03 | Electrical Containment | QP.E.ME.MBL.GEN.3530 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | L8 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-18
QF01012-NES-C04518-SDW-ELC-00-CENT01-7M10008 | CONTAINMENT - L1-UPPER LOBBY MEZZANINE +909M - DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-01 | Electrical Containment | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | M1 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELC-00-CENT01-7M10009 | CONTAINMENT - L1-UPPER LOBBY MEZZANINE +909M - DETAILS - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-01 | Electrical Containment | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | M1 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELP-04-BLAD03-2000004 | EARTHING & LIGHTNING - BLADE-03 (+905, +910.75, +916.5)- SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Earthing & Lightning | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 04 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-ELP-01-BLAD04-2000001 | EARTHING & LIGHTNING - BLADE-04 (+863.85, +870.5, +876.25)- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Earthing & Lightning | QP.E.ME.BL4.GEN.6030 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-16
QF01012-NES-C04518-SDW-ELC-00-CENT01-7RL0002 | CONTAINMENT - RL ROOF & ABOVE - DETAILS | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-12-24 | Electrical Containment | QP.E.ME.MBL.GEN.3530 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | CENT01 | 7 | RL | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-18
QF01012-NES-C04518-SDW-ELC-00-PARK01-2B10001 | CONTAINMENT - B1 PARKING +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | Electrical Containment | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ELC-00-PARK01-7B10005 | CONTAINMENT - B1 PARKING +900.5M - DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-15 | Electrical Containment | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | PARK01 | 7 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ELC-00-PARK01-7B10006 | CONTAINMENT - B1 PARKING +900.5M - DETAILS - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-15 | Electrical Containment | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 00 | PARK01 | 7 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ELC-01-BLAD01-2000001 | CONTAINMENT - BLADE-01 (+870.5, +882)- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Electrical Containment | QP.E.ME.BL1.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELP-02-BLAD04-2000002 | EARTHING & LIGHTNING - BLADE-04 (+882, +887.75, +893.5)- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Earthing & Lightning | QP.E.ME.BL4.GEN.6030 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-16
QF01012-NES-C04518-SDW-ELP-03-BLAD04-2000003 | EARTHING & LIGHTNING - BLADE-04 (+899.25, +905, +910.75)- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Earthing & Lightning | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 03 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-ELP-00-CENT01-2L10001 | EARTHING & LIGHTNING - L1- LOBBY LEVEL +905M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.6910 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | CENT01 | 2 | L1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-ELP-03-CENT01-2L10004 | EARTHING & LIGHTNING - L1- LOBBY LEVEL +905M - SHEET 04 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.6910 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 03 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-ELC-01-BLAD05-2000001 | CONTAINMENT - BLADE-05 (+894.5, +899.5, +905)- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Electrical Containment | QP.E.ME.BL5.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-14
QF01012-NES-C04518-SDW-ELC-01-BLAD05-2000006 | CONTAINMENT - BLADE-05 (+894.5, +899.5, +905)- SHEET 1- DETAILS | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Electrical Containment | QP.E.ME.BL5.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | BLAD05 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-28
QF01012-NES-C04518-SDW-ELC-01-CENT01-2B10002 | CONTAINMENT - B1 SERVICE +900.5M - SHEET 01 - (01 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Electrical Containment | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELC-01-CENT01-2B20002 | CONTAINMENT - B2 SERVICE +893.5M - SHEET 01 - (01 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-01-CENT01-2B30002 | CONTAINMENT - B3 PROMENADE +887.750M - SHEET 01 - (01 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Electrical Containment | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELP-04-CENT01-2L10005 | EARTHING & LIGHTNING - L1- LOBBY LEVEL +905M - SHEET 05 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.6910 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 04 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-ELC-01-CENT01-2L20002 | CONTAINMENT - L2- THEATRE STALLS +913M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Containment | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELC-01-CENT01-2L30002 | CONTAINMENT - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELC-01-CENT01-2L40002 | CONTAINMENT - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Containment | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELP-00-CENT01-2L50001 | EARTHING & LIGHTNING - L5- SECOND CIRCLE & LOFT +928M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-ELC-01-CENT01-2L60002 | CONTAINMENT - L6- SKY GARDEN +935.85M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-01-CENT01-2M10002 | CONTAINMENT - L1-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Electrical Containment | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELP-01-CENT01-2L50002 | EARTHING & LIGHTNING - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-ELC-01-PARK01-2B10002 | CONTAINMENT - B1 PARKING +900.5M - SHEET 01 - (01 OF 03) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Electrical Containment | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 01 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ELC-02-BLAD01-2000002 | CONTAINMENT - BLADE-01 (+887.75, +893.5, +899.25)- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Electrical Containment | QP.E.ME.BL1.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELP-02-CENT01-2L50003 | EARTHING & LIGHTNING - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-ELP-03-CENT01-2L50004 | EARTHING & LIGHTNING - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 03 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-ELP-04-CENT01-2L50005 | EARTHING & LIGHTNING - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 04 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-ELC-02-BLAD05-2000002 | CONTAINMENT - BLADE-05 (+910.75, +917.5, +922.25)- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Electrical Containment | QP.E.ME.BL5.GEN.1580 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-08
QF01012-NES-C04518-SDW-ELC-02-CENT01-2B10003 | CONTAINMENT - B1 SERVICE +900.5M - SHEET 02 - (02 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Electrical Containment | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELC-02-CENT01-2B20003 | CONTAINMENT - B2 SERVICE +893.5M - SHEET 02 - (02 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-02-CENT01-2B30003 | CONTAINMENT - B3 PROMENADE +887.750M - SHEET 02 - (02 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Electrical Containment | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELP-05-CENT01-2L50006 | EARTHING & LIGHTNING - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-ELC-02-CENT01-2L20003 | CONTAINMENT - L2- THEATRE STALLS +913M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Containment | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELC-02-CENT01-2L30003 | CONTAINMENT - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELC-02-CENT01-2L40003 | CONTAINMENT - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Containment | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELP-06-CENT01-2L50007 | EARTHING & LIGHTNING - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 06 | CENT01 | 2 | L5 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-ELC-02-CENT01-2L60003 | CONTAINMENT - L6- SKY GARDEN +935.85M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-02-CENT01-2M10003 | CONTAINMENT - L1-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Electrical Containment | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELP-00-CENT01-2M20001 | EARTHING & LIGHTNING - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELC-02-PARK01-2B10003 | CONTAINMENT - B1 PARKING +900.5M - SHEET 02 - (02 OF 03) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Electrical Containment | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 02 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ELC-03-BLAD01-2000003 | CONTAINMENT - BLADE-01 (+905, +910.75, +917.5)- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Electrical Containment | QP.E.ME.BL1.GEN.2970 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-27
QF01012-NES-C04518-SDW-ELP-01-CENT01-2M20002 | EARTHING & LIGHTNING - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (01 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELP-02-CENT01-2M20003 | EARTHING & LIGHTNING - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (02 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELP-03-CENT01-2M20004 | EARTHING & LIGHTNING - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (03 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 03 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELC-03-BLAD05-2000003 | CONTAINMENT - BLADE-05 (+928, +935.85, +941.60)- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Electrical Containment | QP.E.ME.BL5.GEN.1580 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-08
QF01012-NES-C04518-SDW-ELC-03-CENT01-2B30004 | CONTAINMENT - B3 PROMENADE +887.750M - SHEET 03 - (03 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Electrical Containment | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | CENT01 | 2 | B3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELC-03-CENT01-2L20004 | CONTAINMENT - L2- THEATRE STALLS +913M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Containment | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELC-03-CENT01-2L30004 | CONTAINMENT - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELC-03-CENT01-2L40004 | CONTAINMENT - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Containment | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELP-05-CENT01-2M20006 | EARTHING & LIGHTNING - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (04 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELC-03-CENT01-2L60004 | CONTAINMENT - L6- SKY GARDEN +935.85M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELP-06-CENT01-2M20007 | EARTHING & LIGHTNING - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (05 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Earthing & Lightning | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 06 | CENT01 | 2 | M2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELC-03-PARK01-2B10004 | CONTAINMENT - B1 PARKING +900.5M - SHEET 03 - (03 OF 03) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Electrical Containment | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 03 | PARK01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ELC-04-BLAD01-2000004 | CONTAINMENT - BLADE-01 (+922.25, +928, & +935.85)- SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Electrical Containment | QP.E.ME.BL1.GEN.2970 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-27
QF01012-NES-C04518-SDW-ELC-04-BLAD02-2000004 | CONTAINMENT - BLADE-02 (+928, +935.85, +941.6)- SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Electrical Containment | QP.E.ME.BL2.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-27
QF01012-NES-C04518-SDW-EBW-01-BLAD02-2000001 | ELECTRICAL BUILDER WORK - BLADE-02 (+876.25, +882, +887.75)- SHEET 1 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder Work | QP.E.ME.BL2.GEN.3420 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-29
QF01012-NES-C04518-SDW-ELC-04-BLAD04-2000004 | CONTAINMENT - BLADE-04 (+916.5, +922.25, +928)- SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Containment | QP.E.ME.BL4.GEN.2940 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-15
QF01012-NES-C04518-SDW-ELC-04-BLAD05-2000004 | CONTAINMENT - BLADE-05 (+948.10, +954, +957.35)- SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Electrical Containment | QP.E.ME.BL5.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-28
QF01012-NES-C04518-SDW-ELC-04-CENT01-2B10005 | CONTAINMENT - B1 SERVICE +900.5M - SHEET 04 - (03 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Electrical Containment | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELC-04-CENT01-2B20004 | CONTAINMENT - B2 SERVICE +893.5M - SHEET 04 - (03 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-04-CENT01-2B30005 | CONTAINMENT - B3 PROMENADE +887.750M - SHEET 04 - (04 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Electrical Containment | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | CENT01 | 2 | B3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-EBW-02-BLAD02-2000002 | ELECTRICAL BUILDER WORK - BLADE-02 (+893.5, +899.25, +905)- SHEET 2 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder Work | QP.E.ME.BL2.GEN.3420 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-29
QF01012-NES-C04518-SDW-ELC-04-CENT01-2L20005 | CONTAINMENT - L2- THEATRE STALLS +913M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Containment | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELC-04-CENT01-2L30005 | CONTAINMENT - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELC-04-CENT01-2L40005 | CONTAINMENT - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Containment | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-EBW-03-BLAD02-2000003 | ELECTRICAL BUILDER WORK - BLADE-02 (+910.75, +916.5, +922.25)- SHEET 3 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder Work | QP.E.ME.BL2.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-ELC-04-CENT01-2L60005 | CONTAINMENT - L6- SKY GARDEN +935.85M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-04-CENT01-2M10005 | CONTAINMENT - L1-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Electrical Containment | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 04 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-EBW-01-BLAD03-2000001 | ELECTRICAL BUILDER WORK - BLADE-03 (+847.5, +853.25, +859)- SHEET 1 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Electrical Builder Work | QP.E.ME.BL3.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-07
QF01012-NES-C04518-SDW-ELC-05-BLAD01-2000005 | CONTAINMENT - BLADE-01 (+941.6, ROOF, & +958.45)- SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Electrical Containment | QP.E.ME.BL1.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-15
QF01012-NES-C04518-SDW-ELC-05-BLAD02-2000005 | CONTAINMENT - BLADE-02 (+948.28 , +951.4)- SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Electrical Containment | QP.E.ME.BL2.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-29
QF01012-NES-C04518-SDW-ELC-05-BLAD03-2000005 | CONTAINMENT - BLADE-03 (+921 , +928 , +935.85 )- SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Electrical Containment | QP.E.ME.BL3.GEN.1820 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-11
QF01012-NES-C04518-SDW-ELC-05-BLAD04-2000005 | CONTAINMENT - BLADE-04 (+935.85, +941.60, +947.35)- SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Containment | QP.E.ME.BL4.GEN.2840 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELC-05-BLAD04-2000006 | CONTAINMENT - BLADE-04 (+954,+959, +968.30 ,+975.82)- SHEET 6 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Containment | QP.E.ME.BL4.GEN.2840 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELC-05-BLAD05-2000005 | CONTAINMENT - BLADE-05 (+969.30 , +960.09)- SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Electrical Containment | QP.E.ME.BL5.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-28
QF01012-NES-C04518-SDW-ELC-05-CENT01-2B10006 | CONTAINMENT - B1 SERVICE +900.5M - SHEET 05 - (04 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Electrical Containment | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELC-05-CENT01-2B20005 | CONTAINMENT - B2 SERVICE +893.5M - SHEET 05 - (04 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-05-CENT01-2B30006 | CONTAINMENT - B3 PROMENADE +887.750M - SHEET 05 - (05 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Electrical Containment | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | CENT01 | 2 | B3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-EBW-02-BLAD03-2000002 | ELECTRICAL BUILDER WORK - BLADE-03 (+867.62, +876.25, +882)- SHEET 2 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Electrical Builder Work | QP.E.ME.BL3.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-07
QF01012-NES-C04518-SDW-ELC-05-CENT01-2L20006 | CONTAINMENT - L2- THEATRE STALLS +913M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Containment | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELC-05-CENT01-2L30006 | CONTAINMENT - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELC-05-CENT01-2L40006 | CONTAINMENT - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Containment | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-EBW-03-BLAD03-2000003 | ELECTRICAL BUILDER WORK - BLADE-03 (+887.75, +893.5, +899.25)- SHEET 3 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Electrical Builder Work | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-ELC-05-CENT01-2L60006 | CONTAINMENT - L6- SKY GARDEN +935.85M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-05-CENT01-2M10006 | CONTAINMENT - L1-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Electrical Containment | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 05 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-EBW-04-BLAD03-2000004 | ELECTRICAL BUILDER WORK - BLADE-03 (+905, +910.75, +916.5)- SHEET 4 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Electrical Builder Work | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-ELC-06-BLAD01-2000006 | CONTAINMENT - BLADE-01 (+962.2, +972.48, & +989)- SHEET 6 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Electrical Containment | QP.E.ME.BL1.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 06 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-15
QF01012-NES-C04518-SDW-ELC-06-CENT01-2B30007 | CONTAINMENT - B3 PROMENADE +887.750M - SHEET 06 - (06 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Electrical Containment | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 06 | CENT01 | 2 | B3 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELC-06-CENT01-2L20007 | CONTAINMENT - L2- THEATRE STALLS +913M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Electrical Containment | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 06 | CENT01 | 2 | L2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELC-06-CENT01-2L30007 | CONTAINMENT - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 06 | CENT01 | 2 | L3 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELC-06-CENT01-2L40007 | CONTAINMENT - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Electrical Containment | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 06 | CENT01 | 2 | L4 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-EBW-01-BLAD04-2000001 | ELECTRICAL BUILDER WORK - BLADE-04 (+863.85, +870.5, +876.25)- SHEET 1 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Electrical Builder Work | QP.E.ME.BL4.GEN.6030 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-16
QF01012-NES-C04518-SDW-ELC-06-CENT01-2L60007 | CONTAINMENT - L6- SKY GARDEN +935.85M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Electrical Containment | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 06 | CENT01 | 2 | L6 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELC-06-CENT01-2L80001 | CONTAINMENT - L8 ROYAL MAJLIS +948.28M - SHEET 01 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | Electrical Containment | QP.E.ME.MBL.GEN.3530 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 06 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-18
QF01012-NES-C04518-SDW-EBW-02-BLAD04-2000002 | ELECTRICAL BUILDER WORK - BLADE-04 (+882, +887.75, +893.5)- SHEET 2 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Electrical Builder Work | QP.E.ME.BL4.GEN.6030 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-16
QF01012-NES-C04518-SDW-ELC-06-CENT01-2RL0001 | CONTAINMENT - RL ROOF & ABOVE - SHEET 01 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | Electrical Containment | QP.E.ME.MBL.GEN.3530 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 06 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-18
QF01012-NES-C04518-SDW-ELC-07-CENT01-2B20013 | CONTAINMENT - B2 SERVICE +893.5M - SHEET 07 - (05 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 07 | CENT01 | 2 | B2 | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-08-CENT01-2B20006 | CONTAINMENT - B2 SERVICE +893.5M - SHEET 08 - (06 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-09-CENT01-2B20007 | CONTAINMENT - B2 SERVICE +893.5M - SHEET 09 - (07 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Electrical Containment | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 09 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELC-11-CENT01-2B10011 | CONTAINMENT - B1 SERVICE +900.5M - SHEET 11 - (05 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Electrical Containment | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 11 | CENT01 | 2 | B1 | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELC-11-CENT01-2B30008 | CONTAINMENT - B3 PROMENADE +887.750M - SHEET 11 - (07 OF 07) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Electrical Containment | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELC | 11 | CENT01 | 2 | B3 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELE-00-BLAD01-6ZZ0001 | ELECTRICAL DB SCHEDULE – BLADE-01- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD01 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD01-6ZZ0002 | ELECTRICAL DB SCHEDULE – BLADE-01- 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD01 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD01-6ZZ0003 | ELECTRICAL DB SCHEDULE – BLADE-01- 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD01 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD01-6ZZ0004 | ELECTRICAL CBS SCHEDULE – BLADE-01- 01 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL CBS SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD01 | 6 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD03-6ZZ0001 | ELECTRICAL DB SCHEDULE – BLADE-03- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD03 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD03-6ZZ0002 | ELECTRICAL DB SCHEDULE – BLADE-03- 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD03 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD03-6ZZ0003 | ELECTRICAL DB SCHEDULE – BLADE-03- 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD03 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD04-6ZZ0001 | ELECTRICAL DB SCHEDULE – BLADE-04- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD04 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD04-6ZZ0002 | ELECTRICAL DB SCHEDULE – BLADE-04- 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD04 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD04-6ZZ0003 | ELECTRICAL DB SCHEDULE – BLADE-04- 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD04 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD05-6ZZ0001 | ELECTRICAL DB SCHEDULE – BLADE-05- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD05 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD05-6ZZ0002 | ELECTRICAL DB SCHEDULE – BLADE-05- 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD05 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD05-6ZZ0003 | ELECTRICAL DB SCHEDULE – BLADE-05- 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD05 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-2000001 | POWER SYSTEM - GANTRY LEVELS (+924.5 & +928) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-CENT01-2000002 | POWER SYSTEM - GANTRY LEVELS (+931.1 & +934.2) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-CENT01-2B10001 | MECHANICAL POWER SYSTEM - B1 SERVICE +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-00-CENT01-2B20001 | MECHANICAL POWER SYSTEM - B2 SERVICE +893.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-00-CENT01-2B30001 | MECHANICAL POWER SYSTEM - B3 PROMENADE +887.750M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-07-23 | Mechanical Power | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-EBW-03-BLAD04-2000003 | ELECTRICAL BUILDER WORK - BLADE-04 (+899.25, +910.75, +916.5)- SHEET 3 | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Electrical Builder Work | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-ELE-00-CENT01-2L20001 | MECHANICAL POWER SYSTEM - L2- THEATRE STALLS +913M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-00-CENT01-2L30001 | MECHANICAL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-00-CENT01-2L40001 | MECHANICAL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-EBW-00-CENT01-2L10001 | ELECTRICAL BUILDER WORK - L1- LOBBY LEVEL +905M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Electrical Builder Work | QP.E.ME.MBL.GEN.6910 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 2 | L1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-ELE-00-CENT01-2L60001 | MECHANICAL POWER SYSTEM - L6- SKY GARDEN +935.85M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-00-CENT01-2M10001 | MECHANICAL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-01 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-EBW-01-CENT01-2L10002 | ELECTRICAL BUILDER WORK - L1- LOBBY LEVEL +905M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder Work | QP.E.ME.MBL.GEN.6910 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0001 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0002 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0003 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0004 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 04 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0005 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 05 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0006 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 06 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-EBW-02-CENT01-2L10003 | ELECTRICAL BUILDER WORK - L1- LOBBY LEVEL +905M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder Work | QP.E.ME.MBL.GEN.6910 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-EBW-03-CENT01-2L10004 | ELECTRICAL BUILDER WORK - L1- LOBBY LEVEL +905M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder Work | QP.E.ME.MBL.GEN.6910 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-EBW-04-CENT01-2L10005 | ELECTRICAL BUILDER WORK - L1- LOBBY LEVEL +905M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder Work | QP.E.ME.MBL.GEN.6910 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-EBW-00-CENT01-2L50001 | ELECTRICAL BUILDER WORK - L5- SECOND CIRCLE & LOFT +928M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-EBW-00-CENT01-3L50008 | ELECTRICAL BUILDER WORK - L5- SECOND CIRCLE & LOFT +928M - SECTIONS | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-17 | Electrical Builder Work | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 3 | L5 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-EBW-01-CENT01-2L50002 | ELECTRICAL BUILDER WORK - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-EBW-02-CENT01-2L50003 | ELECTRICAL BUILDER WORK - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-EBW-03-CENT01-2L50004 | ELECTRICAL BUILDER WORK - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-EBW-04-CENT01-2L50005 | ELECTRICAL BUILDER WORK - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-EBW-05-CENT01-2L50006 | ELECTRICAL BUILDER WORK - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-EBW-06-CENT01-2L50007 | ELECTRICAL BUILDER WORK - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7110 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 06 | CENT01 | 2 | L5 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-EBW-00-CENT01-2M20001 | ELECTRICAL BUILDER WORK - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - OVERALL | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0019 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 19 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0019 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0020 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 20 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0020 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0021 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 21 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0021 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0022 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 22 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0022 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0023 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 23 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0023 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0024 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 24 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0024 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0025 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 25 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0025 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0026 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 26 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0026 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0027 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 27 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0027 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0028 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 28 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0028 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0029 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 29 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0029 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0030 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 30 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0030 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0031 | ELECTRICAL CBS SCHEDULE – CENTER BLOCK - 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL CBS SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0031 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0032 | ELECTRICAL CBS SCHEDULE – CENTER BLOCK - 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL CBS SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0032 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-GARD01-2000001 | POWER SYSTEM - GUARD ROOM | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-17 | Power | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | GARD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELE-00-GARD01-6ZZ0001 | ELECTRICAL DB SCHEDULE – GUARD HOUSE- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-12-15 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | GARD01 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-PARK01-2B10001 | MECHANICAL POWER SYSTEM - B1 PARKING +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | Mechanical Power | QP.E.ME.PAR.GEN.1419 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ELE-00-PARK01-6ZZ0001 | ELECTRICAL DB SCHEDULE – PARKING- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-20 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | PARK01 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-PARK01-6ZZ0002 | ELECTRICAL DB SCHEDULE – PARKING- 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-20 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | PARK01 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-PARK01-6ZZ0003 | ELECTRICAL DB SCHEDULE – PARKING- 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-20 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | PARK01 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-SECE001-4ZZ0001 | ELECTRICAL ENLARGED PLAN-SEC MRMU-SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_71 | QF01012 | NES | C04518 | SDW | ELE | 00 | SECE001 | 4 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ELE-00-SECE001-4ZZ0002 | ELECTRICAL ENLARGED PLAN-SEC MRMU-SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_72 | QF01012 | NES | C04518 | SDW | ELE | 00 | SECE001 | 4 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ELE-00-SECE01-2000001 | POWER SYSTEM - SEC ROOM | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-17 | Power | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | SECE01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELE-00-SECE01-6ZZ0001 | ELECTRICAL DB SCHEDULE – SEC ROOM- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-12-15 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | SECE01 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-Z00000-0ZZ0001 | ELECTRICAL STANDARD INSTALLATION DETAILS SHEET 1 | [5 empty] | 2026-08-30 | ELECTRICAL INSTALLATION DETAILS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 0 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-0ZZ0002 | ELECTRICAL STANDARD INSTALLATION DETAILS SHEET 2 | [5 empty] | 2026-08-31 | ELECTRICAL INSTALLATION DETAILS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 0 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-0ZZ0003 | ELECTRICAL STANDARD INSTALLATION DETAILS SHEET 3 | [5 empty] | 2026-08-30 | ELECTRICAL INSTALLATION DETAILS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 0 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-EBW-00-CENT01-3M20008 | ELECTRICAL BUILDER WORK - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SECTIONS | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-17 | Electrical Builder Work | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 00 | CENT01 | 3 | M2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-01-CENT01-2M20002 | ELECTRICAL BUILDER WORK - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-02-CENT01-2M20003 | ELECTRICAL BUILDER WORK - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 02 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-03-CENT01-2M20004 | ELECTRICAL BUILDER WORK - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 03 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-04-CENT01-2M20005 | ELECTRICAL BUILDER WORK - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 04 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-05-CENT01-2M20006 | ELECTRICAL BUILDER WORK - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 05 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-06-CENT01-2M20007 | ELECTRICAL BUILDER WORK - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-EBW-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Electrical Builder work | QP.E.ME.MBL.GEN.7150 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 06 | CENT01 | 2 | M2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0001 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-15 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0002 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-15 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0003 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0004 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0007 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 07 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0008 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 08 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0009 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 09 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0009 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0010 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 10 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0010 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0011 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 11 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0011 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0012 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 12 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0012 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0013 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 13 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0013 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0014 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 14 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0014 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0015 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 15 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0015 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0016 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 16 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0016 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0017 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 17 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0017 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0018 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 18 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0018 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10008 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_UPS ROOM_(Z00-B01-116) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_51 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20006 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_LV PANEL RM_(Z00-B02-007) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_52 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50005 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELE.CP.R_(Z00-L05-322) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50006 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELE.CP.R_(Z00-L05-323) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50003 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELE.CP.R_(Z00-L05-368) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50004 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELE.CP.R_(Z00-L05-378) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0030 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:500 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0030 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0031 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 01 - (01 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0031 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0032 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 02 - (02 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0032 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0033 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 03 - (03 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0033 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0034 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 04 - (04 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0034 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0035 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 05 - (05 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0035 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0036 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 06 - (06 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0036 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0037 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 07 - (07 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0037 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0038 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 08 - (08 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0038 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0039 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 09 - (09 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0039 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0040 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 10 - (10 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0040 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0041 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 11 - (11 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0041 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0042 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 12 - (12 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0042 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0043 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 13 - (13 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0043 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0044 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 14 - (14 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0044 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0045 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 15 - (15 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0045 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0046 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 16 - (16 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0046 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0047 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 17 - (17 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0047 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0048 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 18 - (18 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0048 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0049 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 19 - (19 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0049 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0050 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 20 - (20 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0050 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0051 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 21 - (21 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0051 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0052 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 22 - (22 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0052 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0053 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 23 - (23 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0053 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0054 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 24 - (24 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0054 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0055 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 25 - (25 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0055 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0056 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 26 - (26 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0056 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0057 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 27 - (27 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0057 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0058 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 28 - (28 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0058 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-5ZZ0059 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - DETAILS - (1 OF 2) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 5 | ZZ | 0059 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-5ZZ0060 | POWER SYSTEM - LOBBY LEVEL LANDSCAPE +905M - DETAILS - (1 OF 2) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-12 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 5 | ZZ | 0060 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0001 | MV - SCHEMATIC DIAGRAM |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0002 | LV - SCHEMATIC DIAGRAM FOR TX-01 & TX-02 - SHEET 01 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0003 | LV - SCHEMATIC DIAGRAM FOR TX-03 & TX-04 - SHEET 02 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0004 | LV - SCHEMATIC DIAGRAM FOR TX-05 & TX-06 - SHEET 03 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0005 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 04 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0006 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 05 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0007 | LV - SCHEMATIC DIAGRAM FOR TX-09 - SHEET 06 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0008 | LV - SCHEMATIC DIAGRAM FOR TX-10 - SHEET 07 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0009 | LV - SCHEMATIC DIAGRAM FOR TX-10 - SHEET 08 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0009 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0010 | LV - SCHEMATIC DIAGRAM FOR TX-11 - SHEET 09 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0010 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0011 | LV - SCHEMATIC DIAGRAM FOR TX-01 & TX-02 - SHEET 10 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0011 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0012 | LV - SCHEMATIC DIAGRAM FOR TX-03 & TX-04 - SHEET 11 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0012 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0013 | LV - SCHEMATIC DIAGRAM FOR TX-05 & TX-06 - SHEET 12 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0013 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0014 | LV - SCHEMATIC DIAGRAM FOR TX-05 & TX-06 - SHEET 13 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0014 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0015 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 14 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0015 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0016 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 15 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0016 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0017 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 16 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0017 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0018 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 17 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0018 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0019 | LV - SCHEMATIC DIAGRAM FOR TX-09 - SHEET 18 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0019 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0020 | LV - SCHEMATIC DIAGRAM FOR TX-09 - SHEET 19 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0020 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0021 | LV - SCHEMATIC DIAGRAM FOR TX-09 - SHEET 20 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0021 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0022 | LV - SCHEMATIC DIAGRAM FOR TX-09 - SHEET 21 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0022 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0023 | LV - SCHEMATIC DIAGRAM FOR TX-10 - SHEET 22 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0023 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0024 | LV - SCHEMATIC DIAGRAM FOR TX-10 - SHEET 23 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0024 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0025 | LV - SCHEMATIC DIAGRAM FOR TX-10 - SHEET 24 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0025 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0026 | LV - SCHEMATIC DIAGRAM FOR TX-11 - SHEET 25 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0026 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0027 | LV - SCHEMATIC DIAGRAM FOR TX-11 - SHEET 26 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0027 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0028 | LV - SCHEMATIC DIAGRAM FOR TX-11 - SHEET 27 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0028 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0029 | LV - SCHEMATIC DIAGRAM FOR MFM DETAIL - SHEET 28 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0029 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0040 | MV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0040 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0041 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-01 - SHEET 01 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0041 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0042 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-02 - SHEET 02 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0042 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0043 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-03 - SHEET 03 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0043 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0044 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-04 - SHEET 04 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0044 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0045 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-05 - SHEET 05 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0045 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0046 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-06 - SHEET 06 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0046 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0047 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-07 - SHEET 07 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0047 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0048 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-08 - SHEET 08 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0048 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0049 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-09 - SHEET 09 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0049 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0050 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-09 - SHEET 10 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0050 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0051 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-10 - SHEET 11 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0051 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0052 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-10 - SHEET 12 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0052 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0053 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-11 - SHEET 13 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0053 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-01-CENT01-2B10002 | MECHANICAL POWER SYSTEM - B1 SERVICE +900.5M - SHEET 01 - (01 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-01-CENT01-2B20002 | MECHANICAL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 01 - (01 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-01-CENT01-2B30002 | MECHANICAL POWER SYSTEM - B3 PROMENADE +887.750M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Mechanical Power | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50007 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELE.RIS_(Z00-L04-382) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-ELE-01-CENT01-2L20002 | MECHANICAL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-01-CENT01-2L30002 | MECHANICAL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-01-CENT01-2L40002 | MECHANICAL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4B30004 | ELECTRICAL ENLARGED PLAN-BLADE-4_ELE.RIS_(Z00-B03-452A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | B3 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-ELE-01-CENT01-2L60002 | MECHANICAL POWER SYSTEM - L6- SKY GARDEN +935.85M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-01-CENT01-2M10002 | MECHANICAL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L80001 | ELECTRICAL ENLARGED PLAN-L8 ROYAL MAJLIS+948.28M_UPS_(Z00-L08-054) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_81 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L8 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ELE-01-PARK01-2B10002 | MECHANICAL POWER SYSTEM - B1 PARKING +900.5M - SHEET 01 - (01 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Mechanical Power | QP.E.ME.PAR.GEN.1419 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ELE-02-CENT01-2B10003 | MECHANICAL POWER SYSTEM - B1 SERVICE +900.5M - SHEET 02 - (02 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-02-CENT01-2B20003 | MECHANICAL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 02 - (02 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-02-CENT01-2B30003 | MECHANICAL POWER SYSTEM - B3 PROMENADE +887.750M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Mechanical Power | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-ELS-01-BLAD03-2000001 | EMERGENCY LIGHTING - BLADE-03 (+847.5, +853.25, +859)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Emergency Lighting | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ELE-02-CENT01-2L20003 | MECHANICAL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-02-CENT01-2L30003 | MECHANICAL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-02-CENT01-2L40003 | MECHANICAL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-02-BLAD03-2000002 | EMERGENCY LIGHTING - BLADE-03 (+867.62, +876.25, +882)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Emergency Lighting | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ELE-02-CENT01-2L60003 | MECHANICAL POWER SYSTEM - L6- SKY GARDEN +935.85M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-02-CENT01-2M10003 | MECHANICAL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-03-BLAD03-2000003 | EMERGENCY LIGHTING - BLADE-03 (+887.75, +893.5, +899.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Emergency Lighting | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ELE-02-PARK01-2B10003 | MECHANICAL POWER SYSTEM - B1 PARKING +900.5M - SHEET 02 - (02 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Mechanical Power | QP.E.ME.PAR.GEN.1419 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ELE-03-CENT01-2B10004 | MECHANICAL POWER SYSTEM - B1 SERVICE +900.5M - SHEET 04 - (03 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 03 | CENT01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-04-BLAD03-2000004 | EMERGENCY LIGHTING - BLADE-03 (+905, +910.75, +916.5)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Emergency Lighting | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ELE-03-CENT01-2L20004 | MECHANICAL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 03 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-03-CENT01-2L30004 | MECHANICAL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 03 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-03-CENT01-2L40004 | MECHANICAL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 03 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-01-BLAD04-2000001 | EMERGENCY LIGHTING - BLADE-04 (+863.85, +870.5, +876.25)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Emergency Lighting | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-23
QF01012-NES-C04518-SDW-ELE-03-CENT01-2L60004 | MECHANICAL POWER SYSTEM - L6- SKY GARDEN +935.85M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 03 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-03-CENT01-2M10004 | MECHANICAL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 03 | CENT01 | 2 | M1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-02-BLAD04-2000002 | EMERGENCY LIGHTING - BLADE-04 (+882, +887.75, +893.5)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Emergency Lighting | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-23
QF01012-NES-C04518-SDW-ELE-03-PARK01-2B10004 | MECHANICAL POWER SYSTEM - B1 PARKING +900.5M - SHEET 03 - (03 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Mechanical Power | QP.E.ME.PAR.GEN.1419 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 03 | PARK01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ELE-04-CENT01-2B10005 | MECHANICAL POWER SYSTEM - B1 SERVICE +900.5M - SHEET 05 - (04 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 04 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-04-CENT01-2B20004 | MECHANICAL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 04 - (03 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 04 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-03-BLAD04-2000003 | EMERGENCY LIGHTING - BLADE-04 (+899.25, +905, +910.75)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Emergency Lighting | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-23
QF01012-NES-C04518-SDW-ELE-04-CENT01-2L20005 | MECHANICAL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 04 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-04-CENT01-2L30005 | MECHANICAL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 04 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-04-CENT01-2L40005 | MECHANICAL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 04 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-01-BLAD02-2000001 | EMERGENCY LIGHTING SYSTEM - BLADE-02 (+876.25, +882, +887.75)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-ELE-04-CENT01-2L60005 | MECHANICAL POWER SYSTEM - L6- SKY GARDEN +935.85M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 04 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-04-CENT01-2M10005 | MECHANICAL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 04 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-02-BLAD02-2000002 | EMERGENCY LIGHTING SYSTEM - BLADE-02 (+893.5, +899.25, +905)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-ELE-05-CENT01-2B10006 | MECHANICAL POWER SYSTEM - B1 SERVICE +900.5M - SHEET 07 - (05 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 05 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-05-CENT01-2B20005 | MECHANICAL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 05 - (04 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 05 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-05-CENT01-2B30004 | MECHANICAL POWER SYSTEM - B3 PROMENADE +887.750M - SHEET 05 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Mechanical Power | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 05 | CENT01 | 2 | B3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-ELS-03-BLAD02-2000003 | EMERGENCY LIGHTING SYSTEM - BLADE-02 (+910.75, +916.5, +922.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-ELE-05-CENT01-2L20006 | MECHANICAL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 05 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-05-CENT01-2L30006 | MECHANICAL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 05 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-05-CENT01-2L40006 | MECHANICAL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 05 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-00-CENT01-2L10005 | EMERGENCY LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-05-CENT01-2L60006 | MECHANICAL POWER SYSTEM - L6- SKY GARDEN +935.85M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 05 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-05-CENT01-2M10006 | MECHANICAL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 05 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-01-CENT01-2L10002 | EMERGENCY LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-06-CENT01-2B10007 | MECHANICAL POWER SYSTEM - B1 SERVICE +900.5M - SHEET 08 - (06 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 06 | CENT01 | 2 | B1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-02-CENT01-2L10003 | EMERGENCY LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-06-CENT01-2L20007 | MECHANICAL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 06 | CENT01 | 2 | L2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-06-CENT01-2L30007 | MECHANICAL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 06 | CENT01 | 2 | L3 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-06-CENT01-2L40007 | MECHANICAL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 06 | CENT01 | 2 | L4 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-03-CENT01-2L10004 | EMERGENCY LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-06-CENT01-2L60007 | MECHANICAL POWER SYSTEM - L6- SKY GARDEN +935.85M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 06 | CENT01 | 2 | L6 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-06-CENT01-2L80001 | MECHANICAL POWER SYSTEM - L8 ROYAL MAJLIS +948.28M - SHEET 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 06 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-06-CENT01-2M10007 | MECHANICAL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 06 | CENT01 | 2 | M1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-04-CENT01-2L10005 | EMERGENCY LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-06-CENT01-2RL0001 | MECHANICAL POWER SYSTEM - RL ROOF & ABOVE - SHEET 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 06 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-07-CENT01-2B10008 | MECHANICAL POWER SYSTEM - B1 SERVICE +900.5M - SHEET 09 - (07 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 07 | CENT01 | 2 | B1 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-08-CENT01-2B20006 | MECHANICAL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 08 - (05 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-09-CENT01-2B20007 | MECHANICAL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 07 - (06 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 09 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-11-CENT01-2B20008 | MECHANICAL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 11 - (07 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 11 | CENT01 | 2 | B2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-11-CENT01-2B30005 | MECHANICAL POWER SYSTEM - B3 PROMENADE +887.750M - SHEET 11 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Mechanical Power | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 11 | CENT01 | 2 | B3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-ELL-00-CENT01-2000001 | LIGHTING SYSTEM - GANTRY LEVELS (+924.5 & +928) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.3530 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-18
QF01012-NES-C04518-SDW-ELL-00-CENT01-2000002 | LIGHTING SYSTEM - GANTRY LEVELS (+931.1 & +934.2) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.3530 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-18
QF01012-NES-C04518-SDW-ELL-00-CENT01-2B10001 | LIGHTING SYSTEM - B1 SERVICE +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | Lighting | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELL-00-CENT01-2B20001 | LIGHTING SYSTEM - B2 SERVICE +893.5M LIGHTING SYSTEM - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | Lighting | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELL-00-CENT01-2B30001 | LIGHTING SYSTEM - B3 PROMENADE +887.750M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-07-16 | Lighting | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELS-00-CENT01-2L50001 | EMERGENCY LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELL-00-CENT01-2L20001 | LIGHTING SYSTEM - L2- THEATRE STALLS +913M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | Lighting | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELL-00-CENT01-2L30001 | LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELL-00-CENT01-2L40001 | LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | Lighting | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELS-01-CENT01-2L50002 | EMERGENCY LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELL-00-CENT01-2L60001 | LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELL-00-CENT01-2M10001 | LIGHTING SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-01 | Lighting | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELS-02-CENT01-2L50003 | EMERGENCY LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELL-00-GARD01-2000001 | LIGHTING SYSTEM - GUARD ROOM | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-17 | Lighting | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | GARD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELL-00-PARK01-2B10001 | LIGHTING SYSTEM - B1 PARKING +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | Lighting | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ELL-00-SECE01-2000001 | LIGHTING SYSTEM - SEC ROOM | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-17 | Lighting | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | SECE01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0001 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:500 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0002 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 01 - (01 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0003 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 02 - (02 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0004 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 03 - (03 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0005 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 04 - (04 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0006 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 05 - (05 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0007 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 06 - (06 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0008 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 07 - (07 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0009 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 08 - (08 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0010 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 09 - (09 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0011 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 10 - (10 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0012 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 11 - (11 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0013 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 12 - (12 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0014 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 13 - (13 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0015 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 14 - (14 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0016 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 15 - (15 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0017 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 16 - (16 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0018 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 17 - (17 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0018 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0019 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 18 - (18 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0019 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0020 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 19 - (19 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0020 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0021 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 20 - (20 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0021 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0022 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 21 - (21 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0022 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0023 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 22 - (22 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0023 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0024 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 23 - (23 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0024 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0025 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 24 - (24 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0025 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0026 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 25 - (25 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0026 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0027 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 26 - (26 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0027 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0028 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 27 - (27 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0028 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-2ZZ0029 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - SHEET 28 - (28 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 2 | ZZ | 0029 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-5ZZ0030 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - DETAILS - (1 OF 2) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 5 | ZZ | 0030 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-00-Z00000-5ZZ0031 | LIGHTING SYSTEM - LOBBY LEVEL LANDSCAPE +905M - DETAILS - (2 OF 2) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-19 | Lighting | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | Z00000 | 5 | ZZ | 0031 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELL-01-BLAD01-2000001 | LIGHTING SYSTEM - BLADE-01 (+870.5, +876.25, +882)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Lighting | QP.E.ME.BL1.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELS-03-CENT01-2L50004 | EMERGENCY LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-04-CENT01-2L50005 | EMERGENCY LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-05-CENT01-2L50006 | EMERGENCY LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-06-CENT01-2L50007 | EMERGENCY LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 06 | CENT01 | 2 | L5 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELL-01-BLAD05-2000001 | LIGHTING SYSTEM - BLADE-05 (+894.5, +899.5, +905)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Lighting | QP.E.ME.BL5.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-14
QF01012-NES-C04518-SDW-ELL-01-CENT01-2B10002 | LIGHTING SYSTEM - B1 SERVICE +900.5M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Lighting | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELL-01-CENT01-2B20002 | LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 01 - (01 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Lighting | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELL-01-CENT01-2B30002 | LIGHTING SYSTEM - B3 PROMENADE +887.750M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | Lighting | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELS-00-CENT01-2M20001 | EMERGENCY LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELL-01-CENT01-2L20002 | LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Lighting | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELL-01-CENT01-2L30002 | LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELL-01-CENT01-2L40002 | LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELS-01-CENT01-2M20002 | EMERGENCY LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELL-01-CENT01-2L60002 | LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELL-01-CENT01-2M10002 | LIGHTING SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Lighting | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELS-02-CENT01-2M20003 | EMERGENCY LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELL-01-PARK01-2B10002 | LIGHTING SYSTEM - B1 PARKING +900.5M - SHEET 01 - (01 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Lighting | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ELL-02-BLAD01-2000002 | LIGHTING SYSTEM - BLADE-01 (+887.75, +893.5, +899.25)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Lighting | QP.E.ME.BL1.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELS-03-CENT01-2M20004 | EMERGENCY LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-04-CENT01-2M20005 | EMERGENCY LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELL-02-BLAD05-2000002 | HIGH LEVEL LIGHTING SYSTEM - BLADE-05 (+910.75, +917.5, +922.25)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Lighting | QP.E.ME.BL5.GEN.1580 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-08
QF01012-NES-C04518-SDW-ELL-02-CENT01-2B10003 | LIGHTING SYSTEM - B1 SERVICE +900.5M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Lighting | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELL-02-CENT01-2B20003 | LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 02 - (02 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Lighting | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELL-02-CENT01-2B30003 | LIGHTING SYSTEM - B3 PROMENADE +887.750M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | Lighting | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELS-05-CENT01-2M20006 | EMERGENCY LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELL-02-CENT01-2L20003 | LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Lighting | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELL-02-CENT01-2L30003 | LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELL-02-CENT01-2L40003 | LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELS-06-CENT01-2M20007 | EMERGENCY LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 06 | CENT01 | 2 | M2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELL-02-CENT01-2L60003 | LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELL-02-CENT01-2M10003 | LIGHTING SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Lighting | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0130 | FAÇADE LIGHTING SYSTEM -VMU-01- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-01 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0130 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-ELL-02-PARK01-2B10003 | LIGHTING SYSTEM - B1 PARKING +900.5M - SHEET 02 - (02 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Lighting | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ELL-03-BLAD01-2000003 | LIGHTING SYSTEM - BLADE-01 (+905, +910.75, +917.5)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Lighting | QP.E.ME.BL1.GEN.2970 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-27
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0131 | FAÇADE LIGHTING SYSTEM -VMU-01- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-01 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0131 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0132 | FAÇADE LIGHTING SYSTEM -VMU-01- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-01 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0132 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-ELL-02-BLAD04-2000002 | HIGH LEVEL LIGHTING SYSTEM - BLADE-04 (+882, +887.75, +893.5)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Lighting | QP.E.ME.BL4.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-19
QF01012-NES-C04518-SDW-ELL-03-BLAD05-2000003 | LIGHTING SYSTEM - BLADE-05 (+928, +935.85, +941.60)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Lighting | QP.E.ME.BL5.GEN.1580 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-08
QF01012-NES-C04518-SDW-ELL-03-BLAD04-2000003 | HIGH LEVEL LIGHTING SYSTEM - BLADE-04 (+899.25, +905, +910.75)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Lighting | QP.E.ME.BL4.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-19
QF01012-NES-C04518-SDW-ELL-03-CENT01-2L20004 | LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Lighting | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELL-03-CENT01-2L30004 | LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELL-03-CENT01-2L40004 | LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELL-01-BLAD02-2000001 | LIGHTING SYSTEM - BLADE-02 (+876.25, +882, +887.75)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.BL2.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-28
QF01012-NES-C04518-SDW-ELL-02-BLAD02-2000002 | LIGHTING SYSTEM - BLADE-02 (+893.5, +899.25, +905)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.BL2.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-28
QF01012-NES-C04518-SDW-ELL-03-PARK01-2B10004 | LIGHTING SYSTEM - B1 PARKING +900.5M - SHEET 03 - (03 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Lighting | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | PARK01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ELL-04-BLAD01-2000004 | LIGHTING SYSTEM - BLADE-01 (+922.25, +928, & +935.85)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Lighting | QP.E.ME.BL1.GEN.2970 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-27
QF01012-NES-C04518-SDW-ELL-04-BLAD02-2000004 | LIGHTING SYSTEM - BLADE-02 (+928, +935.85, +941.6)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting | QP.E.ME.BL2.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-27
QF01012-NES-C04518-SDW-ELL-03-BLAD02-2000003 | LIGHTING SYSTEM - BLADE-02 (+910.75, +916.5, +922.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.BL2.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-27
QF01012-NES-C04518-SDW-ELL-04-BLAD04-2000004 | LIGHTING SYSTEM - BLADE-04 (+916.5, +922.25, +928)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.ME.BL4.GEN.2940 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-15
QF01012-NES-C04518-SDW-ELL-04-BLAD05-2000004 | LIGHTING SYSTEM - BLADE-05 (+948.10, +954, +957.35)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | lighting | QP.E.ME.BL5.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-28
QF01012-NES-C04518-SDW-ELL-04-CENT01-2B10005 | LIGHTING SYSTEM - B1 SERVICE +900.5M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Lighting | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELL-04-CENT01-2B20004 | LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 04 - (03 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Lighting | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELL-01-BLAD03-2000001 | LIGHTING SYSTEM - BLADE-03 (+847.5, +853.25, +859)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Lighting | QP.E.ME.BL3.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-22
QF01012-NES-C04518-SDW-ELL-04-CENT01-2L20005 | LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Lighting | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELL-04-CENT01-2L30005 | LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELL-04-CENT01-2L40005 | LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELL-01-BLAD03-2000002 | LIGHTING SYSTEM - BLADE-03 (+867.62, +876.25, +882)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Lighting | QP.E.ME.BL3.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-22
QF01012-NES-C04518-SDW-ELL-04-CENT01-2L60004 | LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELL-04-CENT01-2M10005 | LIGHTING SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Lighting | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELL-03-BLAD03-2000003 | LIGHTING SYSTEM - BLADE-03 (+887.75, +893.5, +899.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Lighting | QP.E.ME.BL3.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-22
QF01012-NES-C04518-SDW-ELL-05-BLAD01-2000005 | LIGHTING SYSTEM - BLADE-01 (+941.6, ROOF, & +958.45)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Lighting | QP.E.ME.BL1.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-15
QF01012-NES-C04518-SDW-ELL-05-BLAD02-2000005 | LIGHTING SYSTEM - BLADE-02 (+948.28 , +951.4)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting | QP.E.ME.BL2.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-29
QF01012-NES-C04518-SDW-ELL-05-BLAD03-2000005 | LIGHTING SYSTEM - BLADE-03 (+921 , +928 , +935.85 )- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Lighting | QP.E.ME.BL3.GEN.1820 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-11
QF01012-NES-C04518-SDW-ELL-05-BLAD04-2000005 | LIGHTING SYSTEM - BLADE-04 (+935.85, +941.60, +947.35)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.ME.BL4.GEN.2840 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELL-05-BLAD04-2000006 | LIGHTING SYSTEM - BLADE-04 (+954,+959, +968.30 ,+975.82)- SHEET 6 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.ME.BL4.GEN.2840 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELL-05-BLAD05-2000005 | LIGHTING SYSTEM - BLADE-05 (+969.30 , +960.09)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Lighting | QP.E.ME.BL5.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-28
QF01012-NES-C04518-SDW-ELL-05-CENT01-2B10006 | LIGHTING SYSTEM - B1 SERVICE +900.5M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Lighting | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ELL-05-CENT01-2B20005 | LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 05 - (04 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Lighting | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELL-05-CENT01-2B30004 | LIGHTING SYSTEM - B3 PROMENADE +887.750M - SHEET 05 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | Lighting | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | CENT01 | 2 | B3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELL-04-BLAD03-2000004 | LIGHTING SYSTEM - BLADE-03 (+905, +910.75, +916.5)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Lighting | QP.E.ME.BL3.GEN.1820 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-11
QF01012-NES-C04518-SDW-ELL-05-CENT01-2L20006 | LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Lighting | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELL-05-CENT01-2L30006 | LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELL-05-CENT01-2L40006 | LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELL-01-BLAD04-2000001 | LIGHTING SYSTEM - BLADE-04 (+863.85, +870.5, +876.25)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Lighting | QP.E.ME.BL4.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-19
QF01012-NES-C04518-SDW-ELL-05-CENT01-2L60005 | LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELL-05-CENT01-2M10006 | LIGHTING SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Lighting | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELL-05-CENT01-2L10006 | LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - SHEET 10 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | CENT01 | 2 | L1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ELL-06-BLAD01-2000006 | LIGHTING SYSTEM - BLADE-01 (+962.2, +972.48, & +989)- SHEET 6 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Lighting | QP.E.ME.BL1.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 06 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-15
QF01012-NES-C04518-SDW-ELL-00-CENT01-2L10001 | LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | L1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ELL-06-CENT01-2L20007 | LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Lighting | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 06 | CENT01 | 2 | L2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ELL-06-CENT01-2L30007 | LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Lighting | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 06 | CENT01 | 2 | L3 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELL-06-CENT01-2L40007 | LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Lighting | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 06 | CENT01 | 2 | L4 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELL-02-CENT01-2L10003 | LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ELL-06-CENT01-2L80001 | LIGHTING SYSTEM - L8 ROYAL MAJLIS +948.28M - SHEET 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | Lighting | QP.E.ME.MBL.GEN.3530 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 06 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-18
QF01012-NES-C04518-SDW-ELL-03-CENT01-2L10004 | LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - SHEET 04 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ELL-06-CENT01-2RL0001 | LIGHTING SYSTEM - ROOF & ABOVE - SHEET 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | Lighting | QP.E.ME.MBL.GEN.3530 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 06 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-18
QF01012-NES-C04518-SDW-ELL-07-BLAD05-2000007 | LOW LEVEL LIGHTING SYSTEM - BLADE-05 (+910.75, +917.5, +922.25)- SHEET 7 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Lighting | QP.E.ME.BL5.GEN.1580 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 07 | BLAD05 | 2 | 00 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-08
QF01012-NES-C04518-SDW-ELL-08-CENT01-2B20006 | LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 08 - (05 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Lighting | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELL-09-CENT01-2B20007 | LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 09 - (06 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Lighting | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 09 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELL-11-CENT01-2B20008 | LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 11 - (07 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Lighting | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 11 | CENT01 | 2 | B2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ELL-11-CENT01-2B20008. | LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 11 - (07 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Lighting | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 11 | CENT01 | 2 | B2 | 0008. | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ELL-11-CENT01-2B30005 | LIGHTING SYSTEM - B3 PROMENADE +887.750M - SHEET 11 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | Lighting | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 11 | CENT01 | 2 | B3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELP-00-CENT01-2B10001 | EARTHING & LIGHTNING - B1 SERVICE +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | Earthing & Lightning | QP.E.ME.MBL.GEN.6870 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ELP-00-CENT01-2B20001 | EARTHING & LIGHTNING - B2 SERVICE +893.5M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | Earthing & Lightning | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-ELP-00-CENT01-2B30001 | EARTHING & LIGHTNING - B3 PROMENADE +887.750M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-07-16 | Earthing & Lightning | QP.E.ME.MBL.GEN.6800 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-01-13
QF01012-NES-C04518-SDW-ELL-04-CENT01-2L10005 | LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - SHEET 05 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ELP-00-CENT01-2L20001 | EARTHING & LIGHTNING - L2- THEATRE STALLS +913M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | Earthing & Lightning | QP.E.ME.MBL.GEN.6990 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-ELP-00-CENT01-2L40001 | EARTHING & LIGHTNING - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | Earthing & Lightning | QP.E.ME.MBL.GEN.7070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-ELL-06-CENT01-2L10007 | LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - SHEET 11 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 06 | CENT01 | 2 | L1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ELP-00-CENT01-2L60001 | EARTHING & LIGHTNING - L6 SKY GARDEN +935.85M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Earthing & Lightning | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELP-00-CENT01-2M10001 | EARTHING & LIGHTNING - L1-UPPER LOBBY MEZZANINE +909M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-01 | Earthing & Lightning | QP.E.ME.MBL.GEN.6950 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-11
QF01012-NES-C04518-SDW-ELL-01-CENT01-2L10002 | LIGHTING SYSTEM - L1- LOBBY LEVEL +905M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ELP-00-GARD01-2000001 | EARTHING & LIGHTNING - GUARD ROOM | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-17 | Earthing & Lightning | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | GARD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELP-00-PARK01-2B10001 | EARTHING & LIGHTNING - B1 PARKING +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | Earthing & Lightning | QP.E.ME.PAR.GEN.1479 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-ELP-00-SECE01-2000001 | EARTHING & LIGHTNING - SEC ROOM | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-17 | Earthing & Lightning | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | SECE01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELP-00-Z00000-0ZZ0001 | EARTHING & LIGHTNING PROTECTION STANDARD INSTALLATION DETAILS - SHEET 1 | [5 empty] | 2027-01-24 | ELECTRICAL INSTALLATION DETAILS | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 0 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-0ZZ0002 | EARTHING & LIGHTNING PROTECTION STANDARD INSTALLATION DETAILS - SHEET 2 | [5 empty] | 2027-01-24 | ELECTRICAL INSTALLATION DETAILS | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 0 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-1ZZ0001 | EARTHING & LIGHTNING ELEVATION | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-24 | Earthing & Lightning | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 1 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-6ZZ0001 | EARTHING SCHEMATIC - SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Earthing & Lightning | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-6ZZ0002 | EARTHING SCHEMATIC - SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Earthing & Lightning | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-6ZZ0003 | EARTHING SCHEMATIC - SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Earthing & Lightning | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-6ZZ0004 | EARTHING SCHEMATIC - SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Earthing & Lightning | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 6 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-6ZZ0005 | EARTHING SCHEMATIC - SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Earthing & Lightning | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 6 | ZZ | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-01-BLAD01-2000001 | EARTHING & LIGHTNING - BLADE-01 (+870.5, +876.25, +882)- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Earthing & Lightning | QP.E.ME.BL1.GEN.3740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-26
QF01012-NES-C04518-SDW-ELL-00-CENT01-2L50001 | LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ELL-01-CENT01-2L50002 | LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ELL-02-CENT01-2L50003 | LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ELP-01-BLAD05-2000001 | EARTHING & LIGHTNING - BLADE-05 (+894.5, +899.5, +905)- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Earthing & Lightning | QP.E.ME.BL5.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-13
QF01012-NES-C04518-SDW-ELP-01-CENT01-2B10002 | EARTHING & LIGHTNING - B1 SERVICE +900.5M - SHEET 01 - (01 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Earthing & Lightning | QP.E.ME.MBL.GEN.6870 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ELP-01-CENT01-2B20002 | EARTHING & LIGHTNING - B2 SERVICE +893.5M - SHEET 01 - (01 OF 09) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Earthing & Lightning | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-ELP-01-CENT01-2B30002 | EARTHING & LIGHTNING - B3 PROMENADE +887.750M - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | Earthing & Lightning | QP.E.ME.MBL.GEN.6800 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-01-13
QF01012-NES-C04518-SDW-ELL-03-CENT01-2L50004 | LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ELP-01-CENT01-2L60002 | EARTHING & LIGHTNING - L6 SKY GARDEN +935.85M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Earthing & Lightning | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELL-04-CENT01-2L50005 | LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ELP-01-PARK01-2B10002 | EARTHING & LIGHTNING - B1 PARKING +900.5M - SHEET 01 - (01 OF 03) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Earthing & Lightning | QP.E.ME.PAR.GEN.1479 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 01 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-ELP-02-BLAD01-2000002 | EARTHING & LIGHTNING - BLADE-01 (+887.75, +893.5, +899.25)- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Earthing & Lightning | QP.E.ME.BL1.GEN.3740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-26
QF01012-NES-C04518-SDW-ELL-05-CENT01-2L50006 | LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ELL-06-CENT01-2L50007 | LIGHTING SYSTEM - L5- SECOND CIRCLE & LOFT +928M- SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 06 | CENT01 | 2 | L5 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ELL-00-CENT01-2M20001 | LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 00 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELP-02-BLAD05-2000002 | EARTHING & LIGHTNING - BLADE-05 (+910.75, +917.5, +922.25)- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Earthing & Lightning | QP.E.ME.BL5.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-13
QF01012-NES-C04518-SDW-ELP-02-CENT01-2B10003 | EARTHING & LIGHTNING - B1 SERVICE +900.5M - SHEET 02 - (02 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Earthing & Lightning | QP.E.ME.MBL.GEN.6870 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ELP-02-CENT01-2B20003 | EARTHING & LIGHTNING - B2 SERVICE +893.5M - SHEET 02 - (02 OF 09) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Earthing & Lightning | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-ELP-02-CENT01-2B30003 | EARTHING & LIGHTNING - B3 PROMENADE +887.750M - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | Earthing & Lightning | QP.E.ME.MBL.GEN.6800 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-01-13
QF01012-NES-C04518-SDW-ELP-02-CENT01-2L20003 | EARTHING & LIGHTNING - L2- THEATRE STALLS +913M - SHEET 02 - (01 OF 03) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Earthing & Lightning | QP.E.ME.MBL.GEN.6990 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-ELL-01-CENT01-2M20002 | LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 01 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELP-02-CENT01-2L60003 | EARTHING & LIGHTNING - L6 SKY GARDEN +935.85M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Earthing & Lightning | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELP-02-CENT01-2M10003 | EARTHING & LIGHTNING - L1-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Earthing & Lightning | QP.E.ME.MBL.GEN.6950 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-11
QF01012-NES-C04518-SDW-ELL-02-CENT01-2M20003 | LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 02 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELP-02-PARK01-2B10003 | EARTHING & LIGHTNING - B1 PARKING +900.5M - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Earthing & Lightning | QP.E.ME.PAR.GEN.1479 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 02 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-ELP-03-BLAD01-2000003 | EARTHING & LIGHTNING - BLADE-01 (+905, +910.75, +917.5)- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Earthing & Lightning | QP.E.ME.BL1.GEN.3780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 03 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-30
QF01012-NES-C04518-SDW-ELL-03-CENT01-2M20004 | LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 03 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELL-04-CENT01-2M20005 | LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 04 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELL-05-CENT01-2M20006 | LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 05 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELP-03-BLAD05-2000003 | EARTHING & LIGHTNING - BLADE-05 (+928, +935.85, +941.60)- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Earthing & Lightning | QP.E.ME.BL5.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 03 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-ELP-03-CENT01-2B10004 | EARTHING & LIGHTNING - B1 SERVICE +900.5M - SHEET 04 - (03 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Earthing & Lightning | QP.E.ME.MBL.GEN.6870 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 03 | CENT01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ELL-06-CENT01-2M20007 | LIGHTING SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Lighting | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELL | 06 | CENT01 | 2 | M2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELE-00-CENT01-2L10005 | MECHANICAL POWER SYSTEM - L1- LOBBY LEVEL +905M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELP-03-CENT01-2L60004 | EARTHING & LIGHTNING - L6 SKY GARDEN +935.85M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Earthing & Lightning | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 03 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELE-01-CENT01-2L10002 | MECHANICAL POWER SYSTEM - L1- LOBBY LEVEL +905M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELP-03-PARK01-2B10004 | EARTHING & LIGHTNING - B1 PARKING +900.5M - SHEET 03 - (03 OF 03) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Earthing & Lightning | QP.E.ME.PAR.GEN.1479 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 03 | PARK01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-ELP-04-BLAD01-2000004 | EARTHING & LIGHTNING - BLADE-01 (+922.25, +928, & +935.85)- SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Earthing & Lightning | QP.E.ME.BL1.GEN.3780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 04 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-30
QF01012-NES-C04518-SDW-ELP-04-BLAD02-2000004 | EARTHING & LIGHTNING - BLADE-02 (+928, +935.85, +941.6)- SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Earthing & Lightning | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 04 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-ELE-02-CENT01-2L10003 | MECHANICAL POWER SYSTEM - L1- LOBBY LEVEL +905M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELP-04-BLAD04-2000004 | EARTHING & LIGHTNING - BLADE-04 (+916.5, +922.25, +928)- SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Earthing & Lightning | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 04 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-ELP-04-BLAD05-2000004 | EARTHING & LIGHTNING - BLADE-05 (+948.10, +954, +957.35)- SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Earthing & Lightning | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 04 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-ELP-04-CENT01-2B10005 | EARTHING & LIGHTNING - B1 SERVICE +900.5M - SHEET 05 - (04 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Earthing & Lightning | QP.E.ME.MBL.GEN.6870 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 04 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ELP-04-CENT01-2B20004 | EARTHING & LIGHTNING - B2 SERVICE +893.5M - SHEET 04 - (03 OF 09) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Earthing & Lightning | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 04 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-ELE-03-CENT01-2L10004 | MECHANICAL POWER SYSTEM - L1- LOBBY LEVEL +905M - SHEET 04 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 03 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-04-CENT01-2L10005 | MECHANICAL POWER SYSTEM - L1- LOBBY LEVEL +905M - SHEET 05 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 04 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELP-04-CENT01-2L60005 | EARTHING & LIGHTNING - L6 SKY GARDEN +935.85M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Earthing & Lightning | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 04 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELP-05-BLAD01-2000005 | EARTHING & LIGHTNING - BLADE-01 (+941.6, ROOF, & +958.45)- SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Earthing & Lightning | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-ELP-05-BLAD02-2000005 | EARTHING & LIGHTNING - BLADE-02 (+948.28 , +951.4)- SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Earthing & Lightning | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-ELP-05-BLAD03-2000005 | EARTHING & LIGHTNING - BLADE-03 (+921 , +928 , +935.85 )- SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Earthing & Lightning | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-ELP-05-BLAD04-2000005 | EARTHING & LIGHTNING - BLADE-04 +935.85, +941.60, +947.35)- SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Earthing & Lightning | QP.E.ME.BL4.GEN.6110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELP-05-BLAD04-2000006 | EARTHING & LIGHTNING - BLADE-04 (+954,+959, +968.30 ,+975.82)- SHEET 6 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Earthing & Lightning | QP.E.ME.BL4.GEN.6110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ELP-05-BLAD05-2000005 | EARTHING & LIGHTNING - BLADE-05 (+969.30 , +960.09)- SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Earthing & Lightning | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-ELP-05-CENT01-2B20005 | EARTHING & LIGHTNING - B2 SERVICE +893.5M - SHEET 05 - (04 OF 09) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Earthing & Lightning | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-ELP-05-CENT01-2B30004 | EARTHING & LIGHTNING - B3 PROMENADE +887.750M - SHEET 05 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-07-16 | Earthing & Lightning | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | CENT01 | 2 | B3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ELP-05-CENT01-2L20006 | EARTHING & LIGHTNING - L2- THEATRE STALLS +913M - SHEET 05 - (02 OF 03) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Earthing & Lightning | QP.E.ME.MBL.GEN.6990 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-ELE-05-CENT01-2L10006 | MECHANICAL POWER SYSTEM - L1- LOBBY LEVEL +905M - SHEET 10 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 05 | CENT01 | 2 | L1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELP-05-CENT01-2L60006 | EARTHING & LIGHTNING - L6 SKY GARDEN +935.85M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Earthing & Lightning | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELP-05-CENT01-2M10006 | EARTHING & LIGHTNING - L1-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Earthing & Lightning | QP.E.ME.MBL.GEN.6950 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 05 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-11
QF01012-NES-C04518-SDW-ELE-06-CENT01-2L10007 | MECHANICAL POWER SYSTEM - L1- LOBBY LEVEL +905M - SHEET 11 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 06 | CENT01 | 2 | L1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELP-06-BLAD01-2000006 | EARTHING & LIGHTNING - BLADE-01 (+962.2, +972.48, & +989)- SHEET 6 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Earthing & Lightning | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 06 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-ELP-06-CENT01-2B10007 | EARTHING & LIGHTNING - B1 SERVICE +900.5M - SHEET 08 - (05 OF 05) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Earthing & Lightning | QP.E.ME.MBL.GEN.6870 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 06 | CENT01 | 2 | B1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ELP-06-CENT01-2B20006 | EARTHING & LIGHTNING - B2 SERVICE +893.5M - SHEET 06 - (05 OF 09) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Earthing & Lightning | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 06 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-ELP-06-CENT01-2L20007 | EARTHING & LIGHTNING - L2- THEATRE STALLS +913M - SHEET 06 - (03 OF 03) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Earthing & Lightning | QP.E.ME.MBL.GEN.6990 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 06 | CENT01 | 2 | L2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-ELP-06-CENT01-2L40007 | EARTHING & LIGHTNING - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Earthing & Lightning | QP.E.ME.MBL.GEN.7070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 06 | CENT01 | 2 | L4 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-ELE-00-CENT01-2L50001 | MECHANICAL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELP-06-CENT01-2L60007 | EARTHING & LIGHTNING - L6 SKY GARDEN +935.85M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Earthing & Lightning | QP.E.ME.MBL.GEN.7190 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 06 | CENT01 | 2 | L6 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-ELP-06-CENT01-2L80001 | EARTHING & LIGHTNING - L8 ROYAL MAJLIS +948.28M - SHEET 01 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | Earthing & Lightning | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 06 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ELE-01-CENT01-2L50002 | MECHANICAL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELP-06-CENT01-2RL0001 | EARTHING & LIGHTNING - RL ROOF & ABOVE - SHEET 01 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | Earthing & Lightning | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 06 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ELP-07-CENT01-2B20007 | EARTHING & LIGHTNING - B2 SERVICE +893.5M - SHEET 07 - (06 OF 09) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Earthing & Lightning | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 07 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-ELP-08-CENT01-2B20008 | EARTHING & LIGHTNING - B2 SERVICE +893.5M - SHEET 08 - (07 OF 09) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Earthing & Lightning | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 08 | CENT01 | 2 | B2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-ELP-09-CENT01-2B20009 | EARTHING & LIGHTNING - B2 SERVICE +893.5M - SHEET 09 - (08 OF 09) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Earthing & Lightning | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 09 | CENT01 | 2 | B2 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-ELP-11-CENT01-2B20010 | EARTHING & LIGHTNING - B2 SERVICE +893.5M - SHEET 11 - (09 OF 09) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Earthing & Lightning | QP.E.ME.MBL.GEN.6850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 11 | CENT01 | 2 | B2 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-ELP-11-CENT01-2B30005 | EARTHING & LIGHTNING - B3 PROMENADE +887.750M - SHEET 11 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-07-16 | Earthing & Lightning | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 11 | CENT01 | 2 | B3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ELS-00-CENT01-2B10001 | EMERGENCY LIGHTING SYSTEM - B1 SERVICE +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-00-CENT01-2B20001 | EMERGENCY LIGHTING SYSTEM - B2 SERVICE +893.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-00-CENT01-2B30001 | EMERGENCY LIGHTING SYSTEM - B3 PROMENADE +887.750M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-07-16 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-02-CENT01-2L50003 | MECHANICAL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-00-CENT01-2L20001 | EMERGENCY LIGHTING SYSTEM - L2- THEATRE STALLS +913M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-00-CENT01-2L30001 | EMERGENCY LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-00-CENT01-2L40001 | EMERGENCY LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-03-CENT01-2L50004 | MECHANICAL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 03 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-00-CENT01-2L60001 | EMERGENCY LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-00-CENT01-2M10001 | EMERGENCY LIGHTING SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-01 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-04-CENT01-2L50005 | MECHANICAL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 04 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-00-GARD01-2000001 | EMERGENCY LIGHTING SYSTEM - GUARD ROOM | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-17 | Emergency Lighting | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | GARD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELS-00-PARK01-2B10001 | EMERGENCY LIGHTING SYSTEM - B1 PARKING +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | Emergency Lighting | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-30
QF01012-NES-C04518-SDW-ELS-00-SECE01-2000001 | EMERGENCY LIGHTING SYSTEM - SEC ROOM | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-17 | Emergency Lighting | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | SECE01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ELS-00-Z00000-6ZZ0001 | EMERGENCY LIGHTING SCHEMATIC - SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Emergency Lighting | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | Z00000 | 6 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELS-00-Z00000-6ZZ0002 | EMERGENCY LIGHTING SCHEMATIC - SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Emergency Lighting | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 00 | Z00000 | 6 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELS-01-BLAD01-2000001 | EMERGENCY LIGHTING SYSTEM - BLADE-01 (+870.5, +876.25, +882)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Emergency Lighting | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-05-CENT01-2L50006 | MECHANICAL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 05 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-06-CENT01-2L50007 | MECHANICAL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 06 | CENT01 | 2 | L5 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-00-CENT01-2M20001 | MECHANICAL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-01-BLAD05-2000001 | EMERGENCY LIGHTING SYSTEM - BLADE-05 (+894.5, +899.5, +905)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Emergency Lighting | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-16
QF01012-NES-C04518-SDW-ELS-01-CENT01-2B10002 | EMERGENCY LIGHTING SYSTEM - B1 SERVICE +900.5M - SHEET 01 - (01 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-01-CENT01-2B20002 | EMERGENCY LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 01 - (01 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-01-CENT01-2B30002 | EMERGENCY LIGHTING SYSTEM - B3 PROMENADE +887.750M - SHEET 01 - (01 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-01-CENT01-2M20002 | MECHANICAL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 01 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-01-CENT01-2L20002 | EMERGENCY LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-01-CENT01-2L30002 | EMERGENCY LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-01-CENT01-2L40002 | EMERGENCY LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-02-CENT01-2M20003 | MECHANICAL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 02 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-01-CENT01-2L60002 | EMERGENCY LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-01-CENT01-2M10002 | EMERGENCY LIGHTING SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-03-CENT01-2M20004 | MECHANICAL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 03 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-01-PARK01-2B10002 | EMERGENCY LIGHTING SYSTEM - B1 PARKING +900.5M - SHEET 01 - (01 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Emergency Lighting | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 01 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-30
QF01012-NES-C04518-SDW-ELS-02-BLAD01-2000002 | EMERGENCY LIGHTING SYSTEM - BLADE-01 (+887.75, +893.5, +899.25)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Emergency Lighting | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-04-CENT01-2M20005 | MECHANICAL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 04 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-05-CENT01-2M20006 | MECHANICAL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 05 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-06-CENT01-2M20007 | MECHANICAL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Mechanical Power | QP.E.ME.MBL.GEN.7280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 06 | CENT01 | 2 | M2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELS-02-BLAD05-2000002 | EMERGENCY LIGHTING SYSTEM - BLADE-05 (+910.75, +917.5, +922.25)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Emergency Lighting | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-16
QF01012-NES-C04518-SDW-ELS-02-CENT01-2B10003 | EMERGENCY LIGHTING SYSTEM - B1 SERVICE +900.5M - SHEET 02 - (02 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-02-CENT01-2B20003 | EMERGENCY LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 02 - (02 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-02-CENT01-2B30003 | EMERGENCY LIGHTING SYSTEM - B3 PROMENADE +887.750M - SHEET 02 - (02 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ESP-01-BLAD02-2000001 | POWER SYSTEM - BLADE-02 (+876.25, +882, +887.75)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Power | QP.E.ME.BL2.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-ELS-02-CENT01-2L20003 | EMERGENCY LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-02-CENT01-2L30003 | EMERGENCY LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-02-CENT01-2L40003 | EMERGENCY LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ESP-02-BLAD02-2000002 | POWER SYSTEM - BLADE-02 (+893.5, +899.25, +905)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Power | QP.E.ME.BL2.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-ELS-02-CENT01-2L60003 | EMERGENCY LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-02-CENT01-2M10003 | EMERGENCY LIGHTING SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ESP-03-BLAD02-2000003 | POWER SYSTEM - BLADE-02 (+910.75, +916.5, +922.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Power | QP.E.ME.BL2.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-ELS-02-PARK01-2B10003 | EMERGENCY LIGHTING SYSTEM - B1 PARKING +900.5M - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Emergency Lighting | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 02 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-30
QF01012-NES-C04518-SDW-ELS-03-BLAD01-2000003 | EMERGENCY LIGHTING SYSTEM - BLADE-01 (+905, +910.75, +917.5)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Emergency Lighting | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ESP-01-BLAD03-2000001 | POWER SYSTEM - BLADE-03 (+847.5, +853.25, +859)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ESP-02-BLAD03-2000002 | POWER SYSTEM - BLADE-03 (+867.62, +876.25 )- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ESP-03-BLAD03-2000003 | POWER SYSTEM - BLADE-03 (+887.75, +893.5, +899.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ELS-03-BLAD05-2000003 | EMERGENCY LIGHTING SYSTEM - BLADE-05 (+928, +935.85, +941.60)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Emergency Lighting | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-16
QF01012-NES-C04518-SDW-ELS-03-CENT01-2B10004 | EMERGENCY LIGHTING SYSTEM - B1 SERVICE +900.5M - SHEET 04 - (03 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | CENT01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ESP-04-BLAD03-2000004 | POWER SYSTEM - BLADE-03 (+905, +910.75, +916.5)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ELS-03-CENT01-2L20004 | EMERGENCY LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-03-CENT01-2L30004 | EMERGENCY LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-03-CENT01-2L40004 | EMERGENCY LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ESP-01-BLAD04-2000001 | POWER SYSTEM - BLADE-04 (+863.85, +870.5, +876.25)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Power | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-ELS-03-CENT01-2L60004 | EMERGENCY LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ESP-02-BLAD04-2000002 | POWER SYSTEM - BLADE-04 (+882, +887.75, +893.5)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Power | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-ELS-03-PARK01-2B10004 | EMERGENCY LIGHTING SYSTEM - B1 PARKING +900.5M - SHEET 03 - (03 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Emergency Lighting | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 03 | PARK01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-30
QF01012-NES-C04518-SDW-ELS-04-BLAD01-2000004 | EMERGENCY LIGHTING SYSTEM - BLADE-01 (+922.25, +928, & +935.85)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Emergency Lighting | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELS-04-BLAD02-2000004 | EMERGENCY LIGHTING SYSTEM - BLADE-02 (+928, +935.85, +941.6)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Emergency Lighting | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-ESP-03-BLAD04-2000003 | POWER SYSTEM - BLADE-04 (+899.25, +905, +910.75)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Power | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-ELS-04-BLAD04-2000004 | EMERGENCY LIGHTING - BLADE-04 (+916.5, +922.25, +928)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Emergency Lighting | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-23
QF01012-NES-C04518-SDW-ELS-04-BLAD05-2000004 | EMERGENCY LIGHTING SYSTEM - BLADE-05 (+948.10, +954, +957.35)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Emergency Lighting | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-16
QF01012-NES-C04518-SDW-ELS-04-CENT01-2B10005 | EMERGENCY LIGHTING SYSTEM - B1 SERVICE +900.5M - SHEET 05 - (04 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-04-CENT01-2B20004 | EMERGENCY LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 04 - (03 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0001 | POWER SYSTEM - SITE PLAN - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:500 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELS-04-CENT01-2L20005 | EMERGENCY LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-04-CENT01-2L30005 | EMERGENCY LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-04-CENT01-2L40005 | EMERGENCY LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0002 | POWER SYSTEM - SITE PLAN - SHEET 01 - (01 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELS-04-CENT01-2L60005 | EMERGENCY LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-04-CENT01-2M10005 | EMERGENCY LIGHTING SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 04 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0003 | POWER SYSTEM - SITE PLAN - SHEET 02 - (02 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELS-05-BLAD01-2000005 | EMERGENCY LIGHTING SYSTEM - BLADE-01 (+941.6, ROOF, & +958.45)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Emergency Lighting | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELS-05-BLAD02-2000005 | EMERGENCY LIGHTING SYSTEM - BLADE-02 (+948.28 , +951.4)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Emergency Lighting | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-ELS-05-BLAD03-2000005 | EMERGENCY LIGHTING - BLADE-03 (+921 , +928 , +935.85 )- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Emergency Lighting | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ELS-05-BLAD04-2000005 | EMERGENCY LIGHTING - BLADE-04 (+935.85, +941.60, +947.35)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Emergency Lighting | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-23
QF01012-NES-C04518-SDW-ELS-05-BLAD04-2000006 | EMERGENCY LIGHTING - BLADE-04 (+954,+959, +968.30 ,+975.82)- SHEET 6 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Emergency Lighting | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-23
QF01012-NES-C04518-SDW-ELS-05-BLAD05-2000005 | EMERGENCY LIGHTING SYSTEM - BLADE-05 (+969.30 , +960.09)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Emergency Lighting | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-16
QF01012-NES-C04518-SDW-ELS-05-CENT01-2B20005 | EMERGENCY LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 05 - (04 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-05-CENT01-2L20006 | EMERGENCY LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-05-CENT01-2L30006 | EMERGENCY LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-05-CENT01-2L40006 | EMERGENCY LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0004 | POWER SYSTEM - SITE PLAN - SHEET 03 - (03 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELS-05-CENT01-2L60006 | EMERGENCY LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-05-CENT01-2M10006 | EMERGENCY LIGHTING SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 05 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0005 | POWER SYSTEM - SITE PLAN - SHEET 04 - (04 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELS-06-BLAD01-2000006 | EMERGENCY LIGHTING SYSTEM - BLADE-01 (+962.2, +972.48, & +989)- SHEET 6 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Emergency Lighting | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 06 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELS-06-CENT01-2B10007 | EMERGENCY LIGHTING SYSTEM - B1 SERVICE +900.5M - SHEET 08 - (05 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 06 | CENT01 | 2 | B1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-06-CENT01-2L20007 | EMERGENCY LIGHTING SYSTEM - L2- THEATRE STALLS +913M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 06 | CENT01 | 2 | L2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-06-CENT01-2L30007 | EMERGENCY LIGHTING SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 06 | CENT01 | 2 | L3 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-06-CENT01-2L40007 | EMERGENCY LIGHTING SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 06 | CENT01 | 2 | L4 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0006 | POWER SYSTEM - SITE PLAN - SHEET 05 - (05 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELS-06-CENT01-2L60007 | EMERGENCY LIGHTING SYSTEM - L6- SKY GARDEN +935.85M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 06 | CENT01 | 2 | L6 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-06-CENT01-2L80001 | EMERGENCY LIGHTING SYSTEM - L8 ROYAL MAJLIS +948.28M - SHEET 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 06 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0007 | POWER SYSTEM - SITE PLAN - SHEET 06 - (06 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELS-06-CENT01-2RL0001 | EMERGENCY LIGHTING SYSTEM - RL ROOF & ABOVE - SHEET 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 06 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-08-CENT01-2B20006 | EMERGENCY LIGHTING SYSTEM - B2 SERVICE +893.5M - SHEET 08 - (05 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ELS-11-CENT01-2B30005 | EMERGENCY LIGHTING SYSTEM - B3 PROMENADE +887.750M - SHEET 11 - (03 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-16 | Emergency Lighting | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELS | 11 | CENT01 | 2 | B3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-10
QF01012-NES-C04518-SDW-ESP-00-CENT01-2B10001 | SMALL POWER SYSTEM - B1 SERVICE +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | Small Power | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ESP-00-CENT01-2B20001 | SMALL POWER SYSTEM - B2 SERVICE +893.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | Small Power | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ESP-00-CENT01-2B30001 | SMALL POWER SYSTEM - B3 PROMENADE +887.750M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-07-23 | Small Power | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0008 | POWER SYSTEM - SITE PLAN - SHEET 07 - (07 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-00-CENT01-2L20001 | SMALL POWER SYSTEM - L2- THEATRE STALLS +913M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | Small Power | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ESP-00-CENT01-2L30001 | SMALL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ESP-00-CENT01-2L40001 | SMALL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | Small Power | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0009 | POWER SYSTEM - SITE PLAN - SHEET 08 - (08 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-00-CENT01-2L60001 | SMALL POWER SYSTEM - L6 SKY GARDEN +935.85M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ESP-00-CENT01-2M10001 | SMALL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-01 | Small Power | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0010 | POWER SYSTEM - SITE PLAN - SHEET 09 - (09 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-00-CENT01-4B20001 | ELECTRICAL ENLARGED PLAN - B2 SERVICE +893.5M - RAW WASH / DEBOX | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | B2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L10011 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-4) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L1 | 0011 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L20012 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-5) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-04 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L2 | 0012 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L30002 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-1) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-07 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6700 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L3 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-12-10
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L400013 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-6) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-11 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L4 | 00013 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L50009 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-2) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-12 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L5 | 0009 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L50010 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-3) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-21 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L5 | 0010 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ESP-00-PARK01-2B10001 | SMALL POWER SYSTEM - B1 PARKING +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | Small Power | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ESP-01-BLAD01-2000001 | POWER SYSTEM - BLADE-01 (+870.5, +882, +887.75)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Power | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0011 | POWER SYSTEM - SITE PLAN - SHEET 10- (10 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0012 | POWER SYSTEM - SITE PLAN - SHEET 11 - (11 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0013 | POWER SYSTEM - SITE PLAN - SHEET 12 - (12 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-01-BLAD05-2000001 | POWER SYSTEM - BLADE-05 (+894.5, +899.5, +905)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Power | QP.E.ME.BL5.GEN.2860 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ESP-01-CENT01-2B10002 | SMALL POWER SYSTEM - B1 SERVICE +900.5M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Small Power | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ESP-01-CENT01-2B20002 | SMALL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 01 - (01 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Small Power | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ESP-01-CENT01-2B30002 | SMALL POWER SYSTEM - B3 PROMENADE +887.750M - SHEET 01 - (01 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Small Power | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0014 | POWER SYSTEM - SITE PLAN - SHEET 13 - (13 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-01-CENT01-2L20002 | SMALL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Small Power | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ESP-01-CENT01-2L30002 | SMALL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ESP-01-CENT01-2L40002 | SMALL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Small Power | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0015 | POWER SYSTEM - SITE PLAN - SHEET 14 - (14 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-01-CENT01-2L60002 | SMALL POWER SYSTEM - L6 SKY GARDEN +935.85M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ESP-01-CENT01-2L80001 | SMALL POWER SYSTEM - L8 ROYAL MAJLIS +948.28M - SHEET 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-12-03 | Small Power | QP.E.ME.MBL.GEN.3530 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-18
QF01012-NES-C04518-SDW-ESP-01-CENT01-2M10002 | SMALL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Small Power | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0016 | POWER SYSTEM - SITE PLAN - SHEET 15 - (15 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-01-PARK01-2B10002 | SMALL POWER SYSTEM - B1 PARKING +900.5M - SHEET 01 - (01 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Small Power | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ESP-02-BLAD01-2000002 | POWER SYSTEM - BLADE-01 (+893.5, +899.25, +905)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Power | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0017 | POWER SYSTEM - SITE PLAN - SHEET 16 - (16 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0018 | POWER SYSTEM - SITE PLAN - SHEET 17 - (17 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0018 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0019 | POWER SYSTEM - SITE PLAN - SHEET 18 - (18 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0019 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-02-BLAD05-2000002 | POWER SYSTEM - BLADE-05 (+910.75, +917.5, +922.25)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Power | QP.E.ME.BL5.GEN.2860 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ESP-02-CENT01-2B10003 | SMALL POWER SYSTEM - B1 SERVICE +900.5M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Small Power | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ESP-02-CENT01-2B20003 | SMALL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 02 - (02 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Small Power | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ESP-02-CENT01-2B30003 | SMALL POWER SYSTEM - B3 PROMENADE +887.750M - SHEET 02 - (02 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Small Power | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0020 | POWER SYSTEM - SITE PLAN - SHEET 19 - (19 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0020 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-02-CENT01-2L20003 | SMALL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Small Power | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ESP-02-CENT01-2L30003 | SMALL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ESP-02-CENT01-2L40003 | SMALL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Small Power | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0021 | POWER SYSTEM - SITE PLAN - SHEET 20 - (20 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0021 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-02-CENT01-2L60003 | SMALL POWER SYSTEM - L6 SKY GARDEN +935.85M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ESP-02-CENT01-2M10003 | SMALL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Small Power | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0022 | POWER SYSTEM - SITE PLAN - SHEET 21 - (21 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0022 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-02-PARK01-2B10003 | SMALL POWER SYSTEM - B1 PARKING +900.5M - SHEET 02 - (02 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Small Power | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ESP-03-BLAD01-2000003 | POWER SYSTEM - BLADE-01 (+905, +910.75, +917.5)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Power | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0023 | POWER SYSTEM - SITE PLAN - SHEET 22 - (22 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0023 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0024 | POWER SYSTEM - SITE PLAN - SHEET 23 - (23 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0024 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0025 | POWER SYSTEM - SITE PLAN - SHEET 24 - (24 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0025 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-03-BLAD05-2000003 | POWER SYSTEM - BLADE-05 (+928, +935.85, +941.60)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Power | QP.E.ME.BL5.GEN.2860 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ESP-03-CENT01-2B30004 | SMALL POWER SYSTEM - B3 PROMENADE +887.750M - SHEET 03 - (03 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Small Power | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | CENT01 | 2 | B3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ESP-03-CENT01-2L20004 | SMALL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Small Power | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ESP-03-CENT01-2L30004 | SMALL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ESP-03-CENT01-2L40004 | SMALL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Small Power | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0026 | POWER SYSTEM - SITE PLAN - SHEET 25 - (25 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0026 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-03-CENT01-2L60004 | SMALL POWER SYSTEM - L6 SKY GARDEN +935.85M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0027 | POWER SYSTEM - SITE PLAN - SHEET 26 - (26 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0027 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-03-PARK01-2B10004 | SMALL POWER SYSTEM - B1 PARKING +900.5M - SHEET 03 - (03 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Small Power | QP.E.ME.PAR.GEN.1088 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | PARK01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ESP-04-BLAD01-2000004 | POWER SYSTEM - BLADE-01 (+922.25, +928, & +935.85)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Power | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ESP-04-BLAD02-2000004 | POWER SYSTEM - BLADE-02 (+928, +935.85, +941.6)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Power | QP.E.ME.BL2.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0028 | POWER SYSTEM - SITE PLAN - SHEET 27 - (27 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0028 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-04-BLAD04-2000004 | POWER SYSTEM - BLADE-04 (+916.5, +922.25, +928)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Power | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-ESP-04-BLAD05-2000004 | POWER SYSTEM - BLADE-05 (+948.10, +954, +957.35)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Power | QP.E.ME.BL5.GEN.2860 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ESP-04-CENT01-2B10005 | SMALL POWER SYSTEM - B1 SERVICE +900.5M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Small Power | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ESP-04-CENT01-2B20004 | SMALL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 04 - (03 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Small Power | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ESP-04-CENT01-2B30005 | SMALL POWER SYSTEM - B3 PROMENADE +887.750M - SHEET 04 - (04 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Small Power | QP.E.ME.MBL.GEN.1350 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | CENT01 | 2 | B3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ0029 | POWER SYSTEM - SITE PLAN - SHEET 28 - (28 OF 28) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Power | QP.E.ME.MBL.GEN.1720 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 0029 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ESP-04-CENT01-2L20005 | SMALL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Small Power | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ESP-04-CENT01-2L30005 | SMALL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ESP-04-CENT01-2L40005 | SMALL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Small Power | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ESP-00-CENT01-2L10005 | SMALL POWER SYSTEM - L1- LOBBY LEVEL +905M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ESP-04-CENT01-2L60005 | SMALL POWER SYSTEM - L6 SKY GARDEN +935.85M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ESP-04-CENT01-2M10005 | SMALL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Small Power | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ESP-01-CENT01-2L10002 | SMALL POWER SYSTEM - L1- LOBBY LEVEL +905M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ESP-05-BLAD01-2000005 | POWER SYSTEM - BLADE-01 (+941.6, ROOF, & +958.45)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Power | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ESP-05-BLAD02-2000005 | POWER SYSTEM - BLADE-02 (+948.28 , +951.4)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Power | QP.E.ME.BL2.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-ESP-05-BLAD03-2000005 | POWER SYSTEM - BLADE-03 (+921 , +928 , +935.85 )- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Power | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ESP-05-BLAD04-2000005 | POWER SYSTEM - BLADE-04 (+935.85, +941.60, +947.35)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Power | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-ESP-05-BLAD04-2000006 | POWER SYSTEM - BLADE-04 (+954,+959, +968.30 ,+975.82)- SHEET 6 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Power | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-ESP-05-BLAD05-2000005 | POWER SYSTEM - BLADE-05 (+969.30 , +960.09)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Power | QP.E.ME.BL5.GEN.2860 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ESP-05-CENT01-2B10006 | SMALL POWER SYSTEM - B1 SERVICE +900.5M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Small Power | QP.E.ME.MBL.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ESP-05-CENT01-2B20005 | SMALL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 05 - (04 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Small Power | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ESP-02-CENT01-2L10003 | SMALL POWER SYSTEM - L1- LOBBY LEVEL +905M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ESP-05-CENT01-2L20006 | SMALL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Small Power | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ESP-05-CENT01-2L30006 | SMALL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ESP-05-CENT01-2L40006 | SMALL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Small Power | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ESP-04-CENT01-2L10005 | SMALL POWER SYSTEM - L1- LOBBY LEVEL +905M - SHEET 04 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ESP-05-CENT01-2L60006 | SMALL POWER SYSTEM - L6 SKY GARDEN +935.85M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ESP-05-CENT01-2M10006 | SMALL POWER SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Small Power | QP.E.ME.MBL.GEN.2070 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ESP-05-CENT01-2L10006 | SMALL POWER SYSTEM - L1- LOBBY LEVEL +905M - SHEET 05 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.1620 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | CENT01 | 2 | L1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ESP-06-BLAD01-2000006 | POWER SYSTEM - BLADE-01 (+962.2, +972.48, & +989)- SHEET 6 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Power | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 06 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ESP-06-CENT01-2L20007 | SMALL POWER SYSTEM - L2- THEATRE STALLS +913M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Small Power | QP.E.ME.MBL.GEN.2270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 06 | CENT01 | 2 | L2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ESP-06-CENT01-2L30007 | SMALL POWER SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.2470 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 06 | CENT01 | 2 | L3 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ESP-06-CENT01-2L40007 | SMALL POWER SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Small Power | QP.E.ME.MBL.GEN.2670 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 06 | CENT01 | 2 | L4 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ESP-00-CENT01-2L50001 | SMALL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ESP-06-CENT01-2L60007 | SMALL POWER SYSTEM - L6-SKY GARDEN +935.85M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Small Power | QP.E.ME.MBL.GEN.3320 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 06 | CENT01 | 2 | L6 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ESP-01-CENT01-2L50002 | SMALL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ESP-06-CENT01-2RL0001 | SMALL POWER SYSTEM - RL ROOF & ABOVE - SHEET 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | Small Power | QP.E.ME.MBL.GEN.3530 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 06 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-18
QF01012-NES-C04518-SDW-ESP-08-CENT01-2B20006 | SMALL POWER SYSTEM - B2 SERVICE +893.5M - SHEET 08 - (05 OF 05) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Small Power | QP.E.ME.MBL.GEN.1450 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ICT-00-BLAD01-0000001 | ICT SINGLE LINE DIAGRAM FOR BLADE-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD01 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-ICT-00-BLAD01-2000001 | ICT SYSTEM PLAN - BLADE-01 (+870.5 M​, +876.2 5 M​ & +882 M​) - SHEET 1 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | ICT | QP.E.ME.BL1.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-BLAD01-2000002 | ICT SYSTEM PLAN - BLADE-01 (+887.75 M​, +893.5 M& +899.25 M) - SHEET 2 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | ICT | QP.E.ME.BL1.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-BLAD01-2000003 | ICT SYSTEM PLAN - BLADE-01 (+905 M, +910.75 M​​​ & +917.5 M​) - SHEET 3 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | ICT | QP.E.ME.BL1.GEN.2980 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-27
QF01012-NES-C04518-SDW-ICT-00-BLAD01-2000004 | ICT SYSTEM PLAN - BLADE-01 (+922.25 M​, +928 M & +935.85 M) - SHEET 4 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | ICT | QP.E.ME.BL1.GEN.2980 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-27
QF01012-NES-C04518-SDW-ICT-00-BLAD01-2000005 | ICT SYSTEM PLAN - BLADE-01 (+941.6M​, ROOF BLADE 1​ & +958.45​ M) - SHEET 5 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | ICT | QP.E.ME.BL1.GEN.1550 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-15
QF01012-NES-C04518-SDW-ICT-00-BLAD01-2000006 | ICT SYSTEM PLAN - BLADE-01 (+962.2 M, +972.48M​​ & +989 M) - SHEET 6 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-31 | ICT | QP.E.ME.BL1.GEN.1550 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-15
QF01012-NES-C04518-SDW-ICT-00-BLAD01-6000001 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL1-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD01 | 6 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-ICT-00-BLAD01-6000002 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL1-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD01 | 6 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-ICT-00-BLAD01-6000003 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL1-03 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD01 | 6 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-ICT-00-BLAD01-6000004 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL1-04 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD01 | 6 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-ICT-00-BLAD02-0000001 | ICT SINGLE LINE DIAGRAM FOR BLADE-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD02 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-ICT-00-BLAD02-2000001 | ICT SYSTEM PLAN - BLADE-02 (+876.25 M​, +882.0​ M & +887.75 M​) - SHEET 1 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | ICT | QP.E.ME.BL2.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-11
QF01012-NES-C04518-SDW-ICT-00-BLAD02-2000002 | ICT SYSTEM PLAN - BLADE-02 (+893.5 M​, +899.25 M & +905 M) - SHEET 2 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | ICT | QP.E.ME.BL2.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-11
QF01012-NES-C04518-SDW-ICT-00-BLAD02-2000003 | ICT SYSTEM PLAN - BLADE-02 (+910.75M, +916.5M & +922.25M) - SHEET 3 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | ICT | QP.E.ME.BL2.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-09
QF01012-NES-C04518-SDW-ICT-00-BLAD02-2000004 | ICT SYSTEM PLAN - BLADE-02 (+928 M, +935.85 M & +941.60 M) - SHEET 4 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | ICT | QP.E.ME.BL2.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-09
QF01012-NES-C04518-SDW-ICT-00-BLAD02-2000005 | ICT SYSTEM PLAN - BLADE-02 (+948.28 M​ & +951.40 M ) - SHEET 5 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-25 | ICT | QP.E.ME.BL2.GEN.2150 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-29
QF01012-NES-C04518-SDW-ICT-00-BLAD02-6000001 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL2-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD02 | 6 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-ICT-00-BLAD02-6000002 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL2-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD02 | 6 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-ICT-00-BLAD02-6000003 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL2-03 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD02 | 6 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-ICT-00-BLAD03-0000001 | ICT SINGLE LINE DIAGRAM FOR BLADE-03 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD03 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-ICT-00-BLAD03-2000001 | ICT SYSTEM PLAN - BLADE-03 (+847.5 M, +853.25 M & +859 M) - SHEET 1 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | ICT | QP.E.ME.BL3.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-ICT-00-BLAD03-2000002 | ICT SYSTEM PLAN - BLADE-03 (+867.62, +876.25, +887.75) - SHEET 2 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | ICT | QP.E.ME.BL3.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-ICT-00-BLAD03-2000003 | ICT SYSTEM PLAN - BLADE-03 (+893.5 M, +899.25 M​ & +905M ) - SHEET 3 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | ICT | QP.E.ME.BL3.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-ICT-00-BLAD03-2000004 | ICT SYSTEM PLAN - BLADE-03 (+910.75 M, +916.5 M & +921 M) - SHEET 4 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | ICT | QP.E.ME.BL3.GEN.1830 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-05
QF01012-NES-C04518-SDW-ICT-00-BLAD03-2000005 | ICT SYSTEM PLAN - BLADE-03 ( +928 M ) - SHEET 5 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-18 | ICT | QP.E.ME.BL3.GEN.1830 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-05
QF01012-NES-C04518-SDW-ICT-00-BLAD03-6000001 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL3-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD03 | 6 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-ICT-00-BLAD03-6000002 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL3-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD03 | 6 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-ICT-00-BLAD03-6000003 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL3-03 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD03 | 6 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-ICT-00-BLAD04-0000001 | ICT SINGLE LINE DIAGRAM FOR BLADE-04 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD04 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-ICT-00-BLAD04-2000001 | ICT SYSTEM PLAN - BLADE-04 (+863.85, +870.5, +876.25) - SHEET 1 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | ICT | QP.E.ME.BL4.GEN.2150 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-24
QF01012-NES-C04518-SDW-ICT-00-BLAD04-2000002 | ICT SYSTEM PLAN - BLADE-04 (+882, +887.75, +893.5) - SHEET 2 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | ICT | QP.E.ME.BL4.GEN.2150 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-24
QF01012-NES-C04518-SDW-ICT-00-BLAD04-2000003 | ICT SYSTEM PLAN - BLADE-04 (+899.25, +910.75, +916.5) - SHEET 3 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | ICT | QP.E.ME.BL4.GEN.2150 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-24
QF01012-NES-C04518-SDW-ICT-00-BLAD04-2000004 | ICT SYSTEM PLAN - BLADE-04 (+922.25, +928, +935.85) - SHEET 4 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | ICT | QP.E.ME.BL4.GEN.2950 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-08
QF01012-NES-C04518-SDW-ICT-00-BLAD04-2000005 | ICT SYSTEM PLAN - BLADE-04 (+941.60, +947.35, +954) - SHEET 5 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | ICT | QP.E.ME.BL4.GEN.2850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ICT-00-BLAD04-2000006 | ICT SYSTEM PLAN - BLADE-04 (+959, +968.30 ,+975.82) - SHEET 6 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | ICT | QP.E.ME.BL4.GEN.2850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ICT-00-BLAD04-6000001 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL4-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD04 | 6 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-ICT-00-BLAD04-6000002 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL4-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD04 | 6 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-ICT-00-BLAD04-6000003 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL4-03 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD04 | 6 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-ICT-00-BLAD04-6000004 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL4-04 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD04 | 6 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-ICT-00-BLAD05-0000001 | ICT SINGLE LINE DIAGRAM FOR BLADE-05 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD05 | 0 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-ICT-00-BLAD05-2000001 | ICT SYSTEM PLAN - BLADE-05 (+894.5, +899.5, +905) - SHEET 1 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | ICT | QP.E.ME.BL5.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-19
QF01012-NES-C04518-SDW-ICT-00-BLAD05-2000002 | ICT SYSTEM PLAN - BLADE-05 (+910.75, +917.5, +922.25) - SHEET 2 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | ICT | QP.E.ME.BL5.GEN.1590 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-03
QF01012-NES-C04518-SDW-ICT-00-BLAD05-2000003 | ICT SYSTEM PLAN - BLADE-05 (+928, +935.85, +941.60) - SHEET 3 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | ICT | QP.E.ME.BL5.GEN.1590 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-03
QF01012-NES-C04518-SDW-ICT-00-BLAD05-2000004 | ICT SYSTEM PLAN - BLADE-05 (+948.10, +954, +957.35) - SHEET 4 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | ICT | QP.E.ME.BL5.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-28
QF01012-NES-C04518-SDW-ICT-00-BLAD05-2000005 | ICT SYSTEM PLAN - BLADE-05 (+969.30, +960.09) - SHEET 5 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | ICT | QP.E.ME.BL5.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-28
QF01012-NES-C04518-SDW-ICT-00-BLAD05-6000001 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL5-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD05 | 6 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-ICT-00-BLAD05-6000002 | DATA OUTLET SCHEDULE FOR IDF-ICT-BL5-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | BLAD05 | 6 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-ICT-00-CENT01-0ZZ0000 | ICT SINGLE LINE DIAGRAM FOR MAIN BUILDING - OVER ALL | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 0 | ZZ | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ICT-00-CENT01-0ZZ0001 | ICT SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 0 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ICT-00-CENT01-0ZZ0002 | ICT SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 0 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ICT-00-CENT01-0ZZ0003 | ICT SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-03 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 0 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ICT-00-CENT01-0ZZ0004 | ICT SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-04 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 0 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ICT-00-CENT01-0ZZ0005 | MASTER CLOCK SCHEMATIC DIAGRAM - OVERALL | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-29 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 0 | ZZ | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ICT-00-CENT01-0ZZ0006 | IPTV SCHEMATIC DIAGRAM - OVERALL | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-29 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 0 | ZZ | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ICT-00-CENT01-2B10000 | ICT SYSTEM OVERALL PLAN - B1 SERVICE +900.5M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2026-12-10 | ICT | QP.E.ME.MBL.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | B1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ICT-00-CENT01-2B20000 | ICT SYSTEM OVERALL PLAN - B2 SERVICE +893.5M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2026-12-03 | ICT | QP.E.ME.MBL.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | B2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ICT-00-CENT01-2B30000 | ICT SYSTEM OVERALL PLAN - B3 PROMENADE +887.750M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | ICT | QP.E.ME.MBL.GEN.1360 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | B3 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ICT-00-CENT01-2L10000 | ICT SYSTEM OVERALL PLAN - L1- LOBBY LEVEL +905M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2026-12-17 | ICT | QP.E.ME.MBL.GEN.1630 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | L1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ICT-00-CENT01-2L20000 | ICT SYSTEM OVERALL PLAN - L2- THEATRE STALLS +913M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2027-01-07 | ICT | QP.E.ME.MBL.GEN.2280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | L2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ICT-00-CENT01-2L30000 | ICT SYSTEM OVERALL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2027-01-14 | ICT | QP.E.ME.MBL.GEN.2480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | L3 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ICT-00-CENT01-2L40000 | ICT SYSTEM OVERALL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2027-01-21 | ICT | QP.E.ME.MBL.GEN.2680 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | L4 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ICT-00-CENT01-2L50000 | ICT SYSTEM OVERALL PLAN - L5- SECOND CIRCLE & LOFT +928M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2027-01-28 | ICT | QP.E.ME.MBL.GEN.2890 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | L5 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-16
QF01012-NES-C04518-SDW-ICT-00-CENT01-2L60000 | ICT SYSTEM OVERALL PLAN - L6- SKY GARDEN +935.85M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2027-02-11 | ICT | QP.E.ME.MBL.GEN.3330 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | L6 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-00-CENT01-2L80001 | ICT SYSTEM OVERALL PLAN - L8 ROYAL MAJLIS +948.28M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | ICT | QP.E.ME.MBL.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-20
QF01012-NES-C04518-SDW-ICT-00-CENT01-2M10000 | ICT SYSTEM OVERALL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2026-12-24 | ICT | QP.E.ME.MBL.GEN.2080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | M1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ICT-00-CENT01-2M20000 | ICT SYSTEM OVERALL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2027-02-04 | ICT | QP.E.ME.MBL.GEN.3110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | M2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-00-CENT01-2RL0001 | ICT SYSTEM OVERALL PLAN - Roof & Above | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-18 | ICT | QP.E.ME.MBL.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-20
QF01012-NES-C04518-SDW-ICT-00-CENT01-6B10001 | DATA OUTLET SCHEDULE FOR IDF-ICT-B01-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-ICT-00-CENT01-6B10002 | DATA OUTLET SCHEDULE FOR IDF-ICT-B01-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-ICT-00-CENT01-6B20001 | DATA OUTLET SCHEDULE FOR IDF-ICT-B02-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.1290 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-ICT-00-CENT01-6B30001 | DATA OUTLET SCHEDULE FOR IDF-ICT-B03-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6520 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-15
QF01012-NES-C04518-SDW-ICT-00-CENT01-6B30002 | DATA OUTLET SCHEDULE FOR IDF-ICT-B03-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6520 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-15
QF01012-NES-C04518-SDW-ICT-00-CENT01-6L10001 | DATA OUTLET SCHEDULE FOR IDF-ICT-B03-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6640 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | L1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-ICT-00-CENT01-6L40001 | DATA OUTLET SCHEDULE FOR IDF-ICT-L4-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6680 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-16
QF01012-NES-C04518-SDW-ICT-00-CENT01-6L50001 | DATA OUTLET SCHEDULE FOR IDF-ICT-L5-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ICT-00-CENT01-6L50002 | DATA OUTLET SCHEDULE FOR IDF-ICT-L5-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ICT-00-CENT01-6L50003 | DATA OUTLET SCHEDULE FOR IDF-ICT-L5-03 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ICT-00-CENT01-6L80001 | DATA OUTLET SCHEDULE FOR IDF-ICT-L8-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6580 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-04-24
QF01012-NES-C04518-SDW-ICT-00-CENT01-6M10001 | DATA OUTLET SCHEDULE FOR IDF-ICT-L1M-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6660 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-22
QF01012-NES-C04518-SDW-ICT-00-CENT01-6M10002 | DATA OUTLET SCHEDULE FOR IDF-ICT-L1M-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6660 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-22
QF01012-NES-C04518-SDW-ICT-00-CENT01-6M10003 | DATA OUTLET SCHEDULE FOR IDF-ICT-L1M-03 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6660 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-22
QF01012-NES-C04518-SDW-ICT-00-CENT01-6M20001 | DATA OUTLET SCHEDULE FOR IDF-ICT-L5.5M-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.5540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-23
QF01012-NES-C04518-SDW-ICT-00-CENT01-6M20002 | DATA OUTLET SCHEDULE FOR IDF-ICT-L5.5M-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.MBL.GEN.6760 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | CENT01 | 6 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ICT-00-PARK01-2B10000 | ICT SYSTEM PARTIAL PLAN - B1 PARKING +900.5M | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:300 | 2027-02-25 | ICT | QP.E.ME.PAR.GEN.1099 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | PARK01 | 2 | B1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ICT-00-PARK01-6B10001 | DATA OUTLET SCHEDULE FOR IDF-ICT-B1 PARK-01 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | PARK01 | 6 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-30
QF01012-NES-C04518-SDW-ICT-00-PARK01-6B10002 | DATA OUTLET SCHEDULE FOR IDF-ICT-B1 PARK-02 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | PARK01 | 6 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-30
QF01012-NES-C04518-SDW-ICT-00-PARK01-6B10003 | DATA OUTLET SCHEDULE FOR IDF-ICT-B1 PARK-03 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | PARK01 | 6 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-30
QF01012-NES-C04518-SDW-ICT-00-Z00000-0ZZ0001 | ICT SINGLE LINE DIAGRAM FOR SITE | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2027-04-15 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 0 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-00-Z00000-0ZZ0101 | ICT INSTALLATION DETAILS - SHEET 1 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2026-11-30 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 0 | ZZ | 0101 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ICT-00-Z00000-0ZZ0102 | ICT INSTALLATION DETAILS - SHEET 2 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2026-11-30 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 0 | ZZ | 0102 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ0000 | ICT OVERALL SITE PLAN | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:500 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-01-CENT01-2B10001 | ICT SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | ICT | QP.E.ME.MBL.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ICT-01-CENT01-2B20001 | ICT SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | ICT | QP.E.ME.MBL.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ICT-01-CENT01-2B30001 | ICT SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 01 - (1 OF 3) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | ICT | QP.E.ME.MBL.GEN.1360 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ICT-01-CENT01-2L10001 | ICT SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 01 - (1 OF 4) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | ICT | QP.E.ME.MBL.GEN.1630 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | CENT01 | 2 | L1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ICT-01-CENT01-2L20001 | ICT SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | ICT | QP.E.ME.MBL.GEN.2280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ICT-01-CENT01-2L30001 | ICT SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | ICT | QP.E.ME.MBL.GEN.2480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ICT-01-CENT01-2L40001 | ICT SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | ICT | QP.E.ME.MBL.GEN.2680 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ICT-01-CENT01-2L50001 | ICT SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.ME.MBL.GEN.2890 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-16
QF01012-NES-C04518-SDW-ICT-01-CENT01-2L60001 | ICT SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 01 - (1 OF 5) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | ICT | QP.E.ME.MBL.GEN.3330 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-01-CENT01-2M10001 | ICT SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (1 OF 4) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | ICT | QP.E.ME.MBL.GEN.2080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ICT-01-CENT01-2M20001 | ICT SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | ICT | QP.E.ME.MBL.GEN.3110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-01-PARK01-2B10001 | ICT SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 01 - (1 OF 3) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | ICT | QP.E.ME.PAR.GEN.1099 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ICT-01-Z00000-2ZZ0001 | ICT PARTIAL SITE PLAN - SHEET 01 - (1 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 01 | Z00000 | 2 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-02-CENT01-2B10002 | ICT SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | ICT | QP.E.ME.MBL.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ICT-02-CENT01-2B20002 | ICT SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | ICT | QP.E.ME.MBL.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ICT-02-CENT01-2B30002 | ICT SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 02 - (2 OF 3) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | ICT | QP.E.ME.MBL.GEN.1360 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ICT-02-CENT01-2L10002 | ICT SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 02 - (2 OF 4) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | ICT | QP.E.ME.MBL.GEN.1630 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ICT-02-CENT01-2L20002 | ICT SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | ICT | QP.E.ME.MBL.GEN.2280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ICT-02-CENT01-2L30002 | ICT SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | ICT | QP.E.ME.MBL.GEN.2480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ICT-02-CENT01-2L40002 | ICT SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | ICT | QP.E.ME.MBL.GEN.2680 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ICT-02-CENT01-2L50002 | ICT SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.ME.MBL.GEN.2890 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-16
QF01012-NES-C04518-SDW-ICT-02-CENT01-2L60002 | ICT SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 02 - (2 OF 5) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | ICT | QP.E.ME.MBL.GEN.3330 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-02-CENT01-2M10002 | ICT SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (2 OF 4) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | ICT | QP.E.ME.MBL.GEN.2080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ICT-02-CENT01-2M20002 | ICT SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | ICT | QP.E.ME.MBL.GEN.3110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-02-PARK01-2B10002 | ICT SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 02 - (2 OF 3) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | ICT | QP.E.ME.PAR.GEN.1099 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ICT-02-Z00000-2ZZ0002 | ICT PARTIAL SITE PLAN - SHEET 02 - (2 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 02 | Z00000 | 2 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-03-CENT01-2L20003 | ICT SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | ICT | QP.E.ME.MBL.GEN.2280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 03 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ICT-03-CENT01-2L30003 | ICT SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | ICT | QP.E.ME.MBL.GEN.2480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 03 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ICT-03-CENT01-2L40003 | ICT SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | ICT | QP.E.ME.MBL.GEN.2680 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 03 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ICT-03-CENT01-2L50003 | ICT SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.ME.MBL.GEN.2890 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 03 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-16
QF01012-NES-C04518-SDW-ICT-03-CENT01-2L60003 | ICT SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 03 - (3 OF 5) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | ICT | QP.E.ME.MBL.GEN.3330 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 03 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-03-CENT01-2M20003 | ICT SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | ICT | QP.E.ME.MBL.GEN.3110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 03 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-03-PARK01-2B10003 | ICT SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 03 - (3 OF 3) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | ICT | QP.E.ME.PAR.GEN.1099 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 03 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-21
QF01012-NES-C04518-SDW-ICT-03-Z00000-2ZZ0003 | ICT PARTIAL SITE PLAN - SHEET 03 - (3 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 03 | Z00000 | 2 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-04-CENT01-2B10003 | ICT SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 04 - (3 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | ICT | QP.E.ME.MBL.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 04 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ICT-04-CENT01-2B20003 | ICT SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 04 - (3 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | ICT | QP.E.ME.MBL.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 04 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ICT-04-CENT01-2L10003 | ICT SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 04 - (3 OF 4) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | ICT | QP.E.ME.MBL.GEN.1630 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 04 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ICT-04-CENT01-2L20004 | ICT SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | ICT | QP.E.ME.MBL.GEN.2280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 04 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ICT-04-CENT01-2L30004 | ICT SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | ICT | QP.E.ME.MBL.GEN.2480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 04 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ICT-04-CENT01-2L40004 | ICT SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | ICT | QP.E.ME.MBL.GEN.2680 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 04 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ICT-04-CENT01-2L50004 | ICT SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.ME.MBL.GEN.2890 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 04 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-16
QF01012-NES-C04518-SDW-ICT-04-CENT01-2L60004 | ICT SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 04 - (4 OF 5) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | ICT | QP.E.ME.MBL.GEN.3330 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 04 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-04-CENT01-2M10004 | ICT SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (3 OF 4) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | ICT | QP.E.ME.MBL.GEN.2080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 04 | CENT01 | 2 | M1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ICT-04-CENT01-2M20004 | ICT SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | ICT | QP.E.ME.MBL.GEN.3110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 04 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-04-Z00000-2ZZ0004 | ICT PARTIAL SITE PLAN - SHEET 04 - (4 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 04 | Z00000 | 2 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-05-CENT01-2B10004 | ICT SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 05 - (4 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | ICT | QP.E.ME.MBL.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 05 | CENT01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ICT-05-CENT01-2B20004 | ICT SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 05 - (4 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | ICT | QP.E.ME.MBL.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 05 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ICT-05-CENT01-2L10004 | ICT SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 05 - (4 OF 4) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | ICT | QP.E.ME.MBL.GEN.1630 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 05 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ICT-05-CENT01-2L20005 | ICT SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | ICT | QP.E.ME.MBL.GEN.2280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 05 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ICT-05-CENT01-2L30005 | ICT SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | ICT | QP.E.ME.MBL.GEN.2480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 05 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ICT-05-CENT01-2L40005 | ICT SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | ICT | QP.E.ME.MBL.GEN.2680 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 05 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ICT-05-CENT01-2L50005 | ICT SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.ME.MBL.GEN.2890 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 05 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-16
QF01012-NES-C04518-SDW-ICT-05-CENT01-2L60005 | ICT SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 05 - (5 OF 5) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-11 | ICT | QP.E.ME.MBL.GEN.3330 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 05 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-05-CENT01-2M10005 | ICT SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (4 OF 4) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-24 | ICT | QP.E.ME.MBL.GEN.2080 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 05 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-08-06
QF01012-NES-C04518-SDW-ICT-05-CENT01-2M20005 | ICT SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | ICT | QP.E.ME.MBL.GEN.3110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 05 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-05-Z00000-2ZZ0005 | ICT PARTIAL SITE PLAN - SHEET 05 - (5 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 05 | Z00000 | 2 | ZZ | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-06-CENT01-2L20006 | ICT SYSTEM PARTIAL PLAN - L2- THEATRE STALLS +913M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | ICT | QP.E.ME.MBL.GEN.2280 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 06 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-09-08
QF01012-NES-C04518-SDW-ICT-06-CENT01-2L30006 | ICT SYSTEM PARTIAL PLAN - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | ICT | QP.E.ME.MBL.GEN.2480 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 06 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ICT-06-CENT01-2L40006 | ICT SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | ICT | QP.E.ME.MBL.GEN.2680 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 06 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-11-14
QF01012-NES-C04518-SDW-ICT-06-CENT01-2L50006 | ICT SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.ME.MBL.GEN.2890 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 06 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-12-16
QF01012-NES-C04518-SDW-ICT-06-CENT01-2M20006 | ICT SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-02-04 | ICT | QP.E.ME.MBL.GEN.3110 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 06 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-18
QF01012-NES-C04518-SDW-ICT-06-Z00000-2ZZ0006 | ICT PARTIAL SITE PLAN - SHEET 06 - (6 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 06 | Z00000 | 2 | ZZ | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-07-CENT01-2B10005 | ICT SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 07 - (5 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | ICT | QP.E.ME.MBL.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 07 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ICT-07-CENT01-2B20005 | ICT SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 07 - (5 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | ICT | QP.E.ME.MBL.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 07 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ICT-07-Z00000-2ZZ0007 | ICT PARTIAL SITE PLAN - SHEET 07 - (7 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 07 | Z00000 | 2 | ZZ | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-08-CENT01-2B10006 | ICT SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 08 - (6 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | ICT | QP.E.ME.MBL.GEN.1780 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 08 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-06-02
QF01012-NES-C04518-SDW-ICT-08-CENT01-2B20006 | ICT SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 08 - (6 OF 6) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | ICT | QP.E.ME.MBL.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-ICT-08-Z00000-2ZZ0008 | ICT PARTIAL SITE PLAN - SHEET 08 - (8 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 08 | Z00000 | 2 | ZZ | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-09-Z00000-2ZZ0009 | ICT PARTIAL SITE PLAN - SHEET 09 - (9 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 09 | Z00000 | 2 | ZZ | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-10-Z00000-2ZZ0010 | ICT PARTIAL SITE PLAN - SHEET 10 - (10 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 10 | Z00000 | 2 | ZZ | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-11-CENT01-2B30004 | ICT SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 11 - (3 OF 3) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | ICT | QP.E.ME.MBL.GEN.1360 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 11 | CENT01 | 2 | B3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-ICT-11-Z00000-2ZZ0011 | ICT PARTIAL SITE PLAN - SHEET 11 - (11 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 11 | Z00000 | 2 | ZZ | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-12-Z00000-2ZZ0012 | ICT PARTIAL SITE PLAN - SHEET 12 - (12 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 12 | Z00000 | 2 | ZZ | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-13-Z00000-2ZZ0013 | ICT PARTIAL SITE PLAN - SHEET 16 - (13 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 13 | Z00000 | 2 | ZZ | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-14-Z00000-2ZZ0014 | ICT PARTIAL SITE PLAN - SHEET 17 - (14 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 14 | Z00000 | 2 | ZZ | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-15-Z00000-2ZZ0015 | ICT PARTIAL SITE PLAN - SHEET 18 - (15 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 15 | Z00000 | 2 | ZZ | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-16-Z00000-2ZZ0016 | ICT PARTIAL SITE PLAN - SHEET 19 - (16 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 16 | Z00000 | 2 | ZZ | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-17-Z00000-2ZZ0017 | ICT PARTIAL SITE PLAN - SHEET 20 - (17 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 17 | Z00000 | 2 | ZZ | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-18-Z00000-2ZZ0018 | ICT PARTIAL SITE PLAN - SHEET 21 - (18 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 18 | Z00000 | 2 | ZZ | 0018 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-19-GARD01-2ZZ0001 | ICT SYSTEM PLAN - GUARD ROOM | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-15 | ICT | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 19 | GARD01 | 2 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ICT-19-Z00000-2ZZ0019 | ICT PARTIAL SITE PLAN - SHEET 22 - (19 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 19 | Z00000 | 2 | ZZ | 0019 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-20-Z00000-2ZZ0020 | ICT PARTIAL SITE PLAN - SHEET 23 - (20 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 20 | Z00000 | 2 | ZZ | 0020 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-21-Z00000-2ZZ0021 | ICT PARTIAL SITE PLAN - SHEET 24 - (21 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 21 | Z00000 | 2 | ZZ | 0021 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-22-Z00000-2ZZ0022 | ICT PARTIAL SITE PLAN - SHEET 25 - (22 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 22 | Z00000 | 2 | ZZ | 0022 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-23-Z00000-2ZZ0023 | ICT PARTIAL SITE PLAN - SHEET 26 - (23 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 23 | Z00000 | 2 | ZZ | 0023 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-24-Z00000-2ZZ0024 | ICT PARTIAL SITE PLAN - SHEET 27 - (24 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 24 | Z00000 | 2 | ZZ | 0024 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-25-Z00000-2ZZ0025 | ICT PARTIAL SITE PLAN - SHEET 28 - (25 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 25 | Z00000 | 2 | ZZ | 0025 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-26-Z00000-2ZZ0026 | ICT PARTIAL SITE PLAN - SHEET 29 - (26 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 26 | Z00000 | 2 | ZZ | 0026 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-27-Z00000-2ZZ0027 | ICT PARTIAL SITE PLAN - SHEET 30 - (27 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 27 | Z00000 | 2 | ZZ | 0027 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ICT-28-Z00000-2ZZ0028 | ICT PARTIAL SITE PLAN - SHEET 31 - (28 OF 28) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | 1:100 | 2027-01-28 | ICT | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 28 | Z00000 | 2 | ZZ | 0028 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-LTC-00-CENT01-2B10001 | LIGHTING CONTROL SYSTEM -B1 SERVICE +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-00-CENT01-2B20001 | LIGHTING CONTROL SYSTEM - B2 SERVICE +893.5M LIGHTING CONTROL SYSTEM - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-00-CENT01-2B30001 | LIGHTING CONTROL SYSTEM - B3 PROMENADE +887.750M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-00-CENT01-2L10005 | LIGHTING CONTROL SYSTEM - L1- LOBBY LEVEL +905M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-00-CENT01-2L20001 | LIGHTING CONTROL SYSTEM - L2- THEATRE STALLS +913M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | CENT01 | 2 | L2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-00-CENT01-2L30001 | LIGHTING CONTROL SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | CENT01 | 2 | L3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-00-CENT01-2L40001 | LIGHTING CONTROL SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-00-CENT01-2L50001 | LIGHTING CONTROL SYSTEM - L5- SECOND CIRCLE & LOFT +928M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-00-CENT01-2L60001 | LIGHTING CONTROL SYSTEM - L6- SKY GARDEN +935.85M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-00-CENT01-2M10001 | LIGHTING CONTROL SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-00-CENT01-2M20001 | LIGHTING CONTROL SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-00-GARD01-2000001 | LIGHTING CONTROL SYSTEM - GUARD ROOM | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | GARD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-LTC-00-PARK01-2B10001 | LIGHTING CONTROL SYSTEM - B1 PARKING +900.5M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | Lighting Control | QP.E.ME.PAR.GEN.1279 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-30
QF01012-NES-C04518-SDW-LTC-00-SECE01-2000001 | LIGHTING CONTROL SYSTEM -SEC ROOM | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | SECE01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-LTC-00-Z00000-6ZZ0001 | LIGHTING CONTROL SYSTEM - SCHEMATIC DIAGRAM | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 00 | Z00000 | 6 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-LTC-01-BLAD01-2000001 | LIGHTING CONTROL SYSTEM - BLADE-01 (+870.5, +876.25, +882)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-LTC-01-BLAD02-2000001 | LIGHTING CONTROL SYSTEM - BLADE-02 (+876.25, +882, +887.75)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL2.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-LTC-01-BLAD03-2000001 | LIGHTING CONTROL SYSTEM - BLADE-03 (+847.5, +853.25, +859)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-LTC-01-BLAD04-2000001 | LIGHTING CONTROL SYSTEM - BLADE-04 (+863.85, +870.5, +876.25)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-LTC-01-BLAD05-2000001 | LIGHTING CONTROL SYSTEM - BLADE-05 (+894.5, +899.5, +905)- SHEET 1 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL5.GEN.2860 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-LTC-01-CENT01-2B10002 | LIGHTING CONTROL SYSTEM - B1 SERVICE +900.5M - SHEET 01 - (01 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-01-CENT01-2B20002 | LIGHTING CONTROL SYSTEM - B2 SERVICE +893.5M - SHEET 01 - (01 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-01-CENT01-2B30002 | LIGHTING CONTROL SYSTEM - B3 PROMENADE +887.750M - SHEET 01 - (01 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-01-CENT01-2L10002 | LIGHTING CONTROL SYSTEM - L1- LOBBY LEVEL +905M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-01-CENT01-2L20002 | LIGHTING CONTROL SYSTEM - L2- THEATRE STALLS +913M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | CENT01 | 2 | L2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-01-CENT01-2L30002 | LIGHTING CONTROL SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | CENT01 | 2 | L3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-01-CENT01-2L40002 | LIGHTING CONTROL SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-01-CENT01-2L50002 | LIGHTING CONTROL SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-01-CENT01-2L60002 | LIGHTING CONTROL SYSTEM - L6- SKY GARDEN +935.85M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-01-CENT01-2M10002 | LIGHTING CONTROL SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-01-CENT01-2M20002 | LIGHTING CONTROL SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-01-PARK01-2B10002 | LIGHTING CONTROL SYSTEM - B1 PARKING +900.5M - SHEET 01 - (01 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.PAR.GEN.1279 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 01 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-30
QF01012-NES-C04518-SDW-LTC-02-BLAD01-2000002 | LIGHTING CONTROL SYSTEM - BLADE-01 (+887.75, +893.5, +899.25)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-LTC-02-BLAD02-2000002 | LIGHTING CONTROL SYSTEM - BLADE-02 (+893.5, +899.25, +905)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL2.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-LTC-02-BLAD03-2000002 | LIGHTING CONTROL SYSTEM - BLADE-03 (+867.62, +876.25, +882)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-LTC-02-BLAD04-2000002 | LIGHTING CONTROL SYSTEM - BLADE-04 (+882, +887.75, +893.5)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-LTC-02-BLAD05-2000002 | LIGHTING CONTROL SYSTEM - BLADE-05 (+910.75, +917.5, +922.25)- SHEET 2 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL5.GEN.2860 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-LTC-02-CENT01-2B10003 | LIGHTING CONTROL SYSTEM - B1 SERVICE +900.5M - SHEET 02 - (02 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-02-CENT01-2B20003 | LIGHTING CONTROL SYSTEM - B2 SERVICE +893.5M - SHEET 02 - (02 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-02-CENT01-2B30003 | LIGHTING CONTROL SYSTEM - B3 PROMENADE +887.750M - SHEET 02 - (02 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-02-CENT01-2L10003 | LIGHTING CONTROL SYSTEM - L1- LOBBY LEVEL +905M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-02-CENT01-2L20003 | LIGHTING CONTROL SYSTEM - L2- THEATRE STALLS +913M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | CENT01 | 2 | L2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-02-CENT01-2L30003 | LIGHTING CONTROL SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | CENT01 | 2 | L3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-02-CENT01-2L40003 | LIGHTING CONTROL SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-02-CENT01-2L50003 | LIGHTING CONTROL SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-02-CENT01-2L60003 | LIGHTING CONTROL SYSTEM - L6- SKY GARDEN +935.85M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-02-CENT01-2M10003 | LIGHTING CONTROL SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-02-CENT01-2M20003 | LIGHTING CONTROL SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-02-PARK01-2B10003 | LIGHTING CONTROL SYSTEM - B1 PARKING +900.5M - SHEET 02 - (02 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.PAR.GEN.1279 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 02 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-30
QF01012-NES-C04518-SDW-LTC-03-BLAD01-2000003 | LIGHTING CONTROL SYSTEM - BLADE-01 (+905, +910.75, +917.5)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-LTC-03-BLAD02-2000003 | LIGHTING CONTROL SYSTEM - BLADE-02 (+910.75, +916.5, +922.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL2.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-LTC-03-BLAD03-2000003 | LIGHTING CONTROL SYSTEM - BLADE-03 (+887.75, +893.5, +899.25)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-LTC-03-BLAD04-2000003 | LIGHTING CONTROL SYSTEM - BLADE-04 (+899.25, +905, +910.75)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-LTC-03-BLAD05-2000003 | LIGHTING CONTROL SYSTEM - BLADE-05 (+928, +935.85, +941.60)- SHEET 3 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL5.GEN.2860 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-LTC-03-CENT01-2B10004 | LIGHTING CONTROL SYSTEM - B1 SERVICE +900.5M - SHEET 04 - (03 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | CENT01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-03-CENT01-2L10004 | LIGHTING CONTROL SYSTEM - L1- LOBBY LEVEL +905M - SHEET 04 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-03-CENT01-2L20004 | LIGHTING CONTROL SYSTEM - L2- THEATRE STALLS +913M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | CENT01 | 2 | L2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-03-CENT01-2L30004 | LIGHTING CONTROL SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | CENT01 | 2 | L3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-03-CENT01-2L40004 | LIGHTING CONTROL SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-03-CENT01-2L50004 | LIGHTING CONTROL SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-03-CENT01-2L60004 | LIGHTING CONTROL SYSTEM - L6- SKY GARDEN +935.85M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-03-CENT01-2M10004 | LIGHTING CONTROL SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | CENT01 | 2 | M1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-03-CENT01-2M20004 | LIGHTING CONTROL SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-03-PARK01-2B10004 | LIGHTING CONTROL SYSTEM - B1 PARKING +900.5M - SHEET 03 - (03 OF 03) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.PAR.GEN.1279 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 03 | PARK01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-30
QF01012-NES-C04518-SDW-LTC-04-BLAD01-2000004 | LIGHTING CONTROL SYSTEM - BLADE-01 (+922.25, +928, & +935.85)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-LTC-04-BLAD02-2000004 | LIGHTING CONTROL SYSTEM - BLADE-02 (+928, +935.85, +941.6)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL2.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-LTC-04-BLAD03-2000004 | LIGHTING CONTROL SYSTEM - BLADE-03 (+905, +910.75, +916.5)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-LTC-04-BLAD04-2000004 | LIGHTING CONTROL SYSTEM - BLADE-04 (+916.5, +922.25, +928)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-LTC-04-BLAD05-2000004 | LIGHTING CONTROL SYSTEM - BLADE-05 (+948.10, +954, +957.35)- SHEET 4 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL5.GEN.2860 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-LTC-04-CENT01-2B10005 | LIGHTING CONTROL SYSTEM - B1 SERVICE +900.5M - SHEET 05 - (04 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-04-CENT01-2B20004 | LIGHTING CONTROL SYSTEM - B2 SERVICE +893.5M - SHEET 04 - (03 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-04-CENT01-2L10005 | LIGHTING CONTROL SYSTEM - L1- LOBBY LEVEL +905M - SHEET 05 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | CENT01 | 2 | L1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-04-CENT01-2L20005 | LIGHTING CONTROL SYSTEM - L2- THEATRE STALLS +913M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | CENT01 | 2 | L2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-04-CENT01-2L30005 | LIGHTING CONTROL SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | CENT01 | 2 | L3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-04-CENT01-2L40005 | LIGHTING CONTROL SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-04-CENT01-2L50005 | LIGHTING CONTROL SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-04-CENT01-2L60005 | LIGHTING CONTROL SYSTEM - L6- SKY GARDEN +935.85M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-04-CENT01-2M10005 | LIGHTING CONTROL SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | CENT01 | 2 | M1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-04-CENT01-2M20005 | LIGHTING CONTROL SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 04 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-05-BLAD01-2000005 | LIGHTING CONTROL SYSTEM - BLADE-01 (+941.6, ROOF, & +958.45)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-LTC-05-BLAD02-2000005 | LIGHTING CONTROL SYSTEM - BLADE-02 (+948.28 , +951.4)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL2.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-07
QF01012-NES-C04518-SDW-LTC-05-BLAD03-2000005 | LIGHTING CONTROL SYSTEM - BLADE-03 (+921 , +928 , +935.85 )- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL3.GEN.3460 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-LTC-05-BLAD04-2000005 | LIGHTING CONTROL SYSTEM - BLADE-04 (+935.85, +941.60, +947.35)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-LTC-05-BLAD04-2000006 | LIGHTING CONTROL SYSTEM - BLADE-04 (+954,+959, +968.30 ,+975.82)- SHEET 6 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL4.GEN.5830 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-09-28
QF01012-NES-C04518-SDW-LTC-05-BLAD05-2000005 | LIGHTING CONTROL SYSTEM - BLADE-05 (+969.30 , +960.09)- SHEET 5 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL5.GEN.2860 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | BLAD05 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-LTC-05-CENT01-2B10006 | LIGHTING CONTROL SYSTEM - B1 SERVICE +900.5M - SHEET 07 - (05 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-05-CENT01-2B20005 | LIGHTING CONTROL SYSTEM - B2 SERVICE +893.5M - SHEET 05 - (04 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-05-CENT01-2B30004 | LIGHTING CONTROL SYSTEM - B3 PROMENADE +887.750M - SHEET 05 - (03 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | CENT01 | 2 | B3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-05-CENT01-2L10006 | LIGHTING CONTROL SYSTEM - L1- LOBBY LEVEL +905M - SHEET 10 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | CENT01 | 2 | L1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-05-CENT01-2L20006 | LIGHTING CONTROL SYSTEM - L2- THEATRE STALLS +913M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | CENT01 | 2 | L2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-05-CENT01-2L30006 | LIGHTING CONTROL SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | CENT01 | 2 | L3 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-05-CENT01-2L40006 | LIGHTING CONTROL SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-05-CENT01-2L50006 | LIGHTING CONTROL SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-05-CENT01-2L60006 | LIGHTING CONTROL SYSTEM - L6- SKY GARDEN +935.85M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-05-CENT01-2M10006 | LIGHTING CONTROL SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | CENT01 | 2 | M1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-05-CENT01-2M20006 | LIGHTING CONTROL SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 05 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-06-BLAD01-2000006 | LIGHTING CONTROL SYSTEM - BLADE-01 (+962.2, +972.48, & +989)- SHEET 6 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.BL1.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-LTC-06-CENT01-2B10007 | LIGHTING CONTROL SYSTEM - B1 SERVICE +900.5M - SHEET 08 - (06 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | CENT01 | 2 | B1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-06-CENT01-2L10007 | LIGHTING CONTROL SYSTEM - L1- LOBBY LEVEL +905M - SHEET 11 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | CENT01 | 2 | L1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-06-CENT01-2L20007 | LIGHTING CONTROL SYSTEM - L2- THEATRE STALLS +913M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | CENT01 | 2 | L2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-06-CENT01-2L30007 | LIGHTING CONTROL SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | CENT01 | 2 | L3 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-06-CENT01-2L40007 | LIGHTING CONTROL SYSTEM - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | CENT01 | 2 | L4 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-06-CENT01-2L50007 | LIGHTING CONTROL SYSTEM - L5- SECOND CIRCLE & LOFT +928M- SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | CENT01 | 2 | L5 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-06-CENT01-2L60007 | LIGHTING CONTROL SYSTEM - L6- SKY GARDEN +935.85M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | CENT01 | 2 | L6 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-06-CENT01-2L80001 | LIGHTING CONTROL SYSTEM - L8 ROYAL MAJLIS +948.28M - SHEET 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-06-CENT01-2M10007 | LIGHTING CONTROL SYSTEM - L1-UPPER LOBBY MEZZANINE +909M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | CENT01 | 2 | M1 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-06-CENT01-2M20007 | LIGHTING CONTROL SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | CENT01 | 2 | M2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-06-CENT01-2RL0001 | LIGHTING CONTROL SYSTEM - ROOF & ABOVE - SHEET 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 06 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-07-CENT01-2B10008 | LIGHTING CONTROL SYSTEM - B1 SERVICE +900.5M - SHEET 09 - (07 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 07 | CENT01 | 2 | B1 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-08-CENT01-2B20006 | LIGHTING CONTROL SYSTEM - B2 SERVICE +893.5M - SHEET 08 - (05 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-09-CENT01-2B20007 | LIGHTING CONTROL SYSTEM - B2 SERVICE +893.5M - SHEET 09 - (06 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 09 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-11-CENT01-2B20008 | LIGHTING CONTROL SYSTEM - B2 SERVICE +893.5M - SHEET 11 - (07 OF 07) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 11 | CENT01 | 2 | B2 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-LTC-11-CENT01-2B30005 | LIGHTING CONTROL SYSTEM - B3 PROMENADE +887.750M - SHEET 11 - (04 OF 04) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | Lighting Control | QP.E.ME.MBL.GEN.5060 | FI_60_25 | QF01012 | NES | C04518 | SDW | LTC | 11 | CENT01 | 2 | B3 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-22
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000001 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +882M - BL1 - IDF (Z00-B03-153) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000002 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +905M - BL1 - IDF (Z00-L01-173) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000003 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +922.25M - BL1 - IDF (Z00-L04-158) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000004 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +935.85M - BL1 - IDF (Z00-L06-159) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000005 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +882M - BL1 - IDF (Z00-B03-153A) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000006 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +928M - BL1 - IDF (Z00-L05-151) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4B30001 | ELECTRICAL ENLARGED PLAN-BLADE-1+870.5M_ELEC.RM_(Z00-B03-167E) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_30 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4L10001 | ELECTRICAL ENLARGED PLAN-BLADE-1+905M_ELEC.RM_(Z00-L01-171) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_32 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | L1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4L30001 | ELECTRICAL ENLARGED PLAN-BLADE-1+917.5M_ELEC.RM_(Z00-L03-151) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_42 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | L3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4L40001 | ELECTRICAL ENLARGED PLAN-BLADE-1+922.25M_ELEC.RM_(Z00-L04-169) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_35 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | L4 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4L50001 | ELECTRICAL ENLARGED PLAN-BLADE-1+928M_ELEC.RM_(Z00-L05-074B) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4L60001 | ELECTRICAL ENLARGED PLAN-BLADE-1+935.85M_ELEC.RM_(Z00-L06-158) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_102 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | L6 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4RL0001 | ELECTRICAL ENLARGED PLAN-BLADE-1+953.3M_ELEC.RM_(Z00-RF-160B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_82 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | RL | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4RL0002 | ELECTRICAL ENLARGED PLAN-BLADE-1+953.3M_ELEC.RM_(Z00-RF-160C) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_83 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | RL | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-0000001 | IDF ROOM ENLARGED DETAIL - BLADE-02 LEVEL +887.75M - BL2 - IDF (Z00-B03-235) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 0 | 00 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-MEP-00-BLAD02-0000003 | IDF ROOM ENLARGED DETAIL - BLADE-02 LEVEL +928M - BL2 - IDF (Z00-L05-210) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 0 | 00 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-MEP-00-BLAD02-0000004 | IDF ROOM ENLARGED DETAIL - BLADE-02 LEVEL +887.75M - BL2 - IDF (Z00-B03-221) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 0 | 00 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-MEP-00-BLAD02-0000005 | IDF ROOM ENLARGED DETAIL - BLADE-02 LEVEL +905M - BL2 - IDF (Z00-L01-211) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 0 | 00 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-MEP-00-BLAD02-0000006 | IDF ROOM ENLARGED DETAIL - BLADE-02 LEVEL +935.85M - BL2 - IDF (Z00-L06-212) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 0 | 00 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4B30001 | ELECTRICAL ENLARGED PLAN-BLADE-2+887.75M_ELEC.RM_(Z00-B03-211) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_89 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4B30002 | ELECTRICAL ENLARGED PLAN-BLADE-2+887.75M_ELEC.RM_(Z00-B03-240) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_90 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | B3 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4L10001 | ELECTRICAL ENLARGED PLAN-BLADE-2+905M_ELEC.RM_(Z00-L01-214) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_33 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | L1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4L50001 | ELECTRICAL ENLARGED PLAN-BLADE-2+928M_ELEC.RM_(Z00-L05-239) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_36 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4L50002 | ELECTRICAL ENLARGED PLAN-BLADE-2_ELEC.RM_(Z00-L05-246) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_100 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | L5 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4L50003 | ELECTRICAL ENLARGED PLAN-BLADE-2+928M_ELEC.RM_(Z00-L05-225) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_43 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | L5 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4L60001 | ELECTRICAL ENLARGED PLAN-BLADE-2+935.85M_ELEC.RM_(Z00-L06-212) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_37 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | L6 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000001 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +876.25M - IDF (Z00-B03-359) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000002 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +905M - IDF (Z00-L01-457) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000003 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +928M - BL3 - IDF (Z00-L05-396) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000004 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +867.62M - IDF (Z00-B03-354) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000005 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +905M - IDF (Z00-L01-390) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000006 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +910.75M - IDF (Z00-L01-330) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000007 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +916.5M - IDF (Z00-L02-391) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000008 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +928M - BL3 - IDF (Z00-L05-395) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4B30001 | ELECTRICAL ENLARGED PLAN-BLADE-3+859.0M_ELEC.RM_(Z00-B03-315) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_91 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4B30002 | ELECTRICAL ENLARGED PLAN-BLADE-3+859.0M_ELEC.RM_(Z00-B03-361) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_92 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | B3 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L20001 | ELECTRICAL ENLARGED PLAN-BLADE-3+916.5M_ELEC.RM_(Z00-L02-367) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_95 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L20002 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELEC.RM_(Z00-L02-335) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_96 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L20003 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELEC.RM_(Z00-L02-336) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_97 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L2 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L20004 | ELECTRICAL ENLARGED PLAN-BLADE-3+910.75M_ELEC.RM_(Z00-L01-319) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_98 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L2 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50001 | ELECTRICAL ENLARGED PLAN-BLADE-3+928M_ELEC.CPB_(Z00-L05-376B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_70 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50002 | ELECTRICAL ENLARGED PLAN-BLADE-3+928M_ELEC.RM_(Z00-L05-376A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-ESP-02-CENT01-2L50003 | SMALL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ESP-03-CENT01-2L50004 | SMALL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ESP-04-CENT01-2L50005 | SMALL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ESP-05-CENT01-2L50006 | SMALL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-ESP-06-CENT01-2L50007 | SMALL POWER SYSTEM - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 06 | CENT01 | 2 | L5 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-01-09
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000001 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +876.25M - IDF (Z00-B03-408) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000002 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +899.25M - BL4 - IDF (Z00-B01-467) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000003 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +916.5M - BL4 - IDF (Z00-L02-406) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000004 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +928M - BL4 - IDF (Z00-L05-426) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000005 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +887.75M - BL4 - IDF (Z00-B03-425) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000006 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +916.5M - BL4 - IDF (Z00-L02-319) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000007 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +941.6M - BL4 - IDF (Z00-L06-407) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | IDF | QP.E.ME.BL1.GEN.3540 | FI_90_72 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4B30001 | ELECTRICAL ENLARGED PLAN-BLADE-4_ELEC.RM_(Z00-B03-463) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_93 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4B30002 | ELECTRICAL ENLARGED PLAN-BLADE-4+876.25M_ELEC.RM_(Z00-B03-452) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_94 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | B3 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4B30003 | ELECTRICAL ENLARGED PLAN-BLADE-4+863.85M_ELEC.RM_(Z00-B03-447) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_31 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | B3 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ESP-00-CENT01-2M20001 | SMALL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - OVERALL | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4L20001 | ELECTRICAL ENLARGED PLAN-BLADE-4+916.5M_ELEC.RM_(Z00-L02-477) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_34 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | L2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4L50001 | ELECTRICAL ENLARGED PLANBLADE-4+928M_ELEC.CPB_(Z00-L05-427) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_101 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4L60001 | ELECTRICAL ENLARGED PLAN-BLADE-4+941.6M_ELEC.RM_(Z00-L06-489B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_39 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | L6 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4L60002 | ELECTRICAL ENLARGED PLAN-BLADE-4+935.85M_ELEC.RM_(Z00-L06-487A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_38 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | L6 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4L60003 | ELECTRICAL ENLARGED PLAN-BLADE-4+941.6M_ELEC.RM_(Z00-L06-489C) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_40 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | L6 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD05-0000001 | IDF ROOM ENLARGED DETAIL - BLADE-05 LEVEL +899.5M - BL5 - IDF (Z00-B01-506G) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 0 | 00 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-MEP-00-BLAD05-0000002 | IDF ROOM ENLARGED DETAIL - BLADE-05 LEVEL +935.85M - BL5-IDF (Z00-L06-510) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 0 | 00 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-MEP-00-BLAD05-0000003 | IDF ROOM ENLARGED DETAIL - BLADE-05 LEVEL +899.5M - BL5 - IDF (Z00-B01-506I) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 0 | 00 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-MEP-00-BLAD05-4B10001 | ELECTRICAL ENLARGED PLAN-BLADE-5+899.5M_ELEC.RM_(Z00-B01-523) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_29 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 4 | B1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD05-4L50001 | ELECTRICAL ENLARGED PLAN-BLADE-1+928M_ELEC.RM_(Z00-L05-524) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 4 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD05-4L60001 | ELECTRICAL ENLARGED PLAN-BLAD05+941.16M_ELEC.RM_(Z00-L08-506U) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_41 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 4 | L6 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10001 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-018) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_44 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10002 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-030) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_45 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10003 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.CB_(Z00-B01-042) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_46 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10004 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-050) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_47 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10005 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-051)-SHEET-01 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_48 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10006 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-084) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_49 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10007 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-090) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_50 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ESP-01-CENT01-2M20002 | SMALL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (01 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 01 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10010 | ELECTRICAL ENLARGED PLAN-CENTRAL-01 B01_ELEC.RM_(Z00-B01-050H) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_88 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0010 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10011 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-051)-SHEET-02 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0011 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20001 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_GEN_(Z00-B02-025)-SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_86 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20002 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_GEN_(Z00-B02-025)-SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_87 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ELE-00-CENT01-4B20003 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_TRANSFORMER_(Z00-B02-004)-SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 4 | B2 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-08-17
QF01012-NES-C04518-SDW-ELE-00-CENT01-4B20004 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_TRANSFORMER_(Z00-B02-004)-SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 4 | B2 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-08-17
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20005 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_ELEC.RM_(Z00-B02-026) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_53 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ESP-02-CENT01-2M20003 | SMALL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (02 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 02 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20007 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_ELEC.RM_(Z00-B02-034) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_54 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20008 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_ELEC.RM_(Z00-B02-034A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_55 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B30001 | ELECTRICAL ENLARGED PLAN-B3 PROMENADE+887.750M_ELEC_(Z00-B03-017) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_56 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L10001 | ELECTRICAL ENLARGED PLAN-L1-LOBBY LEVEL+905M_ELEC.RM_(Z00-L01-033) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_57 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L10002 | ELECTRICAL ENLARGED PLAN-L1-LOBBY LEVEL+905M_ELEC.RM_(Z00-L01-036) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_58 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L1 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L20001 | ELECTRICAL ENLARGED PLAN-L2-THEATRE STALLS+913M_ELEC.RM_(Z00-L02-073) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_60 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L20002 | ELECTRICAL ENLARGED PLAN-L2-THEATRE STALLS+913M_ELEC.RM_(Z00-L02-090B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_61 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L30001 | ELECTRICAL ENLARGED PLAN-L3-STALL MEZZANINE&ADAPTIVE THEATRE+917.5M_ELEC.RM_(Z00-L03-055) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_63 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ELE-00-CENT01-4L30004 | ELECTRICAL ENLARGED PLAN-L3-STALL MEZZANINE&ADAPTIVE THEATRE+917.5M_ELEC.RM_(Z00-L03-007A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_62 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 4 | L3 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L40001 | ELECTRICAL ENLARGED PLAN-L4-FIRST CIRCLE&ADAPTIVE THEATRE+921M_ELEC.CLST_(Z00-L04-018) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_65 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L4 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L40002 | ELECTRICAL ENLARGED PLAN-L4-FIRST CIRCLE&ADAPTIVE THEATRE+921M_ELEC.RM_(Z00-L04-011A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_64 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L4 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L40003 | ELECTRICAL ENLARGED PLAN-L4-FIRST CIRCLE&ADAPTIVE THEATRE+921M_ELEC.RM_(Z00-L04-020) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_28 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L4 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50002 | ELECTRICAL ENLARGED PLAN-L5 SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-052D) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_28 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50003 | ELECTRICAL ENLARGED PLAN-L5 SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-052C) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_27 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50004 | ELECTRICAL ENLARGED PLAN-L5 SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-052B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_26 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50005 | ELECTRICAL ENLARGED PLAN-L5-SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-074A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_68 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50007 | ELECTRICAL ENLARGED PLAN-L5-SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-071B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50008 | ELECTRICAL ENLARGED PLAN-L5-SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-071A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_67 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50009 | ELECTRICAL ENLARGED PLAN-L5-SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-052A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_66 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0009 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L60001 | ELECTRICAL ENLARGED PLAN-L6-SKY GARDEN+935.85M_ELEC.RM_(Z00-L06-025) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_77 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L6 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L60002 | ELECTRICAL ENLARGED PLAN-L6-SKY GARDEN+935.85M_ELEC.RM_(Z00-L06-512) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_79 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L6 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L60003 | ELECTRICAL ENLARGED PLAN-L6-SKY GARDEN+935.85M_ELEC.CB_(Z00-L06-170) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_78 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L6 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L60004 | ELECTRICAL ENLARGED PLAN-L6-SKY GARDEN+935.85M_ELEC.RM_(Z00-L06-004D) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_73 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L6 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ESP-03-CENT01-2M20004 | SMALL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (03 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 03 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L80002 | ELECTRICAL ENLARGED PLAN-L8 ROYAL MAJLIS+948.28M_ELEC.RM_(Z00-L08-021) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_80 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L8 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4M10001 | ELECTRICAL ENLARGED PLAN-L1M+909.0M_ELEC.RM_(Z00-L01-051) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_59 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | M1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4M20001 | ELECTRICAL ENLARGED PLAN-L5.5 LOFT MEP LEVEL+931.1_ELEC.RM_(Z00-L05-110) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_73 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | M2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4M20002 | ELECTRICAL ENLARGED PLAN-L5.5 LOFT MEP LEVEL+931.1_ELEC.RM_(Z00-L05-145) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_74 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | M2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4M20003 | ELECTRICAL ENLARGED PLAN-L5.5 LOFT MEP LEVEL+931.1_ELEC.RM_(Z00-L05-149B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_75 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | M2 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-01-CENT01-0B10001 | IDF ROOM ENLARGED DETAIL - B1 SERVICE +900.5M - IDF(Z00-B01-039) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 01 | CENT01 | 0 | B1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-01-CENT01-0B30001 | IDF ROOM ENLARGED DETAIL - B3 PROMENADE +887.750M - IDF (Z00-B03-019) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 01 | CENT01 | 0 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-07-15
QF01012-NES-C04518-SDW-MEP-01-CENT01-0M20001 | IDF ROOM ENLARGED DETAIL - L5.5 LOFT +931.7M - IDF (Z00-L05-132) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.5540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 01 | CENT01 | 0 | M2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-23
QF01012-NES-C04518-SDW-MEP-01-CENT01-0M20003 | IDF ROOM ENLARGED DETAIL - L5.5 LOFT +931.7M - IDF (Z00-L05-142) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.5540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 01 | CENT01 | 0 | M2 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-23
QF01012-NES-C04518-SDW-MEP-02-CENT01-0B30002 | IDF ROOM ENLARGED DETAIL - B3 PROMENADE +887.750M - IDF (Z00-B03-021) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 02 | CENT01 | 0 | B3 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-07-15
QF01012-NES-C04518-SDW-MEP-02-CENT01-0M10001 | IDF ROOM ENLARGED DETAIL - L1 UPPER LOBBY MEZZANINE LEVEL +909M - IDF (Z00-L01-060) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6660 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 02 | CENT01 | 0 | M1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-22
QF01012-NES-C04518-SDW-MEP-02-CENT01-0M20002 | IDF ROOM ENLARGED DETAIL - L5.5 LOFT +931.7M - IDF (Z00-L05-130) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.5540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 02 | CENT01 | 0 | M2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-23
QF01012-NES-C04518-SDW-MEP-02-CENT01-0M20004 | IDF ROOM ENLARGED DETAIL - L5.5 LOFT +931.7M - IDF (Z00-L05-131) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.5540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 02 | CENT01 | 0 | M2 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-23
QF01012-NES-C04518-SDW-MEP-03-CENT01-0L50001 | IDF ROOM ENLARGED DETAIL - L5 SECOND CIRCLE & LOFT +928M - IDF (Z00-L05-098) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 03 | CENT01 | 0 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-MEP-04-CENT01-0B10006 | MAIN SECURITY CONTROL ENLARGED DETAILS- B1 SERVICE- MAIN SEC. CONTROL (Z00-B01-031) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 04 | CENT01 | 0 | B1 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-MEP-04-CENT01-0B10007 | SECURITY EQUIPMENT ENLARGED DEATILS - B1 SERVICE - SEC.EQUIP (Z00-B01-029) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 04 | CENT01 | 0 | B1 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-MEP-04-CENT01-0B10008 | TETRA ROOM ENLARGED DETAIL- B1 SERVICE +900.5M - TETRA (Z00-B01-139) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 04 | CENT01 | 0 | B1 | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-MEP-04-CENT01-0L40001 | IDF ROOM ENLARGED DETAIL - L4 FIRST CIRCLE & ADAPTIVE THEATRE +921M - IDF (Z00-L04-011) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6720 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 04 | CENT01 | 0 | L4 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-05-CENT01-0B10001 | IDF ROOM ENLARGED DETAIL - B1 SERVICE +900.5M - IDF (Z00-B01-064) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | B1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-05-CENT01-0B10004 | SERVER ROOM / MDF ENLARGED DETAIL - B1 SERVICE +900.5M - SERVER RM / MDF (Z00-B01-041) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | B1 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-MEP-05-CENT01-0B20001 | POE / MTR ROOM ENLARGED DETAIL - B2 SERVICE +893.5M - POE / MTR (Z00-B02-011) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | B2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-08-17
QF01012-NES-C04518-SDW-MEP-05-CENT01-0B20002 | GSM ROOM ENLARGED DETAIL - B2 SERVICE +893.5M - GSM (Z00-B02-018) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2027-01-08 | ICT | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | B2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-08-17
QF01012-NES-C04518-SDW-MEP-05-CENT01-0B20003 | IDF ROOM ENLARGED DETAIL - B2 SERVICE +893.5M - IDF (Z00-B02-030) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1290 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | B2 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-05-CENT01-0L10001 | IDF ROOM ENLARGED DETAIL - L1 LOBBY LEVEL +905M - IDF (Z00-L01-034) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6640 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | L1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-MEP-05-CENT01-0L50002 | IDF ROOM ENLARGED DETAIL - L5 SECOND CIRCLE & LOFT +928M - IDF (Z00-L05-015) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | L5 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-MEP-05-CENT01-0L80001 | IDF ROOM ENLARGED DETAIL - L8 ROYAL MAJLIS +948.28M - IDF(Z00-L08-023) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6580 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | L8 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-04-24
QF01012-NES-C04518-SDW-MEP-05-CENT01-0M10002 | IDF ROOM ENLARGED DETAIL - L1 UPPER LOBBY MEZZANINE LEVEL +909M - IDF (Z00-L01-057) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6660 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | M1 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-22
QF01012-NES-C04518-SDW-MEP-05-CENT01-0M10003 | IDF ROOM ENLARGED DETAIL - L1 UPPER LOBBY MEZZANINE LEVEL +909M - IDF (Z00-L01-052) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6660 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | M1 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-22
QF01012-NES-C04518-SDW-MEP-06-CENT01-0L50003 | IDF ROOM ENLARGED DETAIL - L5 LOFT +928M - IDF (Z00-L05-100) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 06 | CENT01 | 0 | L5 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-MEP-13-PARK01-0B10001 | IDF ENLARGED DETAIL- B1 PARKING +900.5M - IDF (Z00-B01-109) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 13 | PARK01 | 0 | B1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-14-PARK01-0B10002 | IDF ROOM ENLARGED DETAIL - B1 PARKING +900.5M - IDF (Z00-B01-087) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 14 | PARK01 | 0 | B1 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-15-PARK01-0B10003 | IDF ROOM ENLARGED DETAIL - B1 PARKING +900.5M - IDF (Z00-B01-070) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 15 | PARK01 | 0 | B1 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-19-GARD01-2ZZ0001 | GUARDHOUSE ENLARGED DETAIL - L1 LOBBY LEVEL +905M - GUARDHOUSE (Z00-L01-047) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 19 | GARD01 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-SEC-00-BLAD01-0000002 | SECURITY SINGLE LINE DIAGRAM FOR BLADE-01 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD01 | 0 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-SEC-00-BLAD01-2000001 | SECURITY SYSTEM PLAN - BLADE-01 (+870.5 M​, +876.2 5 M​ & +882 M​) - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD01 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-SEC-00-BLAD01-2000002 | SECURITY SYSTEM PLAN - BLADE-01 (+887.75 M​, +893.5 M& +899.25 M) - SHEET 2 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD01 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-SEC-00-BLAD01-2000003 | SECURITY SYSTEM PLAN - BLADE-01 (+905 M, +910.75 M​​​ & +917.5 M​) - SHEET 3 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD01 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-SEC-00-BLAD01-2000004 | SECURITY SYSTEM PLAN - BLADE-01 (+922.25 M​, +928 M & +935.85 M) - SHEET 4 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD01 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-SEC-00-BLAD01-2000005 | SECURITY SYSTEM PLAN - BLADE-01 (+941.6M​, ROOF BLADE 1​ & +958.45​ M) - SHEET 5 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD01 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-SEC-00-BLAD01-2000006 | SECURITY SYSTEM PLAN - BLADE-01 (+962.2 M, +972.48M​​ & +989 M) - SHEET 6 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD01 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-SEC-00-BLAD01-6000016 | SECURITY SCHEDULE FOR BLADE-01 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL1.GEN.3660 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD01 | 6 | 00 | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-SEC-00-BLAD02-0000002 | SECURITY SINGLE LINE DIAGRAM FOR BLADE-02 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD02 | 0 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-SEC-00-BLAD02-2000001 | SECURITY SYSTEM PLAN - BLADE-02 (+876.25 M​, +882.0​ M & +887.75 M​) - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD02 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-SEC-00-BLAD02-2000002 | SECURITY SYSTEM PLAN - BLADE-02 (+893.5 M​, +899.25 M & +905 M) - SHEET 2 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD02 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-SEC-00-BLAD02-2000003 | SECURITY SYSTEM PLAN - BLADE-02 (+910.75M, +916.5M & +922.25M) - SHEET 3 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD02 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-SEC-00-BLAD02-2000004 | SECURITY SYSTEM PLAN - BLADE-02 (+928 M, +935.85 M & +941.60 M) - SHEET 4 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD02 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-SEC-00-BLAD02-2000005 | SECURITY SYSTEM PLAN - BLADE-02 (+948.28 M​ & +951.40 M ) - SHEET 5 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD02 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-SEC-00-BLAD02-6000017 | SECURITY SCHEDULE FOR BLADE-02 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL2.GEN.3340 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD02 | 6 | 00 | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-01
QF01012-NES-C04518-SDW-SEC-00-BLAD03-0000002 | SECURITY SINGLE LINE DIAGRAM FOR BLADE-03 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD03 | 0 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SEC-00-BLAD03-2000001 | SECURITY SYSTEM PLAN - BLADE-03 (+847.5, +853.25, +859) - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD03 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SEC-00-BLAD03-2000002 | SECURITY SYSTEM PLAN - BLADE-03 (+867.62, +876.25, +882) - SHEET 2 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD03 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SEC-00-BLAD03-2000003 | SECURITY SYSTEM PLAN - BLADE-03 (+887.75, +893.5, +899.25) - SHEET 3 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD03 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SEC-00-BLAD03-2000004 | SECURITY SYSTEM PLAN - BLADE-03 (+905, +910.75, +916.5) - SHEET 4 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD03 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SEC-00-BLAD03-2000005 | SECURITY SYSTEM PLAN - BLADE-03(+921 , +928 , +935.85 ) - SHEET 5 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD03 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SEC-00-BLAD03-6000018 | SECURITY SCHEDULE FOR BLADE-03 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL3.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD03 | 6 | 00 | 0018 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SEC-00-BLAD04-0000002 | SECURITY SINGLE LINE DIAGRAM FOR BLADE-04 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD04 | 0 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-SEC-00-BLAD04-2000001 | SECURITY SYSTEM PLAN - BLADE-04 (+863.85, +870.5, +876.25) - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD04 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-SEC-00-BLAD04-2000002 | SECURITY SYSTEM PLAN - BLADE-04 (+882, +887.75, +893.5) - SHEET 2 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD04 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-SEC-00-BLAD04-2000003 | SECURITY SYSTEM PLAN - BLADE-04 (+899.25, +910.75, +916.5) - SHEET 3 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD04 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-SEC-00-BLAD04-2000004 | SECURITY SYSTEM PLAN - BLADE-04 (+922.25, +928, +935.85) - SHEET 4 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD04 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-SEC-00-BLAD04-2000005 | SECURITY SYSTEM PLAN - BLADE-04 (+941.60, +947.35, +954) - SHEET 5 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD04 | 2 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-SEC-00-BLAD04-2000006 | SECURITY SYSTEM PLAN - BLADE-04 (+959, +968.30 ,+975.82) - SHEET 6 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD04 | 2 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-SEC-00-BLAD04-6000019 | SECURITY SCHEDULE FOR BLADE-04 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL4.GEN.5990 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD04 | 6 | 00 | 0019 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-04
QF01012-NES-C04518-SDW-SEC-00-BLAD05-0000002 | SECURITY SINGLE LINE DIAGRAM FOR BLADE-05 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD05 | 0 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-SEC-00-BLAD05-2000001 | SECURITY SYSTEM PLAN - BLADE-05 (+894.5, +899.5, +905) - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD05 | 2 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-SEC-00-BLAD05-2000002 | SECURITY SYSTEM PLAN - BLADE-05 (+910.75, +917.5, +922.25) - SHEET 2 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD05 | 2 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-SEC-00-BLAD05-2000003 | SECURITY SYSTEM PLAN - BLADE-05 (+928, +935.85, +941.60) - SHEET 3 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD05 | 2 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-SEC-00-BLAD05-2000004 | SECURITY SYSTEM PLAN - BLADE-05 (+948.10, +954, +957.35) - SHEET 4 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD05 | 2 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-SEC-00-BLAD05-6000020 | SECURITY SCHEDULE FOR BLADE-05 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.BL5.GEN.2960 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | BLAD05 | 6 | 00 | 0020 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-SEC-00-CENT01-0ZZ0000 | SECURITY SINGLE LINE DIAGRAM FOR MAIN BUILDING - OVER ALL | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 0 | ZZ | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-0ZZ0001 | SECURITY SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-01 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 0 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-0ZZ0002 | SECURITY SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-02 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 0 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-0ZZ0003 | SECURITY SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-03 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 0 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-0ZZ0004 | SECURITY SINGLE LINE DIAGRAM FOR MAIN BUILDING - PART-04 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 0 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-0ZZ0005 | INTRUSION ALARM SYSTEM SCHEMATIC DIAGRAM - OVERALL | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-22 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 0 | ZZ | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-0ZZ0006 | INTERCOM SYSTEM SCHEMATIC DIAGRAM - OVERALL | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-22 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 0 | ZZ | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-0ZZ0007 | DISABLED TOILET ALARM SYSTEM SCHEMATIC DIAGRAM - OVERALL | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-22 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 0 | ZZ | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2B10000 | SECURITY SYSTEM OVERALL PLAN - B1 SERVICE +900.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | B1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2B20000 | SECURITY SYSTEM OVERALL PLAN - B2 SERVICE +893.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | B2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2B30000 | SECURITY SYSTEM OVERALL PLAN - B3 PROMENADE +887.750M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-07-23 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | B3 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2L10000 | SECURITY SYSTEM OVERALL PLAN - L1- LOBBY LEVEL +905M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-08-13 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | L1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2L40000 | SECURITY SYSTEM OVERALL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | L4 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-01-CENT01-2L40001 | SECURITY SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | CENT01 | 2 | L4 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-02-CENT01-2L40002 | SECURITY SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | CENT01 | 2 | L4 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-03-CENT01-2L40003 | SECURITY SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 03 | CENT01 | 2 | L4 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2L60000 | SECURITY SYSTEM OVERALL PLAN - L6- SKY GARDEN +935.85M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | L6 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2L80001 | SECURITY SYSTEM OVERALL PLAN - L8 ROYAL MAJLIS +948.28M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | L8 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2M10000 | SECURITY SYSTEM OVERALL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-08-20 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | M1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-04-CENT01-2L40004 | SECURITY SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 04 | CENT01 | 2 | L4 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2RL0001 | SECURITY SYSTEM OVERALL PLAN - Roof & Above | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | RL | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000002 | SECURITY SCHEDULE FOR B3 PROMENADE +887.750M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000003 | SECURITY SCHEDULE FOR B2 SERVICE +893.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000004 | SECURITY SCHEDULE FOR B1 SERVICE & PARKING +900.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000006 | SECURITY SCHEDULE FOR L1- LOBBY LEVEL +905M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000007 | SECURITY SCHEDULE FOR L1- MEZZ-UPPER LOBBY MEZZANINE +909M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000008 | SECURITY SCHEDULE FOR L2- THEATRE STALLS +913M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000009 | SECURITY SCHEDULE FOR L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000010 | SECURITY SCHEDULE FOR L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000011 | SECURITY SCHEDULE FOR L5- SECOND CIRCLE & LOFT +928M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000012 | SECURITY SCHEDULE FOR L5-MEZZ-LOFT MEP MEZZANINE +931.1M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000013 | SECURITY SCHEDULE FOR L6- SKY GARDEN +935.85M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6000014 | SECURITY SCHEDULE FOR L8 ROYAL MAJLIS +948.28M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | 00 | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-6RL0015 | SECURITY SCHEDULE FOR Roof & Above | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 6 | RL | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-PARK01-2B10000 | SECURITY SYSTEM PARTIAL PLAN - B1 PARKING +900.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | SECURITY | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | PARK01 | 2 | B1 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-SEC-00-PARK01-6000005 | SECURITY SCHEDULE FOR PLAN - B1 PARKING +900.5M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | PARK01 | 6 | 00 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0001 | SECURITY SINGLE LINE DIAGRAM FOR SITE | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0101 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-01 AND ACS-02 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0101 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0102 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-03 AND ACS-04 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0102 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0103 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-05 AND ACS-06 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0103 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0104 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-08 AND ACS-09 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0104 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0105 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-10 AND ACS-11 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0105 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0106 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-12 AND ACS-14 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0106 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0107 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-16 AND ACS-17 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0107 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0108 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-18 AND ACS-19 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0108 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0109 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-20 AND ACS-21 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0109 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0110 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-22 AND ACS-23 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0110 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0111 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-07 AND ACS-15 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-11-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0111 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0116 | STANDARD INSTALLATION DETAILS - DISABLED TOILET ALARM SYSTEM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0116 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0117 | STANDARD INSTALLATION DETAILS - TYPICAL ANTENNA | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0117 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0118 | STANDARD INSTALLATION DETAILS - KEY MANAGEMENT SYSTEM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0118 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0119 | STANDARD INSTALLATION DETAILS - INTERCOM SYSTEM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0119 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0121 | STANDARD INSTALLATION DETAILS - FIXED BOLLARDS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-09-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0121 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0123 | STANDARD INSTALLATION DETAILS - HYDRAULICS BOLLARDS SYSTEM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-09-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0123 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0125 | STANDARD INSTALLATION DETAILS - GATE BARRIER | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0125 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-2ZZ0000 | SECURITY OVERALL SITE PLAN | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:500 | 2027-02-18 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 2 | ZZ | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-6000001 | SECURITY SCHEDULE FOR SITE - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2027-04-29 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 6 | 00 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-01-CENT01-2B10001 | SECURITY SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | CENT01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-01-CENT01-2B20001 | SECURITY SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 01 - (1 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | CENT01 | 2 | B2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-01-CENT01-2B30001 | SECURITY SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 01 - (1 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | CENT01 | 2 | B3 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-01-CENT01-2L10001 | SECURITY SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 01 - (1 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | CENT01 | 2 | L1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-05-CENT01-2L40005 | SECURITY SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | CENT01 | 2 | L4 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-06-CENT01-2L40006 | SECURITY SYSTEM PARTIAL PLAN - L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 06 | CENT01 | 2 | L4 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2L50000 | CCTV SYSTEM OVERALL PLAN - L5- SECOND CIRCLE & LOFT +928M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | L5 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-01-CENT01-2L50001 | CCTV SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-01-CENT01-2L60001 | SECURITY SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | CENT01 | 2 | L6 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-01-CENT01-2M10001 | SECURITY SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 01 - (1 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | CENT01 | 2 | M1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-02-CENT01-2L50002 | CCTV SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-01-PARK01-2B10001 | SECURITY SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 01 - (1 OF 3) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | SECURITY | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | PARK01 | 2 | B1 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-SEC-01-Z00000-2ZZ0001 | SECURITY PARTIAL SITE PLAN - SHEET 01 - (1 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | Z00000 | 2 | ZZ | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-02-CENT01-2B10002 | SECURITY SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | CENT01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-02-CENT01-2B20002 | SECURITY SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 02 - (2 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | CENT01 | 2 | B2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-02-CENT01-2B30002 | SECURITY SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 02 - (2 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | CENT01 | 2 | B3 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-02-CENT01-2L10002 | SECURITY SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 02 - (2 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | CENT01 | 2 | L1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-03-CENT01-2L50003 | CCTV SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 03 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-04-CENT01-2L50004 | CCTV SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 04 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-05-CENT01-2L50005 | CCTV SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-06-CENT01-2L50006 | CCTV SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 06 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-02-CENT01-2L60002 | SECURITY SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | CENT01 | 2 | L6 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-02-CENT01-2M10002 | SECURITY SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 02 - (2 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | CENT01 | 2 | M1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2L50000 | SECURITY SYSTEM OVERALL PLAN - L5- SECOND CIRCLE & LOFT +928M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | L5 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-02-PARK01-2B10002 | SECURITY SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 02 - (2 OF 3) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | SECURITY | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | PARK01 | 2 | B1 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-SEC-02-Z00000-2ZZ0002 | SECURITY PARTIAL SITE PLAN - SHEET 02 - (2 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | Z00000 | 2 | ZZ | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-01-CENT01-2L50001 | SECURITY SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | CENT01 | 2 | L5 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-02-CENT01-2L50002 | SECURITY SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | CENT01 | 2 | L5 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-03-CENT01-2L50003 | SECURITY SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 03 | CENT01 | 2 | L5 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-04-CENT01-2L50004 | SECURITY SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 04 | CENT01 | 2 | L5 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-03-CENT01-2L60003 | SECURITY SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 03 | CENT01 | 2 | L6 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-05-CENT01-2L50005 | SECURITY SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | CENT01 | 2 | L5 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-03-PARK01-2B10003 | SECURITY SYSTEM PARTIAL PLAN - B1 PARKING +900.5M - SHEET 03 - (3 OF 3) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | SECURITY | QP.E.ME.PAR.GEN.1339 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 03 | PARK01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-SEC-03-Z00000-2ZZ0003 | SECURITY PARTIAL SITE PLAN - SHEET 03 - (3 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 03 | Z00000 | 2 | ZZ | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-04-CENT01-2B10003 | SECURITY SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 04 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 04 | CENT01 | 2 | B1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-04-CENT01-2B20003 | SECURITY SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 04 - (3 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 04 | CENT01 | 2 | B2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-04-CENT01-2L10003 | SECURITY SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 04 - (3 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 04 | CENT01 | 2 | L1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-06-CENT01-2L50006 | SECURITY SYSTEM PARTIAL PLAN - L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 06 | CENT01 | 2 | L5 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-00-CENT01-2M20000 | CCTV SYSTEM OVERALL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | CENT01 | 2 | M2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-01-CENT01-2M20001 | CCTV SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 01 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-02-CENT01-2M20002 | CCTV SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 02 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-04-CENT01-2L60004 | SECURITY SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 04 | CENT01 | 2 | L6 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-04-CENT01-2M10003 | SECURITY SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 04 - (3 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 04 | CENT01 | 2 | M1 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-03-CENT01-2M20003 | CCTV SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 03 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-04-Z00000-2ZZ0004 | SECURITY PARTIAL SITE PLAN - SHEET 04 - (4 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 04 | Z00000 | 2 | ZZ | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-05-CENT01-2B10004 | SECURITY SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 05 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | CENT01 | 2 | B1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-05-CENT01-2B20004 | SECURITY SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 05 - (4 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | CENT01 | 2 | B2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-05-CENT01-2B30003 | SECURITY SYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 05 - (3 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | CENT01 | 2 | B3 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-05-CENT01-2L10004 | SECURITY SYSTEM PARTIAL PLAN - L1- LOBBY LEVEL +905M - SHEET 05 - (4 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | CENT01 | 2 | L1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-04-CENT01-2M20004 | CCTV SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 04 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-05-CENT01-2M20005 | CCTV SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 05 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-CTV-06-CENT01-2M20006 | CCTV SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 06 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-00-CENT01-2M20000 | SECURITY SYSTEM OVERALL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:300 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | CENT01 | 2 | M2 | 0000 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-05-CENT01-2L60005 | SECURITY SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | CENT01 | 2 | L6 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-05-CENT01-2M10004 | SECURITY SYSTEM PARTIAL PLAN - L1- MEZZ-UPPER LOBBY MEZZANINE +909M - SHEET 05 - (4 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-20 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | CENT01 | 2 | M1 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-01-CENT01-2M20001 | SECURITY SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 - (1 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 01 | CENT01 | 2 | M2 | 0001 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-05-Z00000-2ZZ0005 | SECURITY PARTIAL SITE PLAN - SHEET 05 - (5 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | Z00000 | 2 | ZZ | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-06-CENT01-2B30004 | SECURITYSYSTEM PARTIAL PLAN - B3 PROMENADE +887.750M - SHEET 06 - (4 OF 4) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 06 | CENT01 | 2 | B3 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-02-CENT01-2M20002 | SECURITY SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 - (2 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 02 | CENT01 | 2 | M2 | 0002 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-03-CENT01-2M20003 | SECURITY SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 - (3 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 03 | CENT01 | 2 | M2 | 0003 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-04-CENT01-2M20004 | SECURITY SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (4 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 04 | CENT01 | 2 | M2 | 0004 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-05-CENT01-2M20005 | SECURITY SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 05 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-06-CENT01-2L60006 | SECURITY SYSTEM PARTIAL PLAN - L6- SKY GARDEN +935.85M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 06 | CENT01 | 2 | L6 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-06-CENT01-2M20006 | SECURITY SYSTEM PARTIAL PLAN - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-09-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 06 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-06-Z00000-2ZZ0006 | SECURITY PARTIAL SITE PLAN - SHEET 06 - (6 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 06 | Z00000 | 2 | ZZ | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-07-CENT01-2B10005 | SECURITY SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 07 - (5 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 07 | CENT01 | 2 | B1 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-07-CENT01-2B20005 | SECURITY SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 07 - (5 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 07 | CENT01 | 2 | B2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-07-Z00000-2ZZ0007 | SECURITY PARTIAL SITE PLAN - SHEET 07 - (7 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 07 | Z00000 | 2 | ZZ | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-08-CENT01-2B10006 | SECURITY SYSTEM PARTIAL PLAN - B1 SERVICE +900.5M - SHEET 08 - (6 OF 6) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 08 | CENT01 | 2 | B1 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-08-CENT01-2B20006 | SECURITY SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 08 - (6 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 08 | CENT01 | 2 | B2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-08-Z00000-2ZZ0008 | SECURITY PARTIAL SITE PLAN - SHEET 08 - (8 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 08 | Z00000 | 2 | ZZ | 0008 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-09-CENT01-2B20007 | SECURITY SYSTEM PARTIAL PLAN - B2 SERVICE +893.5M - SHEET 09 - (7 OF 7) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | SECURITY | QP.E.ME.MBL.GEN.7360 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 09 | CENT01 | 2 | B2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-05-31
QF01012-NES-C04518-SDW-SEC-09-Z00000-2ZZ0009 | SECURITY PARTIAL SITE PLAN - SHEET 09 - (9 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 09 | Z00000 | 2 | ZZ | 0009 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-10-Z00000-2ZZ0010 | SECURITY PARTIAL SITE PLAN - SHEET 10 - (10 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 10 | Z00000 | 2 | ZZ | 0010 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-11-Z00000-2ZZ0011 | SECURITY PARTIAL SITE PLAN - SHEET 11 - (11 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 11 | Z00000 | 2 | ZZ | 0011 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-12-Z00000-2ZZ0012 | SECURITY PARTIAL SITE PLAN - SHEET 12 - (12 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 12 | Z00000 | 2 | ZZ | 0012 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-13-Z00000-2ZZ0013 | SECURITY PARTIAL SITE PLAN - SHEET 16 - (13 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 13 | Z00000 | 2 | ZZ | 0013 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-14-Z00000-2ZZ0014 | SECURITY PARTIAL SITE PLAN - SHEET 17 - (14 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 14 | Z00000 | 2 | ZZ | 0014 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-15-Z00000-2ZZ0015 | SECURITY PARTIAL SITE PLAN - SHEET 18 - (15 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 15 | Z00000 | 2 | ZZ | 0015 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-16-Z00000-2ZZ0016 | SECURITY PARTIAL SITE PLAN - SHEET 19 - (16 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 16 | Z00000 | 2 | ZZ | 0016 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-17-Z00000-2ZZ0017 | SECURITY PARTIAL SITE PLAN - SHEET 20 - (17 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 17 | Z00000 | 2 | ZZ | 0017 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-18-Z00000-2ZZ0018 | SECURITY PARTIAL SITE PLAN - SHEET 21 - (18 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 18 | Z00000 | 2 | ZZ | 0018 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-19-GARD01-2ZZ0001 | SECURITY SYSTEM PLAN - GUARD ROOM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-01-15 | SECURITY | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 19 | GARD01 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-SEC-19-Z00000-2ZZ0019 | SECURITY PARTIAL SITE PLAN - SHEET 22 - (19 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 19 | Z00000 | 2 | ZZ | 0019 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-20-Z00000-2ZZ0020 | SECURITY PARTIAL SITE PLAN - SHEET 23 - (20 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 20 | Z00000 | 2 | ZZ | 0020 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-21-Z00000-2ZZ0021 | SECURITY PARTIAL SITE PLAN - SHEET 24 - (21 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 21 | Z00000 | 2 | ZZ | 0021 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-22-Z00000-2ZZ0022 | SECURITY PARTIAL SITE PLAN - SHEET 25 - (22 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 22 | Z00000 | 2 | ZZ | 0022 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-23-Z00000-2ZZ0023 | SECURITY PARTIAL SITE PLAN - SHEET 26 - (23 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 23 | Z00000 | 2 | ZZ | 0023 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-24-Z00000-2ZZ0024 | SECURITY PARTIAL SITE PLAN - SHEET 27 - (24 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 24 | Z00000 | 2 | ZZ | 0024 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-25-Z00000-2ZZ0025 | SECURITY PARTIAL SITE PLAN - SHEET 28 - (25 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 25 | Z00000 | 2 | ZZ | 0025 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-26-Z00000-2ZZ0026 | SECURITY PARTIAL SITE PLAN - SHEET 29 - (26 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 26 | Z00000 | 2 | ZZ | 0026 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-27-Z00000-2ZZ0027 | SECURITY PARTIAL SITE PLAN - SHEET 30 - (27 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 27 | Z00000 | 2 | ZZ | 0027 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-28-Z00000-2ZZ0028 | SECURITY PARTIAL SITE PLAN - SHEET 31 - (28 OF 28) | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-02-25 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 28 | Z00000 | 2 | ZZ | 0028 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ESP-04-CENT01-2M20005 | SMALL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 - (04 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 04 | CENT01 | 2 | M2 | 0005 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ESP-05-CENT01-2M20006 | SMALL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 - (05 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 05 | CENT01 | 2 | M2 | 0006 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-SDW-ESP-06-CENT01-2M20007 | SMALL POWER SYSTEM - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 - (06 OF 06) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Small Power | QP.E.ME.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 06 | CENT01 | 2 | M2 | 0007 | Electrical | Nesma & Partners | LOD400 |  |  |  | 2027-02-10
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0430 | FAÇADE LIGHTING SYSTEM -VMU-04- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-27 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0430 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0431 | FAÇADE LIGHTING SYSTEM -VMU-04- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-27 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0431 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0432 | FAÇADE LIGHTING SYSTEM -VMU-04- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-27 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0432 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30

## Baseline
1 | 2 | 3 | 4 | 5 | 6 | 7 | Package | Activity Code | Activity | Original Duration | Start | Finish
Shop Drawings | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Shop Drawings ¦ Mobilization | QP.M.GN.GEN.GEN.1400 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Shop Drawings ¦ Mobilization ¦ Tower Crane Foundation - Concrete Works | QP.M.GN.GEN.GEN.1470 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Blades Below Loft | QP.M.GN.GEN.GEN.1540 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Loft | QP.M.GN.GEN.GEN.1560 | Submittal | 12 | 2026-08-29 | 2026-09-10
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Above Loft | QP.M.GN.GEN.GEN.1580 | Submittal | 12 | 2026-10-01 | 2026-10-14
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works | QP.E.CV.MBL.GEN.3460 | Submittal | 28 | 2025-10-11 | 2025-11-11
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works Outside Core Area | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works Outside Core Area | QP.E.CV.MBL.GEN.3540 | Submittal | 14 | 2025-11-12 | 2025-11-27
Shop Drawings | Civil | Blades | Blade 1 | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 1 | QP.E.CV.BL1.GEN.1060 | Submittal | 28 | 2026-02-21 | 2026-03-28
Shop Drawings | Civil | Blades | Blade 2 | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 2 | QP.E.CV.BL2.GEN.1060 | Submittal | 28 | 2026-01-19 | 2026-02-19
Shop Drawings | Civil | Blades | Blade 3 | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 3 | QP.E.CV.BL3.GEN.1060 | Submittal | 28 | 2025-12-17 | 2026-01-18
Shop Drawings | Civil | Blades | Blade 4 | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 4 | QP.E.CV.BL4.GEN.1060 | Submittal | 28 | 2025-12-03 | 2026-01-04
Shop Drawings | Civil | Blades | Blade 5 | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 5 | QP.E.CV.BL5.GEN.1060 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Civil | Parking | Parking | Parking | Parking | Parking | Shop Drawings ¦ Civil ¦ Parking | QP.E.CV.PAR.GEN.1000 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - Foundation Works Core Area | QP.E.CV.MBL.GEN.3000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 03 +887.750M | QP.E.CV.MBL.GEN.3030 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - SOG | QP.E.CV.MBL.GEN.3640 | Submittal | 14 | 2026-03-16 | 2026-04-02
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 02 - Foundation Works Outside Core Area | QP.E.CV.MBL.GEN.3020 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 02 +893.5M | QP.E.CV.MBL.GEN.3070 | Submittal | 21 | 2026-02-18 | 2026-03-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 01 +900.5M | QP.E.CV.MBL.GEN.3100 | Submittal | 28 | 2026-03-16 | 2026-04-19
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01- LOBBY LEVEL +905M | QP.E.CV.MBL.GEN.3120 | Submittal | 25 | 2026-04-20 | 2026-05-18
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01 - MEZZANINE +909M | QP.E.CV.MBL.GEN.3140 | Submittal | 15 | 2026-05-19 | 2026-06-08
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3180 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3380 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3220 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3400 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3240 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3420 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3260 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3440 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | QP.E.CV.MBL.GEN.3280 | Submittal | 25 | 2026-10-08 | 2026-11-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | QP.E.CV.MBL.GEN.3300 | Submittal | 28 | 2027-03-13 | 2027-04-13
Shop Drawings | Concrete | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Premium Theatre Concrete Works | QP.E.CV.MBL.GEN.3150 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Amphitheatre Concrete Works | QP.E.CV.MBL.GEN.3200 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Premium Theater | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Premium Theater | QP.E.CV.MBL.GEN.3660 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Loft and Adaptable Theatre | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Loft and Adaptable Theatre | QP.E.CV.MBL.GEN.3700 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Fly Tower | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Fly Tower | QP.E.CV.MBL.GEN.3710 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Lobby & Plaza | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Lobby & Plaza | QP.E.CV.MBL.GEN.3680 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Royal Majlis | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Royal Majlis | QP.E.CV.MBL.GEN.3740 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Foundation | QP.E.CV.BL1.GEN.1000 | Submittal | 25 | 2026-02-25 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL1.GEN.1040 | Submittal | 25 | 2026-03-29 | 2026-04-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL1.GEN.1080 | Submittal | 18 | 2026-05-12 | 2026-06-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL1.GEN.1020 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL1.GEN.1120 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL1.GEN.1100 | Submittal | 28 | 2026-10-27 | 2026-11-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Foundation | QP.E.CV.BL2.GEN.1000 | Submittal | 21 | 2026-03-02 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL2.GEN.1040 | Submittal | 21 | 2026-03-10 | 2026-04-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL2.GEN.1080 | Submittal | 18 | 2026-04-21 | 2026-05-11
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL2.GEN.1020 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL2.GEN.1140 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL2.GEN.1120 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Foundation | QP.E.CV.BL3.GEN.1000 | Submittal | 21 | 2026-02-07 | 2026-03-03
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Steel Composite Slab Including Embedded items Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Steel Composite Slab Including Embedded items Below Loft | QP.E.CV.BL3.GEN.1030 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL3.GEN.1080 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL3.GEN.1020 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Foundation | QP.E.CV.BL4.GEN.1000 | Submittal | 28 | 2026-01-05 | 2026-02-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL4.GEN.1030 | Submittal | 28 | 2026-02-24 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL4.GEN.1080 | Submittal | 15 | 2026-03-31 | 2026-04-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL4.GEN.1020 | Submittal | 28 | 2026-04-18 | 2026-05-19
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL4.GEN.1100 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL4.GEN.1120 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Foundation | QP.E.CV.BL5.GEN.1000 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL5.GEN.1030 | Submittal | 28 | 2026-03-23 | 2026-04-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL5.GEN.1080 | Submittal | 18 | 2026-03-31 | 2026-04-20
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL5.GEN.1020 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL5.GEN.1100 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL5.GEN.1120 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Foundation Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Foundation Including Embedded items | QP.E.CV.PAR.GEN.1020 | Submittal | 28 | 2027-04-28 | 2027-06-03
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Structural Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Structural Concrete Works Including Embedded items | QP.E.CV.PAR.GEN.1040 | Submittal | 28 | 2027-06-19 | 2027-07-20
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Below Loft | QP.E.ST.GEN.GEN.1090 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1100 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1110 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1050 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1060 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1070 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 3,4,5 | QP.E.ST.GEN.GEN.1000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | QP.E.ST.GEN.GEN.1010 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Truss below Auditorium, Side and Back Stage | QP.E.ST.GEN.GEN.2120 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1220 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1230 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1200 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1210 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1190 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Embedded part - Main Building Above Level 5 | QP.E.ST.GEN.GEN.1040 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Premium Theater - Frame Balconies and Back Stage Dressing | QP.E.ST.GEN.GEN.2140 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Loft and adaptable Theatre | QP.E.ST.GEN.GEN.1340 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1390 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1400 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1310 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1320 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1330 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1470 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ Truss above Auditorium Incl. Metal Deck | QP.E.ST.GEN.GEN.2100 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Temporay Tower ROYAL MAJLIS and Blades above loft | QP.E.ST.GEN.GEN.1490 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2160 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1520 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Truss above Flytower | QP.E.ST.GEN.GEN.2180 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1540 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ Blade 2 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2200 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ Adaptable Theatre Incl. Metal Deck | QP.E.ST.GEN.GEN.1560 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.2220 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Loft Truss and Infilled Beam North Side Incl. Metal Deck | QP.E.ST.GEN.GEN.1610 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1600 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Lobby and Plaza Incl. Metal Deck | QP.E.ST.GEN.GEN.1660 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Frame for Mezzanine | QP.E.ST.GEN.GEN.1670 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Link Bridge and Helix Stair | QP.E.ST.GEN.GEN.1570 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1680 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | Shop Drawings ¦ Structural Steel ¦ Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck ¦ ROYAL MAJLIS | QP.E.ST.GEN.GEN.1640 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1090 | Submittal | 21 | 2026-03-26 | 2026-04-19
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1120 | Submittal | 21 | 2026-09-15 | 2026-10-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Wall Cladding | QP.E.AF.MBL.GEN.4440 | Submittal | 21 | 2026-10-11 | 2026-11-03
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1100 | Submittal | 21 | 2026-11-04 | 2026-11-28
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ FFE | QP.E.AF.MBL.GEN.5260 | Submittal | 21 | 2026-11-29 | 2026-12-22
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1170 | Submittal | 21 | 2026-04-20 | 2026-05-13
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1200 | Submittal | 20 | 2026-11-04 | 2026-11-26
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5700 | Submittal | 21 | 2026-11-28 | 2026-12-21
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1180 | Submittal | 21 | 2026-12-23 | 2027-01-16
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ FFE | QP.E.AF.MBL.GEN.5280 | Submittal | 21 | 2027-01-17 | 2027-02-09
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1220 | Submittal | 21 | 2026-05-14 | 2026-06-10
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1250 | Submittal | 28 | 2026-11-28 | 2026-12-29
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5720 | Submittal | 21 | 2026-12-30 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1230 | Submittal | 21 | 2027-01-24 | 2027-02-16
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ FFE | QP.E.AF.MBL.GEN.5300 | Submittal | 21 | 2027-02-17 | 2027-03-16
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1310 | Submittal | 21 | 2026-06-11 | 2026-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1340 | Submittal | 28 | 2026-12-30 | 2027-01-31
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5800 | Submittal | 21 | 2027-02-01 | 2027-02-25
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1320 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ FFE | QP.E.AF.MBL.GEN.5320 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1400 | Submittal | 21 | 2026-07-06 | 2026-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1430 | Submittal | 20 | 2027-02-01 | 2027-02-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5740 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1410 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ FFE | QP.E.AF.MBL.GEN.5340 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1000 | Submittal | 21 | 2026-07-30 | 2026-08-23
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1030 | Submittal | 20 | 2027-02-25 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5760 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1010 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ FFE | QP.E.AF.MBL.GEN.5360 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1490 | Submittal | 21 | 2026-08-24 | 2026-09-16
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1520 | Submittal | 20 | 2027-03-23 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5820 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1500 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ FFE | QP.E.AF.MBL.GEN.5380 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1580 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1610 | Submittal | 20 | 2027-04-15 | 2027-05-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5840 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1590 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ FFE | QP.E.AF.MBL.GEN.5400 | Submittal | 21 | 2027-07-06 | 2027-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1670 | Submittal | 21 | 2026-12-20 | 2027-01-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1700 | Submittal | 20 | 2027-05-23 | 2027-06-14
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5860 | Submittal | 28 | 2027-06-15 | 2027-07-17
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1680 | Submittal | 28 | 2027-07-18 | 2027-08-18
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ FFE | QP.E.AF.MBL.GEN.5420 | Submittal | 28 | 2027-07-31 | 2027-08-31
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1760 | Submittal | 21 | 2027-01-19 | 2027-02-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1790 | Submittal | 21 | 2027-05-23 | 2027-06-15
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5880 | Submittal | 21 | 2027-07-18 | 2027-08-10
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1770 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ FFE | QP.E.AF.MBL.GEN.5440 | Submittal | 21 | 2027-09-01 | 2027-09-26
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1880 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1910 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5900 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1890 | Submittal | 21 | 2027-09-13 | 2027-10-07
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ FFE | QP.E.AF.MBL.GEN.5460 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1800 | Submittal | 21 | 2027-04-22 | 2027-05-20
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1830 | Submittal | 21 | 2027-07-25 | 2027-08-17
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5920 | Submittal | 21 | 2027-08-25 | 2027-09-18
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1810 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ FFE | QP.E.AF.MBL.GEN.5480 | Submittal | 21 | 2027-10-11 | 2027-11-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1110 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1140 | Submittal | 21 | 2027-05-31 | 2027-06-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1120 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1370 | Submittal | 21 | 2027-03-01 | 2027-03-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1360 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Wall Cladding | QP.E.AF.BL1.GEN.5940 | Submittal | 21 | 2027-07-19 | 2027-08-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1340 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1650 | Submittal | 21 | 2027-06-14 | 2027-07-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1680 | Submittal | 14 | 2027-09-01 | 2027-09-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1660 | Submittal | 21 | 2027-11-18 | 2027-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1080 | Submittal | 21 | 2027-05-26 | 2027-06-19
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1110 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Wall Cladding | QP.E.AF.BL2.GEN.5960 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1090 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1580 | Submittal | 21 | 2027-07-04 | 2027-07-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1610 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1590 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1670 | Submittal | 21 | 2027-07-28 | 2027-08-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1700 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1680 | Submittal | 14 | 2028-01-18 | 2028-02-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1000 | Submittal | 24 | 2026-11-15 | 2026-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1030 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL3.GEN.5980 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1010 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1340 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1370 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1350 | Submittal | 21 | 2027-12-22 | 2028-01-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1210 | Submittal | 24 | 2026-12-27 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1240 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL4.GEN.6000 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1220 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1820 | Submittal | 21 | 2027-04-24 | 2027-05-22
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1850 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1830 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1730 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1760 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1740 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.2280 | Submittal | 24 | 2027-02-07 | 2027-03-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.2340 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.2300 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1130 | Submittal | 21 | 2027-03-22 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1160 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1140 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1500 | Submittal | 28 | 2027-06-29 | 2027-07-31
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1530 | Submittal | 21 | 2027-10-10 | 2027-11-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Wall Cladding | QP.E.AF.BL5.GEN.6020 | Submittal | 21 | 2027-12-16 | 2028-01-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1510 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1000 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1020 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Doors / Openings | QP.E.AF.PAR.GEN.1010 | Submittal | 28 | 2027-12-22 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Specialities | QP.E.AF.MBL.GEN.5160 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1030 | Submittal | 28 | 2027-10-16 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1050 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Doors / Openings | QP.E.AF.PAR.GEN.1040 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Specialities | QP.E.AF.MBL.GEN.5200 | Submittal | 21 | 2028-01-09 | 2028-02-01
Shop Drawings | Architecture and Fitouts | Amphitheatre | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4040 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Architecture and Fitouts | Amphitheatre | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.4070 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Amphitheatre | Wall Cladding | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Wall Cladding | QP.E.AF.MBL.GEN.6040 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | Architecture and Fitouts | Amphitheatre | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4050 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | Shop Drawings ¦ External Building Works (Guard House, SEC Room) | QP.E.EX.GEN.GEN.1270 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Main Building | QP.E.AF.MBL.GEN.6060 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 5 | Water Proofing - Roof - Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 5 | QP.E.AF.BL5.GEN.6180 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 4 | Water Proofing - Roof - Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 4 | QP.E.AF.BL4.GEN.6160 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 3 | Water Proofing - Roof - Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 3 | QP.E.AF.BL3.GEN.6140 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 1 | Water Proofing - Roof - Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 1 | QP.E.AF.BL1.GEN.6100 | Submittal | 21 | 2027-12-09 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 2 | Water Proofing - Roof - Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 2 | QP.E.AF.BL2.GEN.6120 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Wet Areas | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Wet Areas ¦ Main Building | QP.E.AF.MBL.GEN.4400 | Submittal | 21 | 2027-08-08 | 2027-08-31
Shop Drawings | Specialist Systems | Doors/ Openings | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Main Building | QP.E.AF.MBL.GEN.1140 | Submittal | 20 | 2027-06-29 | 2027-07-21
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.1130 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 2 | QP.E.AF.BL2.GEN.1100 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.1020 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.1230 | Submittal | 21 | 2027-08-16 | 2027-09-08
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.2320 | Submittal | 21 | 2027-09-09 | 2027-10-04
Shop Drawings | Specialist Systems | Doors/ Openings | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Amphitheatre | QP.E.AF.MBL.GEN.4060 | Submittal | 28 | 2027-11-13 | 2027-12-14
Shop Drawings | Specialist Systems | Conveying System | Waste Management | Waste Management | Waste Management | Waste Management | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Waste Management | QP.E.CY.GEN.GEN.1280 | Submittal | 14 | 2027-12-02 | 2027-12-18
Shop Drawings | Specialist Systems | Conveying System | Escalators | Escalators | Escalators | Escalators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Escalators | QP.E.CY.GEN.GEN.1040 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | Specialist Systems | Conveying System | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | QP.E.CY.GEN.GEN.1020 | Submittal | 28 | 2026-10-22 | 2026-11-23
Shop Drawings | Specialist Systems | Conveying System | Truck Elevators | Truck Elevators | Truck Elevators | Truck Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Truck Elevators | QP.E.CY.GEN.GEN.1000 | Submittal | 28 | 2026-09-19 | 2026-10-21
Shop Drawings | Specialist Systems | Conveying System | Inclined Elevators | Inclined Elevators | Inclined Elevators | Inclined Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Inclined Elevators | QP.E.CY.GEN.GEN.1050 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Main Building | QP.E.CY.GEN.GEN.1090 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 1 | QP.E.CY.GEN.GEN.1130 | Submittal | 28 | 2027-10-17 | 2027-11-17
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 2 | QP.E.CY.GEN.GEN.1170 | Submittal | 28 | 2027-09-13 | 2027-10-16
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 3 | Balde 3 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 3 | QP.E.CY.GEN.GEN.1210 | Submittal | 28 | 2027-06-07 | 2027-07-08
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 4 | QP.E.CY.GEN.GEN.1110 | Submittal | 28 | 2027-07-10 | 2027-08-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 5 | Balde 5 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 5 | QP.E.CY.GEN.GEN.1150 | Submittal | 28 | 2027-08-11 | 2027-09-12
Shop Drawings | Specialist Systems | Joinery Works | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Main Building | QP.E.AF.MBL.GEN.5540 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.6120 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.6160 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.6180 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.6200 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Shop Drawings ¦ Specialist Systems ¦ Kitchen and Laundary | QP.E.AF.MBL.GEN.5500 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Specialist Systems | Water Features | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Specialist Systems ¦ Water Features | QP.E.AF.MBL.GEN.6100 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Mechanical | QP.E.ME.MBL.GEN.6780 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical | QP.E.ME.MBL.GEN.6800 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6840 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical | QP.E.ME.MBL.GEN.6850 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6860 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical | QP.E.ME.MBL.GEN.6870 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Mechanical | QP.E.ME.MBL.GEN.6900 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical | QP.E.ME.MBL.GEN.6910 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Mechanical | QP.E.ME.MBL.GEN.6940 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical | QP.E.ME.MBL.GEN.6950 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Mechanical | QP.E.ME.MBL.GEN.6980 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Electrical | QP.E.ME.MBL.GEN.6990 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Mechanical | QP.E.ME.MBL.GEN.7020 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical | QP.E.ME.MBL.GEN.7030 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7060 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical | QP.E.ME.MBL.GEN.7070 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7100 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical | QP.E.ME.MBL.GEN.7110 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Mechanical | QP.E.ME.MBL.GEN.7140 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical | QP.E.ME.MBL.GEN.7150 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Mechanical | QP.E.ME.MBL.GEN.7180 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Electrical | QP.E.ME.MBL.GEN.7190 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Mechanical | QP.E.ME.MBL.GEN.7220 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical | QP.E.ME.MBL.GEN.7230 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1320 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1330 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1340 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1350 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ ICT Containment | QP.E.ME.MBL.GEN.1360 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1420 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1430 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1440 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1450 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1460 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1740 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1750 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1760 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1770 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1780 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1590 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1600 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1610 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1620 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.1630 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2040 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2050 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2060 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2070 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ ICT Containment | QP.E.ME.MBL.GEN.2080 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2240 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2250 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2260 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2270 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ ICT Containment | QP.E.ME.MBL.GEN.2280 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2440 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2450 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2460 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2470 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.2480 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2640 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2650 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2660 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2670 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2680 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2850 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2860 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2870 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2880 | Submittal | 28 | 2026-12-08 | 2027-01-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2890 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3070 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3080 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3090 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3100 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ ICT Containment | QP.E.ME.MBL.GEN.3110 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3290 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3300 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3310 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3320 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ ICT Containment | QP.E.ME.MBL.GEN.3330 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3500 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3510 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3520 | Submittal | 28 | 2026-12-23 | 2027-01-24
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3530 | Submittal | 28 | 2027-02-11 | 2027-03-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ ICT Containment | QP.E.ME.MBL.GEN.3540 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.MBL.GEN.5000 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.MBL.GEN.5040 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.MBL.GEN.5060 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.MBL.GEN.5080 | Submittal | 28 | 2027-03-07 | 2027-04-10
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.MBL.GEN.7280 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.MBL.GEN.7300 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.MBL.GEN.7320 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.MBL.GEN.7260 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.MBL.GEN.7340 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | LPG System | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ LPG System | QP.E.ME.MBL.GEN.5100 | Submittal | 21 | 2027-09-22 | 2027-10-17
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.MBL.GEN.7360 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Fire Suppression | QP.E.ME.CBR.GEN.1000 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Plumbing | Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Plumbing | QP.E.ME.CBR.GEN.1011 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ LPG System | QP.E.ME.CBR.GEN.1055 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.CBR.GEN.1022 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Electrical | QP.E.ME.CBR.GEN.1033 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ ELV (Low Current System) | QP.E.ME.CBR.GEN.1044 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.MBL.GEN.7380 | Submittal | 28 | 2027-12-09 | 2028-01-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Diesel | Diesel | Diesel | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Diesel | QP.E.ME.MBL.GEN.7420 | Submittal | 21 | 2028-02-01 | 2028-02-26
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Water Features | Water Features | Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Water Features | QP.E.ME.MBL.GEN.7440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M | QP.E.ME.MBL.GEN.6520 | Submittal | 28 | 2026-06-14 | 2026-07-15
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Grey Water Treatment/ Sewage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Grey Water Treatment/ Sewage | QP.E.ME.MBL.GEN.1050 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Stromwater/ Drainage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Stromwater/ Drainage | QP.E.ME.MBL.GEN.1060 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1040 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M | QP.E.ME.MBL.GEN.6540 | Submittal | 28 | 2026-07-16 | 2026-08-17
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ AHU Room | QP.E.ME.MBL.GEN.1160 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Transformer/ Switchgear/ Panel Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Transformer/ Switchgear/ Panel Room | QP.E.ME.MBL.GEN.1240 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Generator Room/ Diesel Tank | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Generator Room/ Diesel Tank | QP.E.ME.MBL.GEN.1250 | Submittal | 14 | 2026-10-05 | 2026-10-20
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | ETS/ CWP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ ETS/ CWP Room | QP.E.ME.MBL.GEN.1170 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1030 | Submittal | 14 | 2026-09-24 | 2026-10-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1290 | Submittal | 28 | 2026-09-01 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M | QP.E.ME.MBL.GEN.6560 | Submittal | 14 | 2026-08-18 | 2026-09-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1020 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Domestic Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Domestic Water | QP.E.ME.MBL.GEN.1010 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Fire Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Fire Water | QP.E.ME.MBL.GEN.1000 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1280 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 LOBBY LEVEL +905.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 LOBBY LEVEL +905.00M | QP.E.ME.MBL.GEN.6640 | Submittal | 21 | 2026-09-03 | 2026-09-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 UPEER LOBBY LEVEL MEZZANINE +909M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M | QP.E.ME.MBL.GEN.6660 | Submittal | 21 | 2026-09-29 | 2026-10-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L2 THEATRE STALLS +913M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L2 THEATRE STALLS +913M | QP.E.ME.MBL.GEN.6680 | Submittal | 21 | 2026-10-24 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | QP.E.ME.MBL.GEN.6700 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | QP.E.ME.MBL.GEN.6720 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 SECOND CIRCLE AND LOFT +928.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 SECOND CIRCLE AND LOFT +928.00M | QP.E.ME.MBL.GEN.6740 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M | QP.E.ME.MBL.GEN.5540 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - AHU Room | QP.E.ME.MBL.GEN.1180 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Makeup Air Unit and Ecology | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Makeup Air Unit and Ecology | QP.E.ME.MBL.GEN.1190 | Submittal | 14 | 2027-01-06 | 2027-01-21
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Sky Garden Irrigation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Sky Garden Irrigation | QP.E.ME.MBL.GEN.1070 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L6 SKY GARDEN +935.85M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L6 SKY GARDEN +935.85M | QP.E.ME.MBL.GEN.6760 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M | QP.E.ME.MBL.GEN.6580 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | Plant Room - Fan Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M ¦ Plant Room - Fan Room | QP.E.ME.MBL.GEN.6600 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Kitchen and Laundry | Kitchen and Laundry | Kitchen and Laundry | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Kitchen and Laundry | QP.E.ME.MBL.GEN.7400 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | MEP | Panels | Panels | Panels | Panels | Panels | Shop Drawings ¦ MEP ¦ Panels | QP.E.ME.MBL.GEN.6510 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Mechanical | QP.E.ME.BL1.GEN.3720 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical | QP.E.ME.BL1.GEN.3740 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL1.GEN.3760 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL1.GEN.3780 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Mechanical | QP.E.ME.BL1.GEN.3800 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical | QP.E.ME.BL1.GEN.3820 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1020 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1030 | Submittal | 21 | 2027-02-25 | 2027-03-23
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1040 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1050 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ ICT Containment | QP.E.ME.BL1.GEN.1060 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL1.GEN.2940 | Submittal | 21 | 2027-04-11 | 2027-05-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.2950 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.2960 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.2970 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL1.GEN.2980 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1510 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1520 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1530 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1540 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ ICT Containment | QP.E.ME.BL1.GEN.1550 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.BL1.GEN.3280 | Submittal | 21 | 2027-08-30 | 2027-09-22
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL1.GEN.3320 | Submittal | 21 | 2027-10-07 | 2027-10-31
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL1.GEN.3340 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL1.GEN.3360 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL1.GEN.3580 | Submittal | 21 | 2027-11-15 | 2027-12-08
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL1.GEN.3600 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL1.GEN.3620 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL1.GEN.3680 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL1.GEN.3640 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL1.GEN.3660 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3480 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL1.GEN.1000 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL1.GEN.3700 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3400 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical | QP.E.ME.BL2.GEN.3420 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL2.GEN.3440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL2.GEN.3460 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3480 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical | QP.E.ME.BL2.GEN.3500 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1020 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1030 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1040 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1050 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.1060 | Submittal | 21 | 2027-04-18 | 2027-05-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1910 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1920 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1930 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1940 | Submittal | 21 | 2027-04-29 | 2027-05-27
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL2.GEN.1950 | Submittal | 21 | 2027-05-12 | 2027-06-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.2110 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.2120 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.2130 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.2140 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.2150 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL2.GEN.3160 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL2.GEN.3200 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL2.GEN.3220 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL2.GEN.3240 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL2.GEN.3260 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL2.GEN.3280 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL2.GEN.3300 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL2.GEN.3380 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL2.GEN.3320 | Submittal | 28 | 2027-11-22 | 2027-12-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL2.GEN.3340 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3500 | Submittal | 14 | 2028-02-17 | 2028-03-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL2.GEN.1000 | Submittal | 16 | 2028-02-17 | 2028-03-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL2.GEN.3360 | Submittal | 14 | 2028-04-09 | 2028-04-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Mechanical | QP.E.ME.BL3.GEN.3640 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical | QP.E.ME.BL3.GEN.3660 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical | QP.E.ME.BL3.GEN.3700 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Mechanical | QP.E.ME.BL3.GEN.3680 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1020 | Submittal | 21 | 2026-06-17 | 2026-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.1030 | Submittal | 21 | 2026-07-12 | 2026-08-04
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1040 | Submittal | 21 | 2026-08-05 | 2026-08-29
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1050 | Submittal | 21 | 2026-08-30 | 2026-09-22
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ ICT Containment | QP.E.ME.BL3.GEN.1060 | Submittal | 21 | 2026-10-07 | 2026-10-31
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1790 | Submittal | 21 | 2026-12-31 | 2027-01-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.3280 | Submittal | 21 | 2027-01-25 | 2027-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1810 | Submittal | 21 | 2027-02-18 | 2027-03-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1820 | Submittal | 21 | 2027-03-18 | 2027-04-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ ICT Containment | QP.E.ME.BL3.GEN.1830 | Submittal | 21 | 2027-04-12 | 2027-05-05
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL3.GEN.3400 | Submittal | 21 | 2027-06-23 | 2027-07-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL3.GEN.3440 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL3.GEN.3460 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL3.GEN.3480 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL3.GEN.3500 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL3.GEN.3540 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL3.GEN.3560 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL3.GEN.3620 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL3.GEN.3600 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL3.GEN.3580 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3520 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL3.GEN.1000 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL3.GEN.3520 | Submittal | 14 | 2028-04-04 | 2028-04-19
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Mechanical | QP.E.ME.BL4.GEN.6010 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical | QP.E.ME.BL4.GEN.6030 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Mechanical | QP.E.ME.BL4.GEN.6050 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Electrical | QP.E.ME.BL4.GEN.6070 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Mechanical | QP.E.ME.BL4.GEN.6090 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical | QP.E.ME.BL4.GEN.6110 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Fire Suppression | QP.E.ME.BL4.GEN.2110 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2120 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2130 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2140 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ ICT Containment | QP.E.ME.BL4.GEN.2150 | Submittal | 21 | 2026-11-01 | 2026-11-24
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2910 | Submittal | 21 | 2026-12-05 | 2026-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.5550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2930 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2940 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ ICT Containment | QP.E.ME.BL4.GEN.2950 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2810 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2820 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2830 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2840 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ ICT Containment | QP.E.ME.BL4.GEN.2850 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL4.GEN.5770 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL4.GEN.5810 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL4.GEN.5830 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL4.GEN.5850 | Submittal | 21 | 2027-09-29 | 2027-10-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL4.GEN.5870 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL4.GEN.5930 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL4.GEN.5950 | Submittal | 21 | 2027-12-05 | 2027-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL4.GEN.5890 | Submittal | 21 | 2028-01-12 | 2028-02-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL4.GEN.5970 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL4.GEN.5990 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3540 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL4.GEN.3110 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL4.GEN.5910 | Submittal | 14 | 2028-04-02 | 2028-04-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Mechanical | QP.E.ME.BL5.GEN.3040 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical | QP.E.ME.BL5.GEN.3060 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL5.GEN.3080 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL5.GEN.3100 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Mechanical | QP.E.ME.BL5.GEN.3120 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical | QP.E.ME.BL5.GEN.3140 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1020 | Submittal | 21 | 2026-10-29 | 2026-11-22
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1030 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1040 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1050 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ ICT Containment | QP.E.ME.BL5.GEN.1060 | Submittal | 21 | 2026-11-25 | 2026-12-19
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1560 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1570 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1580 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL5.GEN.1590 | Submittal | 21 | 2027-04-10 | 2027-05-03
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1750 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1760 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1770 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1780 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ ICT Containment | QP.E.ME.BL5.GEN.1790 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL5.GEN.2800 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL5.GEN.2840 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL5.GEN.2860 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL5.GEN.2880 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL5.GEN.3020 | Submittal | 14 | 2027-10-24 | 2027-11-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL5.GEN.2900 | Submittal | 14 | 2027-12-01 | 2027-12-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL5.GEN.2920 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL5.GEN.3000 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL5.GEN.2940 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL5.GEN.2960 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3560 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL5.GEN.1000 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL5.GEN.2980 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Mechanical | QP.E.ME.PAR.GEN.1459 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Electrical | QP.E.ME.PAR.GEN.1479 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Mechanical | QP.E.ME.PAR.GEN.1499 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Electrical | QP.E.ME.PAR.GEN.1519 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Fire Suppression | QP.E.ME.PAR.GEN.1000 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1011 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1022 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1033 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ ICT Containment | QP.E.ME.PAR.GEN.1044 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Fire Suppression | QP.E.ME.PAR.GEN.1055 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1066 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1077 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1088 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ ICT Containment | QP.E.ME.PAR.GEN.1099 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.PAR.GEN.1219 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.PAR.GEN.1259 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.PAR.GEN.1279 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.PAR.GEN.1299 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.PAR.GEN.1419 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.PAR.GEN.1319 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.PAR.GEN.1339 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.PAR.GEN.1439 | Submittal | 14 | 2028-02-07 | 2028-02-23
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.PAR.GEN.1359 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.PAR.GEN.1379 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.PAR.GEN.1399 | Submittal | 14 | 2028-03-09 | 2028-03-25
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3600 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3610 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3620 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.4430 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4440 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.4450 | Submittal | 14 | 2027-12-18 | 2028-01-02
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3960 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3970 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3980 | Submittal | 14 | 2028-01-01 | 2028-01-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Fire Suppression | QP.E.ME.MBL.GEN.3930 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3940 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Electrical | QP.E.ME.MBL.GEN.3950 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Fire Suppression | QP.E.ME.MBL.GEN.3810 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3820 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Electrical | QP.E.ME.MBL.GEN.3830 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4400 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4410 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4420 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4340 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4350 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4360 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4520 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4530 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4540 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4640 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4650 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4660 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3870 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3880 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3890 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3840 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3850 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3860 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.4550 | Submittal | 21 | 2028-02-08 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4560 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.4570 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 3, 4 & 5 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 3, 4 & 5 | QP.E.FA.GEN.GEN.1460 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 1 & 2 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 1 & 2 | QP.E.FA.GEN.GEN.2180 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Loft and Lobby | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Loft and Lobby | QP.E.FA.GEN.GEN.2140 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | QP.E.FA.GEN.GEN.2160 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Blades | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Blades | QP.E.FA.GEN.GEN.1820 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Lobby and Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Lobby and Loft | QP.E.FA.GEN.GEN.1770 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Above Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Above Loft | QP.E.FA.GEN.GEN.1780 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Blades | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Blades | QP.E.FA.GEN.GEN.1890 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Main Building | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Main Building | QP.E.FA.GEN.GEN.2230 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Facade | Facade | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 1 | QP.E.FA.GEN.GEN.1920 | Submittal | 28 | 2026-09-29 | 2026-10-31
Shop Drawings | Facade | Facade | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 2 | QP.E.FA.GEN.GEN.1930 | Submittal | 28 | 2026-08-26 | 2026-09-28
Shop Drawings | Facade | Facade | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 3 | QP.E.FA.GEN.GEN.1940 | Submittal | 28 | 2026-05-17 | 2026-06-21
Shop Drawings | Facade | Facade | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 4 | QP.E.FA.GEN.GEN.1950 | Submittal | 28 | 2026-06-22 | 2026-07-23
Shop Drawings | Facade | Facade | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 5 | QP.E.FA.GEN.GEN.1960 | Submittal | 28 | 2026-07-25 | 2026-08-25
Shop Drawings | Facade | Facade | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Facade ¦ Amphitheatre | QP.E.FA.GEN.GEN.2240 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Lobby | Lobby | Lobby | Lobby | Shop Drawings ¦ Facade ¦ Lobby | QP.E.FA.GEN.GEN.2090 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | Loft | Loft | Loft | Loft | Shop Drawings ¦ Facade ¦ Loft | QP.E.FA.GEN.GEN.2100 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Above Loft | Above Loft | Above Loft | Above Loft | Shop Drawings ¦ Facade ¦ Above Loft | QP.E.FA.GEN.GEN.1910 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | Link Bridges | Link Bridges | Link Bridges | Link Bridges | Shop Drawings ¦ Facade ¦ Link Bridges | QP.E.FA.GEN.GEN.2050 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Facade | Facade | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Shop Drawings ¦ Facade ¦ Facade Lighting Fixtures | QP.E.FA.GEN.GEN.1450 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | GRC Cladding | GRC Cladding | GRC Cladding | GRC Cladding | Shop Drawings ¦ Facade ¦ GRC Cladding | QP.E.FA.GEN.GEN.1390 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 1 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 1 | QP.E.CV.MBL.GEN.3060 | Submittal | 28 | 2026-08-06 | 2026-09-07
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 2 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 2 | QP.E.CV.MBL.GEN.3560 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 3 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 3 | QP.E.CV.MBL.GEN.3580 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 4 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 4 | QP.E.CV.MBL.GEN.3600 | Submittal | 28 | 2027-01-03 | 2027-02-03
Shop Drawings | External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Shop Drawings ¦ External Works ¦ Waterproofing for External Works | QP.E.EX.GEN.GEN.1040 | Submittal | 28 | 2026-06-25 | 2026-07-27
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Excavation | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Excavation | QP.E.CV.MBL.GEN.3320 | Submittal | 28 | 2027-01-06 | 2027-02-07
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Blinding Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Blinding Including Embedded Items | QP.E.CV.MBL.GEN.3500 | Submittal | 28 | 2027-02-23 | 2027-03-29
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Foundation Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Foundation Including Embedded Items | QP.E.CV.MBL.GEN.3480 | Submittal | 28 | 2027-04-13 | 2027-05-19
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Structural Concrete Works Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Structural Concrete Works Including Embedded Items | QP.E.CV.MBL.GEN.3520 | Submittal | 28 | 2027-06-03 | 2027-07-05
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4000 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Finishing | Finishing | Finishing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Finishing | QP.E.AF.MBL.GEN.4030 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4010 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Doors / Openings | QP.E.AF.MBL.GEN.4020 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Fire Suppression | QP.E.ME.MBL.GEN.1690 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Plumbing | Plumbing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Plumbing | QP.E.ME.MBL.GEN.1700 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.1710 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Electrical | Electrical | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Electrical | QP.E.ME.MBL.GEN.1720 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ ELV (Low Current System) | QP.E.ME.MBL.GEN.1730 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | External Utilities | Irrigation Works | Irrigation Works | Irrigation Works | Irrigation Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ Irrigation Works | QP.E.EX.GEN.GEN.1090 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Drainage Works | External Drainage Works | External Drainage Works | External Drainage Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Drainage Works | QP.E.EX.GEN.GEN.1110 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Lighting Works | External Lighting Works | External Lighting Works | External Lighting Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Lighting Works | QP.E.EX.GEN.GEN.1170 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | External Utilities | Low Current | Low Current | Low Current | Low Current | Shop Drawings ¦ External Works ¦ External Utilities ¦ Low Current | QP.E.EX.GEN.GEN.1100 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Shop Drawings ¦ External Works ¦ Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 | Submittal | 14 | 2027-08-07 | 2027-08-22
Shop Drawings | External Works | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Shop Drawings ¦ External Works ¦ Water and Environment | QP.E.EX.GEN.GEN.1220 | Submittal | 21 | 2026-11-23 | 2026-12-16
Shop Drawings | External Works | External Fixtures | External Fixtures | External Fixtures | External Fixtures | External Fixtures | Shop Drawings ¦ External Works ¦ External Fixtures | QP.E.EX.GEN.GEN.1260 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | External Works | LPG System | LPG System | LPG System | LPG System | LPG System | Shop Drawings ¦ External Works ¦ LPG System | QP.E.EX.GEN.GEN.1300 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Fit-out | Fit-out | Fit-out | Fit-out | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Fit-out | QP.C.PS.GEN.GEN.2590 | Submittal | 110 | 2026-07-30 | 2026-12-06
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Stage Engineering | Stage Engineering | Stage Engineering | Stage Engineering | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Stage Engineering | QP.C.PS.GEN.GEN.2560 | Submittal | 110 | 2026-12-07 | 2027-04-17
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | AV / Broadcast | AV / Broadcast | AV / Broadcast | AV / Broadcast | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ AV / Broadcast | QP.C.PS.GEN.GEN.1200 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ Technology (ICT) | QP.C.PS.GEN.GEN.1810 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Control Systems | Control Systems | Control Systems | Control Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Control Systems | QP.C.PS.GEN.GEN.1880 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Lighting Systems | Lighting Systems | Lighting Systems | Lighting Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Lighting Systems | QP.C.PS.GEN.GEN.1850 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Conveying System Finishes | QP.C.PS.GEN.GEN.2120 | Submittal | 150 | 2027-06-07 | 2027-11-29
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | HVAC System | HVAC System | HVAC System | HVAC System | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ HVAC System | QP.C.PS.GEN.GEN.2100 | Submittal | 90 | 2027-11-01 | 2028-02-13
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | ID Finishes | ID Finishes | ID Finishes | ID Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ ID Finishes | QP.C.PS.GEN.GEN.1930 | Submittal | 90 | 2027-07-18 | 2027-10-31
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Water Features | QP.C.PS.GEN.GEN.1960 | Submittal | 120 | 2027-02-16 | 2027-07-13
Shop Drawings | Provisional Sums | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | Shop Drawings ¦ Provisional Sums ¦ PS5 - Signage and Wayfinding | QP.C.PS.GEN.GEN.2140 | Submittal | 60 | 2028-07-29 | 2028-10-07
Shop Drawings | Provisional Sums | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | Shop Drawings ¦ Provisional Sums ¦ PS6 - Soft Landscaping | QP.C.PS.GEN.GEN.2180 | Submittal | 160 | 2027-08-30 | 2028-03-08
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Concrete Superstructure | QP.C.PS.GEN.GEN.2360 | Submittal | 30 | 2028-06-08 | 2028-07-12
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Foundation | Foundation | Foundation | Foundation | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Foundation | QP.C.PS.GEN.GEN.2260 | Submittal | 30 | 2028-05-01 | 2028-06-07
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Landscape | Landscape | Landscape | Landscape | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Landscape | QP.C.PS.GEN.GEN.2320 | Submittal | 30 | 2028-07-31 | 2028-09-03
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Promenade Bridge MEP | QP.C.PS.GEN.GEN.2340 | Submittal | 30 | 2028-06-26 | 2028-07-30
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Technology (ICT) | QP.C.PS.GEN.GEN.2400 | Submittal | 150 | 2027-04-11 | 2027-10-07
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Traffic & Car Parking | QP.C.PS.GEN.GEN.2500 | Submittal | 150 | 2027-07-12 | 2028-01-03

## Picklists
| #VALUE! |  | Numbering System Document - Metadata Mapping
DOCUMENT NUMBERING DROPDOWN ATTRIBUTES | [18 empty] | QIC GENERAL DROPDOWN ATTRIBUTES
FIELD 01 - PROJECT CODE |  | FIELD 02 - ORIGINATOR |  | FIELD 03 - CONTRACT REFERENCE |  | FIELD 04 - DOCUMENT TYPES |  | FIELD 05 - DISCIPLINE |  | FIELD 06 - AREA/ZONE |  | FIELD 07 - VENUE/BUILDING |  | FIELD 08 - SERIAL NUMBER |  |  |  |  | DOCUMENT DETAILS |  |  | SUITABILITY STATUS |  | NAP GENERAL DROPDOWN ATTRIBUTES
Ab. 01 | 1 - Project Name | Ab. 02 | 2 - Originator Name | Ab. 03 | 3 - Contract Reference | Ab. 04 | 4 - Document Type | Ab. 05 | 5 - Discipline | Ab. 06 | 6 - Area/Zone | Ab. 07 | 7 - Venue/Building | Ab. 08A | 8A - Drawing Type | Ab. 08B | 8B - Level | 8C - Sequence Number | Authoring Software | File/Exchange Format | Scope Area | Code | Status | Scale | Classification ID | Classification | Corporate Discipline | Author
QF01012 | Qiddaya Performing Arts Center | NES | Nesma and Partners | C04518 | Contract Number | AGD | Agenda | ACO | Acoustic | 00 | Overall | Z00000 | Overall | 0 | General (General Notes, Abbreviations, Legends, Single Line Diagrams, General Detail) | 00 | Non-Specific ( For Blade ) | 4 Digit Sequence Number For Drawings/Models | Revit | .rvt | Design Management | S0 (WIP) | Initial status or WIP | NTS | FI_60_25 | Drawing | Architectural | Nesma & Partners
[6 empty] | AVV | Agreed Value of Variation | ADM | Administration | 01 | Zone Sheet 1 | CENT01 | Center Block | 1 | Elevations (Vertical View) | B1 | Basement 1 - Parking A +900.50 | 3 Digit Sequence Number For Documents | Civil3D | .nwc | Architecture / LDC | S1 (Shared) | Suitable for Coordination | AS INDICATED | FI_90_75 | Schedule or table | Electrical | JINGGONG
[6 empty] | ASB | As Built | ARC | Architectural | 02 | Zone Sheet 2 | GARD01 | Guard House | 2 | Plans (Overall, Horizontal View, Floor Plan, Ceiling Plan, Site Plan, Loading Plan) | B2 | Basement 2 - Service +893.50 |  | MicrosoftWord | .nwd | Landscape | S2 (Shared) | Suitable for Information | 1:1 | FI_60_53 | Model | Façade | ALUTEC
[6 empty] | AUR | Audit Report | ADT | Area Development | 03 | Zone Sheet 3 | BLAD01 | Blade 01 | 3 | Sections (Sectional View, Wall Section, Riser) | B3 | Basement 3 - Promenade +887.750 |  | MicrosoftExcel | .ifc | Interior Design | S3 (Shared) | Suitable for Review and Comment | 1:2 | FI_60_15 | Clash Rendition | Fire & Life Safety | AFCO
[6 empty] | BOQ | Bill of Quantities | ASM | Assets Management | 04 | Zone Sheet 4 | BLAD02 | Blade 02 | 4 | Large-scale Views (Enlarged Details) (Plans, Elevations, Stair Sections, etc) | FL | Foundation level |  | Navisworks | .pdf | Signage & Wayfinding | S4 (Shared) | Suitable for Review and Authorisation | 1:5 | FI_40_10 | Calculations | Interior Design | DOKA
[6 empty] | BEP | BIM Execution Plan | AVL | Audio Visual | 05 | Zone Sheet 5 | BLAD03 | Blade 03 | 5 | Details (Any detail view, such as Wall / Floor / Manhole Detail, etc) | L1 | Lobby Level +905.0 |  | inDesign | .jpg | Public Interaction & Activation | S5 (Shared) | Suitable for Review and Acceptance | 1:10 | FI_90_72 | Report | Infrastructure | RAWABI
[6 empty] | BIM | BIM Model | AUV | Audio/Video | 06 | Zone Sheet 6 | BLAD04 | Blade 04 | 6 | Schedules and Diagrams | L2 | Theater Stalls +913.0 |  | Inviso | .xls | Structure | A1 (Published) | Authorised and Accepted-Concept Design | 1:20 | FI_10_90 | Transmittal | Landscape | FALLPROTEC
[6 empty] | BRF | Brief | BRG | Bridges | 07 | Zone Sheet 7 | BLAD05 | Blade 05 | 7 | Combination of different views | L3 | Stalles Mezz & AD Theater +917.5 |  | JPG | .xer | Geotechnical Engineering | A2 (Published) | Authorised and Accepted-Schematic Design 100% | 1:25 | FI_90_47 | Log | Mechanical | TKE
[6 empty] | BUD | Budget | BRC | Broadcast | 08 | Zone Sheet 8 | MBLAD1 | Mini Blade 01 | 8 | User-Defined (For types that do not fall in other categories) | L4 | First Circle & AD Theater +921.0 |  | Recap | .dwf | Civil Engineering | A3 (Published) | Authorised and Accepted-Detailed Design 100% | 1:50 | FI_80_50 | Method statement | Structural | Subcontractor - Unassigned
[6 empty] | CAL | Calculation | BIM | Building Information Modelling | 09 | Zone Sheet 9 | MBLAD4 | Mini Blade 04 | 9 | 3D Representation (Isometric, Perspectives, Photographes) | L5 | Second Circle & Loft |  | Rhino | .dwg | MEP Engineering | A4 (Published) | Authorised and Accepted-Tender | 1:100 | FI_90_64 | Plan |  | Provisional Sum
[6 empty] | CER | Certificate | BMS | Building Management System | 10 | Zone Sheet 10 | SECE01 | SEC Room |  |  | L6 | SKY Garden +935.85 |  | Sketchup | .bcf | Fire & Life Safety | A5 (Published) | Authorised and Accepted-IFC | 1:150 |  |  |  | NAP PMO
[6 empty] | COR | Change Order | CWC | Chilled Water / Cooling | 11 | Zone Sheet 11 | PARK01 | Parking Building |  |  | L8 | Royal Majlis +948.10M |  | Autocad | .3ds | Pitch Design & Sports Playing Surfaces | A6 (Published) | Authorised and Accepted-Construction (Shop Drawing) | 1:200 |  |  |  | Sana Al-Jazerah
[6 empty] | CRA | Change Request Authorization | CIV | Civil | 12 | Zone Sheet 12 |  |  |  |  | M1 | Mez Upper Lobby +909.0 |  | ArcGIS | .skp | Specialist Lighting (Services and Systems) | A7 (Published) | Authorised and Accepted-As Built | 1:250
[6 empty] | CDT | Clash Detection Report | CPM | Contracts & Procurement | 13 | Zone Sheet 13 |  |  |  |  | M2 | Mez Loft MEP +931.10 |  |  | .docx | Acoustics | A8(Published) | Authorised and Accepted-In Use | 1:300
[6 empty] | CLM | Claim | CIN | Controls & Instrumentation | 14 | Zone Sheet 14 |  |  |  |  | RL | Roof Level |  |  | .rvt,.nwd,.ifc | AV / Broadcast |  |  | 1:350
[6 empty] | CIN | Client Instruction | CRE | Creative Designer | 15 | Zone Sheet 15 |  |  |  |  | ZZ | Overall |  |  | .nwc,.nwd,.ifc | Security |  |  | 1:500
[6 empty] | CRS | Comments Resolution Sheet | CDM | Crowd Management | 16 | Zone Sheet 16 | [8 empty] | .dwg,.nwc,.ifc | Vertical Transport
[6 empty] | CON | Contract | CUL | Culvert | 17 | Zone Sheet 17 | [8 empty] | .docx,.pdf | Facade & Roof Envelope
[6 empty] | COS | Cost Estimate | DRN | Drainage | 18 | Zone Sheet 18 | [8 empty] | .xer,.pdf | Crowd Modelling / Pedestrian Flow
[6 empty] | DAB | Dashboard | ELP | Earthing & Lighting Protection | 19 | Zone Sheet 19 | [8 empty] | .xls,.pdf | Sustainability
[6 empty] | DOA | Delegation of Authority | ELE | Electrical | 20 | Zone Sheet 20 | [8 empty] | .msp,.pdf | Accessibility
[6 empty] | DES | Design | ELC | Electrical Containment | 21 | Zone Sheet 21 | [8 empty] | .dwg,.pdf | Architect of Record
[6 empty] | MTX | Distribution Matrix | ENV | Environmental | 22 | Zone Sheet 22 | [8 empty] | .indd | Food & Beverage & Operations
[6 empty] | DSS | Dossier | EQP | Equipment | 23 | Zone Sheet 23 | [8 empty] | .pdf, .indd | Utilities, Roads & Infrastructure
[6 empty] | DRW | Drawing | FAC | Facade | 24 | Zone Sheet 24 | [8 empty] | .rvt,.nwc,.ifc | Traffic & Car Parking
[6 empty] | ENI | Engineer Instruction | FED | Federated | 25 | Zone Sheet 25 | [8 empty] | .gdb | Technology (ICT)
[6 empty] | EXP | Expenses | FIN | Finance | 26 | Zone Sheet 26 | [9 empty] | Sports & Specialist Lighting
[6 empty] | HOC | Handover Certificate | FAE | Fire Alarm & Emergency Lighting | 27 | Zone Sheet 27 | [9 empty] | BMS & Access Control
[6 empty] | IRT | Incident Report | FLS | Fire Life Safety | 28 | Zone Sheet 28 | [9 empty] | Waste Management
[6 empty] | ITP | Inspection & Test Plan | FPR | Fire Protection | [11 empty] | Health & Safety in Design
[6 empty] | INS | Instruction | FFE | Furniture Fixture & Equipment | [11 empty] | Wind
[6 empty] | IAB | Insurance and Bonds | GEN | General
[6 empty] | INV | Invoice | GIS | Geospatial Information System
[6 empty] | LAR | Laydown Area Access Request | GEH | Geotechnical & Hydraulics
[6 empty] | LTR | Letter | GRA | Graphics
[6 empty] | LIC | License | HSE | Health and Safety
[6 empty] | LST | List | EHV | High Voltage
[6 empty] | MAN | Manual | HVC | HVAC
[6 empty] | MPL | Master Plan | ICT | Information & Communication Technology
[6 empty] | MAR | Material Approval Request | INF | Infrastructure
[6 empty] | MIR | Material Inspection Request | INS | Installation
[6 empty] | MST | Method Statement | ITS | Intelligent Transportation System
[6 empty] | MOM | Minutes of Meeting | INT | Interior Design
[6 empty] | MIX | Mix Design | IRR | Irrigation
[6 empty] | MOD | Model | KNL | Kitchen & Laundry
[6 empty] | MRP | Monthly Report | LSE | Landscape
[6 empty] | NOC | No Objection Certificate | ELL | Lighting
[6 empty] | NCR | Non-Conformance Report | LTC | Lighting Control
[6 empty] | NDA | Non-Disclosure Agreement | ELV | Low Voltage
[6 empty] | NTC | Notice | LPG | LPG
[6 empty] | OMM | Operation & Maintenance Manual | MAR | Marine Engineering
[6 empty] | ORC | Organizational Chart | MPL | Master Planning
[6 empty] | OTR | Overtime Request | MEC | Mechanical
[6 empty] | PAP | Payment Application | EMV | Medium Voltage
[6 empty] | PYC | Payment Certificate | MEP | MEPF
[6 empty] | PRM | Permit | NTD | Non-Technical Document
[6 empty] | PAF | Personnel Approval Form | OSE | Operating Supplies and Equipment
[6 empty] | PIV | Photographs, Images & Videos | OTH | Others
[6 empty] | PLN | Plan | PLB | Plumbing
[6 empty] | PLT | Plant | PTW | Potable Water
[6 empty] | PPG | Policy & Procedure | PJC | Project Control
[6 empty] | PQS | Prequalification Submittal | QMS | Quality Management
[6 empty] | PRE | Presentation | RID | Rides
[6 empty] | PRO | Procedure | ERL | Road Lighting
[6 empty] | PEP | Project Execution Plan | RKW | Rockwork
[6 empty] | PRS | Proposal | SEC | Security System
[6 empty] | POR | Purchase Order | SEW | Sewage
[6 empty] | REG | Register | SHW | Show
[6 empty] | REP | Report | SGN | Signage / Wayfinding
[6 empty] | RFC | Request For Change | ESP | Small Power
[6 empty] | RSM | Resume | SSC | Smart City
[6 empty] | SVR | Safety Violation Report | SPL | Specialist Lighting
[6 empty] | SMP | Sample | SWD | Storm Water Drainage
[6 empty] | SCH | Schedule | STR | Structural
[6 empty] | SDW | Shop Drawing | SUR | Surveying / Mapping
[6 empty] | SIN | Site Instruction | SUS | Sustainability
[6 empty] | SOR | Site Observation Report | TEL | Telecommunication
[6 empty] | SPE | Specification | TNC | Testing/Commissioning
[6 empty] | STD | Standard | TFC | Traffic System
[6 empty] | SFA | Statement of Final Account | UTI | Utilities
[6 empty] | STR | Strategy | VNT | Ventilation Ductwork
[6 empty] | TOC | Taking Over Certificate | VTR | Vertical Transportation
[6 empty] | TOR | Task Order | VES | Voice Evacuation
[6 empty] | TEM | Template | WSM | Waste Management
[6 empty] | TDC | Tender Document | WTR | Water
[6 empty] | TRP | Test Report | CTV | CCTV System
[6 empty] | TMS | Time Sheet | ACS | Access Control System
[6 empty] | VOR | Variation Order | EFL | Facade Lighting
[6 empty] | WAR | Warranty / Guarantees | DES | Diesel
[6 empty] | WRP | Weekly Report | SMK | Smoke Ductwork
[6 empty] | WIR | Work Inspection Request | STL | Steel Structure
[6 empty] | RLM | RedLine Mark Drawing | FWR | Formwork
[6 empty] | MDP | Master Information Delivery Plan | ELS | Emergency Lighting system
[6 empty] | TDP | Task Information Delivery Plan | EBW | Electrical Builder Works
[8 empty] | MBW | Mechanical Builder Works
[8 empty] | EBC | Electrical Busway
[8 empty] | WFT | Water Features
[8 empty] | LOG | Logistics