## TIDP_Sheet
TASK INFORMATION DELIVERY PLAN (TIDP)
CLIENT | Qiddaya | #VALUE!
PROJECT | Qiddaya Performing Arts Center (QPAC)
ORGANISATION | Nesma & Partners
DISCIPLINE | Landscape
APPROVER | BSBG
DATE CREATED | 2025-11-25
DATE LAST UPDATED | 2026-08-13
REVISION NUMBER | 01
DOCUMENT REFERENCE | QF01012-NES-C04518-TDP-LSE-00-000000-000001
This document shall be populated and kept up-to-date by the task team | [10 empty] | REFER TO THE FILE NAMING CONVENTION IN THE BIM EXECUTION PLAN | [10 empty] | DATA EXCHANGE #01 | [5 empty] | DATA EXCHANGE #02
[11 empty] | DOC REFERENCE GENERATOR | [10 empty] | STAGE: | CONSTRUCTION |  |  |  |  | STAGE: | HAND OVER
[22 empty] | PROGRAMME REF: | [5 empty] | PROGRAMME REF:
[5 empty] | EXCHANGE FORMATS | [5 empty] | FIELD 01 | FIELD 02 | FIELD 03 | FIELD 04 | FIELD 05 | FIELD 06 | FIELD 07 | FIELD 08 |  |  |  |  | LEVEL OF INFORMATION NEED | [5 empty] | LEVEL OF INFORMATION NEED
DOCUMENT NUMBER | DOCUMENT TITLE | EXTRACTED FROM MODEL | SCOPE AREA | AUTHORING SOFTWARE | EXCHANGE FORMAT | SCALE | DELIVERY MILESTONE | PACKAGE NAME | ACTIVITY ID | CLASSIFICATION CODE | PROJECT | ORIGINATOR | CONTRACT | DOCUMENT TYPE | DISCIPLINE | AREA/ZONE | VENUE/BUILDING | DRAWING TYPE | LEVEL | SEQUENCE NUMBER | CORPORATE DISCIPLINE | 01-AUTHOR | 01-GEOMETRICAL | 01-NON GEOMETRICAL | 01-DURATION (DAYS) | 01-PREDECESSOR | 01-EXCHANGE DATE | 02-AUTHOR | 02-GEOMETRICAL | 02-NON GEOMETRICAL | 02-DURATION (DAYS) | 02-PREDECESSOR | 02-EXCHANGE DATE
QF01012-NES-C04518-SDW-LSE-00-Z00000-0ZZ0000 | GENERAL |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | GENERAL | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 0 | ZZ | 0000 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-2ZZ0000 | SHEDULES |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-17 | SHEDULES | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 2 | ZZ | 0000 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-6ZZ0000 | Landscape - General Arrangement - Overall Layout |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 6 | ZZ | 0000 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-01-Z00000-2ZZ0001 | Landscape - General Arrangement - Layout Plan - Sheet 01 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 01 | Z00000 | 2 | ZZ | 0001 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-02-Z00000-2ZZ0002 | Landscape - General Arrangement - Layout Plan - Sheet 02 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 02 | Z00000 | 2 | ZZ | 0002 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-03-Z00000-2ZZ0003 | Landscape - General Arrangement - Layout Plan - Sheet 03 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 03 | Z00000 | 2 | ZZ | 0003 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-04-Z00000-2ZZ0004 | Landscape - General Arrangement - Layout Plan - Sheet 04 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 04 | Z00000 | 2 | ZZ | 0004 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-05-Z00000-2ZZ0005 | Landscape - General Arrangement - Layout Plan - Sheet 05 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 05 | Z00000 | 2 | ZZ | 0005 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-06-Z00000-2ZZ0006 | Landscape - General Arrangement - Layout Plan - Sheet 06 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 06 | Z00000 | 2 | ZZ | 0006 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-07-Z00000-2ZZ0007 | Landscape - General Arrangement - Layout Plan - Sheet 07 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 07 | Z00000 | 2 | ZZ | 0007 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-08-Z00000-2ZZ0008 | Landscape - General Arrangement - Layout Plan - Sheet 08 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 08 | Z00000 | 2 | ZZ | 0008 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-09-Z00000-2ZZ0009 | Landscape - General Arrangement - Layout Plan - Sheet 09 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 09 | Z00000 | 2 | ZZ | 0009 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-10-Z00000-2ZZ0010 | Landscape - General Arrangement - Layout Plan - Sheet 10 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 10 | Z00000 | 2 | ZZ | 0010 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-11-Z00000-2ZZ0011 | Landscape - General Arrangement - Layout Plan - Sheet 11 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 11 | Z00000 | 2 | ZZ | 0011 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-12-Z00000-2ZZ0012 | Landscape - General Arrangement - Layout Plan - Sheet 12 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 12 | Z00000 | 2 | ZZ | 0012 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-13-Z00000-2ZZ0013 | Landscape - General Arrangement - Layout Plan - Sheet 13 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 13 | Z00000 | 2 | ZZ | 0013 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-14-Z00000-2ZZ0014 | Landscape - General Arrangement - Layout Plan - Sheet 14 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 14 | Z00000 | 2 | ZZ | 0014 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-15-Z00000-2ZZ0015 | Landscape - General Arrangement - Layout Plan - Sheet 15 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 15 | Z00000 | 2 | ZZ | 0015 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-16-Z00000-2ZZ0016 | Landscape - General Arrangement - Layout Plan - Sheet 16 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 16 | Z00000 | 2 | ZZ | 0016 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-17-Z00000-2ZZ0017 | Landscape - General Arrangement - Layout Plan - Sheet 17 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 17 | Z00000 | 2 | ZZ | 0017 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-18-Z00000-2ZZ0018 | Landscape - General Arrangement - Layout Plan - Sheet 18 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 18 | Z00000 | 2 | ZZ | 0018 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-19-Z00000-2ZZ0019 | Landscape - General Arrangement - Layout Plan - Sheet 19 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 19 | Z00000 | 2 | ZZ | 0019 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-20-Z00000-2ZZ0020 | Landscape - General Arrangement - Layout Plan - Sheet 20 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 20 | Z00000 | 2 | ZZ | 0020 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-21-Z00000-2ZZ0021 | Landscape - General Arrangement - Layout Plan - Sheet 21 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 21 | Z00000 | 2 | ZZ | 0021 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-22-Z00000-2ZZ0022 | Landscape - General Arrangement - Layout Plan - Sheet 22 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 22 | Z00000 | 2 | ZZ | 0022 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-23-Z00000-2ZZ0023 | Landscape - General Arrangement - Layout Plan - Sheet 23 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 23 | Z00000 | 2 | ZZ | 0023 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-24-Z00000-2ZZ0024 | Landscape - General Arrangement - Layout Plan - Sheet 24 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 24 | Z00000 | 2 | ZZ | 0024 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-25-Z00000-2ZZ0025 | Landscape - General Arrangement - Layout Plan - Sheet 25 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 25 | Z00000 | 2 | ZZ | 0025 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-26-Z00000-2ZZ0026 | Landscape - General Arrangement - Layout Plan - Sheet 26 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 26 | Z00000 | 2 | ZZ | 0026 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-27-Z00000-2ZZ0027 | Landscape - General Arrangement - Layout Plan - Sheet 27 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 27 | Z00000 | 2 | ZZ | 0027 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0028 | Landscape - General Arrangement - Layout Plan - Sheet 28 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - General Arragement | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0028 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-2ZZ0100 | Landscape - Hardscape - Overall Layout |  | Landscape | Revit | .docx,.pdf | 1:300 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 2 | ZZ | 0100 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-01-Z00000-2ZZ0101 | Landscape - Hardscape - Layout Plan - Sheet 01 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 01 | Z00000 | 2 | ZZ | 0101 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-02-Z00000-2ZZ0102 | Landscape - Hardscape - Layout Plan - Sheet 02 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 02 | Z00000 | 2 | ZZ | 0102 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-03-Z00000-2ZZ0103 | Landscape - Hardscape - Layout Plan - Sheet 03 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 03 | Z00000 | 2 | ZZ | 0103 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-04-Z00000-2ZZ0104 | Landscape - Hardscape - Layout Plan - Sheet 04 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 04 | Z00000 | 2 | ZZ | 0104 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-05-Z00000-2ZZ0105 | Landscape - Hardscape - Layout Plan - Sheet 05 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 05 | Z00000 | 2 | ZZ | 0105 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-06-Z00000-2ZZ0106 | Landscape - Hardscape - Layout Plan - Sheet 06 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 06 | Z00000 | 2 | ZZ | 0106 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-07-Z00000-2ZZ0107 | Landscape - Hardscape - Layout Plan - Sheet 07 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 07 | Z00000 | 2 | ZZ | 0107 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-08-Z00000-2ZZ0108 | Landscape - Hardscape - Layout Plan - Sheet 08 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 08 | Z00000 | 2 | ZZ | 0108 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-09-Z00000-2ZZ0109 | Landscape - Hardscape - Layout Plan - Sheet 09 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 09 | Z00000 | 2 | ZZ | 0109 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-10-Z00000-2ZZ0110 | Landscape - Hardscape - Layout Plan - Sheet 10 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 10 | Z00000 | 2 | ZZ | 0110 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-11-Z00000-2ZZ0111 | Landscape - Hardscape - Layout Plan - Sheet 11 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 11 | Z00000 | 2 | ZZ | 0111 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-12-Z00000-2ZZ0112 | Landscape - Hardscape - Layout Plan - Sheet 12 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 12 | Z00000 | 2 | ZZ | 0112 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-13-Z00000-2ZZ0113 | Landscape - Hardscape - Layout Plan - Sheet 13 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 13 | Z00000 | 2 | ZZ | 0113 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-14-Z00000-2ZZ0114 | Landscape - Hardscape - Layout Plan - Sheet 14 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 14 | Z00000 | 2 | ZZ | 0114 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-15-Z00000-2ZZ0115 | Landscape - Hardscape - Layout Plan - Sheet 15 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 15 | Z00000 | 2 | ZZ | 0115 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-16-Z00000-2ZZ0116 | Landscape - Hardscape - Layout Plan - Sheet 16 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 16 | Z00000 | 2 | ZZ | 0116 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-17-Z00000-2ZZ0117 | Landscape - Hardscape - Layout Plan - Sheet 17 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 17 | Z00000 | 2 | ZZ | 0117 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-18-Z00000-2ZZ0118 | Landscape - Hardscape - Layout Plan - Sheet 18 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 18 | Z00000 | 2 | ZZ | 0118 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-19-Z00000-2ZZ0119 | Landscape - Hardscape - Layout Plan - Sheet 19 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 19 | Z00000 | 2 | ZZ | 0119 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-20-Z00000-2ZZ0120 | Landscape - Hardscape - Layout Plan - Sheet 20 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 20 | Z00000 | 2 | ZZ | 0120 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-21-Z00000-2ZZ0121 | Landscape - Hardscape - Layout Plan - Sheet 21 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 21 | Z00000 | 2 | ZZ | 0121 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-22-Z00000-2ZZ0122 | Landscape - Hardscape - Layout Plan - Sheet 22 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 22 | Z00000 | 2 | ZZ | 0122 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-23-Z00000-2ZZ0123 | Landscape - Hardscape - Layout Plan - Sheet 23 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 23 | Z00000 | 2 | ZZ | 0123 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-24-Z00000-2ZZ0124 | Landscape - Hardscape - Layout Plan - Sheet 24 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 24 | Z00000 | 2 | ZZ | 0124 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-25-Z00000-2ZZ0125 | Landscape - Hardscape - Layout Plan - Sheet 25 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 25 | Z00000 | 2 | ZZ | 0125 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-26-Z00000-2ZZ0126 | Landscape - Hardscape - Layout Plan - Sheet 26 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 26 | Z00000 | 2 | ZZ | 0126 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-27-Z00000-2ZZ0127 | Landscape - Hardscape - Layout Plan - Sheet 27 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 27 | Z00000 | 2 | ZZ | 0127 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0128 | Landscape - Hardscape - Layout Plan - Sheet 28 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0128 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-29-Z00000-2ZZ0129 | Landscape - Hardscape - Layout Plan - Sheet 29 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 29 | Z00000 | 2 | ZZ | 0129 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-30-Z00000-2ZZ0130 | Landscape - Hardscape - Layout Plan - Sheet 30 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 30 | Z00000 | 2 | ZZ | 0130 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-31-Z00000-2ZZ0131 | Landscape - Hardscape - Layout Plan - Sheet 31 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 31 | Z00000 | 2 | ZZ | 0131 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-32-Z00000-2ZZ0132 | Landscape - Hardscape - Layout Plan - Sheet 32 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 32 | Z00000 | 2 | ZZ | 0132 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-33-Z00000-2ZZ0133 | Landscape - Hardscape - Layout Plan - Sheet 33 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 33 | Z00000 | 2 | ZZ | 0133 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-34-Z00000-2ZZ0134 | Landscape - Hardscape - Layout Plan - Sheet 34 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 34 | Z00000 | 2 | ZZ | 0134 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-35-Z00000-2ZZ0135 | Landscape - Hardscape - Layout Plan - Sheet 35 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 35 | Z00000 | 2 | ZZ | 0135 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-36-Z00000-2ZZ0136 | Landscape - Hardscape - Layout Plan - Sheet 36 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 36 | Z00000 | 2 | ZZ | 0136 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-37-Z00000-2ZZ0137 | Landscape - Hardscape - Layout Plan - Sheet 37 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 37 | Z00000 | 2 | ZZ | 0137 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-38-Z00000-2ZZ0138 | Landscape - Hardscape - Layout Plan - Sheet 38 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 38 | Z00000 | 2 | ZZ | 0138 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-39-Z00000-2ZZ0139 | Landscape - Hardscape - Layout Plan - Sheet 39 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 39 | Z00000 | 2 | ZZ | 0139 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-40-Z00000-2ZZ0140 | Landscape - Hardscape - Layout Plan - Sheet 40 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 40 | Z00000 | 2 | ZZ | 0140 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-41-Z00000-2ZZ0141 | Landscape - Hardscape - Layout Plan - Sheet 41 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 41 | Z00000 | 2 | ZZ | 0141 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-42-Z00000-2ZZ0142 | Landscape - Hardscape - Layout Plan - Sheet 42 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 42 | Z00000 | 2 | ZZ | 0142 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-43-Z00000-2ZZ0143 | Landscape - Hardscape - Layout Plan - Sheet 43 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 43 | Z00000 | 2 | ZZ | 0143 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-44-Z00000-2ZZ0144 | Landscape - Hardscape - Layout Plan - Sheet 44 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 44 | Z00000 | 2 | ZZ | 0144 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-45-Z00000-2ZZ0145 | Landscape - Hardscape - Layout Plan - Sheet 45 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 45 | Z00000 | 2 | ZZ | 0145 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-46-Z00000-2ZZ0146 | Landscape - Hardscape - Layout Plan - Sheet 46 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 46 | Z00000 | 2 | ZZ | 0146 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-47-Z00000-2ZZ0147 | Landscape - Hardscape - Layout Plan - Sheet 47 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 47 | Z00000 | 2 | ZZ | 0147 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-48-Z00000-2ZZ0148 | Landscape - Hardscape - Layout Plan - Sheet 48 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 48 | Z00000 | 2 | ZZ | 0148 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-49-Z00000-2ZZ0149 | Landscape - Hardscape - Layout Plan - Sheet 49 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 49 | Z00000 | 2 | ZZ | 0149 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-50-Z00000-2ZZ0150 | Landscape - Hardscape - Layout Plan - Sheet 50 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 50 | Z00000 | 2 | ZZ | 0150 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-51-Z00000-2ZZ0151 | Landscape - Hardscape - Layout Plan - Sheet 51 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 51 | Z00000 | 2 | ZZ | 0151 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-52-Z00000-2ZZ0152 | Landscape - Hardscape - Layout Plan - Sheet 52 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 52 | Z00000 | 2 | ZZ | 0152 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-53-Z00000-2ZZ0153 | Landscape - Hardscape - Layout Plan - Sheet 53 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 53 | Z00000 | 2 | ZZ | 0153 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-54-Z00000-2ZZ0154 | Landscape - Hardscape - Layout Plan - Sheet 54 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 54 | Z00000 | 2 | ZZ | 0154 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-55-Z00000-2ZZ0155 | Landscape - Hardscape - Layout Plan - Sheet 55 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 55 | Z00000 | 2 | ZZ | 0155 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-56-Z00000-2ZZ0156 | Landscape - Hardscape - Layout Plan - Sheet 56 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 56 | Z00000 | 2 | ZZ | 0156 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-57-Z00000-2ZZ0157 | Landscape - Hardscape - Layout Plan - Sheet 57 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 57 | Z00000 | 2 | ZZ | 0157 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-58-Z00000-2ZZ0158 | Landscape - Hardscape - Layout Plan - Sheet 58 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 58 | Z00000 | 2 | ZZ | 0158 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-59-Z00000-2ZZ0159 | Landscape - Hardscape - Layout Plan - Sheet 59 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 59 | Z00000 | 2 | ZZ | 0159 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-60-Z00000-2ZZ0160 | Landscape - Hardscape - Layout Plan - Sheet 60 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 60 | Z00000 | 2 | ZZ | 0160 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-61-Z00000-2ZZ0161 | Landscape - Hardscape - Layout Plan - Sheet 61 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 61 | Z00000 | 2 | ZZ | 0161 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-62-Z00000-2ZZ0162 | Landscape - Hardscape - Layout Plan - Sheet 62 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 62 | Z00000 | 2 | ZZ | 0162 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-63-Z00000-2ZZ0163 | Landscape - Hardscape - Layout Plan - Sheet 63 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 63 | Z00000 | 2 | ZZ | 0163 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-64-Z00000-2ZZ0164 | Landscape - Hardscape - Layout Plan - Sheet 64 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 64 | Z00000 | 2 | ZZ | 0164 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-65-Z00000-2ZZ0165 | Landscape - Hardscape - Layout Plan - Sheet 65 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 65 | Z00000 | 2 | ZZ | 0165 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-66-Z00000-2ZZ0166 | Landscape - Hardscape - Layout Plan - Sheet 66 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 66 | Z00000 | 2 | ZZ | 0166 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-67-Z00000-2ZZ0167 | Landscape - Hardscape - Layout Plan - Sheet 67 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 67 | Z00000 | 2 | ZZ | 0167 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-68-Z00000-2ZZ0168 | Landscape - Hardscape - Layout Plan - Sheet 68 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 68 | Z00000 | 2 | ZZ | 0168 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-69-Z00000-2ZZ0169 | Landscape - Hardscape - Layout Plan - Sheet 69 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 69 | Z00000 | 2 | ZZ | 0169 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-70-Z00000-2ZZ0170 | Landscape - Hardscape - Layout Plan - Sheet 70 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 70 | Z00000 | 2 | ZZ | 0170 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-71-Z00000-2ZZ0171 | Landscape - Hardscape - Layout Plan - Sheet 71 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 71 | Z00000 | 2 | ZZ | 0171 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-72-Z00000-2ZZ0172 | Landscape - Hardscape - Layout Plan - Sheet 72 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 72 | Z00000 | 2 | ZZ | 0172 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-73-Z00000-2ZZ0173 | Landscape - Hardscape - Layout Plan - Sheet 73 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 73 | Z00000 | 2 | ZZ | 0173 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-74-Z00000-2ZZ0174 | Landscape - Hardscape - Layout Plan - Sheet 74 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 74 | Z00000 | 2 | ZZ | 0174 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-75-Z00000-2ZZ0175 | Landscape - Hardscape - Layout Plan - Sheet 75 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 75 | Z00000 | 2 | ZZ | 0175 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-76-Z00000-2ZZ0176 | Landscape - Hardscape - Layout Plan - Sheet 76 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 76 | Z00000 | 2 | ZZ | 0176 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-77-Z00000-2ZZ0177 | Landscape - Hardscape - Layout Plan - Sheet 77 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 77 | Z00000 | 2 | ZZ | 0177 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-78-Z00000-2ZZ0178 | Landscape - Hardscape - Layout Plan - Sheet 78 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 78 | Z00000 | 2 | ZZ | 0178 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-79-Z00000-2ZZ0179 | Landscape - Hardscape - Layout Plan - Sheet 79 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 79 | Z00000 | 2 | ZZ | 0179 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-80-Z00000-2ZZ0180 | Landscape - Hardscape - Layout Plan - Sheet 80 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 80 | Z00000 | 2 | ZZ | 0180 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-81-Z00000-2ZZ0181 | Landscape - Hardscape - Layout Plan - Sheet 81 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 81 | Z00000 | 2 | ZZ | 0181 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-82-Z00000-2ZZ0182 | Landscape - Hardscape - Layout Plan - Sheet 82 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 82 | Z00000 | 2 | ZZ | 0182 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-83-Z00000-2ZZ0183 | Landscape - Hardscape - Layout Plan - Sheet 83 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 83 | Z00000 | 2 | ZZ | 0183 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-84-Z00000-2ZZ0184 | Landscape - Hardscape - Layout Plan - Sheet 84 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 84 | Z00000 | 2 | ZZ | 0184 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-85-Z00000-2ZZ0185 | Landscape - Hardscape - Layout Plan - Sheet 85 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 85 | Z00000 | 2 | ZZ | 0185 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-86-Z00000-2ZZ0186 | Landscape - Hardscape - Layout Plan - Sheet 86 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 86 | Z00000 | 2 | ZZ | 0186 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-87-Z00000-2ZZ0187 | Landscape - Hardscape - Layout Plan - Sheet 87 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 87 | Z00000 | 2 | ZZ | 0187 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-88-Z00000-2ZZ0188 | Landscape - Hardscape - Layout Plan - Sheet 88 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 88 | Z00000 | 2 | ZZ | 0188 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-89-Z00000-2ZZ0189 | Landscape - Hardscape - Layout Plan - Sheet 89 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 89 | Z00000 | 2 | ZZ | 0189 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-90-Z00000-2ZZ0190 | Landscape - Hardscape - Layout Plan - Sheet 90 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 90 | Z00000 | 2 | ZZ | 0190 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-91-Z00000-2ZZ0191 | Landscape - Hardscape - Layout Plan - Sheet 91 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 91 | Z00000 | 2 | ZZ | 0191 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-92-Z00000-2ZZ0192 | Landscape - Hardscape - Layout Plan - Sheet 92 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 92 | Z00000 | 2 | ZZ | 0192 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-93-Z00000-2ZZ0193 | Landscape - Hardscape - Layout Plan - Sheet 93 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 93 | Z00000 | 2 | ZZ | 0193 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-94-Z00000-2ZZ0194 | Landscape - Hardscape - Layout Plan - Sheet 94 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 94 | Z00000 | 2 | ZZ | 0194 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-95-Z00000-2ZZ0195 | Landscape - Hardscape - Layout Plan - Sheet 95 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 95 | Z00000 | 2 | ZZ | 0195 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-96-Z00000-2ZZ0196 | Landscape - Hardscape - Layout Plan - Sheet 96 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 96 | Z00000 | 2 | ZZ | 0196 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-97-Z00000-2ZZ0197 | Landscape - Hardscape - Layout Plan - Sheet 97 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 97 | Z00000 | 2 | ZZ | 0197 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-98-Z00000-2ZZ0198 | Landscape - Hardscape - Layout Plan - Sheet 98 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 98 | Z00000 | 2 | ZZ | 0198 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-99-Z00000-2ZZ0199 | Landscape - Hardscape - Layout Plan - Sheet 99 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 99 | Z00000 | 2 | ZZ | 0199 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-100-Z00000-2ZZ0200 | Landscape - Hardscape - Layout Plan - Sheet 100 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 100 | Z00000 | 2 | ZZ | 0200 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-101-Z00000-2ZZ0201 | Landscape - Hardscape - Layout Plan - Sheet 101 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 101 | Z00000 | 2 | ZZ | 0201 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-102-Z00000-2ZZ0202 | Landscape - Hardscape - Layout Plan - Sheet 102 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 102 | Z00000 | 2 | ZZ | 0202 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-103-Z00000-2ZZ0203 | Landscape - Hardscape - Layout Plan - Sheet 103 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 103 | Z00000 | 2 | ZZ | 0203 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-104-Z00000-2ZZ0204 | Landscape - Hardscape - Layout Plan - Sheet 104 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 104 | Z00000 | 2 | ZZ | 0204 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-105-Z00000-2ZZ0205 | Landscape - Hardscape - Layout Plan - Sheet 105 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 105 | Z00000 | 2 | ZZ | 0205 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-106-Z00000-2ZZ0206 | Landscape - Hardscape - Layout Plan - Sheet 106 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 106 | Z00000 | 2 | ZZ | 0206 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-107-Z00000-2ZZ0207 | Landscape - Hardscape - Layout Plan - Sheet 107 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 107 | Z00000 | 2 | ZZ | 0207 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-108-Z00000-2ZZ0208 | Landscape - Hardscape - Layout Plan - Sheet 108 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 108 | Z00000 | 2 | ZZ | 0208 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-109-Z00000-2ZZ0209 | Landscape - Hardscape - Layout Plan - Sheet 109 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 109 | Z00000 | 2 | ZZ | 0209 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-110-Z00000-2ZZ0210 | Landscape - Hardscape - Layout Plan - Sheet 110 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 110 | Z00000 | 2 | ZZ | 0210 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-111-Z00000-2ZZ0211 | Landscape - Hardscape - Layout Plan - Sheet 111 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 111 | Z00000 | 2 | ZZ | 0211 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-112-Z00000-2ZZ0212 | Landscape - Hardscape - Layout Plan - Sheet 112 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 112 | Z00000 | 2 | ZZ | 0212 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-113-Z00000-2ZZ0213 | Landscape - Hardscape - Layout Plan - Sheet 113 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 113 | Z00000 | 2 | ZZ | 0213 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-114-Z00000-2ZZ0214 | Landscape - Hardscape - Layout Plan - Sheet 114 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 114 | Z00000 | 2 | ZZ | 0214 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-115-Z00000-2ZZ0215 | Landscape - Hardscape - Layout Plan - Sheet 115 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 115 | Z00000 | 2 | ZZ | 0215 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-116-Z00000-2ZZ0216 | Landscape - Hardscape - Layout Plan - Sheet 116 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 116 | Z00000 | 2 | ZZ | 0216 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-117-Z00000-2ZZ0217 | Landscape - Hardscape - Layout Plan - Sheet 117 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 117 | Z00000 | 2 | ZZ | 0217 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-118-Z00000-2ZZ0218 | Landscape - Hardscape - Layout Plan - Sheet 118 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 118 | Z00000 | 2 | ZZ | 0218 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-119-Z00000-2ZZ0219 | Landscape - Hardscape - Layout Plan - Sheet 119 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 119 | Z00000 | 2 | ZZ | 0219 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-120-Z00000-2ZZ0220 | Landscape - Hardscape - Layout Plan - Sheet 120 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 120 | Z00000 | 2 | ZZ | 0220 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-121-Z00000-2ZZ0221 | Landscape - Hardscape - Layout Plan - Sheet 121 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 121 | Z00000 | 2 | ZZ | 0221 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-122-Z00000-2ZZ0222 | Landscape - Hardscape - Layout Plan - Sheet 122 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 122 | Z00000 | 2 | ZZ | 0222 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-123-Z00000-2ZZ0223 | Landscape - Hardscape - Layout Plan - Sheet 123 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 123 | Z00000 | 2 | ZZ | 0223 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-124-Z00000-2ZZ0224 | Landscape - Hardscape - Layout Plan - Sheet 124 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 124 | Z00000 | 2 | ZZ | 0224 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-125-Z00000-2ZZ0225 | Landscape - Hardscape - Layout Plan - Sheet 125 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 125 | Z00000 | 2 | ZZ | 0225 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-126-Z00000-2ZZ0226 | Landscape - Hardscape - Layout Plan - Sheet 126 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 126 | Z00000 | 2 | ZZ | 0226 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-127-Z00000-2ZZ0227 | Landscape - Hardscape - Layout Plan - Sheet 127 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 127 | Z00000 | 2 | ZZ | 0227 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-128-Z00000-2ZZ0228 | Landscape - Hardscape - Layout Plan - Sheet 128 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 128 | Z00000 | 2 | ZZ | 0228 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-129-Z00000-2ZZ0229 | Landscape - Hardscape - Layout Plan - Sheet 129 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 129 | Z00000 | 2 | ZZ | 0229 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-130-Z00000-2ZZ0230 | Landscape - Hardscape - Layout Plan - Sheet 130 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 130 | Z00000 | 2 | ZZ | 0230 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-131-Z00000-2ZZ0231 | Landscape - Hardscape - Layout Plan - Sheet 131 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 131 | Z00000 | 2 | ZZ | 0231 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-132-Z00000-2ZZ0232 | Landscape - Hardscape - Layout Plan - Sheet 132 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 132 | Z00000 | 2 | ZZ | 0232 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-133-Z00000-2ZZ0233 | Landscape - Hardscape - Layout Plan - Sheet 133 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 133 | Z00000 | 2 | ZZ | 0233 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-134-Z00000-2ZZ0234 | Landscape - Hardscape - Layout Plan - Sheet 134 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 134 | Z00000 | 2 | ZZ | 0234 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-135-Z00000-2ZZ0235 | Landscape - Hardscape - Layout Plan - Sheet 135 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 135 | Z00000 | 2 | ZZ | 0235 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-136-Z00000-2ZZ0236 | Landscape - Hardscape - Layout Plan - Sheet 136 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 136 | Z00000 | 2 | ZZ | 0236 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-137-Z00000-2ZZ0237 | Landscape - Hardscape - Layout Plan - Sheet 137 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 137 | Z00000 | 2 | ZZ | 0237 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-138-Z00000-2ZZ0238 | Landscape - Hardscape - Layout Plan - Sheet 138 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 138 | Z00000 | 2 | ZZ | 0238 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-139-Z00000-2ZZ0239 | Landscape - Hardscape - Layout Plan - Sheet 139 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 139 | Z00000 | 2 | ZZ | 0239 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-140-Z00000-2ZZ0240 | Landscape - Hardscape - Layout Plan - Sheet 140 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 140 | Z00000 | 2 | ZZ | 0240 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-141-Z00000-2ZZ0241 | Landscape - Hardscape - Layout Plan - Sheet 141 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 141 | Z00000 | 2 | ZZ | 0241 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-142-Z00000-2ZZ0242 | Landscape - Hardscape - Layout Plan - Sheet 142 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 142 | Z00000 | 2 | ZZ | 0242 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-143-Z00000-2ZZ0243 | Landscape - Hardscape - Layout Plan - Sheet 143 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 143 | Z00000 | 2 | ZZ | 0243 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-144-Z00000-2ZZ0244 | Landscape - Hardscape - Layout Plan - Sheet 144 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 144 | Z00000 | 2 | ZZ | 0244 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-145-Z00000-2ZZ0245 | Landscape - Hardscape - Layout Plan - Sheet 145 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 145 | Z00000 | 2 | ZZ | 0245 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-146-Z00000-2ZZ0246 | Landscape - Hardscape - Layout Plan - Sheet 146 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 146 | Z00000 | 2 | ZZ | 0246 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-147-Z00000-2ZZ0247 | Landscape - Hardscape - Layout Plan - Sheet 147 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 147 | Z00000 | 2 | ZZ | 0247 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-148-Z00000-2ZZ0248 | Landscape - Hardscape - Layout Plan - Sheet 148 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 148 | Z00000 | 2 | ZZ | 0248 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-149-Z00000-2ZZ0249 | Landscape - Hardscape - Layout Plan - Sheet 149 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 149 | Z00000 | 2 | ZZ | 0249 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-150-Z00000-2ZZ0250 | Landscape - Hardscape - Layout Plan - Sheet 150 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 150 | Z00000 | 2 | ZZ | 0250 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-151-Z00000-2ZZ0251 | Landscape - Hardscape - Layout Plan - Sheet 151 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 151 | Z00000 | 2 | ZZ | 0251 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-152-Z00000-2ZZ0252 | Landscape - Hardscape - Layout Plan - Sheet 152 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 152 | Z00000 | 2 | ZZ | 0252 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-153-Z00000-2ZZ0253 | Landscape - Hardscape - Layout Plan - Sheet 153 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 153 | Z00000 | 2 | ZZ | 0253 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-154-Z00000-2ZZ0254 | Landscape - Hardscape - Layout Plan - Sheet 154 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 154 | Z00000 | 2 | ZZ | 0254 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-155-Z00000-2ZZ0255 | Landscape - Hardscape - Layout Plan - Sheet 155 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 155 | Z00000 | 2 | ZZ | 0255 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-156-Z00000-2ZZ0256 | Landscape - Hardscape - Layout Plan - Sheet 156 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 156 | Z00000 | 2 | ZZ | 0256 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-157-Z00000-2ZZ0257 | Landscape - Hardscape - Layout Plan - Sheet 157 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 157 | Z00000 | 2 | ZZ | 0257 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-158-Z00000-2ZZ0258 | Landscape - Hardscape - Layout Plan - Sheet 158 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 158 | Z00000 | 2 | ZZ | 0258 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-159-Z00000-2ZZ0259 | Landscape - Hardscape - Layout Plan - Sheet 159 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 159 | Z00000 | 2 | ZZ | 0259 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-160-Z00000-2ZZ0260 | Landscape - Hardscape - Layout Plan - Sheet 160 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 160 | Z00000 | 2 | ZZ | 0260 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-161-Z00000-2ZZ0261 | Landscape - Hardscape - Layout Plan - Sheet 161 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 161 | Z00000 | 2 | ZZ | 0261 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-162-Z00000-2ZZ0262 | Landscape - Hardscape - Layout Plan - Sheet 162 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 162 | Z00000 | 2 | ZZ | 0262 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-163-Z00000-2ZZ0263 | Landscape - Hardscape - Layout Plan - Sheet 163 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 163 | Z00000 | 2 | ZZ | 0263 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-164-Z00000-2ZZ0264 | Landscape - Hardscape - Layout Plan - Sheet 164 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 164 | Z00000 | 2 | ZZ | 0264 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-165-Z00000-2ZZ0265 | Landscape - Hardscape - Layout Plan - Sheet 165 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 165 | Z00000 | 2 | ZZ | 0265 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-166-Z00000-2ZZ0266 | Landscape - Hardscape - Layout Plan - Sheet 166 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 166 | Z00000 | 2 | ZZ | 0266 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-167-Z00000-2ZZ0267 | Landscape - Hardscape - Layout Plan - Sheet 167 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 167 | Z00000 | 2 | ZZ | 0267 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-168-Z00000-2ZZ0268 | Landscape - Hardscape - Layout Plan - Sheet 168 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 168 | Z00000 | 2 | ZZ | 0268 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-169-Z00000-2ZZ0269 | Landscape - Hardscape - Layout Plan - Sheet 169 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 169 | Z00000 | 2 | ZZ | 0269 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-170-Z00000-2ZZ0270 | Landscape - Hardscape - Layout Plan - Sheet 170 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 170 | Z00000 | 2 | ZZ | 0270 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-171-Z00000-2ZZ0271 | Landscape - Hardscape - Layout Plan - Sheet 171 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 171 | Z00000 | 2 | ZZ | 0271 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-172-Z00000-2ZZ0272 | Landscape - Hardscape - Layout Plan - Sheet 172 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 172 | Z00000 | 2 | ZZ | 0272 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-173-Z00000-2ZZ0273 | Landscape - Hardscape - Layout Plan - Sheet 173 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 173 | Z00000 | 2 | ZZ | 0273 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-174-Z00000-2ZZ0274 | Landscape - Hardscape - Layout Plan - Sheet 174 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 174 | Z00000 | 2 | ZZ | 0274 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-175-Z00000-2ZZ0275 | Landscape - Hardscape - Layout Plan - Sheet 175 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 175 | Z00000 | 2 | ZZ | 0275 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-176-Z00000-2ZZ0276 | Landscape - Hardscape - Layout Plan - Sheet 176 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 176 | Z00000 | 2 | ZZ | 0276 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-177-Z00000-2ZZ0277 | Landscape - Hardscape - Layout Plan - Sheet 177 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 177 | Z00000 | 2 | ZZ | 0277 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-178-Z00000-2ZZ0278 | Landscape - Hardscape - Layout Plan - Sheet 178 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 178 | Z00000 | 2 | ZZ | 0278 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-179-Z00000-2ZZ0279 | Landscape - Hardscape - Layout Plan - Sheet 179 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 179 | Z00000 | 2 | ZZ | 0279 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-180-Z00000-2ZZ0280 | Landscape - Hardscape - Layout Plan - Sheet 180 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 180 | Z00000 | 2 | ZZ | 0280 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-181-Z00000-2ZZ0281 | Landscape - Hardscape - Layout Plan - Sheet 181 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 181 | Z00000 | 2 | ZZ | 0281 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-182-Z00000-2ZZ0282 | Landscape - Hardscape - Layout Plan - Sheet 182 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 182 | Z00000 | 2 | ZZ | 0282 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-183-Z00000-2ZZ0283 | Landscape - Hardscape - Layout Plan - Sheet 183 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 183 | Z00000 | 2 | ZZ | 0283 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-184-Z00000-2ZZ0284 | Landscape - Hardscape - Layout Plan - Sheet 184 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 184 | Z00000 | 2 | ZZ | 0284 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-185-Z00000-2ZZ0285 | Landscape - Hardscape - Layout Plan - Sheet 185 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 185 | Z00000 | 2 | ZZ | 0285 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-186-Z00000-2ZZ0286 | Landscape - Hardscape - Layout Plan - Sheet 186 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 186 | Z00000 | 2 | ZZ | 0286 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-187-Z00000-2ZZ0287 | Landscape - Hardscape - Layout Plan - Sheet 187 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 187 | Z00000 | 2 | ZZ | 0287 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-188-Z00000-2ZZ0288 | Landscape - Hardscape - Layout Plan - Sheet 188 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 188 | Z00000 | 2 | ZZ | 0288 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-189-Z00000-2ZZ0289 | Landscape - Hardscape - Layout Plan - Sheet 189 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 189 | Z00000 | 2 | ZZ | 0289 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-190-Z00000-2ZZ0290 | Landscape - Hardscape - Layout Plan - Sheet 190 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 190 | Z00000 | 2 | ZZ | 0290 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-191-Z00000-2ZZ0291 | Landscape - Hardscape - Layout Plan - Sheet 191 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 191 | Z00000 | 2 | ZZ | 0291 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-192-Z00000-2ZZ0292 | Landscape - Hardscape - Layout Plan - Sheet 192 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 192 | Z00000 | 2 | ZZ | 0292 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-193-Z00000-2ZZ0293 | Landscape - Hardscape - Layout Plan - Sheet 193 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 193 | Z00000 | 2 | ZZ | 0293 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-194-Z00000-2ZZ0294 | Landscape - Hardscape - Layout Plan - Sheet 194 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 194 | Z00000 | 2 | ZZ | 0294 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-195-Z00000-2ZZ0295 | Landscape - Hardscape - Layout Plan - Sheet 195 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 195 | Z00000 | 2 | ZZ | 0295 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-196-Z00000-2ZZ0296 | Landscape - Hardscape - Layout Plan - Sheet 196 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 196 | Z00000 | 2 | ZZ | 0296 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-197-Z00000-2ZZ0297 | Landscape - Hardscape - Layout Plan - Sheet 197 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 197 | Z00000 | 2 | ZZ | 0297 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-198-Z00000-2ZZ0298 | Landscape - Hardscape - Layout Plan - Sheet 198 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 198 | Z00000 | 2 | ZZ | 0298 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-199-Z00000-2ZZ0299 | Landscape - Hardscape - Layout Plan - Sheet 199 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 199 | Z00000 | 2 | ZZ | 0299 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-200-Z00000-2ZZ0300 | Landscape - Hardscape - Layout Plan - Sheet 200 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 200 | Z00000 | 2 | ZZ | 0300 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-201-Z00000-2ZZ0301 | Landscape - Hardscape - Layout Plan - Sheet 201 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 201 | Z00000 | 2 | ZZ | 0301 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-202-Z00000-2ZZ0302 | Landscape - Hardscape - Layout Plan - Sheet 202 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 202 | Z00000 | 2 | ZZ | 0302 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-203-Z00000-2ZZ0303 | Landscape - Hardscape - Layout Plan - Sheet 203 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 203 | Z00000 | 2 | ZZ | 0303 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-204-Z00000-2ZZ0304 | Landscape - Hardscape - Layout Plan - Sheet 204 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 204 | Z00000 | 2 | ZZ | 0304 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-205-Z00000-2ZZ0305 | Landscape - Hardscape - Layout Plan - Sheet 205 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 205 | Z00000 | 2 | ZZ | 0305 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-206-Z00000-2ZZ0306 | Landscape - Hardscape - Layout Plan - Sheet 206 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 206 | Z00000 | 2 | ZZ | 0306 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-207-Z00000-2ZZ0307 | Landscape - Hardscape - Layout Plan - Sheet 207 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 207 | Z00000 | 2 | ZZ | 0307 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-208-Z00000-2ZZ0308 | Landscape - Hardscape - Layout Plan - Sheet 208 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 208 | Z00000 | 2 | ZZ | 0308 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-209-Z00000-2ZZ0309 | Landscape - Hardscape - Layout Plan - Sheet 209 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 209 | Z00000 | 2 | ZZ | 0309 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-210-Z00000-2ZZ0310 | Landscape - Hardscape - Layout Plan - Sheet 210 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 210 | Z00000 | 2 | ZZ | 0310 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-211-Z00000-2ZZ0311 | Landscape - Hardscape - Layout Plan - Sheet 211 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 211 | Z00000 | 2 | ZZ | 0311 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-212-Z00000-2ZZ0312 | Landscape - Hardscape - Layout Plan - Sheet 212 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 212 | Z00000 | 2 | ZZ | 0312 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-213-Z00000-2ZZ0313 | Landscape - Hardscape - Layout Plan - Sheet 213 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 213 | Z00000 | 2 | ZZ | 0313 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-214-Z00000-2ZZ0314 | Landscape - Hardscape - Layout Plan - Sheet 214 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 214 | Z00000 | 2 | ZZ | 0314 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-215-Z00000-2ZZ0315 | Landscape - Hardscape - Layout Plan - Sheet 215 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 215 | Z00000 | 2 | ZZ | 0315 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-216-Z00000-2ZZ0316 | Landscape - Hardscape - Layout Plan - Sheet 216 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 216 | Z00000 | 2 | ZZ | 0316 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-217-Z00000-2ZZ0317 | Landscape - Hardscape - Layout Plan - Sheet 217 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 217 | Z00000 | 2 | ZZ | 0317 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-218-Z00000-2ZZ0318 | Landscape - Hardscape - Layout Plan - Sheet 218 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 218 | Z00000 | 2 | ZZ | 0318 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-219-Z00000-2ZZ0319 | Landscape - Hardscape - Layout Plan - Sheet 219 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 219 | Z00000 | 2 | ZZ | 0319 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-220-Z00000-2ZZ0320 | Landscape - Hardscape - Layout Plan - Sheet 220 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 220 | Z00000 | 2 | ZZ | 0320 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-221-Z00000-2ZZ0321 | Landscape - Hardscape - Layout Plan - Sheet 221 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 221 | Z00000 | 2 | ZZ | 0321 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-222-Z00000-2ZZ0322 | Landscape - Hardscape - Layout Plan - Sheet 222 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 222 | Z00000 | 2 | ZZ | 0322 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-223-Z00000-2ZZ0323 | Landscape - Hardscape - Layout Plan - Sheet 223 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 223 | Z00000 | 2 | ZZ | 0323 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-224-Z00000-2ZZ0324 | Landscape - Hardscape - Layout Plan - Sheet 224 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 224 | Z00000 | 2 | ZZ | 0324 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-225-Z00000-2ZZ0325 | Landscape - Hardscape - Layout Plan - Sheet 225 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 225 | Z00000 | 2 | ZZ | 0325 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-226-Z00000-2ZZ0326 | Landscape - Hardscape - Layout Plan - Sheet 226 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 226 | Z00000 | 2 | ZZ | 0326 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-227-Z00000-2ZZ0327 | Landscape - Hardscape - Layout Plan - Sheet 227 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 227 | Z00000 | 2 | ZZ | 0327 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-228-Z00000-2ZZ0328 | Landscape - Hardscape - Layout Plan - Sheet 228 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 228 | Z00000 | 2 | ZZ | 0328 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-229-Z00000-2ZZ0329 | Landscape - Hardscape - Layout Plan - Sheet 229 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 229 | Z00000 | 2 | ZZ | 0329 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-230-Z00000-2ZZ0330 | Landscape - Hardscape - Layout Plan - Sheet 230 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 230 | Z00000 | 2 | ZZ | 0330 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-231-Z00000-2ZZ0331 | Landscape - Hardscape - Layout Plan - Sheet 231 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 231 | Z00000 | 2 | ZZ | 0331 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-232-Z00000-2ZZ0332 | Landscape - Hardscape - Layout Plan - Sheet 232 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 232 | Z00000 | 2 | ZZ | 0332 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-233-Z00000-2ZZ0333 | Landscape - Hardscape - Layout Plan - Sheet 233 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 233 | Z00000 | 2 | ZZ | 0333 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-234-Z00000-2ZZ0334 | Landscape - Hardscape - Layout Plan - Sheet 234 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 234 | Z00000 | 2 | ZZ | 0334 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-235-Z00000-2ZZ0335 | Landscape - Hardscape - Layout Plan - Sheet 235 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 235 | Z00000 | 2 | ZZ | 0335 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-236-Z00000-2ZZ0336 | Landscape - Hardscape - Layout Plan - Sheet 236 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 236 | Z00000 | 2 | ZZ | 0336 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-237-Z00000-2ZZ0337 | Landscape - Hardscape - Layout Plan - Sheet 237 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 237 | Z00000 | 2 | ZZ | 0337 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-238-Z00000-2ZZ0338 | Landscape - Hardscape - Layout Plan - Sheet 238 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 238 | Z00000 | 2 | ZZ | 0338 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-239-Z00000-2ZZ0339 | Landscape - Hardscape - Layout Plan - Sheet 239 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 239 | Z00000 | 2 | ZZ | 0339 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-240-Z00000-2ZZ0340 | Landscape - Hardscape - Layout Plan - Sheet 240 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 240 | Z00000 | 2 | ZZ | 0340 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-241-Z00000-2ZZ0341 | Landscape - Hardscape - Layout Plan - Sheet 241 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 241 | Z00000 | 2 | ZZ | 0341 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-242-Z00000-2ZZ0342 | Landscape - Hardscape - Layout Plan - Sheet 242 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 242 | Z00000 | 2 | ZZ | 0342 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-243-Z00000-2ZZ0343 | Landscape - Hardscape - Layout Plan - Sheet 243 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 243 | Z00000 | 2 | ZZ | 0343 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-244-Z00000-2ZZ0344 | Landscape - Hardscape - Layout Plan - Sheet 244 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 244 | Z00000 | 2 | ZZ | 0344 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-245-Z00000-2ZZ0345 | Landscape - Hardscape - Layout Plan - Sheet 245 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 245 | Z00000 | 2 | ZZ | 0345 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-246-Z00000-2ZZ0346 | Landscape - Hardscape - Layout Plan - Sheet 246 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 246 | Z00000 | 2 | ZZ | 0346 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-247-Z00000-2ZZ0347 | Landscape - Hardscape - Layout Plan - Sheet 247 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 247 | Z00000 | 2 | ZZ | 0347 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-248-Z00000-2ZZ0348 | Landscape - Hardscape - Layout Plan - Sheet 248 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 248 | Z00000 | 2 | ZZ | 0348 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-249-Z00000-2ZZ0349 | Landscape - Hardscape - Layout Plan - Sheet 249 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 249 | Z00000 | 2 | ZZ | 0349 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-250-Z00000-2ZZ0350 | Landscape - Hardscape - Layout Plan - Sheet 250 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 250 | Z00000 | 2 | ZZ | 0350 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-251-Z00000-2ZZ0351 | Landscape - Hardscape - Layout Plan - Sheet 251 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 251 | Z00000 | 2 | ZZ | 0351 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-252-Z00000-2ZZ0352 | Landscape - Hardscape - Layout Plan - Sheet 252 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 252 | Z00000 | 2 | ZZ | 0352 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-253-Z00000-2ZZ0353 | Landscape - Hardscape - Layout Plan - Sheet 253 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 253 | Z00000 | 2 | ZZ | 0353 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-254-Z00000-2ZZ0354 | Landscape - Hardscape - Layout Plan - Sheet 254 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 254 | Z00000 | 2 | ZZ | 0354 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-255-Z00000-2ZZ0355 | Landscape - Hardscape - Layout Plan - Sheet 255 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 255 | Z00000 | 2 | ZZ | 0355 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-256-Z00000-2ZZ0356 | Landscape - Hardscape - Layout Plan - Sheet 256 |  | Landscape | Revit | .docx,.pdf | 1:50 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 256 | Z00000 | 2 | ZZ | 0356 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-2ZZ0150 | Landscape - Hardscape Setting-Out - Overall Layout |  | Landscape | Revit | .docx,.pdf | 1:300 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 2 | ZZ | 0150 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-01-Z00000-2ZZ0151 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 01 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 01 | Z00000 | 2 | ZZ | 0151 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-02-Z00000-2ZZ0152 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 02 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 02 | Z00000 | 2 | ZZ | 0152 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-03-Z00000-2ZZ0153 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 03 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 03 | Z00000 | 2 | ZZ | 0153 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-04-Z00000-2ZZ0154 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 04 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 04 | Z00000 | 2 | ZZ | 0154 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-05-Z00000-2ZZ0155 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 05 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 05 | Z00000 | 2 | ZZ | 0155 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-06-Z00000-2ZZ0156 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 06 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 06 | Z00000 | 2 | ZZ | 0156 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-07-Z00000-2ZZ0157 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 07 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 07 | Z00000 | 2 | ZZ | 0157 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-08-Z00000-2ZZ0158 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 08 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 08 | Z00000 | 2 | ZZ | 0158 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-09-Z00000-2ZZ0159 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 09 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 09 | Z00000 | 2 | ZZ | 0159 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-10-Z00000-2ZZ0160 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 10 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 10 | Z00000 | 2 | ZZ | 0160 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-11-Z00000-2ZZ0161 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 11 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 11 | Z00000 | 2 | ZZ | 0161 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-12-Z00000-2ZZ0162 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 12 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 12 | Z00000 | 2 | ZZ | 0162 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-13-Z00000-2ZZ0163 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 13 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 13 | Z00000 | 2 | ZZ | 0163 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-14-Z00000-2ZZ0164 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 14 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 14 | Z00000 | 2 | ZZ | 0164 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-15-Z00000-2ZZ0165 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 15 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 15 | Z00000 | 2 | ZZ | 0165 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-16-Z00000-2ZZ0166 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 16 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 16 | Z00000 | 2 | ZZ | 0166 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-17-Z00000-2ZZ0167 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 17 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 17 | Z00000 | 2 | ZZ | 0167 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-18-Z00000-2ZZ0168 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 18 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 18 | Z00000 | 2 | ZZ | 0168 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-19-Z00000-2ZZ0169 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 19 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 19 | Z00000 | 2 | ZZ | 0169 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-20-Z00000-2ZZ0170 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 20 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 20 | Z00000 | 2 | ZZ | 0170 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-21-Z00000-2ZZ0171 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 21 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 21 | Z00000 | 2 | ZZ | 0171 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-22-Z00000-2ZZ0172 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 22 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 22 | Z00000 | 2 | ZZ | 0172 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-23-Z00000-2ZZ0173 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 23 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 23 | Z00000 | 2 | ZZ | 0173 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-24-Z00000-2ZZ0174 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 24 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 24 | Z00000 | 2 | ZZ | 0174 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-25-Z00000-2ZZ0175 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 25 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 25 | Z00000 | 2 | ZZ | 0175 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-26-Z00000-2ZZ0176 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 26 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 26 | Z00000 | 2 | ZZ | 0176 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-27-Z00000-2ZZ0177 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 27 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 27 | Z00000 | 2 | ZZ | 0177 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0178 | Landscape - Hardscape Setting-Out - Layout Plan - Sheet 28 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0178 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0179 | Landscape Levels Overall Plan |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0179 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0180 | Landscape Levels Sheet 01 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0180 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0181 | Landscape Levels Sheet 02 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0181 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0182 | Landscape Levels Sheet 03 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0182 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0183 | Landscape Levels Sheet 04 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0183 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0184 | Landscape Levels Sheet 05 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0184 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0185 | Landscape Levels Sheet 06 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0185 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0186 | Landscape Levels Sheet 07 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0186 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0187 | Landscape Levels Sheet 08 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0187 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0188 | Landscape Levels Sheet 09 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0188 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0189 | Landscape Levels Sheet 10 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0189 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0190 | Landscape Levels Sheet 11 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0190 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0191 | Landscape Levels Sheet 12 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0191 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0192 | Landscape Levels Sheet 13 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0192 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0193 | Landscape Levels Sheet 14 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0193 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0194 | Landscape Levels Sheet 15 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0194 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0195 | Landscape Levels Sheet 16 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0195 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0196 | Landscape Levels Sheet 17 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0196 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0197 | Landscape Levels Sheet 18 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0197 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0198 | Landscape Levels Sheet 19 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0198 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0199 | Landscape Levels Sheet 20 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0199 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0200 | Landscape Levels Sheet 21 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0200 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0201 | Landscape Levels Sheet 22 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0201 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0202 | Landscape Levels Sheet 23 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0202 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0203 | Landscape Levels Sheet 24 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0203 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0204 | Landscape Levels Sheet 25 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0204 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0205 | Landscape Levels Sheet 26 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0205 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0206 | Landscape Levels Sheet 27 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0206 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0207 | Landscape Levels Sheet 28 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0207 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0208 | Landscape Levels Sheet 29 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0208 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0209 | Landscape Levels Sheet 30 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0209 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0210 | Landscape Levels Sheet 31 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0210 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0211 | Landscape Levels Sheet 32 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0211 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0212 | Landscape Levels Sheet 33 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0212 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0213 | Landscape Levels Sheet 34 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0213 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0214 | Landscape Levels Sheet 35 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0214 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0215 | Landscape Levels Sheet 36 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0215 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0216 | Landscape Levels Sheet 37 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0216 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0217 | Landscape Levels Sheet 38 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0217 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0218 | Landscape Levels Sheet 39 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0218 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0219 | Landscape Levels Sheet 40 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0219 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0220 | Landscape Levels Sheet 41 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0220 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0221 | Landscape Levels Sheet 42 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0221 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0222 | Landscape Levels Sheet 43 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0222 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0223 | Landscape Levels Sheet 44 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0223 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0224 | Landscape Levels Sheet 45 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0224 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0225 | Landscape Levels Sheet 46 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0225 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0226 | Landscape Levels Sheet 47 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0226 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0227 | Landscape Levels Sheet 48 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0227 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0228 | Landscape Levels Sheet 49 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0228 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0229 | Landscape Levels Sheet 50 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0229 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0230 | Landscape Levels Sheet 51 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0230 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0231 | Landscape Levels Sheet 52 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0231 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0232 | Landscape Levels Sheet 53 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0232 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0233 | Landscape Levels Sheet 54 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0233 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0234 | Landscape Levels Sheet 55 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0234 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0235 | Landscape Levels Sheet 56 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0235 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0236 | Landscape Levels Sheet 57 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0236 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0237 | Landscape Levels Sheet 58 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0237 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0238 | Landscape Levels Sheet 59 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0238 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0239 | Landscape Levels Sheet 60 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0239 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0240 | Landscape Levels Sheet 61 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0240 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0241 | Landscape Levels Sheet 62 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0241 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0242 | Landscape Levels Sheet 63 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0242 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0243 | Landscape Levels Sheet 64 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0243 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-2ZZ0300 | Landscape - Furniture - Overall Layout |  | Landscape | Revit | .docx,.pdf | 1:300 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 2 | ZZ | 0300 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-01-Z00000-2ZZ0301 | Landscape - Furniture - Layout Plan - Sheet 01 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 01 | Z00000 | 2 | ZZ | 0301 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-02-Z00000-2ZZ0302 | Landscape - Furniture - Layout Plan - Sheet 02 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 02 | Z00000 | 2 | ZZ | 0302 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-03-Z00000-2ZZ0303 | Landscape - Furniture - Layout Plan - Sheet 03 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 03 | Z00000 | 2 | ZZ | 0303 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-04-Z00000-2ZZ0304 | Landscape - Furniture - Layout Plan - Sheet 04 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 04 | Z00000 | 2 | ZZ | 0304 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-05-Z00000-2ZZ0305 | Landscape - Furniture - Layout Plan - Sheet 05 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 05 | Z00000 | 2 | ZZ | 0305 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-06-Z00000-2ZZ0306 | Landscape - Furniture - Layout Plan - Sheet 06 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 06 | Z00000 | 2 | ZZ | 0306 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-07-Z00000-2ZZ0307 | Landscape - Furniture - Layout Plan - Sheet 07 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 07 | Z00000 | 2 | ZZ | 0307 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-08-Z00000-2ZZ0308 | Landscape - Furniture - Layout Plan - Sheet 08 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 08 | Z00000 | 2 | ZZ | 0308 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-09-Z00000-2ZZ0309 | Landscape - Furniture - Layout Plan - Sheet 09 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 09 | Z00000 | 2 | ZZ | 0309 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-10-Z00000-2ZZ0310 | Landscape - Furniture - Layout Plan - Sheet 10 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 10 | Z00000 | 2 | ZZ | 0310 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-11-Z00000-2ZZ0311 | Landscape - Furniture - Layout Plan - Sheet 11 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 11 | Z00000 | 2 | ZZ | 0311 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-12-Z00000-2ZZ0312 | Landscape - Furniture - Layout Plan - Sheet 12 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 12 | Z00000 | 2 | ZZ | 0312 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-13-Z00000-2ZZ0313 | Landscape - Furniture - Layout Plan - Sheet 13 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 13 | Z00000 | 2 | ZZ | 0313 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-14-Z00000-2ZZ0314 | Landscape - Furniture - Layout Plan - Sheet 14 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 14 | Z00000 | 2 | ZZ | 0314 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-15-Z00000-2ZZ0315 | Landscape - Furniture - Layout Plan - Sheet 15 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 15 | Z00000 | 2 | ZZ | 0315 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-16-Z00000-2ZZ0316 | Landscape - Furniture - Layout Plan - Sheet 16 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 16 | Z00000 | 2 | ZZ | 0316 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-17-Z00000-2ZZ0317 | Landscape - Furniture - Layout Plan - Sheet 17 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 17 | Z00000 | 2 | ZZ | 0317 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-18-Z00000-2ZZ0318 | Landscape - Furniture - Layout Plan - Sheet 18 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 18 | Z00000 | 2 | ZZ | 0318 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-19-Z00000-2ZZ0319 | Landscape - Furniture - Layout Plan - Sheet 19 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 19 | Z00000 | 2 | ZZ | 0319 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-20-Z00000-2ZZ0320 | Landscape - Furniture - Layout Plan - Sheet 20 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 20 | Z00000 | 2 | ZZ | 0320 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-21-Z00000-2ZZ0321 | Landscape - Furniture - Layout Plan - Sheet 21 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 21 | Z00000 | 2 | ZZ | 0321 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-22-Z00000-2ZZ0322 | Landscape - Furniture - Layout Plan - Sheet 22 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 22 | Z00000 | 2 | ZZ | 0322 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-23-Z00000-2ZZ0323 | Landscape - Furniture - Layout Plan - Sheet 23 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 23 | Z00000 | 2 | ZZ | 0323 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-24-Z00000-2ZZ0324 | Landscape - Furniture - Layout Plan - Sheet 24 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 24 | Z00000 | 2 | ZZ | 0324 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-25-Z00000-2ZZ0325 | Landscape - Furniture - Layout Plan - Sheet 25 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 25 | Z00000 | 2 | ZZ | 0325 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-26-Z00000-2ZZ0326 | Landscape - Furniture - Layout Plan - Sheet 26 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 26 | Z00000 | 2 | ZZ | 0326 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-27-Z00000-2ZZ0327 | Landscape - Furniture - Layout Plan - Sheet 27 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 27 | Z00000 | 2 | ZZ | 0327 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0328 | Landscape - Furniture - Layout Plan - Sheet 28 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0328 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-00-Z00000-2ZZ0350 | Landscape - Furniture Setting-Out - Overall Layout |  | Landscape | Revit | .docx,.pdf | 1:300 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 2 | ZZ | 0350 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-01-Z00000-2ZZ0351 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 01 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 01 | Z00000 | 2 | ZZ | 0351 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-02-Z00000-2ZZ0352 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 02 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 02 | Z00000 | 2 | ZZ | 0352 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-03-Z00000-2ZZ0353 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 03 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 03 | Z00000 | 2 | ZZ | 0353 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-04-Z00000-2ZZ0354 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 04 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 04 | Z00000 | 2 | ZZ | 0354 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-05-Z00000-2ZZ0355 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 05 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 05 | Z00000 | 2 | ZZ | 0355 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-06-Z00000-2ZZ0356 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 06 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 06 | Z00000 | 2 | ZZ | 0356 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-07-Z00000-2ZZ0357 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 07 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 07 | Z00000 | 2 | ZZ | 0357 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-08-Z00000-2ZZ0358 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 08 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 08 | Z00000 | 2 | ZZ | 0358 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-09-Z00000-2ZZ0359 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 09 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 09 | Z00000 | 2 | ZZ | 0359 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-10-Z00000-2ZZ0360 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 10 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 10 | Z00000 | 2 | ZZ | 0360 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-11-Z00000-2ZZ0361 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 11 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 11 | Z00000 | 2 | ZZ | 0361 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-12-Z00000-2ZZ0362 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 12 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 12 | Z00000 | 2 | ZZ | 0362 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-13-Z00000-2ZZ0363 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 13 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 13 | Z00000 | 2 | ZZ | 0363 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-14-Z00000-2ZZ0364 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 14 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 14 | Z00000 | 2 | ZZ | 0364 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-15-Z00000-2ZZ0365 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 15 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 15 | Z00000 | 2 | ZZ | 0365 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-16-Z00000-2ZZ0366 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 16 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 16 | Z00000 | 2 | ZZ | 0366 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-17-Z00000-2ZZ0367 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 17 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 17 | Z00000 | 2 | ZZ | 0367 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-18-Z00000-2ZZ0368 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 18 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 18 | Z00000 | 2 | ZZ | 0368 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-19-Z00000-2ZZ0369 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 19 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 19 | Z00000 | 2 | ZZ | 0369 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-20-Z00000-2ZZ0370 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 20 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 20 | Z00000 | 2 | ZZ | 0370 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-21-Z00000-2ZZ0371 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 21 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 21 | Z00000 | 2 | ZZ | 0371 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-22-Z00000-2ZZ0372 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 22 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 22 | Z00000 | 2 | ZZ | 0372 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-23-Z00000-2ZZ0373 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 23 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 23 | Z00000 | 2 | ZZ | 0373 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-24-Z00000-2ZZ0374 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 24 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 24 | Z00000 | 2 | ZZ | 0374 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-25-Z00000-2ZZ0375 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 25 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 25 | Z00000 | 2 | ZZ | 0375 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-26-Z00000-2ZZ0376 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 26 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 26 | Z00000 | 2 | ZZ | 0376 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-27-Z00000-2ZZ0377 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 27 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 27 | Z00000 | 2 | ZZ | 0377 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0378 | Landscape - Furniture Setting-Out - Layout Plan - Sheet 28 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Furniture | QP.E.EX.GEN.GEN.1260 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0378 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-10
QF01012-NES-C04518-SDW-LSE-00-Z00000-2ZZ0500 | Landscape - Irrigation Network - Overall Layout |  | Landscape | Revit | .docx,.pdf | 1:300 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 2 | ZZ | 0500 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-01-Z00000-2ZZ0501 | Landscape - Irrigation Network - Layout Plan - Sheet 01 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 01 | Z00000 | 2 | ZZ | 0501 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-02-Z00000-2ZZ0502 | Landscape - Irrigation Network - Layout Plan - Sheet 02 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 02 | Z00000 | 2 | ZZ | 0502 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-03-Z00000-2ZZ0503 | Landscape - Irrigation Network - Layout Plan - Sheet 03 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 03 | Z00000 | 2 | ZZ | 0503 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-04-Z00000-2ZZ0504 | Landscape - Irrigation Network - Layout Plan - Sheet 04 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 04 | Z00000 | 2 | ZZ | 0504 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-05-Z00000-2ZZ0505 | Landscape - Irrigation Network - Layout Plan - Sheet 05 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 05 | Z00000 | 2 | ZZ | 0505 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-06-Z00000-2ZZ0506 | Landscape - Irrigation Network - Layout Plan - Sheet 06 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 06 | Z00000 | 2 | ZZ | 0506 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-07-Z00000-2ZZ0507 | Landscape - Irrigation Network - Layout Plan - Sheet 07 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 07 | Z00000 | 2 | ZZ | 0507 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-08-Z00000-2ZZ0508 | Landscape - Irrigation Network - Layout Plan - Sheet 08 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 08 | Z00000 | 2 | ZZ | 0508 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-09-Z00000-2ZZ0509 | Landscape - Irrigation Network - Layout Plan - Sheet 09 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 09 | Z00000 | 2 | ZZ | 0509 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-10-Z00000-2ZZ0510 | Landscape - Irrigation Network - Layout Plan - Sheet 10 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 10 | Z00000 | 2 | ZZ | 0510 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-11-Z00000-2ZZ0511 | Landscape - Irrigation Network - Layout Plan - Sheet 11 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 11 | Z00000 | 2 | ZZ | 0511 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-12-Z00000-2ZZ0512 | Landscape - Irrigation Network - Layout Plan - Sheet 12 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 12 | Z00000 | 2 | ZZ | 0512 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-13-Z00000-2ZZ0513 | Landscape - Irrigation Network - Layout Plan - Sheet 13 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 13 | Z00000 | 2 | ZZ | 0513 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-14-Z00000-2ZZ0514 | Landscape - Irrigation Network - Layout Plan - Sheet 14 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 14 | Z00000 | 2 | ZZ | 0514 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-15-Z00000-2ZZ0515 | Landscape - Irrigation Network - Layout Plan - Sheet 15 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 15 | Z00000 | 2 | ZZ | 0515 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-16-Z00000-2ZZ0516 | Landscape - Irrigation Network - Layout Plan - Sheet 16 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 16 | Z00000 | 2 | ZZ | 0516 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-17-Z00000-2ZZ0517 | Landscape - Irrigation Network - Layout Plan - Sheet 17 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 17 | Z00000 | 2 | ZZ | 0517 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-18-Z00000-2ZZ0518 | Landscape - Irrigation Network - Layout Plan - Sheet 18 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 18 | Z00000 | 2 | ZZ | 0518 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-19-Z00000-2ZZ0519 | Landscape - Irrigation Network - Layout Plan - Sheet 19 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 19 | Z00000 | 2 | ZZ | 0519 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-20-Z00000-2ZZ0520 | Landscape - Irrigation Network - Layout Plan - Sheet 20 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 20 | Z00000 | 2 | ZZ | 0520 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-21-Z00000-2ZZ0521 | Landscape - Irrigation Network - Layout Plan - Sheet 21 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 21 | Z00000 | 2 | ZZ | 0521 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-22-Z00000-2ZZ0522 | Landscape - Irrigation Network - Layout Plan - Sheet 22 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 22 | Z00000 | 2 | ZZ | 0522 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-23-Z00000-2ZZ0523 | Landscape - Irrigation Network - Layout Plan - Sheet 23 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 23 | Z00000 | 2 | ZZ | 0523 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-24-Z00000-2ZZ0524 | Landscape - Irrigation Network - Layout Plan - Sheet 24 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 24 | Z00000 | 2 | ZZ | 0524 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-25-Z00000-2ZZ0525 | Landscape - Irrigation Network - Layout Plan - Sheet 25 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 25 | Z00000 | 2 | ZZ | 0525 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-26-Z00000-2ZZ0526 | Landscape - Irrigation Network - Layout Plan - Sheet 26 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 26 | Z00000 | 2 | ZZ | 0526 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-27-Z00000-2ZZ0527 | Landscape - Irrigation Network - Layout Plan - Sheet 27 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 27 | Z00000 | 2 | ZZ | 0527 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-28-Z00000-2ZZ0528 | Landscape - Irrigation Network - Layout Plan - Sheet 28 |  | Landscape | Revit | .docx,.pdf | 1:100 | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 28 | Z00000 | 2 | ZZ | 0528 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01013-NES-C04519-SDW-LSE-29-Z00001-3ZZ0529 | Landscape - Irrigation Network - Layout Plan - Sheet 29 |  | Landscape | Revit | .docx,.pdf | 1:101 | 2027-04-17 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1091 |  | QF01013 | NES | C04519 | SDW | LSE | 29 | Z00001 | 3 | ZZ | 0529 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01014-NES-C04520-SDW-LSE-30-Z00002-4ZZ0530 | Landscape - Irrigation Network - Layout Plan - Sheet 30 |  | Landscape | Revit | .docx,.pdf | 1:102 | 2027-04-18 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1092 |  | QF01014 | NES | C04520 | SDW | LSE | 30 | Z00002 | 4 | ZZ | 0530 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01015-NES-C04521-SDW-LSE-31-Z00003-5ZZ0531 | Landscape - Irrigation Network - Layout Plan - Sheet 31 |  | Landscape | Revit | .docx,.pdf | 1:103 | 2027-04-19 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1093 |  | QF01015 | NES | C04521 | SDW | LSE | 31 | Z00003 | 5 | ZZ | 0531 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01016-NES-C04522-SDW-LSE-32-Z00004-6ZZ0532 | Landscape - Irrigation Network - Layout Plan - Sheet 32 |  | Landscape | Revit | .docx,.pdf | 1:104 | 2027-04-20 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1094 |  | QF01016 | NES | C04522 | SDW | LSE | 32 | Z00004 | 6 | ZZ | 0532 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01017-NES-C04523-SDW-LSE-33-Z00005-7ZZ0533 | Landscape - Irrigation Network - Layout Plan - Sheet 33 |  | Landscape | Revit | .docx,.pdf | 1:105 | 2027-04-21 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1095 |  | QF01017 | NES | C04523 | SDW | LSE | 33 | Z00005 | 7 | ZZ | 0533 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01018-NES-C04524-SDW-LSE-34-Z00006-8ZZ0534 | Landscape - Irrigation Network - Layout Plan - Sheet 34 |  | Landscape | Revit | .docx,.pdf | 1:106 | 2027-04-22 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1096 |  | QF01018 | NES | C04524 | SDW | LSE | 34 | Z00006 | 8 | ZZ | 0534 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01019-NES-C04525-SDW-LSE-35-Z00007-9ZZ0535 | Landscape - Irrigation Network - Layout Plan - Sheet 35 |  | Landscape | Revit | .docx,.pdf | 1:107 | 2027-04-23 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1097 |  | QF01019 | NES | C04525 | SDW | LSE | 35 | Z00007 | 9 | ZZ | 0535 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01020-NES-C04526-SDW-LSE-36-Z00008-10ZZ0536 | Landscape - Irrigation Network - Layout Plan - Sheet 36 |  | Landscape | Revit | .docx,.pdf | 1:108 | 2027-04-24 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1098 |  | QF01020 | NES | C04526 | SDW | LSE | 36 | Z00008 | 10 | ZZ | 0536 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01021-NES-C04527-SDW-LSE-37-Z00009-11ZZ0537 | Landscape - Irrigation Network - Layout Plan - Sheet 37 |  | Landscape | Revit | .docx,.pdf | 1:109 | 2027-04-25 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1099 |  | QF01021 | NES | C04527 | SDW | LSE | 37 | Z00009 | 11 | ZZ | 0537 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01022-NES-C04528-SDW-LSE-38-Z00010-12ZZ0538 | Landscape - Irrigation Network - Layout Plan - Sheet 38 |  | Landscape | Revit | .docx,.pdf | 1:110 | 2027-04-26 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1100 |  | QF01022 | NES | C04528 | SDW | LSE | 38 | Z00010 | 12 | ZZ | 0538 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-03-30
QF01023-NES-C04529-SDW-LSE-39-Z00011-13ZZ0539 | Landscape - Irrigation Network - Layout Plan - Sheet 39 |  | Landscape | Revit | .docx,.pdf | 1:111 | 2027-04-27 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1101 |  | QF01023 | NES | C04529 | SDW | LSE | 39 | Z00011 | 13 | ZZ | 0539 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01024-NES-C04530-SDW-LSE-40-Z00012-14ZZ0540 | Landscape - Irrigation Network - Layout Plan - Sheet 40 |  | Landscape | Revit | .docx,.pdf | 1:112 | 2027-04-28 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1102 |  | QF01024 | NES | C04530 | SDW | LSE | 40 | Z00012 | 14 | ZZ | 0540 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01025-NES-C04531-SDW-LSE-41-Z00013-15ZZ0541 | Landscape - Irrigation Network - Layout Plan - Sheet 41 |  | Landscape | Revit | .docx,.pdf | 1:113 | 2027-04-29 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1103 |  | QF01025 | NES | C04531 | SDW | LSE | 41 | Z00013 | 15 | ZZ | 0541 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01026-NES-C04532-SDW-LSE-42-Z00014-16ZZ0542 | Landscape - Irrigation Network - Layout Plan - Sheet 42 |  | Landscape | Revit | .docx,.pdf | 1:114 | 2027-04-30 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1104 |  | QF01026 | NES | C04532 | SDW | LSE | 42 | Z00014 | 16 | ZZ | 0542 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01027-NES-C04533-SDW-LSE-43-Z00015-17ZZ0543 | Landscape - Irrigation Network - Layout Plan - Sheet 43 |  | Landscape | Revit | .docx,.pdf | 1:115 | 2027-05-01 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1105 |  | QF01027 | NES | C04533 | SDW | LSE | 43 | Z00015 | 17 | ZZ | 0543 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01028-NES-C04534-SDW-LSE-44-Z00016-18ZZ0544 | Landscape - Irrigation Network - Layout Plan - Sheet 44 |  | Landscape | Revit | .docx,.pdf | 1:116 | 2027-05-02 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1106 |  | QF01028 | NES | C04534 | SDW | LSE | 44 | Z00016 | 18 | ZZ | 0544 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01029-NES-C04535-SDW-LSE-45-Z00017-19ZZ0545 | Landscape - Irrigation Network - Layout Plan - Sheet 45 |  | Landscape | Revit | .docx,.pdf | 1:117 | 2027-05-03 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1107 |  | QF01029 | NES | C04535 | SDW | LSE | 45 | Z00017 | 19 | ZZ | 0545 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01030-NES-C04536-SDW-LSE-46-Z00018-20ZZ0546 | Landscape - Irrigation Network - Layout Plan - Sheet 46 |  | Landscape | Revit | .docx,.pdf | 1:118 | 2027-05-04 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1108 |  | QF01030 | NES | C04536 | SDW | LSE | 46 | Z00018 | 20 | ZZ | 0546 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01031-NES-C04537-SDW-LSE-47-Z00019-21ZZ0547 | Landscape - Irrigation Network - Layout Plan - Sheet 47 |  | Landscape | Revit | .docx,.pdf | 1:119 | 2027-05-05 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1109 |  | QF01031 | NES | C04537 | SDW | LSE | 47 | Z00019 | 21 | ZZ | 0547 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01032-NES-C04538-SDW-LSE-48-Z00020-22ZZ0548 | Landscape - Irrigation Network - Layout Plan - Sheet 48 |  | Landscape | Revit | .docx,.pdf | 1:120 | 2027-05-06 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1110 |  | QF01032 | NES | C04538 | SDW | LSE | 48 | Z00020 | 22 | ZZ | 0548 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01033-NES-C04539-SDW-LSE-49-Z00021-23ZZ0549 | Landscape - Irrigation Network - Layout Plan - Sheet 49 |  | Landscape | Revit | .docx,.pdf | 1:121 | 2027-05-07 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1111 |  | QF01033 | NES | C04539 | SDW | LSE | 49 | Z00021 | 23 | ZZ | 0549 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01034-NES-C04540-SDW-LSE-50-Z00022-24ZZ0550 | Landscape - Irrigation Network - Layout Plan - Sheet 50 |  | Landscape | Revit | .docx,.pdf | 1:122 | 2027-05-08 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1112 |  | QF01034 | NES | C04540 | SDW | LSE | 50 | Z00022 | 24 | ZZ | 0550 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01035-NES-C04541-SDW-LSE-51-Z00023-25ZZ0551 | Landscape - Irrigation Network - Layout Plan - Sheet 51 |  | Landscape | Revit | .docx,.pdf | 1:123 | 2027-05-09 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1113 |  | QF01035 | NES | C04541 | SDW | LSE | 51 | Z00023 | 25 | ZZ | 0551 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01036-NES-C04542-SDW-LSE-52-Z00024-26ZZ0552 | Landscape - Irrigation Network - Layout Plan - Sheet 52 |  | Landscape | Revit | .docx,.pdf | 1:124 | 2027-05-10 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1114 |  | QF01036 | NES | C04542 | SDW | LSE | 52 | Z00024 | 26 | ZZ | 0552 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01037-NES-C04543-SDW-LSE-53-Z00025-27ZZ0553 | Landscape - Irrigation Network - Layout Plan - Sheet 53 |  | Landscape | Revit | .docx,.pdf | 1:125 | 2027-05-11 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1115 |  | QF01037 | NES | C04543 | SDW | LSE | 53 | Z00025 | 27 | ZZ | 0553 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01038-NES-C04544-SDW-LSE-54-Z00026-28ZZ0554 | Landscape - Irrigation Network - Layout Plan - Sheet 54 |  | Landscape | Revit | .docx,.pdf | 1:126 | 2027-05-12 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1116 |  | QF01038 | NES | C04544 | SDW | LSE | 54 | Z00026 | 28 | ZZ | 0554 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01039-NES-C04545-SDW-LSE-55-Z00027-29ZZ0555 | Landscape - Irrigation Network - Layout Plan - Sheet 55 |  | Landscape | Revit | .docx,.pdf | 1:127 | 2027-05-13 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1117 |  | QF01039 | NES | C04545 | SDW | LSE | 55 | Z00027 | 29 | ZZ | 0555 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01040-NES-C04546-SDW-LSE-56-Z00028-30ZZ0556 | Landscape - Irrigation Network - Layout Plan - Sheet 56 |  | Landscape | Revit | .docx,.pdf | 1:128 | 2027-05-14 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1118 |  | QF01040 | NES | C04546 | SDW | LSE | 56 | Z00028 | 30 | ZZ | 0556 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01041-NES-C04547-SDW-LSE-57-Z00029-31ZZ0557 | Landscape - Irrigation Network - Layout Plan - Sheet 57 |  | Landscape | Revit | .docx,.pdf | 1:129 | 2027-05-15 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1119 |  | QF01041 | NES | C04547 | SDW | LSE | 57 | Z00029 | 31 | ZZ | 0557 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01042-NES-C04548-SDW-LSE-58-Z00030-32ZZ0558 | Landscape - Irrigation Network - Layout Plan - Sheet 58 |  | Landscape | Revit | .docx,.pdf | 1:130 | 2027-05-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1120 |  | QF01042 | NES | C04548 | SDW | LSE | 58 | Z00030 | 32 | ZZ | 0558 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01043-NES-C04549-SDW-LSE-59-Z00031-33ZZ0559 | Landscape - Irrigation Network - Layout Plan - Sheet 59 |  | Landscape | Revit | .docx,.pdf | 1:131 | 2027-05-17 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1121 |  | QF01043 | NES | C04549 | SDW | LSE | 59 | Z00031 | 33 | ZZ | 0559 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01044-NES-C04550-SDW-LSE-60-Z00032-34ZZ0560 | Landscape - Irrigation Network - Layout Plan - Sheet 60 |  | Landscape | Revit | .docx,.pdf | 1:132 | 2027-05-18 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1122 |  | QF01044 | NES | C04550 | SDW | LSE | 60 | Z00032 | 34 | ZZ | 0560 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01045-NES-C04551-SDW-LSE-61-Z00033-35ZZ0561 | Landscape - Irrigation Network - Layout Plan - Sheet 61 |  | Landscape | Revit | .docx,.pdf | 1:133 | 2027-05-19 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1123 |  | QF01045 | NES | C04551 | SDW | LSE | 61 | Z00033 | 35 | ZZ | 0561 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01046-NES-C04552-SDW-LSE-62-Z00034-36ZZ0562 | Landscape - Irrigation Network - Layout Plan - Sheet 62 |  | Landscape | Revit | .docx,.pdf | 1:134 | 2027-05-20 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1124 |  | QF01046 | NES | C04552 | SDW | LSE | 62 | Z00034 | 36 | ZZ | 0562 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01047-NES-C04553-SDW-LSE-63-Z00035-37ZZ0563 | Landscape - Irrigation Network - Layout Plan - Sheet 63 |  | Landscape | Revit | .docx,.pdf | 1:135 | 2027-05-21 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1125 |  | QF01047 | NES | C04553 | SDW | LSE | 63 | Z00035 | 37 | ZZ | 0563 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01048-NES-C04554-SDW-LSE-64-Z00036-38ZZ0564 | Landscape - Irrigation Network - Layout Plan - Sheet 64 |  | Landscape | Revit | .docx,.pdf | 1:136 | 2027-05-22 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1126 |  | QF01048 | NES | C04554 | SDW | LSE | 64 | Z00036 | 38 | ZZ | 0564 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01049-NES-C04555-SDW-LSE-65-Z00037-39ZZ0565 | Landscape - Irrigation Network - Layout Plan - Sheet 65 |  | Landscape | Revit | .docx,.pdf | 1:137 | 2027-05-23 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1127 |  | QF01049 | NES | C04555 | SDW | LSE | 65 | Z00037 | 39 | ZZ | 0565 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01050-NES-C04556-SDW-LSE-66-Z00038-40ZZ0566 | Landscape - Irrigation Network - Layout Plan - Sheet 66 |  | Landscape | Revit | .docx,.pdf | 1:138 | 2027-05-24 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1128 |  | QF01050 | NES | C04556 | SDW | LSE | 66 | Z00038 | 40 | ZZ | 0566 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01051-NES-C04557-SDW-LSE-67-Z00039-41ZZ0567 | Landscape - Irrigation Network - Layout Plan - Sheet 67 |  | Landscape | Revit | .docx,.pdf | 1:139 | 2027-05-25 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1129 |  | QF01051 | NES | C04557 | SDW | LSE | 67 | Z00039 | 41 | ZZ | 0567 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01052-NES-C04558-SDW-LSE-68-Z00040-42ZZ0568 | Landscape - Irrigation Network - Layout Plan - Sheet 68 |  | Landscape | Revit | .docx,.pdf | 1:140 | 2027-05-26 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1130 |  | QF01052 | NES | C04558 | SDW | LSE | 68 | Z00040 | 42 | ZZ | 0568 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01053-NES-C04559-SDW-LSE-69-Z00041-43ZZ0569 | Landscape - Irrigation Network - Layout Plan - Sheet 69 |  | Landscape | Revit | .docx,.pdf | 1:141 | 2027-05-27 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1131 |  | QF01053 | NES | C04559 | SDW | LSE | 69 | Z00041 | 43 | ZZ | 0569 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01054-NES-C04560-SDW-LSE-70-Z00042-44ZZ0570 | Landscape - Irrigation Network - Layout Plan - Sheet 70 |  | Landscape | Revit | .docx,.pdf | 1:142 | 2027-05-28 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1132 |  | QF01054 | NES | C04560 | SDW | LSE | 70 | Z00042 | 44 | ZZ | 0570 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01055-NES-C04561-SDW-LSE-71-Z00043-45ZZ0571 | Landscape - Irrigation Network - Layout Plan - Sheet 71 |  | Landscape | Revit | .docx,.pdf | 1:143 | 2027-05-29 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1133 |  | QF01055 | NES | C04561 | SDW | LSE | 71 | Z00043 | 45 | ZZ | 0571 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01056-NES-C04562-SDW-LSE-72-Z00044-46ZZ0572 | Landscape - Irrigation Network - Layout Plan - Sheet 72 |  | Landscape | Revit | .docx,.pdf | 1:144 | 2027-05-30 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1134 |  | QF01056 | NES | C04562 | SDW | LSE | 72 | Z00044 | 46 | ZZ | 0572 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01057-NES-C04563-SDW-LSE-73-Z00045-47ZZ0573 | Landscape - Irrigation Network - Layout Plan - Sheet 73 |  | Landscape | Revit | .docx,.pdf | 1:145 | 2027-05-31 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1135 |  | QF01057 | NES | C04563 | SDW | LSE | 73 | Z00045 | 47 | ZZ | 0573 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01058-NES-C04564-SDW-LSE-74-Z00046-48ZZ0574 | Landscape - Irrigation Network - Layout Plan - Sheet 74 |  | Landscape | Revit | .docx,.pdf | 1:146 | 2027-06-01 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1136 |  | QF01058 | NES | C04564 | SDW | LSE | 74 | Z00046 | 48 | ZZ | 0574 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01059-NES-C04565-SDW-LSE-75-Z00047-49ZZ0575 | Landscape - Irrigation Network - Layout Plan - Sheet 75 |  | Landscape | Revit | .docx,.pdf | 1:147 | 2027-06-02 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1137 |  | QF01059 | NES | C04565 | SDW | LSE | 75 | Z00047 | 49 | ZZ | 0575 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01060-NES-C04566-SDW-LSE-76-Z00048-50ZZ0576 | Landscape - Irrigation Network - Layout Plan - Sheet 76 |  | Landscape | Revit | .docx,.pdf | 1:148 | 2027-06-03 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1138 |  | QF01060 | NES | C04566 | SDW | LSE | 76 | Z00048 | 50 | ZZ | 0576 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01061-NES-C04567-SDW-LSE-77-Z00049-51ZZ0577 | Landscape - Irrigation Network - Layout Plan - Sheet 77 |  | Landscape | Revit | .docx,.pdf | 1:149 | 2027-06-04 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1139 |  | QF01061 | NES | C04567 | SDW | LSE | 77 | Z00049 | 51 | ZZ | 0577 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01062-NES-C04568-SDW-LSE-78-Z00050-52ZZ0578 | Landscape - Irrigation Network - Layout Plan - Sheet 78 |  | Landscape | Revit | .docx,.pdf | 1:150 | 2027-06-05 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1140 |  | QF01062 | NES | C04568 | SDW | LSE | 78 | Z00050 | 52 | ZZ | 0578 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01063-NES-C04569-SDW-LSE-79-Z00051-53ZZ0579 | Landscape - Irrigation Network - Layout Plan - Sheet 79 |  | Landscape | Revit | .docx,.pdf | 1:151 | 2027-06-06 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1141 |  | QF01063 | NES | C04569 | SDW | LSE | 79 | Z00051 | 53 | ZZ | 0579 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01064-NES-C04570-SDW-LSE-80-Z00052-54ZZ0580 | Landscape - Irrigation Network - Layout Plan - Sheet 80 |  | Landscape | Revit | .docx,.pdf | 1:152 | 2027-06-07 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1142 |  | QF01064 | NES | C04570 | SDW | LSE | 80 | Z00052 | 54 | ZZ | 0580 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01065-NES-C04571-SDW-LSE-81-Z00053-55ZZ0581 | Landscape - Irrigation Network - Layout Plan - Sheet 81 |  | Landscape | Revit | .docx,.pdf | 1:153 | 2027-06-08 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1143 |  | QF01065 | NES | C04571 | SDW | LSE | 81 | Z00053 | 55 | ZZ | 0581 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01066-NES-C04572-SDW-LSE-82-Z00054-56ZZ0582 | Landscape - Irrigation Network - Layout Plan - Sheet 82 |  | Landscape | Revit | .docx,.pdf | 1:154 | 2027-06-09 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1144 |  | QF01066 | NES | C04572 | SDW | LSE | 82 | Z00054 | 56 | ZZ | 0582 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01067-NES-C04573-SDW-LSE-83-Z00055-57ZZ0583 | Landscape - Irrigation Network - Layout Plan - Sheet 83 |  | Landscape | Revit | .docx,.pdf | 1:155 | 2027-06-10 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1145 |  | QF01067 | NES | C04573 | SDW | LSE | 83 | Z00055 | 57 | ZZ | 0583 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01068-NES-C04574-SDW-LSE-84-Z00056-58ZZ0584 | Landscape - Irrigation Network - Layout Plan - Sheet 84 |  | Landscape | Revit | .docx,.pdf | 1:156 | 2027-06-11 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1146 |  | QF01068 | NES | C04574 | SDW | LSE | 84 | Z00056 | 58 | ZZ | 0584 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01069-NES-C04575-SDW-LSE-85-Z00057-59ZZ0585 | Landscape - Irrigation Network - Layout Plan - Sheet 85 |  | Landscape | Revit | .docx,.pdf | 1:157 | 2027-06-12 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1147 |  | QF01069 | NES | C04575 | SDW | LSE | 85 | Z00057 | 59 | ZZ | 0585 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01070-NES-C04576-SDW-LSE-86-Z00058-60ZZ0586 | Landscape - Irrigation Network - Layout Plan - Sheet 86 |  | Landscape | Revit | .docx,.pdf | 1:158 | 2027-06-13 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1148 |  | QF01070 | NES | C04576 | SDW | LSE | 86 | Z00058 | 60 | ZZ | 0586 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01071-NES-C04577-SDW-LSE-87-Z00059-61ZZ0587 | Landscape - Irrigation Network - Layout Plan - Sheet 87 |  | Landscape | Revit | .docx,.pdf | 1:159 | 2027-06-14 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1149 |  | QF01071 | NES | C04577 | SDW | LSE | 87 | Z00059 | 61 | ZZ | 0587 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01072-NES-C04578-SDW-LSE-88-Z00060-62ZZ0588 | Landscape - Irrigation Network - Layout Plan - Sheet 88 |  | Landscape | Revit | .docx,.pdf | 1:160 | 2027-06-15 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1150 |  | QF01072 | NES | C04578 | SDW | LSE | 88 | Z00060 | 62 | ZZ | 0588 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01073-NES-C04579-SDW-LSE-89-Z00061-63ZZ0589 | Landscape - Irrigation Network - Layout Plan - Sheet 89 |  | Landscape | Revit | .docx,.pdf | 1:161 | 2027-06-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1151 |  | QF01073 | NES | C04579 | SDW | LSE | 89 | Z00061 | 63 | ZZ | 0589 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01074-NES-C04580-SDW-LSE-90-Z00062-64ZZ0590 | Landscape - Irrigation Network - Layout Plan - Sheet 90 |  | Landscape | Revit | .docx,.pdf | 1:162 | 2027-06-17 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1152 |  | QF01074 | NES | C04580 | SDW | LSE | 90 | Z00062 | 64 | ZZ | 0590 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01075-NES-C04581-SDW-LSE-91-Z00063-65ZZ0591 | Landscape - Irrigation Network - Layout Plan - Sheet 91 |  | Landscape | Revit | .docx,.pdf | 1:163 | 2027-06-18 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1153 |  | QF01075 | NES | C04581 | SDW | LSE | 91 | Z00063 | 65 | ZZ | 0591 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01076-NES-C04582-SDW-LSE-92-Z00064-66ZZ0592 | Landscape - Irrigation Network - Layout Plan - Sheet 92 |  | Landscape | Revit | .docx,.pdf | 1:164 | 2027-06-19 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1154 |  | QF01076 | NES | C04582 | SDW | LSE | 92 | Z00064 | 66 | ZZ | 0592 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01077-NES-C04583-SDW-LSE-93-Z00065-67ZZ0593 | Landscape - Irrigation Network - Layout Plan - Sheet 93 |  | Landscape | Revit | .docx,.pdf | 1:165 | 2027-06-20 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1155 |  | QF01077 | NES | C04583 | SDW | LSE | 93 | Z00065 | 67 | ZZ | 0593 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01078-NES-C04584-SDW-LSE-94-Z00066-68ZZ0594 | Landscape - Irrigation Network - Layout Plan - Sheet 94 |  | Landscape | Revit | .docx,.pdf | 1:166 | 2027-06-21 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1156 |  | QF01078 | NES | C04584 | SDW | LSE | 94 | Z00066 | 68 | ZZ | 0594 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01079-NES-C04585-SDW-LSE-95-Z00067-69ZZ0595 | Landscape - Irrigation Network - Layout Plan - Sheet 95 |  | Landscape | Revit | .docx,.pdf | 1:167 | 2027-06-22 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1157 |  | QF01079 | NES | C04585 | SDW | LSE | 95 | Z00067 | 69 | ZZ | 0595 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01080-NES-C04586-SDW-LSE-96-Z00068-70ZZ0596 | Landscape - Irrigation Network - Layout Plan - Sheet 96 |  | Landscape | Revit | .docx,.pdf | 1:168 | 2027-06-23 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1158 |  | QF01080 | NES | C04586 | SDW | LSE | 96 | Z00068 | 70 | ZZ | 0596 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01081-NES-C04587-SDW-LSE-97-Z00069-71ZZ0597 | Landscape - Irrigation Network - Layout Plan - Sheet 97 |  | Landscape | Revit | .docx,.pdf | 1:169 | 2027-06-24 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1159 |  | QF01081 | NES | C04587 | SDW | LSE | 97 | Z00069 | 71 | ZZ | 0597 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01082-NES-C04588-SDW-LSE-98-Z00070-72ZZ0598 | Landscape - Irrigation Network - Layout Plan - Sheet 98 |  | Landscape | Revit | .docx,.pdf | 1:170 | 2027-06-25 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1160 |  | QF01082 | NES | C04588 | SDW | LSE | 98 | Z00070 | 72 | ZZ | 0598 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01083-NES-C04589-SDW-LSE-99-Z00071-73ZZ0599 | Landscape - Irrigation Network - Layout Plan - Sheet 99 |  | Landscape | Revit | .docx,.pdf | 1:171 | 2027-06-26 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1161 |  | QF01083 | NES | C04589 | SDW | LSE | 99 | Z00071 | 73 | ZZ | 0599 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01084-NES-C04590-SDW-LSE-100-Z00072-74ZZ0600 | Landscape - Irrigation Network - Layout Plan - Sheet 100 |  | Landscape | Revit | .docx,.pdf | 1:172 | 2027-06-27 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1162 |  | QF01084 | NES | C04590 | SDW | LSE | 100 | Z00072 | 74 | ZZ | 0600 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01085-NES-C04591-SDW-LSE-101-Z00073-75ZZ0601 | Landscape - Irrigation Network - Layout Plan - Sheet 101 |  | Landscape | Revit | .docx,.pdf | 1:173 | 2027-06-28 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1163 |  | QF01085 | NES | C04591 | SDW | LSE | 101 | Z00073 | 75 | ZZ | 0601 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01086-NES-C04592-SDW-LSE-102-Z00074-76ZZ0602 | Landscape - Irrigation Network - Layout Plan - Sheet 102 |  | Landscape | Revit | .docx,.pdf | 1:174 | 2027-06-29 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1164 |  | QF01086 | NES | C04592 | SDW | LSE | 102 | Z00074 | 76 | ZZ | 0602 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01087-NES-C04593-SDW-LSE-103-Z00075-77ZZ0603 | Landscape - Irrigation Network - Layout Plan - Sheet 103 |  | Landscape | Revit | .docx,.pdf | 1:175 | 2027-06-30 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1165 |  | QF01087 | NES | C04593 | SDW | LSE | 103 | Z00075 | 77 | ZZ | 0603 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01088-NES-C04594-SDW-LSE-104-Z00076-78ZZ0604 | Landscape - Irrigation Network - Layout Plan - Sheet 104 |  | Landscape | Revit | .docx,.pdf | 1:176 | 2027-07-01 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1166 |  | QF01088 | NES | C04594 | SDW | LSE | 104 | Z00076 | 78 | ZZ | 0604 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01089-NES-C04595-SDW-LSE-105-Z00077-79ZZ0605 | Landscape - Irrigation Network - Layout Plan - Sheet 105 |  | Landscape | Revit | .docx,.pdf | 1:177 | 2027-07-02 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1167 |  | QF01089 | NES | C04595 | SDW | LSE | 105 | Z00077 | 79 | ZZ | 0605 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01090-NES-C04596-SDW-LSE-106-Z00078-80ZZ0606 | Landscape - Irrigation Network - Layout Plan - Sheet 106 |  | Landscape | Revit | .docx,.pdf | 1:178 | 2027-07-03 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1168 |  | QF01090 | NES | C04596 | SDW | LSE | 106 | Z00078 | 80 | ZZ | 0606 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01091-NES-C04597-SDW-LSE-107-Z00079-81ZZ0607 | Landscape - Irrigation Network - Layout Plan - Sheet 107 |  | Landscape | Revit | .docx,.pdf | 1:179 | 2027-07-04 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1169 |  | QF01091 | NES | C04597 | SDW | LSE | 107 | Z00079 | 81 | ZZ | 0607 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01092-NES-C04598-SDW-LSE-108-Z00080-82ZZ0608 | Landscape - Irrigation Network - Layout Plan - Sheet 108 |  | Landscape | Revit | .docx,.pdf | 1:180 | 2027-07-05 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1170 |  | QF01092 | NES | C04598 | SDW | LSE | 108 | Z00080 | 82 | ZZ | 0608 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-02-23
QF01093-NES-C04599-SDW-LSE-109-Z00081-83ZZ0609 | Landscape - Irrigation Network - Layout Plan - Sheet 109 |  | Landscape | Revit | .docx,.pdf | 1:181 | 2027-07-06 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1171 |  | QF01093 | NES | C04599 | SDW | LSE | 109 | Z00081 | 83 | ZZ | 0609 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01094-NES-C04600-SDW-LSE-110-Z00082-84ZZ0610 | Landscape - Irrigation Network - Layout Plan - Sheet 110 |  | Landscape | Revit | .docx,.pdf | 1:182 | 2027-07-07 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1172 |  | QF01094 | NES | C04600 | SDW | LSE | 110 | Z00082 | 84 | ZZ | 0610 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01095-NES-C04601-SDW-LSE-111-Z00083-85ZZ0611 | Landscape - Irrigation Network - Layout Plan - Sheet 111 |  | Landscape | Revit | .docx,.pdf | 1:183 | 2027-07-08 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1173 |  | QF01095 | NES | C04601 | SDW | LSE | 111 | Z00083 | 85 | ZZ | 0611 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01096-NES-C04602-SDW-LSE-112-Z00084-86ZZ0612 | Landscape - Irrigation Network - Layout Plan - Sheet 112 |  | Landscape | Revit | .docx,.pdf | 1:184 | 2027-07-09 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1174 |  | QF01096 | NES | C04602 | SDW | LSE | 112 | Z00084 | 86 | ZZ | 0612 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01097-NES-C04603-SDW-LSE-113-Z00085-87ZZ0613 | Landscape - Irrigation Network - Layout Plan - Sheet 113 |  | Landscape | Revit | .docx,.pdf | 1:185 | 2027-07-10 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1175 |  | QF01097 | NES | C04603 | SDW | LSE | 113 | Z00085 | 87 | ZZ | 0613 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01098-NES-C04604-SDW-LSE-114-Z00086-88ZZ0614 | Landscape - Irrigation Network - Layout Plan - Sheet 114 |  | Landscape | Revit | .docx,.pdf | 1:186 | 2027-07-11 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1176 |  | QF01098 | NES | C04604 | SDW | LSE | 114 | Z00086 | 88 | ZZ | 0614 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01099-NES-C04605-SDW-LSE-115-Z00087-89ZZ0615 | Landscape - Irrigation Network - Layout Plan - Sheet 115 |  | Landscape | Revit | .docx,.pdf | 1:187 | 2027-07-12 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1177 |  | QF01099 | NES | C04605 | SDW | LSE | 115 | Z00087 | 89 | ZZ | 0615 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01100-NES-C04606-SDW-LSE-116-Z00088-90ZZ0616 | Landscape - Irrigation Network - Layout Plan - Sheet 116 |  | Landscape | Revit | .docx,.pdf | 1:188 | 2027-07-13 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1178 |  | QF01100 | NES | C04606 | SDW | LSE | 116 | Z00088 | 90 | ZZ | 0616 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01101-NES-C04607-SDW-LSE-117-Z00089-91ZZ0617 | Landscape - Irrigation Network - Layout Plan - Sheet 117 |  | Landscape | Revit | .docx,.pdf | 1:189 | 2027-07-14 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1179 |  | QF01101 | NES | C04607 | SDW | LSE | 117 | Z00089 | 91 | ZZ | 0617 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01102-NES-C04608-SDW-LSE-118-Z00090-92ZZ0618 | Landscape - Irrigation Network - Layout Plan - Sheet 118 |  | Landscape | Revit | .docx,.pdf | 1:190 | 2027-07-15 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1180 |  | QF01102 | NES | C04608 | SDW | LSE | 118 | Z00090 | 92 | ZZ | 0618 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01103-NES-C04609-SDW-LSE-119-Z00091-93ZZ0619 | Landscape - Irrigation Network - Layout Plan - Sheet 119 |  | Landscape | Revit | .docx,.pdf | 1:191 | 2027-07-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1181 |  | QF01103 | NES | C04609 | SDW | LSE | 119 | Z00091 | 93 | ZZ | 0619 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01104-NES-C04610-SDW-LSE-120-Z00092-94ZZ0620 | Landscape - Irrigation Network - Layout Plan - Sheet 120 |  | Landscape | Revit | .docx,.pdf | 1:192 | 2027-07-17 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1182 |  | QF01104 | NES | C04610 | SDW | LSE | 120 | Z00092 | 94 | ZZ | 0620 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01105-NES-C04611-SDW-LSE-121-Z00093-95ZZ0621 | Landscape - Irrigation Network - Layout Plan - Sheet 121 |  | Landscape | Revit | .docx,.pdf | 1:193 | 2027-07-18 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1183 |  | QF01105 | NES | C04611 | SDW | LSE | 121 | Z00093 | 95 | ZZ | 0621 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01106-NES-C04612-SDW-LSE-122-Z00094-96ZZ0622 | Landscape - Irrigation Network - Layout Plan - Sheet 122 |  | Landscape | Revit | .docx,.pdf | 1:194 | 2027-07-19 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1184 |  | QF01106 | NES | C04612 | SDW | LSE | 122 | Z00094 | 96 | ZZ | 0622 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01107-NES-C04613-SDW-LSE-123-Z00095-97ZZ0623 | Landscape - Irrigation Network - Layout Plan - Sheet 123 |  | Landscape | Revit | .docx,.pdf | 1:195 | 2027-07-20 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1185 |  | QF01107 | NES | C04613 | SDW | LSE | 123 | Z00095 | 97 | ZZ | 0623 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01108-NES-C04614-SDW-LSE-124-Z00096-98ZZ0624 | Landscape - Irrigation Network - Layout Plan - Sheet 124 |  | Landscape | Revit | .docx,.pdf | 1:196 | 2027-07-21 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1186 |  | QF01108 | NES | C04614 | SDW | LSE | 124 | Z00096 | 98 | ZZ | 0624 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01012-NES-C04518-SDW-LSE-00-Z00000-6ZZ0001 | Landscape - Irrigation - Schedules - Sheet 01 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 6 | ZZ | 0001 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-00-Z00000-6ZZ0002 | Landscape - Irrigation - Schedules - Sheet 02 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 6 | ZZ | 0002 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-SDW-LSE-00-Z00000-6ZZ0003 | Landscape - Irrigation - Schedules - Sheet 03 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 6 | ZZ | 0003 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-CAL-LSE-00-Z00000-0ZZ001 | Landscape - Irrigation - Calculation |  | Landscape | Revit | .docx |  | 2027-04-16 | Landscape - Irrigation | QP.E.EX.GEN.GEN.1090 |  | QF01012 | NES | C04518 | CAL | LSE | 00 | Z00000 | 0 | ZZ | 001 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2027-01-20
QF01012-NES-C04518-MOD-LSE-00-Z00000-0ZZ0001 | Landscape - BIM Model |  | Landscape | Revit | .rvt,.nwc,.ifc |  | 2027-04-16 |  | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | MOD | LSE | 00 | Z00000 | 0 | ZZ | 0001 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-MOD-LSE-00-Z00000-0ZZ0002 | Landscape - Irrigation - BIM Model |  | Landscape | Revit | .rvt,.nwc,.ifc |  | 2027-04-16 |  |  |  | QF01012 | NES | C04518 | MOD | LSE | 00 | Z00000 | 0 | ZZ | 0002 | Landscape | Nesma & Partners | LOD400 | LOD400
QF01012-NES-C04518-SDW-LSE-00-Z00000-0ZZ0001 | Landscape - General Notes & Abbreviations |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 0 | ZZ | 0001 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-01-Z00000-0ZZ0001 | Detail Reference Plans 01 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 01 | Z00000 | 0 | ZZ | 0001 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-02-Z00000-0ZZ0002 | Detail Reference Plans 02 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 02 | Z00000 | 0 | ZZ | 0002 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-03-Z00000-0ZZ0003 | Detail Reference Plans 03 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 03 | Z00000 | 0 | ZZ | 0003 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-04-Z00000-0ZZ0004 | Detail Reference Plans 04 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 04 | Z00000 | 0 | ZZ | 0004 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-05-Z00000-0ZZ0005 | Detail Reference Plans 05 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 05 | Z00000 | 0 | ZZ | 0005 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-06-Z00000-0ZZ0006 | Detail Reference Plans 06 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 06 | Z00000 | 0 | ZZ | 0006 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-07-Z00000-0ZZ0007 | Detail Reference Plans 07 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 07 | Z00000 | 0 | ZZ | 0007 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-08-Z00000-0ZZ0008 | Detail Reference Plans 08 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 08 | Z00000 | 0 | ZZ | 0008 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-09-Z00000-0ZZ0009 | Detail Reference Plans 09 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 09 | Z00000 | 0 | ZZ | 0009 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-10-Z00000-0ZZ0010 | Detail Reference Plans 10 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 10 | Z00000 | 0 | ZZ | 0010 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-11-Z00000-0ZZ0011 | Detail Reference Plans 11 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 11 | Z00000 | 0 | ZZ | 0011 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-12-Z00000-0ZZ0012 | Detail Reference Plans 12 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 12 | Z00000 | 0 | ZZ | 0012 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-13-Z00000-0ZZ0013 | Detail Reference Plans 13 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 13 | Z00000 | 0 | ZZ | 0013 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-14-Z00000-0ZZ0014 | Detail Reference Plans 14 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 14 | Z00000 | 0 | ZZ | 0014 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-15-Z00000-0ZZ0015 | Detail Reference Plans 15 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 15 | Z00000 | 0 | ZZ | 0015 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-16-Z00000-0ZZ0016 | Detail Reference Plans 16 |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 16 | Z00000 | 0 | ZZ | 0016 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-17-Z00000-0ZZ0002 | Landscape - Legends |  | Landscape | Revit | .docx,.pdf | NTS | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 17 | Z00000 | 0 | ZZ | 0002 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-18-Z00000-0ZZ0011 | Landscape Typical Details - Sheet 01 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 18 | Z00000 | 0 | ZZ | 0011 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-19-Z00000-0ZZ0012 | Landscape Typical Details - Sheet 02 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 19 | Z00000 | 0 | ZZ | 0012 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-20-Z00000-0ZZ0013 | Landscape Typical Details - Sheet 03 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 20 | Z00000 | 0 | ZZ | 0013 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-21-Z00000-0ZZ0014 | Landscape Typical Details - Sheet 04 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 21 | Z00000 | 0 | ZZ | 0014 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-22-Z00000-0ZZ0015 | Landscape Typical Details - Sheet 05 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 22 | Z00000 | 0 | ZZ | 0015 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-23-Z00000-0ZZ0016 | Landscape Typical Details - Sheet 06 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 23 | Z00000 | 0 | ZZ | 0016 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-24-Z00000-0ZZ0017 | Landscape Typical Details - Sheet 07 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 24 | Z00000 | 0 | ZZ | 0017 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-0ZZ0018 | Landscape Typical Details - Sheet 08 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 0 | ZZ | 0018 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-0ZZ0019 | Landscape Typical Details - Sheet 09 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 0 | ZZ | 0019 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-0ZZ0020 | Landscape Typical Details - Sheet 10 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - General Drawings | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 0 | ZZ | 0020 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0001 | Landscape Enlarged Details - Sheet 01 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0001 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0002 | Landscape Enlarged Details - Sheet 02 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0002 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0003 | Landscape Enlarged Details - Sheet 03 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0003 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0004 | Landscape Enlarged Details - Sheet 04 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0004 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0005 | Landscape Enlarged Details - Sheet 05 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0005 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0006 | Landscape Enlarged Details - Sheet 06 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0006 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0007 | Landscape Enlarged Details - Sheet 07 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0007 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0008 | Landscape Enlarged Details - Sheet 08 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0008 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0009 | Landscape Enlarged Details - Sheet 09 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0009 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0010 | Landscape Enlarged Details - Sheet 10 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0010 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0011 | Landscape Enlarged Details - Sheet 11 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0011 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0012 | Landscape Enlarged Details - Sheet 12 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0012 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0013 | Landscape Enlarged Details - Sheet 13 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0013 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0014 | Landscape Enlarged Details - Sheet 14 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0014 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0015 | Landscape Enlarged Details - Sheet 15 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0015 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0016 | Landscape Enlarged Details - Sheet 16 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0016 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0017 | Landscape Enlarged Details - Sheet 17 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0017 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0018 | Landscape Enlarged Details - Sheet 18 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0018 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0019 | Landscape Enlarged Details - Sheet 19 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0019 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0020 | Landscape Enlarged Details - Sheet 20 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0020 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0021 | Landscape Enlarged Details - Sheet 21 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0021 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0022 | Landscape Enlarged Details - Sheet 22 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0022 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0023 | Landscape Enlarged Details - Sheet 23 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0023 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0024 | Landscape Enlarged Details - Sheet 24 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0024 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0025 | Landscape Enlarged Details - Sheet 25 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0025 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0026 | Landscape Enlarged Details - Sheet 26 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0026 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0027 | Landscape Enlarged Details - Sheet 27 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0027 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0028 | Landscape Enlarged Details - Sheet 28 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0028 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0029 | Landscape Enlarged Details - Sheet 29 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0029 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0030 | Landscape Enlarged Details - Sheet 30 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0030 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0031 | Landscape Enlarged Details - Sheet 31 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0031 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0032 | Landscape Enlarged Details - Sheet 32 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0032 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0033 | Landscape Enlarged Details - Sheet 33 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0033 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0034 | Landscape Enlarged Details - Sheet 34 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0034 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0035 | Landscape Enlarged Details - Sheet 35 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0035 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0036 | Landscape Enlarged Details - Sheet 36 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0036 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0037 | Landscape Enlarged Details - Sheet 37 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0037 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0038 | Landscape Enlarged Details - Sheet 38 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0038 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0039 | Landscape Enlarged Details - Sheet 39 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0039 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0040 | Landscape Enlarged Details - Sheet 40 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0040 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0041 | Landscape Enlarged Details - Sheet 41 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0041 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0042 | Landscape Enlarged Details - Sheet 42 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0042 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0043 | Landscape Enlarged Details - Sheet 43 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0043 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0044 | Landscape Enlarged Details - Sheet 44 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0044 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0045 | Landscape Enlarged Details - Sheet 45 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0045 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0046 | Landscape Enlarged Details - Sheet 46 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0046 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0047 | Landscape Enlarged Details - Sheet 47 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0047 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0048 | Landscape Enlarged Details - Sheet 48 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0048 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0049 | Landscape Enlarged Details - Sheet 49 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0049 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0050 | Landscape Enlarged Details - Sheet 50 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0050 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0051 | Landscape Enlarged Details - Sheet 51 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0051 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0052 | Landscape Enlarged Details - Sheet 52 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0052 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0053 | Landscape Enlarged Details - Sheet 53 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0053 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0054 | Landscape Enlarged Details - Sheet 54 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0054 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0055 | Landscape Enlarged Details - Sheet 55 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0055 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0056 | Landscape Enlarged Details - Sheet 56 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0056 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0057 | Landscape Enlarged Details - Sheet 57 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0057 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0058 | Landscape Enlarged Details - Sheet 58 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0058 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0059 | Landscape Enlarged Details - Sheet 59 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0059 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0060 | Landscape Enlarged Details - Sheet 60 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0060 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0061 | Landscape Enlarged Details - Sheet 61 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0061 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0062 | Landscape Enlarged Details - Sheet 62 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0062 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0063 | Landscape Enlarged Details - Sheet 63 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0063 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0064 | Landscape Enlarged Details - Sheet 64 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0064 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0065 | Landscape Enlarged Details - Sheet 65 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0065 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0066 | Landscape Enlarged Details - Sheet 66 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0066 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0067 | Landscape Enlarged Details - Sheet 67 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0067 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0068 | Landscape Enlarged Details - Sheet 68 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0068 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0069 | Landscape Enlarged Details - Sheet 69 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0069 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0070 | Landscape Enlarged Details - Sheet 70 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0070 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0071 | Landscape Enlarged Details - Sheet 71 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0071 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0072 | Landscape Enlarged Details - Sheet 72 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0072 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0073 | Landscape Enlarged Details - Sheet 73 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0073 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0074 | Landscape Enlarged Details - Sheet 74 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0074 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0075 | Landscape Enlarged Details - Sheet 75 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0075 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0076 | Landscape Enlarged Details - Sheet 76 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0076 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0077 | Landscape Enlarged Details - Sheet 77 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0077 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0078 | Landscape Enlarged Details - Sheet 78 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0078 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0079 | Landscape Enlarged Details - Sheet 79 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0079 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0080 | Landscape Enlarged Details - Sheet 80 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0080 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0081 | Landscape Enlarged Details - Sheet 81 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0081 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0082 | Landscape Enlarged Details - Sheet 82 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0082 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0083 | Landscape Enlarged Details - Sheet 83 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0083 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0084 | Landscape Enlarged Details - Sheet 84 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0084 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0085 | Landscape Enlarged Details - Sheet 85 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0085 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0086 | Landscape Enlarged Details - Sheet 86 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0086 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0087 | Landscape Enlarged Details - Sheet 87 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0087 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0088 | Landscape Enlarged Details - Sheet 88 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0088 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0089 | Landscape Enlarged Details - Sheet 89 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0089 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-4ZZ0090 | Landscape Enlarged Details - Sheet 90 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Enlarged Details | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 4 | ZZ | 0090 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0001 | Landscape - Sections - Sheet 01 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0001 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0002 | Landscape - Sections - Sheet 02 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0002 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0003 | Landscape - Sections - Sheet 03 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0003 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0004 | Landscape - Sections - Sheet 04 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0004 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0005 | Landscape - Sections - Sheet 05 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0005 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0006 | Landscape - Sections - Sheet 06 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0006 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0007 | Landscape - Sections - Sheet 07 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0007 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0008 | Landscape - Sections - Sheet 08 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0008 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0009 | Landscape - Sections - Sheet 09 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0009 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0010 | Landscape - Sections - Sheet 10 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0010 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0011 | Landscape - Sections - Sheet 11 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0011 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0012 | Landscape - Sections - Sheet 12 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0012 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0013 | Landscape - Sections - Sheet 13 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0013 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0014 | Landscape - Sections - Sheet 14 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0014 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0015 | Landscape - Sections - Sheet 15 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0015 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0016 | Landscape - Sections - Sheet 16 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0016 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0017 | Landscape - Sections - Sheet 17 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0017 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0018 | Landscape - Sections - Sheet 18 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0018 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0019 | Landscape - Sections - Sheet 19 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0019 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0020 | Landscape - Sections - Sheet 20 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0020 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0021 | Landscape - Sections - Sheet 21 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0021 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0022 | Landscape - Sections - Sheet 22 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0022 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0023 | Landscape - Sections - Sheet 23 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0023 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0024 | Landscape - Sections - Sheet 24 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0024 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0025 | Landscape - Sections - Sheet 25 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0025 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0026 | Landscape - Sections - Sheet 26 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0026 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0027 | Landscape - Sections - Sheet 27 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0027 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0028 | Landscape - Sections - Sheet 28 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0028 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0029 | Landscape - Sections - Sheet 29 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0029 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0030 | Landscape - Sections - Sheet 30 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0030 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0031 | Landscape - Sections - Sheet 31 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0031 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0032 | Landscape - Sections - Sheet 32 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0032 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0033 | Landscape - Sections - Sheet 33 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0033 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0034 | Landscape - Sections - Sheet 34 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0034 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0035 | Landscape - Sections - Sheet 35 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0035 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0036 | Landscape - Sections - Sheet 36 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0036 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0037 | Landscape - Sections - Sheet 37 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0037 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0038 | Landscape - Sections - Sheet 38 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0038 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0039 | Landscape - Sections - Sheet 39 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0039 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-3ZZ0040 | Landscape - Sections - Sheet 40 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 3 | ZZ | 0040 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0001 | Coordinated Utilities Plans Ovrall Plan |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0001 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0002 | Coordinated Utilities Plans Sheet 1 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0002 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0003 | Coordinated Utilities Plans Sheet 2 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0003 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0004 | Coordinated Utilities Plans Sheet 3 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0004 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0005 | Coordinated Utilities Plans Sheet 4 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0005 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0006 | Coordinated Utilities Plans Sheet 5 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0006 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0007 | Coordinated Utilities Plans Sheet 6 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0007 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0008 | Coordinated Utilities Plans Sheet 7 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0008 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0009 | Coordinated Utilities Plans Sheet 8 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0009 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0010 | Coordinated Utilities Plans Sheet 9 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0010 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0011 | Coordinated Utilities Plans Sheet 10 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0011 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0012 | Coordinated Utilities Plans Sheet 11 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0012 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0013 | Coordinated Utilities Plans Sheet 12 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0013 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0014 | Coordinated Utilities Plans Sheet 13 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0014 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0015 | Coordinated Utilities Plans Sheet 14 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0015 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0016 | Coordinated Utilities Plans Sheet 15 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0016 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0017 | Coordinated Utilities Plans Sheet 16 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0017 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0018 | Coordinated Utilities Plans Sheet 17 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0018 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0019 | Coordinated Utilities Plans Sheet 18 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0019 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0020 | Coordinated Utilities Plans Sheet 19 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0020 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0021 | Coordinated Utilities Plans Sheet 20 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0021 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0022 | Coordinated Utilities Plans Sheet 21 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0022 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0023 | Coordinated Utilities Plans Sheet 22 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0023 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0024 | Coordinated Utilities Plans Sheet 23 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0024 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0025 | Coordinated Utilities Plans Sheet 24 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0025 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0026 | Coordinated Utilities Plans Sheet 25 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0026 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0027 | Coordinated Utilities Plans Sheet 26 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0027 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0028 | Coordinated Utilities Plans Sheet 27 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0028 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0029 | Coordinated Utilities Plans Sheet 28 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0029 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0030 | Coordinated Utilities Plans Sheet 29 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0030 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0031 | Coordinated Utilities Plans Sheet 30 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0031 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0032 | Coordinated Utilities Plans Sheet 31 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0032 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0033 | Coordinated Utilities Plans Sheet 32 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0033 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0034 | Coordinated Utilities Plans Sheet 33 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0034 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0035 | Coordinated Utilities Plans Sheet 34 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0035 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0036 | Coordinated Utilities Plans Sheet 35 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0036 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0037 | Coordinated Utilities Plans Sheet 36 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0037 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0038 | Coordinated Utilities Plans Sheet 37 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0038 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0039 | Coordinated Utilities Plans Sheet 38 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0039 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0040 | Coordinated Utilities Plans Sheet 39 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0040 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0041 | Coordinated Utilities Plans Sheet 40 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0041 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0042 | Coordinated Utilities Plans Sheet 41 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0042 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0043 | Coordinated Utilities Plans Sheet 42 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0043 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0044 | Coordinated Utilities Plans Sheet 43 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0044 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0045 | Coordinated Utilities Plans Sheet 44 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0045 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0046 | Coordinated Utilities Plans Sheet 45 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0046 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0047 | Coordinated Utilities Plans Sheet 46 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0047 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0048 | Coordinated Utilities Plans Sheet 47 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0048 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0049 | Coordinated Utilities Plans Sheet 48 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0049 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0050 | Coordinated Utilities Plans Sheet 49 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0050 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0051 | Coordinated Utilities Plans Sheet 50 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0051 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0052 | Coordinated Utilities Plans Sheet 51 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0052 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0053 | Coordinated Utilities Plans Sheet 52 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0053 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0054 | Coordinated Utilities Plans Sheet 53 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0054 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0055 | Coordinated Utilities Plans Sheet 54 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0055 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0056 | Coordinated Utilities Plans Sheet 55 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0056 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0057 | Coordinated Utilities Plans Sheet 56 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0057 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0058 | Coordinated Utilities Plans Sheet 57 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0058 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0059 | Coordinated Utilities Plans Sheet 58 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0059 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0060 | Coordinated Utilities Plans Sheet 59 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0060 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0061 | Coordinated Utilities Plans Sheet 60 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0061 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0062 | Coordinated Utilities Plans Sheet 61 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0062 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0063 | Coordinated Utilities Plans Sheet 62 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0063 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0064 | Coordinated Utilities Plans Sheet 63 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0064 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
QF01012-NES-C04518-SDW-LSE-00-Z00000-5ZZ0065 | Coordinated Utilities Plans Sheet 64 |  | Landscape | Revit | .docx,.pdf | AS INDICATED | 2027-04-16 | Landscape - Sections | QP.E.EX.GEN.GEN.1200 |  | QF01012 | NES | C04518 | SDW | LSE | 00 | Z00000 | 5 | ZZ | 0065 | Landscape | Nesma & Partners | LOD400 | LOD400 |  |  | 2026-09-12
------- | [20 empty] | Landscape
------- | [20 empty] | Landscape

## Baseline (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | Package | Activity Code | Activity | Original Duration | Start | Finish
Shop Drawings | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Shop Drawings ¦ Mobilization | QP.M.GN.GEN.GEN.1400 | Submittal | 12 | 2025-10-18 | 2025-10-30
Shop Drawings | Mobilization | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Shop Drawings ¦ Mobilization ¦ Tower Crane Foundation - Concrete Works | QP.M.GN.GEN.GEN.1470 | Submittal | 12 | 2025-10-18 | 2025-10-30
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Blades Below Loft | QP.M.GN.GEN.GEN.1540 | Submittal | 12 | 2026-01-08 | 2026-01-21
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Loft | QP.M.GN.GEN.GEN.1560 | Submittal | 12 | 2026-06-20 | 2026-07-02
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Above Loft | QP.M.GN.GEN.GEN.1580 | Submittal | 12 | 2026-07-22 | 2026-08-04
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works | QP.E.CV.MBL.GEN.3460 | Submittal | 7 | 2025-11-04 | 2025-11-11
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works Outside Core Area | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works Outside Core Area | QP.E.CV.MBL.GEN.3540 | Submittal | 14 | 2025-11-12 | 2025-11-27
Shop Drawings | Civil | Blades | Blade 1 | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 1 | QP.E.CV.BL1.GEN.1060 | Submittal | 25 | 2025-12-07 | 2026-01-04
Shop Drawings | Civil | Blades | Blade 2 | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 2 | QP.E.CV.BL2.GEN.1060 | Submittal | 25 | 2025-12-14 | 2026-01-11
Shop Drawings | Civil | Blades | Blade 3 | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 3 | QP.E.CV.BL3.GEN.1060 | Submittal | 25 | 2025-11-30 | 2025-12-28
Shop Drawings | Civil | Blades | Blade 4 | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 4 | QP.E.CV.BL4.GEN.1060 | Submittal | 25 | 2025-11-23 | 2025-12-21
Shop Drawings | Civil | Blades | Blade 5 | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 5 | QP.E.CV.BL5.GEN.1060 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Civil | Parking | Parking | Parking | Parking | Parking | Shop Drawings ¦ Civil ¦ Parking | QP.E.CV.PAR.GEN.1000 | Submittal | 21 | 2027-03-04 | 2027-03-30
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - Foundation Works Core Area | QP.E.CV.MBL.GEN.3000 | Submittal | 28 | 2025-11-18 | 2025-12-20
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 03 +887.750M | QP.E.CV.MBL.GEN.3030 | Submittal | 28 | 2025-12-21 | 2026-01-21
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - SOG | QP.E.CV.MBL.GEN.3640 | Submittal | 14 | 2026-01-06 | 2026-01-21
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 02 - Foundation Works Outside Core Area | QP.E.CV.MBL.GEN.3020 | Submittal | 14 | 2025-12-21 | 2026-01-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 02 +893.5M | QP.E.CV.MBL.GEN.3070 | Submittal | 28 | 2025-12-21 | 2026-01-21
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 01 +900.5M | QP.E.CV.MBL.GEN.3100 | Submittal | 28 | 2026-01-22 | 2026-02-24
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01- LOBBY LEVEL +905M | QP.E.CV.MBL.GEN.3120 | Submittal | 25 | 2026-02-25 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01 - MEZZANINE +909M | QP.E.CV.MBL.GEN.3140 | Submittal | 15 | 2026-03-29 | 2026-04-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3180 | Submittal | 25 | 2026-04-15 | 2026-05-13
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3380 | Submittal | 25 | 2026-04-15 | 2026-05-13
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3220 | Submittal | 25 | 2026-05-14 | 2026-06-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3400 | Submittal | 25 | 2026-05-14 | 2026-06-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3240 | Submittal | 25 | 2026-06-16 | 2026-07-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3420 | Submittal | 25 | 2026-06-16 | 2026-07-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3260 | Submittal | 25 | 2026-07-15 | 2026-08-12
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3440 | Submittal | 25 | 2026-07-15 | 2026-08-12
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | QP.E.CV.MBL.GEN.3280 | Submittal | 25 | 2026-08-13 | 2026-09-10
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | QP.E.CV.MBL.GEN.3300 | Submittal | 28 | 2027-01-17 | 2027-02-17
Shop Drawings | Concrete | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Premium Theatre Concrete Works | QP.E.CV.MBL.GEN.3150 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | Concrete | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Amphitheatre Concrete Works | QP.E.CV.MBL.GEN.3200 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Premium Theater | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Premium Theater | QP.E.CV.MBL.GEN.3660 | Submittal | 28 | 2026-01-08 | 2026-02-09
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Loft and Adaptable Theatre | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Loft and Adaptable Theatre | QP.E.CV.MBL.GEN.3700 | Submittal | 28 | 2026-03-08 | 2026-04-11
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Fly Tower | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Fly Tower | QP.E.CV.MBL.GEN.3710 | Submittal | 28 | 2026-04-26 | 2026-05-31
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Lobby & Plaza | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Lobby & Plaza | QP.E.CV.MBL.GEN.3680 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Royal Majlis | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Royal Majlis | QP.E.CV.MBL.GEN.3740 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Foundation | QP.E.CV.BL1.GEN.1000 | Submittal | 25 | 2025-12-07 | 2026-01-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL1.GEN.1040 | Submittal | 28 | 2026-01-08 | 2026-02-09
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL1.GEN.1080 | Submittal | 18 | 2026-03-26 | 2026-04-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL1.GEN.1020 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL1.GEN.1120 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL1.GEN.1100 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Foundation | QP.E.CV.BL2.GEN.1000 | Submittal | 25 | 2025-12-14 | 2026-01-11
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL2.GEN.1040 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL2.GEN.1080 | Submittal | 18 | 2026-03-03 | 2026-03-25
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL2.GEN.1020 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL2.GEN.1140 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL2.GEN.1120 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Foundation | QP.E.CV.BL3.GEN.1000 | Submittal | 25 | 2025-11-30 | 2025-12-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Steel Composite Slab Including Embedded items Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Steel Composite Slab Including Embedded items Below Loft | QP.E.CV.BL3.GEN.1030 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL3.GEN.1080 | Submittal | 18 | 2025-12-29 | 2026-01-18
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL3.GEN.1020 | Submittal | 28 | 2026-01-31 | 2026-03-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Foundation | QP.E.CV.BL4.GEN.1000 | Submittal | 25 | 2025-11-23 | 2025-12-21
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL4.GEN.1030 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL4.GEN.1080 | Submittal | 18 | 2026-01-19 | 2026-02-08
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL4.GEN.1020 | Submittal | 28 | 2026-02-09 | 2026-03-14
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL4.GEN.1100 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL4.GEN.1120 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Foundation | QP.E.CV.BL5.GEN.1000 | Submittal | 25 | 2025-11-16 | 2025-12-14
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL5.GEN.1030 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL5.GEN.1080 | Submittal | 18 | 2026-02-09 | 2026-03-02
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL5.GEN.1020 | Submittal | 28 | 2026-03-03 | 2026-04-06
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL5.GEN.1100 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL5.GEN.1120 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Foundation Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Foundation Including Embedded items | QP.E.CV.PAR.GEN.1020 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Structural Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Structural Concrete Works Including Embedded items | QP.E.CV.PAR.GEN.1040 | Submittal | 28 | 2027-06-05 | 2027-07-06
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Below Loft | QP.E.ST.GEN.GEN.1090 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1100 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1110 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1050 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1060 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1070 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 3,4,5 | QP.E.ST.GEN.GEN.1000 | Submittal | 21 | 2025-11-12 | 2025-12-06
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | QP.E.ST.GEN.GEN.1010 | Submittal | 21 | 2025-11-12 | 2025-12-06
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Truss below Auditorium, Side and Back Stage | QP.E.ST.GEN.GEN.2120 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1220 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1230 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1200 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1210 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1190 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Embedded part - Main Building Above Level 5 | QP.E.ST.GEN.GEN.1040 | Submittal | 21 | 2025-12-07 | 2025-12-30
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Premium Theater - Frame Balconies and Back Stage Dressing | QP.E.ST.GEN.GEN.2140 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Loft and adaptable Theatre | QP.E.ST.GEN.GEN.1340 | Submittal | 28 | 2026-01-22 | 2026-02-24
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1390 | Submittal | 28 | 2026-02-02 | 2026-03-07
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1400 | Submittal | 28 | 2026-02-02 | 2026-03-07
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1310 | Submittal | 28 | 2026-02-02 | 2026-03-07
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1320 | Submittal | 28 | 2026-02-02 | 2026-03-07
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1330 | Submittal | 28 | 2026-02-02 | 2026-03-07
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1470 | Submittal | 28 | 2026-03-08 | 2026-04-11
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ Truss above Auditorium Incl. Metal Deck | QP.E.ST.GEN.GEN.2100 | Submittal | 28 | 2026-03-08 | 2026-04-11
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Temporay Tower ROYAL MAJLIS and Blades above loft | QP.E.ST.GEN.GEN.1490 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2160 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1520 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Truss above Flytower | QP.E.ST.GEN.GEN.2180 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1540 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ Blade 2 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2200 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ Adaptable Theatre Incl. Metal Deck | QP.E.ST.GEN.GEN.1560 | Submittal | 28 | 2026-06-20 | 2026-07-21
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.2220 | Submittal | 28 | 2026-06-20 | 2026-07-21
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Loft Truss and Infilled Beam North Side Incl. Metal Deck | QP.E.ST.GEN.GEN.1610 | Submittal | 28 | 2026-07-22 | 2026-08-23
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1600 | Submittal | 28 | 2026-07-22 | 2026-08-23
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Lobby and Plaza Incl. Metal Deck | QP.E.ST.GEN.GEN.1660 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Frame for Mezzanine | QP.E.ST.GEN.GEN.1670 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Link Bridge and Helix Stair | QP.E.ST.GEN.GEN.1570 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1680 | Submittal | 28 | 2026-09-27 | 2026-10-28
Shop Drawings | Structural Steel | Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | Shop Drawings ¦ Structural Steel ¦ Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck ¦ ROYAL MAJLIS | QP.E.ST.GEN.GEN.1640 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1090 | Submittal | 21 | 2026-03-29 | 2026-04-21
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1120 | Submittal | 21 | 2026-08-15 | 2026-09-07
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Wall Cladding | QP.E.AF.MBL.GEN.4440 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1100 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ FFE | QP.E.AF.MBL.GEN.5260 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1170 | Submittal | 21 | 2026-04-22 | 2026-05-16
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1200 | Submittal | 21 | 2026-09-08 | 2026-10-03
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5700 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1180 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ FFE | QP.E.AF.MBL.GEN.5280 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1220 | Submittal | 21 | 2026-05-17 | 2026-06-13
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1250 | Submittal | 21 | 2026-10-04 | 2026-10-27
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5720 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1230 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ FFE | QP.E.AF.MBL.GEN.5300 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1310 | Submittal | 21 | 2026-06-14 | 2026-07-07
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1340 | Submittal | 21 | 2026-10-28 | 2026-11-21
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5800 | Submittal | 21 | 2027-01-19 | 2027-02-11
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1320 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ FFE | QP.E.AF.MBL.GEN.5320 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1400 | Submittal | 21 | 2026-07-08 | 2026-08-01
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1430 | Submittal | 21 | 2026-11-22 | 2026-12-15
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5740 | Submittal | 21 | 2027-02-13 | 2027-03-09
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1410 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ FFE | QP.E.AF.MBL.GEN.5340 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1000 | Submittal | 21 | 2026-08-02 | 2026-08-25
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1030 | Submittal | 21 | 2026-12-16 | 2027-01-09
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5760 | Submittal | 21 | 2027-02-13 | 2027-03-09
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1010 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ FFE | QP.E.AF.MBL.GEN.5360 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1490 | Submittal | 21 | 2026-08-26 | 2026-09-19
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1520 | Submittal | 21 | 2027-01-10 | 2027-02-02
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5820 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1500 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ FFE | QP.E.AF.MBL.GEN.5380 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1580 | Submittal | 21 | 2026-09-20 | 2026-10-14
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1610 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5840 | Submittal | 21 | 2027-05-01 | 2027-05-29
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1590 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ FFE | QP.E.AF.MBL.GEN.5400 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1670 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1700 | Submittal | 28 | 2027-04-18 | 2027-05-24
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5860 | Submittal | 28 | 2027-05-30 | 2027-06-30
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1680 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ FFE | QP.E.AF.MBL.GEN.5420 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1760 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1790 | Submittal | 21 | 2027-05-25 | 2027-06-17
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5880 | Submittal | 21 | 2027-07-01 | 2027-07-25
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1770 | Submittal | 21 | 2027-07-12 | 2027-08-04
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ FFE | QP.E.AF.MBL.GEN.5440 | Submittal | 21 | 2027-07-12 | 2027-08-04
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1880 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1910 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5900 | Submittal | 21 | 2027-07-26 | 2027-08-18
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1890 | Submittal | 21 | 2027-08-05 | 2027-08-29
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ FFE | QP.E.AF.MBL.GEN.5460 | Submittal | 21 | 2027-08-05 | 2027-08-29
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1800 | Submittal | 21 | 2027-03-31 | 2027-04-24
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1830 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5920 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1810 | Submittal | 21 | 2027-08-30 | 2027-09-22
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ FFE | QP.E.AF.MBL.GEN.5480 | Submittal | 21 | 2027-09-15 | 2027-10-10
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1110 | Submittal | 28 | 2026-11-12 | 2026-12-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1140 | Submittal | 28 | 2027-04-05 | 2027-05-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1120 | Submittal | 28 | 2027-02-13 | 2027-03-20
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1370 | Submittal | 28 | 2026-12-15 | 2027-01-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1360 | Submittal | 28 | 2027-05-08 | 2027-06-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Wall Cladding | QP.E.AF.BL1.GEN.5940 | Submittal | 28 | 2027-05-30 | 2027-06-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1340 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1650 | Submittal | 28 | 2027-01-17 | 2027-02-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1680 | Submittal | 28 | 2027-06-14 | 2027-07-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1660 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1080 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1110 | Submittal | 28 | 2027-03-03 | 2027-04-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Wall Cladding | QP.E.AF.BL2.GEN.5960 | Submittal | 28 | 2027-03-21 | 2027-04-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1090 | Submittal | 28 | 2027-03-21 | 2027-04-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1580 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1610 | Submittal | 28 | 2027-04-18 | 2027-05-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1590 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1670 | Submittal | 28 | 2027-01-28 | 2027-03-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1700 | Submittal | 28 | 2027-05-25 | 2027-06-26
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1680 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1000 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1030 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL3.GEN.5980 | Submittal | 28 | 2027-04-22 | 2027-05-29
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1010 | Submittal | 28 | 2027-04-22 | 2027-05-29
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1340 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1370 | Submittal | 28 | 2027-04-18 | 2027-05-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1350 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1210 | Submittal | 28 | 2026-07-20 | 2026-08-20
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1240 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL4.GEN.6000 | Submittal | 28 | 2027-09-15 | 2027-10-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1220 | Submittal | 28 | 2027-04-22 | 2027-05-29
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1820 | Submittal | 21 | 2026-10-24 | 2026-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1850 | Submittal | 21 | 2027-04-26 | 2027-05-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1830 | Submittal | 21 | 2027-06-09 | 2027-07-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1730 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1760 | Submittal | 28 | 2027-05-25 | 2027-06-26
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1740 | Submittal | 28 | 2027-07-04 | 2027-08-04
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.2280 | Submittal | 28 | 2026-08-22 | 2026-09-22
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.2340 | Submittal | 28 | 2026-09-24 | 2026-10-26
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.2300 | Submittal | 28 | 2027-05-30 | 2027-06-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1130 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1160 | Submittal | 21 | 2027-05-25 | 2027-06-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1140 | Submittal | 21 | 2027-07-01 | 2027-07-25
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1500 | Submittal | 28 | 2027-01-13 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1530 | Submittal | 28 | 2027-07-04 | 2027-08-04
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Wall Cladding | QP.E.AF.BL5.GEN.6020 | Submittal | 28 | 2027-09-15 | 2027-10-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1510 | Submittal | 28 | 2027-07-26 | 2027-08-26
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1000 | Submittal | 28 | 2027-07-21 | 2027-08-22
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1020 | Submittal | 21 | 2027-08-23 | 2027-09-15
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Doors / Openings | QP.E.AF.PAR.GEN.1010 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Specialities | QP.E.AF.MBL.GEN.5160 | Submittal | 21 | 2027-10-19 | 2027-11-11
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1030 | Submittal | 28 | 2027-09-08 | 2027-10-11
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1050 | Submittal | 21 | 2027-10-12 | 2027-11-04
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Doors / Openings | QP.E.AF.PAR.GEN.1040 | Submittal | 21 | 2027-10-12 | 2027-11-04
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Specialities | QP.E.AF.MBL.GEN.5200 | Submittal | 21 | 2027-11-13 | 2027-12-06
Shop Drawings | Architecture and Fitouts | Amphitheatre | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4040 | Submittal | 28 | 2027-08-23 | 2027-09-25
Shop Drawings | Architecture and Fitouts | Amphitheatre | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.4070 | Submittal | 21 | 2027-09-26 | 2027-10-19
Shop Drawings | Architecture and Fitouts | Amphitheatre | Wall Cladding | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Wall Cladding | QP.E.AF.MBL.GEN.6040 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Amphitheatre | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4050 | Submittal | 21 | 2027-10-20 | 2027-11-13
Shop Drawings | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | Shop Drawings ¦ External Building Works (Guard House, SEC Room) | QP.E.EX.GEN.GEN.1270 | Submittal | 28 | 2027-02-11 | 2027-03-18
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Main Building | QP.E.AF.MBL.GEN.6060 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 5 | Water Proofing - Roof - Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 5 | QP.E.AF.BL5.GEN.6180 | Submittal | 21 | 2027-05-25 | 2027-06-17
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 4 | Water Proofing - Roof - Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 4 | QP.E.AF.BL4.GEN.6160 | Submittal | 21 | 2027-04-26 | 2027-05-24
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 3 | Water Proofing - Roof - Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 3 | QP.E.AF.BL3.GEN.6140 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 1 | Water Proofing - Roof - Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 1 | QP.E.AF.BL1.GEN.6100 | Submittal | 21 | 2027-05-08 | 2027-06-05
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 2 | Water Proofing - Roof - Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 2 | QP.E.AF.BL2.GEN.6120 | Submittal | 21 | 2027-04-18 | 2027-05-11
Shop Drawings | Specialist Systems | Waterproofing | Wet Areas | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Wet Areas ¦ Main Building | QP.E.AF.MBL.GEN.4400 | Submittal | 21 | 2026-04-30 | 2026-05-24
Shop Drawings | Specialist Systems | Doors/ Openings | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Main Building | QP.E.AF.MBL.GEN.1140 | Submittal | 28 | 2027-01-24 | 2027-02-25
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.1130 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 2 | QP.E.AF.BL2.GEN.1100 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.1020 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.1230 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.2320 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Doors/ Openings | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Amphitheatre | QP.E.AF.MBL.GEN.4060 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Conveying System | Waste Management | Waste Management | Waste Management | Waste Management | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Waste Management | QP.E.CY.GEN.GEN.1280 | Submittal | 21 | 2027-06-26 | 2027-07-19
Shop Drawings | Specialist Systems | Conveying System | Escalators | Escalators | Escalators | Escalators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Escalators | QP.E.CY.GEN.GEN.1040 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Specialist Systems | Conveying System | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | QP.E.CY.GEN.GEN.1020 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | Specialist Systems | Conveying System | Truck Elevators | Truck Elevators | Truck Elevators | Truck Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Truck Elevators | QP.E.CY.GEN.GEN.1000 | Submittal | 28 | 2026-06-16 | 2026-07-18
Shop Drawings | Specialist Systems | Conveying System | Inclined Elevators | Inclined Elevators | Inclined Elevators | Inclined Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Inclined Elevators | QP.E.CY.GEN.GEN.1050 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | Specialist Systems | Conveying System | BMU | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Main Building | QP.E.CY.GEN.GEN.1090 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 1 | QP.E.CY.GEN.GEN.1130 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 2 | QP.E.CY.GEN.GEN.1170 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 3 | Balde 3 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 3 | QP.E.CY.GEN.GEN.1210 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 4 | QP.E.CY.GEN.GEN.1110 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 5 | Balde 5 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 5 | QP.E.CY.GEN.GEN.1150 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Joinery Works | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Main Building | QP.E.AF.MBL.GEN.5540 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.6120 | Submittal | 21 | 2027-06-14 | 2027-07-07
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.6160 | Submittal | 21 | 2027-05-25 | 2027-06-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.6180 | Submittal | 21 | 2027-05-25 | 2027-06-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.6200 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | Specialist Systems | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Shop Drawings ¦ Specialist Systems ¦ Kitchen and Laundary | QP.E.AF.MBL.GEN.5500 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | Specialist Systems | Water Features | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Specialist Systems ¦ Water Features | QP.E.AF.MBL.GEN.6100 | Submittal | 21 | 2026-09-13 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Mechanical | QP.E.ME.MBL.GEN.6780 | Submittal | 18 | 2026-01-06 | 2026-01-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical | QP.E.ME.MBL.GEN.6800 | Submittal | 18 | 2026-01-06 | 2026-01-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6840 | Submittal | 18 | 2026-01-06 | 2026-01-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical | QP.E.ME.MBL.GEN.6850 | Submittal | 18 | 2026-01-06 | 2026-01-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6860 | Submittal | 18 | 2026-02-03 | 2026-02-24
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical | QP.E.ME.MBL.GEN.6870 | Submittal | 18 | 2026-02-03 | 2026-02-24
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Mechanical | QP.E.ME.MBL.GEN.6900 | Submittal | 18 | 2026-03-05 | 2026-03-28
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical | QP.E.ME.MBL.GEN.6910 | Submittal | 18 | 2026-03-05 | 2026-03-28
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Mechanical | QP.E.ME.MBL.GEN.6940 | Submittal | 18 | 2026-03-29 | 2026-04-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical | QP.E.ME.MBL.GEN.6950 | Submittal | 18 | 2026-03-29 | 2026-04-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Mechanical | QP.E.ME.MBL.GEN.6980 | Submittal | 18 | 2026-04-23 | 2026-05-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Electrical | QP.E.ME.MBL.GEN.6990 | Submittal | 18 | 2026-04-23 | 2026-05-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Mechanical | QP.E.ME.MBL.GEN.7020 | Submittal | 18 | 2026-05-23 | 2026-06-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical | QP.E.ME.MBL.GEN.7030 | Submittal | 18 | 2026-05-23 | 2026-06-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7060 | Submittal | 18 | 2026-06-24 | 2026-07-14
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical | QP.E.ME.MBL.GEN.7070 | Submittal | 18 | 2026-06-24 | 2026-07-14
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7100 | Submittal | 18 | 2026-07-23 | 2026-08-12
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical | QP.E.ME.MBL.GEN.7110 | Submittal | 18 | 2026-07-23 | 2026-08-12
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Mechanical | QP.E.ME.MBL.GEN.7140 | Submittal | 18 | 2026-08-22 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical | QP.E.ME.MBL.GEN.7150 | Submittal | 18 | 2026-08-22 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Mechanical | QP.E.ME.MBL.GEN.7180 | Submittal | 18 | 2026-08-22 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Electrical | QP.E.ME.MBL.GEN.7190 | Submittal | 18 | 2026-08-22 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Mechanical | QP.E.ME.MBL.GEN.7220 | Submittal | 18 | 2026-09-12 | 2026-10-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical | QP.E.ME.MBL.GEN.7230 | Submittal | 18 | 2026-09-12 | 2026-10-03
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1320 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1330 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1340 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1350 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ ICT Containment | QP.E.ME.MBL.GEN.1360 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1420 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1430 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1440 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1450 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1460 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1740 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1750 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1760 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1770 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1780 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1590 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1600 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1610 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1620 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.1630 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2040 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2050 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2060 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2070 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ ICT Containment | QP.E.ME.MBL.GEN.2080 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2240 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2250 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2260 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2270 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ ICT Containment | QP.E.ME.MBL.GEN.2280 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2440 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2450 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2460 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2470 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.2480 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2640 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2650 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2660 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2670 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2680 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2850 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2860 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2870 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2880 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2890 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3070 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3080 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3090 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3100 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ ICT Containment | QP.E.ME.MBL.GEN.3110 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3290 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3300 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3310 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3320 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ ICT Containment | QP.E.ME.MBL.GEN.3330 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3500 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3510 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3520 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3530 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ ICT Containment | QP.E.ME.MBL.GEN.3540 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.MBL.GEN.5000 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.MBL.GEN.5040 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.MBL.GEN.5060 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.MBL.GEN.5080 | Submittal | 28 | 2027-05-19 | 2027-06-20
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.MBL.GEN.7280 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.MBL.GEN.7300 | Submittal | 28 | 2027-05-19 | 2027-06-20
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.MBL.GEN.7320 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.MBL.GEN.7260 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.MBL.GEN.7340 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | LPG System | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ LPG System | QP.E.ME.MBL.GEN.5100 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.MBL.GEN.7360 | Submittal | 28 | 2027-07-24 | 2027-08-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Fire Suppression | QP.E.ME.CBR.GEN.1000 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Plumbing | Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Plumbing | QP.E.ME.CBR.GEN.1011 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ LPG System | QP.E.ME.CBR.GEN.1055 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.CBR.GEN.1022 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Electrical | QP.E.ME.CBR.GEN.1033 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ ELV (Low Current System) | QP.E.ME.CBR.GEN.1044 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.MBL.GEN.7380 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Diesel | Diesel | Diesel | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Diesel | QP.E.ME.MBL.GEN.7420 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Water Features | Water Features | Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Water Features | QP.E.ME.MBL.GEN.7440 | Submittal | 28 | 2027-06-26 | 2027-07-27
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M | QP.E.ME.MBL.GEN.6520 | Submittal | 14 | 2026-11-17 | 2026-12-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Grey Water Treatment/ Sewage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Grey Water Treatment/ Sewage | QP.E.ME.MBL.GEN.1050 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Stromwater/ Drainage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Stromwater/ Drainage | QP.E.ME.MBL.GEN.1060 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1040 | Submittal | 21 | 2026-12-03 | 2026-12-27
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M | QP.E.ME.MBL.GEN.6540 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ AHU Room | QP.E.ME.MBL.GEN.1160 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Transformer/ Switchgear/ Panel Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Transformer/ Switchgear/ Panel Room | QP.E.ME.MBL.GEN.1240 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Generator Room/ Diesel Tank | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Generator Room/ Diesel Tank | QP.E.ME.MBL.GEN.1250 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | ETS/ CWP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ ETS/ CWP Room | QP.E.ME.MBL.GEN.1170 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1030 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1290 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M | QP.E.ME.MBL.GEN.6560 | Submittal | 14 | 2026-12-20 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1020 | Submittal | 14 | 2026-12-20 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Domestic Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Domestic Water | QP.E.ME.MBL.GEN.1010 | Submittal | 14 | 2026-12-20 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Fire Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Fire Water | QP.E.ME.MBL.GEN.1000 | Submittal | 14 | 2026-12-20 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1280 | Submittal | 14 | 2026-12-20 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 LOBBY LEVEL +905.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 LOBBY LEVEL +905.00M | QP.E.ME.MBL.GEN.6640 | Submittal | 14 | 2027-01-05 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 UPEER LOBBY LEVEL MEZZANINE +909M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M | QP.E.ME.MBL.GEN.6660 | Submittal | 14 | 2027-01-21 | 2027-02-06
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L2 THEATRE STALLS +913M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L2 THEATRE STALLS +913M | QP.E.ME.MBL.GEN.6680 | Submittal | 14 | 2027-02-07 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | QP.E.ME.MBL.GEN.6700 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | QP.E.ME.MBL.GEN.6720 | Submittal | 14 | 2027-03-15 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 SECOND CIRCLE AND LOFT +928.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 SECOND CIRCLE AND LOFT +928.00M | QP.E.ME.MBL.GEN.6740 | Submittal | 14 | 2027-03-31 | 2027-04-15
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M | QP.E.ME.MBL.GEN.5540 | Submittal | 14 | 2027-04-17 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - AHU Room | QP.E.ME.MBL.GEN.1180 | Submittal | 14 | 2027-05-03 | 2027-05-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Makeup Air Unit and Ecology | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Makeup Air Unit and Ecology | QP.E.ME.MBL.GEN.1190 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Sky Garden Irrigation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Sky Garden Irrigation | QP.E.ME.MBL.GEN.1070 | Submittal | 14 | 2027-04-17 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L6 SKY GARDEN +935.85M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L6 SKY GARDEN +935.85M | QP.E.ME.MBL.GEN.6760 | Submittal | 14 | 2027-05-03 | 2027-05-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M | QP.E.ME.MBL.GEN.6580 | Submittal | 14 | 2027-05-24 | 2027-06-08
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | Plant Room - Fan Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M ¦ Plant Room - Fan Room | QP.E.ME.MBL.GEN.6600 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Kitchen and Laundry | Kitchen and Laundry | Kitchen and Laundry | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Kitchen and Laundry | QP.E.ME.MBL.GEN.7400 | Submittal | 28 | 2027-08-14 | 2027-09-14
Shop Drawings | MEP | Panels | Panels | Panels | Panels | Panels | Shop Drawings ¦ MEP ¦ Panels | QP.E.ME.MBL.GEN.6510 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Mechanical | QP.E.ME.BL1.GEN.3720 | Submittal | 18 | 2026-02-10 | 2026-03-03
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical | QP.E.ME.BL1.GEN.3740 | Submittal | 18 | 2026-02-10 | 2026-03-03
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL1.GEN.3760 | Submittal | 28 | 2026-09-27 | 2026-10-28
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL1.GEN.3780 | Submittal | 28 | 2026-09-27 | 2026-10-28
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Mechanical | QP.E.ME.BL1.GEN.3800 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical | QP.E.ME.BL1.GEN.3820 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1020 | Submittal | 28 | 2026-11-12 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1030 | Submittal | 28 | 2026-08-12 | 2026-09-13
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1040 | Submittal | 28 | 2026-08-12 | 2026-09-13
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1050 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ ICT Containment | QP.E.ME.BL1.GEN.1060 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL1.GEN.2940 | Submittal | 28 | 2026-12-29 | 2027-01-30
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.2950 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.2960 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.2970 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL1.GEN.2980 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1510 | Submittal | 28 | 2027-02-14 | 2027-03-21
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1520 | Submittal | 28 | 2027-02-04 | 2027-03-09
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1530 | Submittal | 28 | 2027-03-13 | 2027-04-13
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1540 | Submittal | 28 | 2027-02-04 | 2027-03-09
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ ICT Containment | QP.E.ME.BL1.GEN.1550 | Submittal | 28 | 2027-02-04 | 2027-03-09
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.BL1.GEN.3280 | Submittal | 28 | 2027-04-05 | 2027-05-06
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL1.GEN.3320 | Submittal | 28 | 2027-05-08 | 2027-06-13
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL1.GEN.3340 | Submittal | 28 | 2027-06-14 | 2027-07-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL1.GEN.3360 | Submittal | 28 | 2027-07-17 | 2027-08-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL1.GEN.3580 | Submittal | 28 | 2027-06-14 | 2027-07-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL1.GEN.3600 | Submittal | 28 | 2027-09-01 | 2027-10-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL1.GEN.3620 | Submittal | 28 | 2027-10-05 | 2027-11-06
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL1.GEN.3680 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL1.GEN.3640 | Submittal | 28 | 2027-09-01 | 2027-10-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL1.GEN.3660 | Submittal | 28 | 2027-10-05 | 2027-11-06
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3480 | Submittal | 21 | 2027-11-07 | 2027-11-30
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL1.GEN.1000 | Submittal | 21 | 2027-11-07 | 2027-11-30
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL1.GEN.3700 | Submittal | 28 | 2027-07-17 | 2027-08-17
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3400 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical | QP.E.ME.BL2.GEN.3420 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL2.GEN.3440 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL2.GEN.3460 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3480 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical | QP.E.ME.BL2.GEN.3500 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1020 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1030 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1040 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1050 | Submittal | 28 | 2026-05-30 | 2026-06-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.1060 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1910 | Submittal | 28 | 2026-12-27 | 2027-01-27
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1920 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1930 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1940 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL2.GEN.1950 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.2110 | Submittal | 28 | 2027-01-28 | 2027-03-02
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.2120 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.2130 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.2140 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.2150 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL2.GEN.3160 | Submittal | 28 | 2027-03-03 | 2027-04-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL2.GEN.3200 | Submittal | 28 | 2027-04-07 | 2027-05-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL2.GEN.3220 | Submittal | 28 | 2027-05-10 | 2027-06-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL2.GEN.3240 | Submittal | 28 | 2027-06-16 | 2027-07-18
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL2.GEN.3260 | Submittal | 28 | 2027-05-10 | 2027-06-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL2.GEN.3280 | Submittal | 28 | 2027-07-19 | 2027-08-19
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL2.GEN.3300 | Submittal | 28 | 2027-08-21 | 2027-09-21
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL2.GEN.3380 | Submittal | 28 | 2027-04-07 | 2027-05-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL2.GEN.3320 | Submittal | 28 | 2027-07-19 | 2027-08-19
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL2.GEN.3340 | Submittal | 28 | 2027-08-21 | 2027-09-21
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3500 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL2.GEN.1000 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL2.GEN.3360 | Submittal | 28 | 2027-06-16 | 2027-07-18
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Mechanical | QP.E.ME.BL3.GEN.3640 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical | QP.E.ME.BL3.GEN.3660 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical | QP.E.ME.BL3.GEN.3700 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Mechanical | QP.E.ME.BL3.GEN.3680 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1020 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.1030 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1040 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1050 | Submittal | 28 | 2026-04-09 | 2026-05-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ ICT Containment | QP.E.ME.BL3.GEN.1060 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1790 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.3280 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1810 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1820 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ ICT Containment | QP.E.ME.BL3.GEN.1830 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL3.GEN.3400 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL3.GEN.3440 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL3.GEN.3460 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL3.GEN.3480 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL3.GEN.3500 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL3.GEN.3540 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL3.GEN.3560 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL3.GEN.3620 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL3.GEN.3600 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL3.GEN.3580 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3520 | Submittal | 21 | 2027-08-28 | 2027-09-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL3.GEN.1000 | Submittal | 21 | 2027-09-21 | 2027-10-16
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL3.GEN.3520 | Submittal | 28 | 2027-10-17 | 2027-11-17
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Mechanical | QP.E.ME.BL4.GEN.6010 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical | QP.E.ME.BL4.GEN.6030 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Mechanical | QP.E.ME.BL4.GEN.6050 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Electrical | QP.E.ME.BL4.GEN.6070 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Mechanical | QP.E.ME.BL4.GEN.6090 | Submittal | 28 | 2026-06-20 | 2026-07-21
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical | QP.E.ME.BL4.GEN.6110 | Submittal | 28 | 2026-06-20 | 2026-07-21
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Fire Suppression | QP.E.ME.BL4.GEN.2110 | Submittal | 28 | 2026-07-20 | 2026-08-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2120 | Submittal | 28 | 2026-07-20 | 2026-08-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2130 | Submittal | 28 | 2026-07-20 | 2026-08-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2140 | Submittal | 28 | 2026-04-21 | 2026-05-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ ICT Containment | QP.E.ME.BL4.GEN.2150 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2910 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.5550 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2930 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2940 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ ICT Containment | QP.E.ME.BL4.GEN.2950 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2810 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2820 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2830 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2840 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ ICT Containment | QP.E.ME.BL4.GEN.2850 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL4.GEN.5770 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL4.GEN.5810 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL4.GEN.5830 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL4.GEN.5850 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL4.GEN.5870 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL4.GEN.5930 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL4.GEN.5950 | Submittal | 28 | 2027-08-14 | 2027-09-14
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL4.GEN.5890 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL4.GEN.5970 | Submittal | 28 | 2027-07-26 | 2027-08-26
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL4.GEN.5990 | Submittal | 28 | 2027-08-28 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3540 | Submittal | 21 | 2027-09-11 | 2027-10-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL4.GEN.3110 | Submittal | 21 | 2027-09-11 | 2027-10-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL4.GEN.5910 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Mechanical | QP.E.ME.BL5.GEN.3040 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical | QP.E.ME.BL5.GEN.3060 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL5.GEN.3080 | Submittal | 21 | 2026-05-14 | 2026-06-10
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL5.GEN.3100 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Mechanical | QP.E.ME.BL5.GEN.3120 | Submittal | 28 | 2026-06-11 | 2026-07-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical | QP.E.ME.BL5.GEN.3140 | Submittal | 28 | 2026-06-20 | 2026-07-21
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1020 | Submittal | 28 | 2026-08-01 | 2026-09-01
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1030 | Submittal | 28 | 2026-08-01 | 2026-09-01
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1040 | Submittal | 28 | 2026-08-01 | 2026-09-01
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1050 | Submittal | 28 | 2026-05-03 | 2026-06-07
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ ICT Containment | QP.E.ME.BL5.GEN.1060 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1550 | Submittal | 21 | 2026-12-20 | 2027-01-12
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1560 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1570 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1580 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL5.GEN.1590 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1750 | Submittal | 28 | 2027-01-13 | 2027-02-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1760 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1770 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1780 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ ICT Containment | QP.E.ME.BL5.GEN.1790 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL5.GEN.2800 | Submittal | 28 | 2027-02-15 | 2027-03-22
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL5.GEN.2840 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL5.GEN.2860 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL5.GEN.2880 | Submittal | 28 | 2027-06-01 | 2027-07-03
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL5.GEN.3020 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL5.GEN.2900 | Submittal | 28 | 2027-07-04 | 2027-08-04
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL5.GEN.2920 | Submittal | 28 | 2027-08-05 | 2027-09-06
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL5.GEN.3000 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL5.GEN.2940 | Submittal | 28 | 2027-07-04 | 2027-08-04
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL5.GEN.2960 | Submittal | 28 | 2027-08-05 | 2027-09-06
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3560 | Submittal | 28 | 2027-09-07 | 2027-10-10
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL5.GEN.1000 | Submittal | 28 | 2027-09-07 | 2027-10-10
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL5.GEN.2980 | Submittal | 28 | 2027-06-01 | 2027-07-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Mechanical | QP.E.ME.PAR.GEN.1459 | Submittal | 21 | 2027-05-22 | 2027-06-14
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Electrical | QP.E.ME.PAR.GEN.1479 | Submittal | 21 | 2027-05-22 | 2027-06-14
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Mechanical | QP.E.ME.PAR.GEN.1499 | Submittal | 21 | 2027-05-22 | 2027-06-14
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Electrical | QP.E.ME.PAR.GEN.1519 | Submittal | 21 | 2027-05-22 | 2027-06-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Fire Suppression | QP.E.ME.PAR.GEN.1000 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1011 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1022 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1033 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ ICT Containment | QP.E.ME.PAR.GEN.1044 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Fire Suppression | QP.E.ME.PAR.GEN.1055 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1066 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1077 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1088 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ ICT Containment | QP.E.ME.PAR.GEN.1099 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.PAR.GEN.1219 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.PAR.GEN.1259 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.PAR.GEN.1279 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.PAR.GEN.1299 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.PAR.GEN.1419 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.PAR.GEN.1319 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.PAR.GEN.1339 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.PAR.GEN.1439 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.PAR.GEN.1359 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.PAR.GEN.1379 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.PAR.GEN.1399 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3600 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3610 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3620 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.4430 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4440 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.4450 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3960 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3970 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3980 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Fire Suppression | QP.E.ME.MBL.GEN.3930 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3940 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Electrical | QP.E.ME.MBL.GEN.3950 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Fire Suppression | QP.E.ME.MBL.GEN.3810 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3820 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Electrical | QP.E.ME.MBL.GEN.3830 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4400 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4410 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4420 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4340 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4350 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4360 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4520 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4530 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4540 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4640 | Submittal | 21 | 2027-06-01 | 2027-06-24
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4650 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4660 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3870 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3880 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3890 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3840 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3850 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3860 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.4550 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4560 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.4570 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 3, 4 & 5 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 3, 4 & 5 | QP.E.FA.GEN.GEN.1460 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 1 & 2 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 1 & 2 | QP.E.FA.GEN.GEN.2180 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Loft and Lobby | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Loft and Lobby | QP.E.FA.GEN.GEN.2140 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | QP.E.FA.GEN.GEN.2160 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Blades | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Blades | QP.E.FA.GEN.GEN.1820 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Lobby and Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Lobby and Loft | QP.E.FA.GEN.GEN.1770 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Above Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Above Loft | QP.E.FA.GEN.GEN.1780 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Blades | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Blades | QP.E.FA.GEN.GEN.1890 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Main Building | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Main Building | QP.E.FA.GEN.GEN.2230 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Facade | Facade | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 1 | QP.E.FA.GEN.GEN.1920 | Submittal | 28 | 2026-09-29 | 2026-10-31
Shop Drawings | Facade | Facade | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 2 | QP.E.FA.GEN.GEN.1930 | Submittal | 28 | 2026-08-26 | 2026-09-28
Shop Drawings | Facade | Facade | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 3 | QP.E.FA.GEN.GEN.1940 | Submittal | 28 | 2026-05-17 | 2026-06-21
Shop Drawings | Facade | Facade | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 4 | QP.E.FA.GEN.GEN.1950 | Submittal | 28 | 2026-06-22 | 2026-07-23
Shop Drawings | Facade | Facade | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 5 | QP.E.FA.GEN.GEN.1960 | Submittal | 28 | 2026-07-25 | 2026-08-25
Shop Drawings | Facade | Facade | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Facade ¦ Amphitheatre | QP.E.FA.GEN.GEN.2240 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Lobby | Lobby | Lobby | Lobby | Shop Drawings ¦ Facade ¦ Lobby | QP.E.FA.GEN.GEN.2090 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | Loft | Loft | Loft | Loft | Shop Drawings ¦ Facade ¦ Loft | QP.E.FA.GEN.GEN.2100 | Submittal | 28 | 2027-02-07 | 2027-03-14
Shop Drawings | Facade | Facade | Above Loft | Above Loft | Above Loft | Above Loft | Shop Drawings ¦ Facade ¦ Above Loft | QP.E.FA.GEN.GEN.1910 | Submittal | 28 | 2027-04-17 | 2027-05-23
Shop Drawings | Facade | Facade | Link Bridges | Link Bridges | Link Bridges | Link Bridges | Shop Drawings ¦ Facade ¦ Link Bridges | QP.E.FA.GEN.GEN.2050 | Submittal | 28 | 2027-02-07 | 2027-03-14
Shop Drawings | Facade | Facade | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Shop Drawings ¦ Facade ¦ Facade Lighting Fixtures | QP.E.FA.GEN.GEN.1450 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | GRC Cladding | GRC Cladding | GRC Cladding | GRC Cladding | Shop Drawings ¦ Facade ¦ GRC Cladding | QP.E.FA.GEN.GEN.1390 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 1 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 1 | QP.E.CV.MBL.GEN.3060 | Submittal | 28 | 2026-06-16 | 2026-07-18
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 2 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 2 | QP.E.CV.MBL.GEN.3560 | Submittal | 28 | 2026-08-19 | 2026-09-20
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 3 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 3 | QP.E.CV.MBL.GEN.3580 | Submittal | 28 | 2026-09-21 | 2026-10-24
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 4 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 4 | QP.E.CV.MBL.GEN.3600 | Submittal | 28 | 2026-10-25 | 2026-11-25
Shop Drawings | External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Shop Drawings ¦ External Works ¦ Waterproofing for External Works | QP.E.EX.GEN.GEN.1040 | Submittal | 28 | 2026-06-25 | 2026-07-27
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Excavation | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Excavation | QP.E.CV.MBL.GEN.3320 | Submittal | 15 | 2027-03-31 | 2027-04-17
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Blinding Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Blinding Including Embedded Items | QP.E.CV.MBL.GEN.3500 | Submittal | 15 | 2027-04-18 | 2027-05-04
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Foundation Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Foundation Including Embedded Items | QP.E.CV.MBL.GEN.3480 | Submittal | 28 | 2027-05-05 | 2027-06-10
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Structural Concrete Works Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Structural Concrete Works Including Embedded Items | QP.E.CV.MBL.GEN.3520 | Submittal | 28 | 2027-06-12 | 2027-07-13
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4000 | Submittal | 28 | 2027-07-14 | 2027-08-15
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Finishing | Finishing | Finishing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Finishing | QP.E.AF.MBL.GEN.4030 | Submittal | 21 | 2027-02-10 | 2027-03-07
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4010 | Submittal | 21 | 2027-01-17 | 2027-02-09
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Doors / Openings | QP.E.AF.MBL.GEN.4020 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Fire Suppression | QP.E.ME.MBL.GEN.1690 | Submittal | 21 | 2027-07-14 | 2027-08-07
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Plumbing | Plumbing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Plumbing | QP.E.ME.MBL.GEN.1700 | Submittal | 21 | 2027-07-14 | 2027-08-07
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.1710 | Submittal | 21 | 2027-07-14 | 2027-08-07
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Electrical | Electrical | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Electrical | QP.E.ME.MBL.GEN.1720 | Submittal | 21 | 2027-07-14 | 2027-08-07
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ ELV (Low Current System) | QP.E.ME.MBL.GEN.1730 | Submittal | 21 | 2027-07-14 | 2027-08-07
Shop Drawings | External Works | External Utilities | Irrigation Works | Irrigation Works | Irrigation Works | Irrigation Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ Irrigation Works | QP.E.EX.GEN.GEN.1090 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | External Works | External Utilities | External Drainage Works | External Drainage Works | External Drainage Works | External Drainage Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Drainage Works | QP.E.EX.GEN.GEN.1110 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | External Works | External Utilities | External Lighting Works | External Lighting Works | External Lighting Works | External Lighting Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Lighting Works | QP.E.EX.GEN.GEN.1170 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | External Works | External Utilities | Low Current | Low Current | Low Current | Low Current | Shop Drawings ¦ External Works ¦ External Utilities ¦ Low Current | QP.E.EX.GEN.GEN.1100 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | External Works | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Shop Drawings ¦ External Works ¦ Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 | Submittal | 28 | 2026-08-11 | 2026-09-12
Shop Drawings | External Works | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Shop Drawings ¦ External Works ¦ Water and Environment | QP.E.EX.GEN.GEN.1220 | Submittal | 21 | 2026-09-13 | 2026-10-07
Shop Drawings | External Works | External Fixtures | External Fixtures | External Fixtures | External Fixtures | External Fixtures | Shop Drawings ¦ External Works ¦ External Fixtures | QP.E.EX.GEN.GEN.1260 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | External Works | LPG System | LPG System | LPG System | LPG System | LPG System | Shop Drawings ¦ External Works ¦ LPG System | QP.E.EX.GEN.GEN.1300 | Submittal | 28 | 2027-01-21 | 2027-02-23

## Picklists
| #VALUE! |  | Numbering System Document - Metadata Mapping
DOCUMENT NUMBERING DROPDOWN ATTRIBUTES | [18 empty] | QIC GENERAL DROPDOWN ATTRIBUTES
FIELD 01 - PROJECT CODE |  | FIELD 02 - ORIGINATOR |  | FIELD 03 - CONTRACT REFERENCE |  | FIELD 04 - DOCUMENT TYPES |  | FIELD 05 - DISCIPLINE |  | FIELD 06 - AREA/ZONE |  | FIELD 07 - VENUE/BUILDING |  | FIELD 08 - SERIAL NUMBER |  |  |  |  | DOCUMENT DETAILS |  |  | SUITABILITY STATUS |  | NAP GENERAL DROPDOWN ATTRIBUTES
Ab. 01 | 1 - Project Name | Ab. 02 | 2 - Originator Name | Ab. 03 | 3 - Contract Reference | Ab. 04 | 4 - Document Type | Ab. 05 | 5 - Discipline | Ab. 06 | 6 - Area/Zone | Ab. 07 | 7 - Venue/Building | Ab. 08A | 8A - Drawing Type | Ab. 08B | 8B - Level | 8C - Sequence Number | Authoring Software | File/Exchange Format | Scope Area | Code | Status | Scale | Classification ID | Classification | Corporate Discipline | Author
QF01012 | Qiddaya Performing Arts Center | NES | Nesma and Partners | C04518 | Contract Number | AGD | Agenda | ACO | Acoustic | 00 | Overall | Z00000 | Overall | 0 | General (General Notes, Abbreviations, Legends, Single Line Diagrams, General Detail) | 00 | Non-Specific ( For Blade ) | 4 Digit Sequence Number For Drawings/Models | Revit | .rvt | Design Management | S0 (WIP) | Initial status or WIP | NTS | FI_60_25 | Drawing | Architectural | Nesma & Partners
[6 empty] | AVV | Agreed Value of Variation | ADM | Administration | 01 | Zone Sheet 1 | CENT01 | Center Block | 1 | Elevations (Vertical View) | B1 | Basement 1 - Parking A +900.50 | 3 Digit Sequence Number For Documents | Civil3D | .nwc | Architecture / LDC | S1 (Shared) | Suitable for Coordination | AS INDICATED | FI_90_75 | Schedule or table | Electrical
[6 empty] | ASB | As Built | ARC | Architectural | 02 | Zone Sheet 2 | GARD01 | Guard House | 2 | Plans (Overall, Horizontal View, Floor Plan, Ceiling Plan, Site Plan, Loading Plan) | B2 | Basement 2 - Service +893.50 |  | MicrosoftWord | .nwd | Landscape | S2 (Shared) | Suitable for Information | 1:1 | FI_60_53 | Model | Façade
[6 empty] | AUR | Audit Report | ADT | Area Development | 03 | Zone Sheet 3 | BLAD01 | Blade 01 | 3 | Sections (Sectional View, Wall Section, Riser) | B3 | Basement 3 - Promenade +887.750 |  | MicrosoftExcel | .ifc | Interior Design | S3 (Shared) | Suitable for Review and Comment | 1:2 | FI_60_15 | Clash Rendition | Fire & Life Safety
[6 empty] | BOQ | Bill of Quantities | ASM | Assets Management | 04 | Zone Sheet 4 | BLAD02 | Blade 02 | 4 | Large-scale Views (Enlarged Details) (Plans, Elevations, Stair Sections, etc) | FL | Foundation level |  | Navisworks | .pdf | Signage & Wayfinding | S4 (Shared) | Suitable for Review and Authorisation | 1:5 | FI_40_10 | Calculations | Interior Design
[6 empty] | BEP | BIM Execution Plan | AVL | Audio Visual | 05 | Zone Sheet 5 | BLAD03 | Blade 03 | 5 | Details (Any detail view, such as Wall / Floor / Manhole Detail, etc) | L1 | Lobby Level +905.0 |  | inDesign | .jpg | Public Interaction & Activation | S5 (Shared) | Suitable for Review and Acceptance | 1:10 | FI_90_72 | Report | Infrastructure
[6 empty] | BIM | BIM Model | AUV | Audio/Video | 06 | Zone Sheet 6 | BLAD04 | Blade 04 | 6 | Schedules and Diagrams | L2 | Theater Stalls +913.0 |  | Inviso | .xls | Structure | A1 (Published) | Authorised and Accepted-Concept Design | 1:20 | FI_10_90 | Transmittal | Landscape
[6 empty] | BRF | Brief | BRG | Bridges | 07 | Zone Sheet 7 | BLAD05 | Blade 05 | 7 | Combination of different views | L3 | Stalles Mezz & AD Theater +917.5 |  | JPG | .xer | Geotechnical Engineering | A2 (Published) | Authorised and Accepted-Schematic Design 100% | 1:25 | FI_90_47 | Log | Mechanical
[6 empty] | BUD | Budget | BRC | Broadcast | 08 | Zone Sheet 8 | MBLAD1 | Mini Blade 01 | 8 | User-Defined (For types that do not fall in other categories) | L4 | First Circle & AD Theater +921.0 |  | Recap | .dwf | Civil Engineering | A3 (Published) | Authorised and Accepted-Detailed Design 100% | 1:50 | FI_80_50 | Method statement | Structural
[6 empty] | CAL | Calculation | BIM | Building Information Modelling | 09 | Zone Sheet 9 | MBLAD4 | Mini Blade 04 | 9 | 3D Representation (Isometric, Perspectives, Photographes) | L5 | Second Circle & Loft |  | Rhino | .dwg | MEP Engineering | A4 (Published) | Authorised and Accepted-Tender | 1:100 | FI_90_64 | Plan
[6 empty] | CER | Certificate | BMS | Building Management System | 10 | Zone Sheet 10 | SECE001 | SEC Room |  |  | L6 | SKY Garden +935.85 |  | Sketchup | .bcf | Fire & Life Safety | A5 (Published) | Authorised and Accepted-IFC | 1:150
[6 empty] | COR | Change Order | CWC | Chilled Water / Cooling | 11 | Zone Sheet 11 | PARK01 | Parking Building |  |  | L8 | Royal Majlis +948.10M |  | Autocad | .3ds | Pitch Design & Sports Playing Surfaces | A6 (Published) | Authorised and Accepted-Construction (Shop Drawing) | 1:200
[6 empty] | CRA | Change Request Authorization | CIV | Civil | 12 | Zone Sheet 12 |  |  |  |  | M1 | Mez Upper Lobby +909.0 |  | ArcGIS | .skp | Specialist Lighting (Services and Systems) | A7 (Published) | Authorised and Accepted-As Built | 1:250
[6 empty] | CDT | Clash Detection Report | CPM | Contracts & Procurement | 13 | Zone Sheet 13 |  |  |  |  | M2 | Mez Loft MEP +931.10 |  |  | .docx | Acoustics | A8(Published) | Authorised and Accepted-In Use | 1:300
[6 empty] | CLM | Claim | CIN | Controls & Instrumentation | 14 | Zone Sheet 14 |  |  |  |  | RL | Roof Level |  |  | .rvt,.nwd,.ifc | AV / Broadcast |  |  | 1:350
[6 empty] | CIN | Client Instruction | CRE | Creative Designer | 15 | Zone Sheet 15 |  |  |  |  | ZZ | Overall |  |  | .nwc,.nwd,.ifc | Security |  |  | 1:500
[6 empty] | CRS | Comments Resolution Sheet | CDM | Crowd Management | 16 | Zone Sheet 16 | [8 empty] | .dwg,.nwc,.ifc | Vertical Transport
[6 empty] | CON | Contract | CUL | Culvert | 17 | Zone Sheet 17 | [8 empty] | .docx,.pdf | Facade & Roof Envelope
[6 empty] | COS | Cost Estimate | DRN | Drainage | 18 | Zone Sheet 18 | [8 empty] | .xer,.pdf | Crowd Modelling / Pedestrian Flow
[6 empty] | DAB | Dashboard | ELP | Earthing & Lighting Protection | 19 | Zone Sheet 19 | [8 empty] | .xls,.pdf | Sustainability
[6 empty] | DOA | Delegation of Authority | ELE | Electrical | 20 | Zone Sheet 20 | [8 empty] | .msp,.pdf | Accessibility
[6 empty] | DES | Design | ELC | Electrical Containment | 21 | Zone Sheet 21 | [8 empty] | .dwg,.pdf | Architect of Record
[6 empty] | MTX | Distribution Matrix | ENV | Environmental | 22 | Zone Sheet 22 | [8 empty] | .indd | Food & Beverage & Operations
[6 empty] | DSS | Dossier | EQP | Equipment | 23 | Zone Sheet 23 | [8 empty] | .pdf, .indd | Utilities, Roads & Infrastructure
[6 empty] | DRW | Drawing | FAC | Facade | 24 | Zone Sheet 24 | [8 empty] | .rvt,.nwc,.ifc | Traffic & Car Parking
[6 empty] | ENI | Engineer Instruction | FED | Federated | 25 | Zone Sheet 25 | [8 empty] | .gdb | Technology (ICT)
[6 empty] | EXP | Expenses | FIN | Finance | 26 | Zone Sheet 26 | [9 empty] | Sports & Specialist Lighting
[6 empty] | HOC | Handover Certificate | FAE | Fire Alarm & Emergency Lighting | 27 | Zone Sheet 27 | [9 empty] | BMS & Access Control
[6 empty] | IRT | Incident Report | FLS | Fire Life Safety | 28 | Zone Sheet 28 | [9 empty] | Waste Management
[6 empty] | ITP | Inspection & Test Plan | FPR | Fire Protection | [11 empty] | Health & Safety in Design
[6 empty] | INS | Instruction | FFE | Furniture Fixture & Equipment | [11 empty] | Wind
[6 empty] | IAB | Insurance and Bonds | GEN | General
[6 empty] | INV | Invoice | GIS | Geospatial Information System
[6 empty] | LAR | Laydown Area Access Request | GEH | Geotechnical & Hydraulics
[6 empty] | LTR | Letter | GRA | Graphics
[6 empty] | LIC | License | HSE | Health and Safety
[6 empty] | LST | List | EHV | High Voltage
[6 empty] | MAN | Manual | HVC | HVAC
[6 empty] | MPL | Master Plan | ICT | Information & Communication Technology
[6 empty] | MAR | Material Approval Request | INF | Infrastructure
[6 empty] | MIR | Material Inspection Request | INS | Installation
[6 empty] | MST | Method Statement | ITS | Intelligent Transportation System
[6 empty] | MOM | Minutes of Meeting | INT | Interior Design
[6 empty] | MIX | Mix Design | IRR | Irrigation
[6 empty] | MOD | Model | KNL | Kitchen & Laundry
[6 empty] | MRP | Monthly Report | LSE | Landscape
[6 empty] | NOC | No Objection Certificate | ELL | Lighting
[6 empty] | NCR | Non-Conformance Report | LTC | Lighting Control
[6 empty] | NDA | Non-Disclosure Agreement | ELV | Low Voltage
[6 empty] | NTC | Notice | LPG | LPG
[6 empty] | OMM | Operation & Maintenance Manual | MAR | Marine Engineering
[6 empty] | ORC | Organizational Chart | MPL | Master Planning
[6 empty] | OTR | Overtime Request | MEC | Mechanical
[6 empty] | PAP | Payment Application | EMV | Medium Voltage
[6 empty] | PYC | Payment Certificate | MEP | MEPF
[6 empty] | PRM | Permit | NTD | Non-Technical Document
[6 empty] | PAF | Personnel Approval Form | OSE | Operating Supplies and Equipment
[6 empty] | PIV | Photographs, Images & Videos | OTH | Others
[6 empty] | PLN | Plan | PLB | Plumbing
[6 empty] | PLT | Plant | PTW | Potable Water
[6 empty] | PPG | Policy & Procedure | PJC | Project Control
[6 empty] | PQS | Prequalification Submittal | QMS | Quality Management
[6 empty] | PRE | Presentation | RID | Rides
[6 empty] | PRO | Procedure | ERL | Road Lighting
[6 empty] | PEP | Project Execution Plan | RKW | Rockwork
[6 empty] | PRS | Proposal | SEC | Security System
[6 empty] | POR | Purchase Order | SEW | Sewage
[6 empty] | REG | Register | SHW | Show
[6 empty] | REP | Report | SGN | Signage / Wayfinding
[6 empty] | RFC | Request For Change | ESP | Small Power
[6 empty] | RSM | Resume | SSC | Smart City
[6 empty] | SVR | Safety Violation Report | SPL | Specialist Lighting
[6 empty] | SMP | Sample | SWD | Storm Water Drainage
[6 empty] | SCH | Schedule | STR | Structural
[6 empty] | SDW | Shop Drawing | SUR | Surveying / Mapping
[6 empty] | SIN | Site Instruction | SUS | Sustainability
[6 empty] | SOR | Site Observation Report | TEL | Telecommunication
[6 empty] | SPE | Specification | TNC | Testing/Commissioning
[6 empty] | STD | Standard | TFC | Traffic System
[6 empty] | SFA | Statement of Final Account | UTI | Utilities
[6 empty] | STR | Strategy | VNT | Ventilation Ductwork
[6 empty] | TOC | Taking Over Certificate | VTR | Vertical Transportation
[6 empty] | TOR | Task Order | VES | Voice Evacuation
[6 empty] | TEM | Template | WSM | Waste Management
[6 empty] | TDC | Tender Document | WTR | Water
[6 empty] | TRP | Test Report | CTV | CCTV System
[6 empty] | TMS | Time Sheet | ACS | Access Control System
[6 empty] | VOR | Variation Order | EFL | Facade Lighting
[6 empty] | WAR | Warranty / Guarantees | DES | Diesel
[6 empty] | WRP | Weekly Report | SMK | Smoke Ductwork
[6 empty] | WIR | Work Inspection Request | STL | Steel Structure
[6 empty] | RLM | RedLine Mark Drawing | FWR | Formwork
[6 empty] | MDP | Master Information Delivery Plan | ELS | Emergency Lighting system
[6 empty] | TDP | Task Information Delivery Plan | EBW | Electrical Builder Works
[8 empty] | MBW | Mechanical Builder Works
[8 empty] | EBC | Electrical Busway