## TIDP_Sheet
TASK INFORMATION DELIVERY PLAN (TIDP)
CLIENT | Qiddiya | #VALUE!
PROJECT | Qiddiya Performing Arts Center (QPAC)
ORGANISATION | Nesma & Partners
DISCIPLINE | Structural
APPROVER | BSBG
DATE CREATED
DATE LAST UPDATED
REVISION NUMBER | 00
DOCUMENT REFERENCE | QF01012-NES-C04518-TDP-XXX-00-000000-000001
This document shall be populated and kept up-to-date by the task team | [10 empty] | REFER TO THE FILE NAMING CONVENTION IN THE BIM EXECUTION PLAN | [10 empty] | DATA EXCHANGE #01 | [5 empty] | DATA EXCHANGE #02
[11 empty] | DOC REFERENCE GENERATOR | [10 empty] | STAGE: | CONSTRUCTION |  |  |  |  | STAGE: | HAND OVER
[22 empty] | PROGRAMME REF: | [5 empty] | PROGRAMME REF:
[5 empty] | EXCHANGE FORMATS | [5 empty] | FIELD 01 | FIELD 02 | FIELD 03 | FIELD 04 | FIELD 05 | FIELD 06 | FIELD 07 | FIELD 08 |  |  |  |  | LEVEL OF INFORMATION NEED | [5 empty] | LEVEL OF INFORMATION NEED
DOCUMENT NUMBER | DOCUMENT TITLE | EXTRACTED FROM MODEL | SCOPE AREA | AUTHORING SOFTWARE | EXCHANGE FORMAT | SCALE | DELIVERY MILESTONE | PACKAGE NAME | ACTIVITY ID | CLASSIFICATION CODE | PROJECT | ORIGINATOR | CONTRACT | DOCUMENT TYPE | DISCIPLINE | AREA/ZONE | VENUE/BUILDING | DRAWING TYPE | LEVEL | SEQUENCE NUMBER | CORPORATE DISCIPLINE | 01-AUTHOR | 01-GEOMETRICAL | 01-NON GEOMETRICAL | 01-DURATION (DAYS) | 01-PREDECESSOR | 01-EXCHANGE DATE | 02-AUTHOR | 02-GEOMETRICAL | 02-NON GEOMETRICAL | 02-DURATION (DAYS) | 02-PREDECESSOR | 02-EXCHANGE DATE
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0004 | BLADE 4 - Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0004 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0005 | BLADE 4 - Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0005 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0207 | BLADE 3 - +853.25M PRE-CAMBER VALUES (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-10-09 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0207 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0208 | BLADE 3 - +858.8M PRE-CAMBER VALUES (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-10-09 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0208 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0228 | BLADE 3 - FLOORING BEAMS DETAILS-3 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-10-09 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0228 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0002 | Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0001 | BL1 -Anchor Bolt Layout |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0002 | BL1 +876.25M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0003 | BL1 +882M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0004 | BL1 +887.75M PROMENADE |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0005 | BL1 +893.5M - B2 LEVEL |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0006 | BL1 +899.25M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0006 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0007 | BL1 +905M LOBBY LEVEL |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0007 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0008 | BL1 +910.75M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0008 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0009 | BL1 +917.5M STALLS MEZZANINE |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0009 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0010 | BL1 +922.25M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0010 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0012 | BL1 +935.85M SKY GARDEN |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0012 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0013 | BL1 +941.6M - LOADING PLAN |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-09 |  | QP.E.ST.GEN.GEN.1600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0013 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0014 | BL1 +944.85M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-09 |  | QP.E.ST.GEN.GEN.1600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0014 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0015 | BL1 +952.8M ROOF |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-09 |  | QP.E.ST.GEN.GEN.1600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0015 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0016 | BL1 +958.75M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-05 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0016 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0017 | BL1 +962.2M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-05 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0017 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0018 | BL1 -MINI BLADE +948M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-05 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0018 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0019 | BL1 -MINI BLADE +957M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-05 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0019 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0020 | BL1 -MINI BLADE +963M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-05 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0020 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0021 | BL1 +876.25M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0021 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0022 | BL1 +882M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0022 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0023 | BL1 +887.75M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0023 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0024 | BL1 +893.5M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0024 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0025 | BL1 +899.25M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0025 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0026 | BL1 +905M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0026 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0027 | BL1 +910.75M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0027 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0028 | BL1 +917.5M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0028 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0029 | BL1 +922.25M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0029 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0031 | BL1 +935.85M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0031 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0032 | BL1 +941.6M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-09 |  | QP.E.ST.GEN.GEN.1600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0032 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0033 | BL1 +944.85M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-09 |  | QP.E.ST.GEN.GEN.1600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0033 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0034 | BL1 +952.8M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-09 |  | QP.E.ST.GEN.GEN.1600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0034 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0035 | BL1 +958.75M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-05 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0035 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0036 | BL1 +962.2M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-05 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0036 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0201 | BLADE 3 - ELEVATIONS A (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0201 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0202 | BLADE 3 - ELEVATIONS B (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0202 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0203 | BLADE 3 - ELEVATIONS C (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0203 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0204 | BLADE 3 - ELEVATIONS D (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0204 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0205 | BLADE 3 - ELEVATIONS E (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0205 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0206 | BLADE 3 - ELEVATIONS F (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0206 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0207 | BLADE 3 - ELEVATIONS G (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0207 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0201 | BLADE 3 - OVERALL FRAMING KEY (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0201 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0202 | BLADE 3 - ELEVATOR COLUMNS KEY (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0202 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0203 | BLADE 3 - CORE ELEMENTS KEY (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0203 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0204 | BLADE 3 - COLUMN LAYOUT PLAN (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0204 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0205 | BLADE 3 - +853.25M LAYOUT (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0205 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0206 | BLADE 3 - +858.8M LAYOUT (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0206 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0214 | BLADE 3 - Anchor Bolt Support Detail MZJ10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0214 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0215 | BLADE 3 - Anchor Bolt Support Detail MZJ11 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0215 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0216 | BLADE 3 - Anchor Bolt Layout at +853.25M |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0216 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0229 | BLADE 3 - Anchor Bolt Details-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0229 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0230 | BLADE 3 - Anchor Bolt Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0230 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0231 | BLADE 3 - Anchor Bolt Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0231 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0232 | BLADE 3 - Anchor Bolt Details-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0232 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0003 | BLADE 3 -Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0217 | BLADE 3 - FACADE FRAME ELEMENTS DETAILS (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0217 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0218 | BLADE 3 - ELEVATOR COLUMNS DETAILS (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0218 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0219 | BLADE 3 - CORE ELEMENTS DETAILS-1 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0219 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0220 | BLADE 3 - CORE ELEMENTS DETAILS-2 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0220 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0221 | BLADE 3 - CORE ELEMENTS DETAILS-3 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0221 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0222 | BLADE 3 - CORE ELEMENTS DETAILS-4 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0222 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0223 | BLADE 3 - CORE ELEMENTS DETAILS-5 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0223 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0224 | BLADE 3 - CORE ELEMENTS DETAILS-6 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0224 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0225 | BLADE 3 - CORE ELEMENTS DETAILS-7 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0225 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0226 | BLADE 3 - FLOORING BEAMS DETAILS-1 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0226 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0227 | BLADE 3 - FLOORING BEAMS DETAILS-2 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0227 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1ZZ0013 | BL1 -FLOOR SLABS 3D VIEWS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-05 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | ZZ | 0013 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD01-1ZZ0014 | BL1 -OVERALL FRAMING KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-05 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | ZZ | 0014 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD01-1ZZ0015 | BL1 -CORE/FAÇADE FRAMING KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-05 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | ZZ | 0015 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD01-1ZZ0016 | BL1 -FLOOR/MINI BLADE FRAMING PLAN KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-05 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | ZZ | 0016 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0401 | BLADE 5 - ELEVATIONS A (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0401 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0402 | BLADE 5 - ELEVATIONS B (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0402 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0403 | BLADE 5 - ELEVATIONS C (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0403 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0404 | BLADE 5 - ELEVATIONS D (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0404 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0401 | BLADE 5 - 3D VIEW (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0401 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0402 | BLADE 5 - COLUMN LAYOUT PLAN (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0402 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0403 | BLADE 5 - +899.5M B1 PARKING (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0403 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0404 | BLADE 5 - +905M LOBBY LEVEL (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0404 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0415 | BLADE 5 - +899.5M B1 PARKING DETAILS-5 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0415 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0416 | BLADE 5 - +905M LOBBY LEVEL DETAILS-1 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0416 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0417 | BLADE 5 - +905M LOBBY LEVEL DETAILS-2 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0417 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0418 | BLADE 5 - +905M LOBBY LEVEL DETAILS-3 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0418 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0419 | BLADE 5 - +905M LOBBY LEVEL DETAILS-4 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0419 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0420 | BLADE 5 - +905M LOBBY LEVEL DETAILS-5 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0420 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0001 | BL1 -Anchor Bolt Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0002 | BL1 -Anchor Bolt Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0003 | BL1 -Anchor Bolt Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0004 | BL1 -Anchor Bolt Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0005 | BL1 -Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0006 | BL1 -Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0006 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0007 | BL1 -Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0007 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0008 | BL1 -Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0008 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0009 | BL1 -Details-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0009 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0010 | BL1 -Details-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0010 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0011 | BL1 -Details-7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0011 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0012 | BL1 -Details-8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0012 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0013 | BL1 -Details-9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0013 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0014 | BL1 -Details-10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1390 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0014 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0101 | BL2 -Anchor Bolt Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0101 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0102 | BL2 -Anchor Bolt Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0102 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0103 | BL2 -Anchor Bolt Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0103 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0104 | BL2 -Anchor Bolt Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0104 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0105 | BL2 -Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0105 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0106 | BL2 -Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0106 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0107 | BL2 -Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0107 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0108 | BL2 -Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0108 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0109 | BL2 -Details-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0109 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0110 | BL2 -Details-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0110 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0111 | BL2 -Details-7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0111 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0112 | BL2 -Details-8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0112 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0113 | BL2 -Details-9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0113 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0201 | BL3 -Anchor Bolt Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0201 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0202 | BL3 -Anchor Bolt Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0202 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0203 | BL3 -Anchor Bolt Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0203 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0204 | BL3 -Anchor Bolt Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0204 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0205 | BL3 -Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0205 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0206 | BL3 -Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0206 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0207 | BL3 -Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0207 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0208 | BL3 -Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0208 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0209 | BL3 -Details-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0209 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0210 | BL3 -Details-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0210 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0211 | BL3 -Details-7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0211 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0212 | BL3 -Details-8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0212 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0213 | BL3 -Details-9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0213 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0301 | BL4 -Anchor Bolt Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0301 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0302 | BL4 -Anchor Bolt Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0302 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0303 | BL4 -Anchor Bolt Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0303 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0304 | BL4 -Anchor Bolt Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0304 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0305 | BL4 -Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0305 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0306 | BL4 -Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0306 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0307 | BL4 -Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0307 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0308 | BL4 -Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0308 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0309 | BL4 -Details-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0309 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0310 | BL4 -Details-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0310 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0311 | BL4 -Details-7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0311 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0312 | BL4 -Details-8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0312 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0313 | BL4 -Details-9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0313 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0314 | BL4 -Details-10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0314 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0401 | BL5 -Anchor Bolt Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0401 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0402 | BL5 -Anchor Bolt Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0402 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0403 | BL5 -Anchor Bolt Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0403 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0404 | BL5 -Anchor Bolt Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0404 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0405 | BL5 -Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0405 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0406 | BL5 -Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0406 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0407 | BL5 -Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0407 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0408 | BL5 -Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0408 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0409 | BL5 -Details-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0409 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0410 | BL5 -Details-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0410 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0411 | BL5 -Details-7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-01-15 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0411 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0412 | BL5 -Details-8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0412 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0413 | BL5 -Details-9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0413 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0414 | BL5 -Details-10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-02-17 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0414 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0501 | Central Block -Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0501 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0502 | Central Block -Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0502 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0518 | Central Block -Details-18 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0518 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0519 | Central Block -Details-19 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0519 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0520 | Central Block -Details-20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0520 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0521 | Central Block -Details-21 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0521 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0522 | Central Block -Details-22 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0522 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0523 | Central Block -Details-23 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0523 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0524 | Central Block -Details-24 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0524 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0525 | Central Block -Details-25 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0525 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0526 | Central Block -Details-26 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0526 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0527 | Central Block -Details-27 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0527 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0528 | Central Block -Details-28 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0528 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0529 | Central Block -Details-29 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0529 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0530 | Central Block -Details-30 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-24 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0530 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0301 | BLADE 4 - ELEVATIONS A (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0301 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0302 | BLADE 4 - ELEVATIONS B (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0302 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0303 | BLADE 4 - ELEVATIONS C (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0303 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0304 | BLADE 4 - ELEVATIONS D (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0304 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0305 | BLADE 4 - ELEVATIONS E (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0305 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0306 | BLADE 4 - ELEVATIONS F (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0306 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0307 | BLADE 4 - ELEVATIONS G (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0307 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0309 | BLADE 4 - ELEVATIONS B (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0309 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0310 | BLADE 4 - ELEVATIONS C (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0310 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0311 | BLADE 4 - ELEVATIONS D (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0311 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0312 | BLADE 4 - ELEVATIONS E (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0312 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0313 | BLADE 4 - ELEVATIONS F (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0313 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0314 | BLADE 4 - ELEVATIONS G (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0314 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0301 | BLADE 4 - FACADE FRAME ELEMENTS KEY-1 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0301 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0302 | BLADE 4 - FACADE FRAME ELEMENTS KEY-2 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0302 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0303 | BLADE 4 - FLOORING BEAMS KEY (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0303 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0304 | BLADE 4 - ELEVATOR COLUMNS KEY (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0304 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0305 | BLADE 4 - CORE ELEMENTS KEY (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0305 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0306 | BLADE 4 - COLUMN LAYOUT PLAN (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0306 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0307 | BLADE 4 - +870.50M Layout (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0307 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0308 | BLADE 4 - +876.05M Layout (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0308 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0309 | BLADE 4 - +870.50M PRE-CAMBER VALUES (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0309 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0310 | BLADE 4 - +876.05M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0310 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0315 | BLADE 4 - CORE ELEMENTS DETAILS-2 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0315 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0316 | BLADE 4 - CORE ELEMENTS DETAILS-3 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0316 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0317 | BLADE 4 - CORE ELEMENTS DETAILS-4 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0317 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0318 | BLADE 4 - CORE ELEMENTS DETAILS-5 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0318 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0319 | BLADE 4 - CORE ELEMENTS DETAILS-6 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0319 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0320 | BLADE 4 - CORE ELEMENTS DETAILS-7 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0320 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0321 | BLADE 4 - CORE ELEMENTS DETAILS-8 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0321 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0322 | BLADE 4 - ELEVATOR COLUMNS DETAILS (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0322 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0323 | BLADE 4 - FLOORING BEAMS DETAILS-1 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0323 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0324 | BLADE 4 - FLOORING BEAMS DETAILS-2 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0324 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0325 | BLADE 4 - FLOORING BEAMS DETAILS-3 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0325 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0326 | BLADE 4 - FLOORING BEAMS DETAILS-4 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0326 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0405 | BLADE 5 - +899.5M PRE-CAMBER VALUES (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0405 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0406 | BLADE 5 - +905M PRE-CAMBER VALUES (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0406 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0327 | BLADE 4 - FLOORING BEAMS DETAILS-5 (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0327 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0209 | BLADE 3 - ELEVATIONS B (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0209 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0210 | BLADE 3 - ELEVATIONS C (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0210 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0211 | BLADE 3 - ELEVATIONS D (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0211 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0212 | BLADE 3 - ELEVATIONS E (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0212 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0213 | BLADE 3 - ELEVATIONS F (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0213 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0214 | BLADE 3 - ELEVATIONS G (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0214 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0209 | BLADE 3 - OVERALL FRAMING KEY (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0209 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0210 | BLADE 3 - ELEVATOR COLUMNS KEY (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0210 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0211 | BLADE 3 - CORE ELEMENTS KEY (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0211 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0212 | BLADE 3 - FLOORING BEAMS 3D (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0212 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0213 | BLADE 3 - +862.52M LAYOUT |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0213 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0214 | BLADE 3 - +867.42M LAYOUT |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0214 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0215 | BLADE 3 - +876.15M LAYOUT |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0215 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0216 | BLADE 3 - +881.65M LAYOUT |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0216 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0217 | BLADE 3 - +887.65M LAYOUT |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0217 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0218 | BLADE 3 - +862.52M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0218 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0219 | BLADE 3 - +867.42M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0219 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0220 | BLADE 3 - +876.15M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0220 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0221 | BLADE 3 - +881.65M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0221 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0222 | BLADE 3 - +887.65M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0222 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0235 | BLADE 3 - FACADE FRAME ELEMENTS DETAILS (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0235 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0236 | BLADE 3 - FACADE FRAME ELEMENTS DETAILS (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0236 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0237 | BLADE 3 - CORE ELEMENTS DETAILS-9 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0237 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0238 | BLADE 3 - CORE ELEMENTS DETAILS-10 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0238 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0239 | BLADE 3 - CORE ELEMENTS DETAILS-11 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0239 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0240 | BLADE 3 - CORE ELEMENTS DETAILS-12 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0240 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0241 | BLADE 3 - CORE ELEMENTS DETAILS-13 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0241 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0242 | BLADE 3 - CORE ELEMENTS DETAILS-14 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0242 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0243 | BLADE 3 - CORE ELEMENTS DETAILS-15 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0243 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0244 | BLADE 3 - CORE ELEMENTS DETAILS-16 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0244 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0245 | BLADE 3 - CORE ELEMENTS DETAILS-17 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0245 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0246 | BLADE 3 - CORE ELEMENTS DETAILS-18 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0246 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0247 | BLADE 3 - ELEVATOR COLUMNS DETAILS (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0247 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0248 | BLADE 3 - ELEVATOR COLUMNS DETAILS (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0248 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0249 | BLADE 3 - ELEVATOR COLUMNS DETAILS (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0249 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0250 | BLADE 3 - FLOORING BEAMS DETAILS-4 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0250 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0251 | BLADE 3 - FLOORING BEAMS DETAILS-5 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0251 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0252 | BLADE 3 - FLOORING BEAMS DETAILS-6 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0252 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0253 | BLADE 3 - FLOORING BEAMS DETAILS-7 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0253 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0254 | BLADE 3 - FLOORING BEAMS DETAILS-8 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0254 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0208 | BLADE 3 - ELEVATIONS A (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0208 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0308 | BLADE 4 - ELEVATIONS A (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0308 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0311 | BLADE 4 - CORE ELEMENTS KEY (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0311 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0312 | BLADE 4 - FLOORING BEAMS KEY (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0312 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0313 | BLADE 4 - +881.75M Layout (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0313 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0314 | BLADE 4 - +887.65M Layout (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0314 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0315 | BLADE 4 - +893.25M Layout (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0315 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0316 | BLADE 4 - +899.25M Layout (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0316 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0317 | BLADE 4 - +881.75M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0317 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0318 | BLADE 4 - +887.65M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0318 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0319 | BLADE 4 - +893.25M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0319 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0320 | BLADE 4 - +899.25M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0320 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0328 | BLADE 4 - FACADE FRAME ELEMENTS DETAILS-1 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0328 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0329 | BLADE 4 - FACADE FRAME ELEMENTS DETAILS-2 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0329 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0330 | BLADE 4 - CORE ELEMENTS DETAILS-1 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0330 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0331 | BLADE 4 - CORE ELEMENTS DETAILS-2 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0331 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0332 | BLADE 4 - CORE ELEMENTS DETAILS-3 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0332 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0333 | BLADE 4 - CORE ELEMENTS DETAILS-4 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0333 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0334 | BLADE 4 - CORE ELEMENTS DETAILS-5 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0334 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0335 | BLADE 4 - CORE ELEMENTS DETAILS-6 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0335 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0336 | BLADE 4 - CORE ELEMENTS DETAILS-7 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0336 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0337 | BLADE 4 - CORE ELEMENTS DETAILS-8 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0337 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0338 | BLADE 4 - CORE ELEMENTS DETAILS-9 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0338 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0339 | BLADE 4 - CORE ELEMENTS DETAILS-10 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0339 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0340 | BLADE 4 - CORE ELEMENTS DETAILS-11 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0340 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0341 | BLADE 4 - CORE ELEMENTS DETAILS-12 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0341 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0342 | BLADE 4 - ELEVATOR COLUMNS DETAILS (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0342 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0343 | BLADE 4 - FLOORING BEAMS DETAILS-1 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0343 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0344 | BLADE 4 - FLOORING BEAMS DETAILS-2 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0344 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0345 | BLADE 4 - FLOORING BEAMS DETAILS-3 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0345 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0346 | BLADE 4 - FLOORING BEAMS DETAILS-4 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0346 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0347 | BLADE 4 - FLOORING BEAMS DETAILS-5 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0347 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0348 | BLADE 4 - FLOORING BEAMS DETAILS-6 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0348 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0405 | BLADE 5 - ELEVATIONS A (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0405 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0406 | BLADE 5 - ELEVATIONS B (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0406 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0407 | BLADE 5 - ELEVATIONS C (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0407 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0407 | BLADE 5 - 3D VIEW (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0407 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0408 | BLADE 5 - +910.65M (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0408 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0409 | BLADE 5 - +917.4M (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0409 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0410 | BLADE 5 - +910.65M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0410 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0411 | BLADE 5 - +917.4M PRE-CAMBER VALUES (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0411 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0421 | BLADE 5 - +910.65M DETAILS-1 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0421 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0422 | BLADE 5 - +910.65M DETAILS-2 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0422 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0423 | BLADE 5 - +910.65M DETAILS-3 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0423 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0424 | BLADE 5 - +910.65M DETAILS-4 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0424 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0425 | BLADE 5 - +910.65M DETAILS-5 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0425 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0426 | BLADE 5 - +917.4M DETAILS-1 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0426 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0427 | BLADE 5 - +917.4M DETAILS-2 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0427 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0428 | BLADE 5 - +917.4M DETAILS-3 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0428 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0429 | BLADE 5 - +917.4M DETAILS-4 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0429 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0430 | BLADE 5 - +917.4M DETAILS-5 (BATCH 1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0430 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0601 | L1 LOBBY & PLAZA - SECTIONS SHEET 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0601 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0602 | L1 LOBBY & PLAZA - SECTIONS SHEET 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0602 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0603 | L1 LOBBY & PLAZA - SECTIONS SHEET 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0603 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0604 | L1 LOBBY & PLAZA - SECTIONS SHEET 4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0604 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0601 | B1 LOBBY & PLAZA - ANCHOR BOLTS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0601 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0602 | L1 LOBBY & PLAZA - ANCHOR BOLTS SHEET 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0602 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0603 | L1 LOBBY & PLAZA - ANCHOR BOLTS SHEET 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0603 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0604 | L1 LOBBY & PLAZA - ANCHOR BOLTS SHEET 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0604 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0605 | L1 LOBBY & PLAZA - ANCHOR BOLTS SHEET 4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0605 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0606 | L1 MEZZANINE LOBBY & PLAZA - ANCHOR BOLTS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0606 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0601 | B1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0601 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0602 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0602 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0603 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0603 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0604 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0604 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0605 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0605 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0606 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0606 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0607 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0607 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0608 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0608 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0609 | L1 MEZZANINE LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0609 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0610 | B1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0610 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0006 | BLADE 5 - Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0006 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0007 | BLADE 5 - Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0007 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0015 | BLADE 1 - Anchor Bolt Support Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0015 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0016 | BLADE 1 - Anchor Bolt Support Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0016 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0017 | BLADE 1 - Anchor Bolt Support Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0017 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0018 | BLADE 1 - Anchor Bolt Support Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0018 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0019 | BLADE 1 - Anchor Bolt Support Details-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0019 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0020 | BLADE 1 - Anchor Bolt Support Details-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0020 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0021 | BLADE 1 - Anchor Bolt Support Details-7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0021 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0022 | BLADE 1 - Anchor Bolt Support Details-8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0022 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0023 | BLADE 1 - Anchor Bolt Support Details-9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0023 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0101 | BLADE 2 - Anchor Bolt 3D view |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0101 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0408 | BLADE 5 - ELEVATIONS A (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0408 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0409 | BLADE 5 - ELEVATIONS B (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0409 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0410 | BLADE 5 - ELEVATIONS C (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0410 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0411 | BLADE 5 - ELEVATIONS A (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0411 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0412 | BLADE 5 - ELEVATIONS B (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0412 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0413 | BLADE 5 - ELEVATIONS C (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0413 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0417 | BLADE 5 - +922.15M (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0417 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0418 | BLADE 5 - +927.9M (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0418 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0419 | BLADE 5 - 3D VIEW (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0419 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0420 | BLADE 5 - +922.15M PRE-CAMBER VALUES (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0420 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0421 | BLADE 5 - +927.9M PRE-CAMBER VALUES (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0421 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0422 | BLADE 5 - +935.75M (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0422 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0423 | BLADE 5 - 3D VIEW (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0423 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0424 | BLADE 5 - +935.75M PRE-CAMBER VALUES (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0424 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0425 | BLADE 5 - +932.20M (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0425 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0431 | BLADE 5 - +922.15M DETAILS-1 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0431 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0432 | BLADE 5 - +922.15M DETAILS-2 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0432 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0433 | BLADE 5 - +922.15M DETAILS-3 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0433 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0434 | BLADE 5 - +922.15M DETAILS-4 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0434 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0435 | BLADE 5 - +922.15M DETAILS-5 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0435 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0436 | BLADE 5 - +927.9M DETAILS-1 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0436 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0437 | BLADE 5 - +927.9M DETAILS-2 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0437 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0438 | BLADE 5 - +927.9M DETAILS-3 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0438 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0439 | BLADE 5 - +927.9M DETAILS-4 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0439 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0440 | BLADE 5 - +927.9M DETAILS-5 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0440 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0441 | BLADE 5 - +935.75M DETAILS-1 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0441 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0442 | BLADE 5 - +935.75M DETAILS-2 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0442 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0443 | BLADE 5 - +935.75M DETAILS-3 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0443 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0444 | BLADE 5 - +935.75M DETAILS-4 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0444 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0445 | BLADE 5 - +935.75M DETAILS-5 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0445 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0235 | BLADE 5-Welding Details-sheet 33 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0235 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0236 | BLADE 5-Welding Details-sheet 34 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0236 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0238 | BLADE 5-Welding Details-sheet 36 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0238 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0239 | BLADE 5-Welding Details-sheet 37 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0239 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0240 | BLADE 5-Welding Details-sheet 38 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0240 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0241 | BLADE 5-Welding Details-sheet 39 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0241 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0242 | BLADE 5-Welding Details-sheet 40 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0242 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0243 | BLADE 5-Welding Details-sheet 41 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0243 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0244 | BLADE 5-Welding Details-sheet 42 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0244 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0245 | BLADE 5-Welding Details-sheet 43 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0245 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0246 | BLADE 5-Welding Details-sheet 44 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0246 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0247 | BLADE 5-Welding Details-sheet 45 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0247 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0248 | BLADE 5-Welding Details-sheet 46 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0248 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0249 | BLADE 5-Welding Details-sheet 47 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0249 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0253 | BLADE 5-Welding Details-sheet 51 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0253 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0254 | BLADE 5-Welding Details-sheet 52 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0254 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0255 | BLADE 5-Welding Details-sheet 53 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0255 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0256 | BLADE 5-Welding Details-sheet 54 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0256 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0257 | BLADE 5-Welding Details-sheet 55 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0257 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0258 | BLADE 5-Welding Details-sheet 56 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0258 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0611 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 11 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0611 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0612 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 12 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0612 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0613 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 13 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0613 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0614 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 14 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0614 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0615 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 15 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0615 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0616 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 16 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0616 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0617 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 17 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0617 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0223 | BL3 +853.25M Temporary Support Layout |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0223 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0224 | BL3 +858.8M Temporary Support Layout |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0224 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0225 | BL3 +867.42M Temporary Support Layout |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0225 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0226 | BL3 +876.15M Temporary Support Layout |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0226 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0227 | BL3 +887.65M Temporary Support Layout |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0227 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0321 | BLADE4 - +870.50 M Temporary Support Layout |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0321 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0322 | BLADE4 - +876.05 M Temporary Support Layout |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0322 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0323 | BLADE4 - +887.65 M Temporary Support Layout |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0323 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0324 | BLADE4 - +899.25 M Temporary Support Layout |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0324 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0349 | BLADE4 -TEMPORARY SUPPORT DETAILS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0349 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0412 | BLADE 5 - Temporary Support (BATCH 1.1&1.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0412 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0501 | TRUSS BELOW SIDE AND BACK STAGE - SECTION SHEET 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0501 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0502 | TRUSS BELOW SIDE AND BACK STAGE - SECTION SHEET 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0502 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0503 | TRUSS BELOW SIDE AND BACK STAGE - SECTION SHEET 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0503 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0504 | TRUSS BELOW SIDE AND BACK STAGE - SECTION SHEET 4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0504 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0505 | TRUSS BELOW SIDE AND BACK STAGE - SECTION SHEET 5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0505 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0506 | TRUSS BELOW SIDE AND BACK STAGE - SECTION SHEET 6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0506 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0501 | TRUSS BELOW SIDE AND BACK STAGE - ANCHOR BOLT SHEET 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0501 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0502 | TRUSS BELOW SIDE AND BACK STAGE - ANCHOR BOLT SHEET 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0502 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0503 | TRUSS BELOW SIDE AND BACK STAGE - ANCHOR BOLT SHEET 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0503 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0504 | TRUSS BELOW SIDE AND BACK STAGE - LAYOUT PLAN SHEET 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0504 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0505 | TRUSS BELOW SIDE AND BACK STAGE - LAYOUT PLAN SHEET 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0505 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0506 | TRUSS BELOW SIDE AND BACK STAGE - LAYOUT PLAN SHEET 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0506 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0215 | BLADE 3 - ELEVATIONS A (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0215 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0216 | BLADE 3 - ELEVATIONS B (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0216 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0217 | BLADE 3 - ELEVATIONS C (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0217 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0218 | BLADE 3 - ELEVATIONS D (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0218 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0219 | BLADE 3 - ELEVATIONS E (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0219 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0220 | BLADE 3 - ELEVATIONS F (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0220 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0221 | BLADE 3 - ELEVATIONS G (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0221 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0234 | BLADE 3 - CORE ELEMENTS KEY (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0234 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0235 | BLADE 3 - CORE ELEMENTS KEY (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0235 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0236 | BLADE 3 - FACADE FRAMING KEY (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0236 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0237 | BLADE 3 - FACADE FRAMING KEY (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0237 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0238 | BLADE 3 - ELEVATOR COLUMNS KEY (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0238 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0239 | BLADE 3 - ELEVATOR COLUMNS KEY (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0239 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0240 | BLADE 3 - +894.48M LAYOUT |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0240 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0241 | BLADE 3 - +900.23M LAYOUT |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0241 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0242 | BLADE 3 - +904.9M LAYOUT |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0242 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0243 | BLADE 3 - +910.65M LAYOUT |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0243 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0244 | BLADE 3 - +894.48M PRE-CAMBER VALUES (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0244 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0245 | BLADE 3 - +900.23M PRE-CAMBER VALUES (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0245 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0246 | BLADE 3 - +904.9M PRE-CAMBER VALUES (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0246 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0247 | BLADE 3 - +910.65M PRE-CAMBER VALUES (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0247 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0255 | BLADE 3 - CORE ELEMENTS DETAILS-19 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0255 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0256 | BLADE 3 - CORE ELEMENTS DETAILS-20 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0256 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0257 | BLADE 3 - CORE ELEMENTS DETAILS-21 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0257 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0258 | BLADE 3 - CORE ELEMENTS DETAILS-22 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0258 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0259 | BLADE 3 - CORE ELEMENTS DETAILS-23 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0259 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0260 | BLADE 3 - CORE ELEMENTS DETAILS-24 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0260 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0261 | BLADE 3 - CORE ELEMENTS DETAILS-25 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0261 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0262 | BLADE 3 - CORE ELEMENTS DETAILS-26 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0262 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0263 | BLADE 3 - CORE ELEMENTS DETAILS-27 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0263 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0264 | BLADE 3 - CORE ELEMENTS DETAILS-28 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0264 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0265 | BLADE 3 - CORE ELEMENTS DETAILS-29 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0265 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0266 | BLADE 3 - CORE ELEMENTS DETAILS-30 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0266 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0267 | BLADE 3 - CORE ELEMENTS DETAILS-31 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0267 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0268 | BLADE 3 - CORE ELEMENTS DETAILS-32 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0268 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0269 | BLADE 3 - CORE ELEMENTS DETAILS-33 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0269 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0270 | BLADE 3 - CORE ELEMENTS DETAILS-34 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0270 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0271 | BLADE 3 - CORE ELEMENTS DETAILS-35 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0271 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0272 | BLADE 3 - CORE ELEMENTS DETAILS-36 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0272 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0273 | BLADE 3 - CORE ELEMENTS DETAILS-37 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0273 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0274 | BLADE 3 - CORE ELEMENTS DETAILS-38 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0274 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0275 | BLADE 3 - ELEVATOR COLUMNS DETAILS (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0275 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0276 | BLADE 3 - ELEVATOR COLUMNS DETAILS (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0276 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0277 | BLADE 3 - ELEVATOR COLUMNS DETAILS (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0277 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0278 | BLADE 3 - ELEVATOR COLUMNS DETAILS (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0278 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0279 | BLADE 3 - FACADE FRAME ELEMENTS DETAILS (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0279 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0280 | BLADE 3 - FACADE FRAME ELEMENTS DETAILS (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0280 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0281 | BLADE 3 - FACADE FRAME ELEMENTS DETAILS (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0281 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0282 | BLADE 3 - FACADE FRAME ELEMENTS DETAILS (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0282 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0283 | BLADE 3 - FLOORING BEAMS DETAILS-9 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0283 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0284 | BLADE 3 - FLOORING BEAMS DETAILS-10 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0284 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0285 | BLADE 3 - FLOORING BEAMS DETAILS-11 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0285 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0286 | BLADE 3 - FLOORING BEAMS DETAILS-12 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0286 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0287 | BLADE 3 - FLOORING BEAMS DETAILS-13 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0287 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0288 | BLADE 3 - FLOORING BEAMS DETAILS-14 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0288 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0289 | BLADE 3 - FLOORING BEAMS DETAILS-15 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0289 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0290 | BLADE 3 - FLOORING BEAMS DETAILS-16 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0290 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0291 | BLADE 3 - FLOORING BEAMS DETAILS-17 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0291 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0292 | BLADE 3 - FLOORING BEAMS DETAILS-18 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0292 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0293 | BLADE 3 - FLOORING BEAMS DETAILS-19 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0293 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0294 | BLADE 3 - FLOORING BEAMS DETAILS-20 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0294 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0295 | BLADE 3 - FLOORING BEAMS DETAILS-21 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0295 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0296 | BLADE 3 - FLOORING BEAMS DETAILS-22 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0296 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0297 | BLADE 3 - FLOORING BEAMS DETAILS-23 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0297 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0298 | BLADE 3 - FLOORING BEAMS DETAILS-24 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0298 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0426 | BLADE 5 - FACADE FRAME ELEMENTS (BATCH2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0426 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0427 | BLADE 5 - +932.20M (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0427 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0428 | BLADE 5 - +935.75M (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0428 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0429 | BLADE 5 - +935.75M MAIN BEAMS (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0429 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0430 | BLADE 5 - +935.75M SECONDARY BEAMS (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0430 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0431 | BLADE 5 - +935.75M PRE-CAMBER VALUES (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0431 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0446 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-6 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0446 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0447 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-7 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0447 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0448 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-8 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0448 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0449 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-9 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0449 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0450 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-10 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0450 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0451 | BLADE 5 - +927.9M MAIN BEAMS DETAILS-1 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0451 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0452 | BLADE 5 - +927.9M MAIN BEAMS DETAILS-2 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0452 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0453 | BLADE 5 - +927.9M MAIN BEAMS DETAILS-3 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0453 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0454 | BLADE 5 - +927.9M MAIN BEAMS DETAILS-4 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0454 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0455 | BLADE 5 - +927.9M SECONDARY BEAMS DETAILS-1 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0455 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0456 | BLADE 5 - +927.9M SECONDARY BEAMS DETAILS-2 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0456 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0457 | BLADE 5 - +927.9M SECONDARY BEAMS DETAILS-3 (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0457 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0458 | BLADE 5 - CORE ELEMENTS DETAILS-1 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0458 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0459 | BLADE 5 - CORE ELEMENTS DETAILS-2 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0459 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0460 | BLADE 5 - CORE ELEMENTS DETAILS-3 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0460 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0461 | BLADE 5 - CORE ELEMENTS DETAILS-4 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0461 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0462 | BLADE 5 - CORE ELEMENTS DETAILS-5 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0462 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0463 | BLADE 5 - CORE ELEMENTS DETAILS-6 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0463 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0464 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-1 (BATCH2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0464 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0465 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-2 (BATCH2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0465 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0466 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-3 (BATCH2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0466 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0467 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-4 (BATCH2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0467 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0468 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-5 (BATCH2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0468 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0469 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-6 (BATCH2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0469 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0470 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-7 (BATCH2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0470 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0471 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-8 (BATCH2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0471 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0472 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-9 (BATCH2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0472 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0473 | BLADE 5 - FACADE FRAME ELEMENTS DETAILS-10 (BATCH2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0473 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0474 | BLADE 5 - +935.75M MAIN BEAMS DETAILS-1 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0474 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0475 | BLADE 5 - +935.75M MAIN BEAMS DETAILS-2 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0475 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0476 | BLADE 5 - +935.75M MAIN BEAMS DETAILS-3 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0476 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0477 | BLADE 5 - +935.75M MAIN BEAMS DETAILS-4 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0477 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0478 | BLADE 5 - +935.75M MAIN BEAMS DETAILS-5 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0478 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0479 | BLADE 5 - +935.75M SECONDARY BEAMS DEITAILS-1(BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0479 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0480 | BLADE 5 - +935.75M SECONDARY BEAMS DEITAILS-2 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0480 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0481 | BLADE 5 - +935.75M SECONDARY BEAMS DEITAILS-3 (BATCH 2.2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0481 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0322 | BLADE 5-Welding Details-sheet 57 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0322 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0330 | BLADE 5-Welding Details-sheet 58 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0330 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0331 | BLADE 5-Welding Details-sheet 59 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0331 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0332 | BLADE 5-Welding Details-sheet 60 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0332 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0333 | BLADE 5-Welding Details-sheet 61 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0333 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0334 | BLADE 5-Welding Details-sheet 62 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0334 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0335 | BLADE 5-Welding Details-sheet 63 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0335 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0336 | BLADE 5-Welding Details-sheet 64 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0336 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0337 | BLADE 5-Welding Details-sheet 65 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0337 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-2ZZ0037 | BLADE 1 +962.2M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-16 |  | QP.E.ST.GEN.GEN.1680 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 2 | ZZ | 0037 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0102 | BLADE 2 -Anchor Bolt Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0102 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0103 | BLADE 2 -Anchor Bolt Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0103 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0104 | BLADE 2 -Anchor Bolt Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0104 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0105 | BLADE 2 -Anchor Bolt Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0105 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0106 | BLADE 2 +882M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0106 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0107 | BLADE 2 +887.75M PROMENADE |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0107 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0108 | BLADE 2 +893.5M - B2 SERVICE |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-26 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0108 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0109 | BLADE 2 +899.25M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-26 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0109 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0110 | BLADE 2 +905M LOBBY LEVEL |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0110 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0111 | BLADE 2 +910.75M |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0111 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0112 | BLADE 2 +916.5M STALLS MEZZANINE |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0112 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0113 | BLADE 2 +922.25M |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0113 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0114 | BLADE 2 +928M LOFT |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0114 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0115 | BLADE 2 +935.85M SKY GARDEN |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0115 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0116 | BLADE 2 +941.6M |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0116 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0117 | BLADE 2 +944.85M |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0117 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0118 | BLADE 2 +948.1M L8 ROYAL MAJLIS |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0118 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0119 | BLADE 2 +951.1M |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0119 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0120 | BLADE 2 -ROOF +953M |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0120 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0121 | BLADE 2 -ROOF +954M |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0121 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0122 | BLADE 2 +882M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0122 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0123 | BLADE 2 +887.75M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0123 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0124 | BLADE 2 +893.5M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0124 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0125 | BLADE 2 +899.25M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0125 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0126 | BLADE 2 +905M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0126 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0127 | BLADE 2 +910.75M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0127 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0128 | BLADE 2 +916.5M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0128 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0129 | BLADE 2 +922.25M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0129 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0130 | BLADE 2 +928M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0130 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0131 | BLADE 2 +935.85M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-03 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0131 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0132 | BLADE 2 +941.6M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0132 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0133 | BLADE 2 +944.85M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0133 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0134 | BLADE 2 +948.1M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0134 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-2ZZ0135 | BLADE 2 +951.1M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 2 | ZZ | 0135 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0230 | BLADE 3 +893.5M - B2 SERVICE |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-06 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0230 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0231 | BLADE 3 +899.25M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-06 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0231 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0232 | BLADE 3 +905M LOBBY LEVEL |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-06 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0232 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0233 | BLADE 3 +910.75M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-06 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0233 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0248 | BLADE 3 +921M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-06 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0248 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD03-2ZZ0249 | BLADE 3 +928M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-06 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 2 | ZZ | 0249 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0329 | BLADE 4 +905M LOBBY LEVEL |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0329 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0330 | BLADE 4 +905M LOBBY LEVEL |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0330 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0331 | BLADE 4 +910.75M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0331 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0332 | BLADE 4 +916.5M STALLS MEZZANINE |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0332 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0333 | BLADE 4 +922.25M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0333 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0334 | BLADE 4 +928M LOFT |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-10 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0334 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0335 | BLADE 4 +935.85M SKY GARDEN |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-10 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0335 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0336 | BLADE 4 +941.6M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0336 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0337 | BLADE 4 +947.35M MEP SERVICE |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0337 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0338 | BLADE 4 +950.65M MEP TOP OF LIFT |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0338 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0339 | BLADE 4 -MINI BLADE +947.35M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0339 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0340 | BLADE 4 -MINI BLADE +956M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0340 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0347 | BLADE 4 +905M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0347 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0348 | BLADE 4 +910.75M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0348 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0349 | BLADE 4 +916.5M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0349 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0350 | BLADE 4 +922.25M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0350 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0351 | BLADE 4 +928M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-10 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0351 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0352 | BLADE 4 +935.85M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-10 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0352 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0353 | BLADE 4 +941.6M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0353 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0354 | BLADE 4 +947.35M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0354 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD04-2ZZ0355 | BLADE 4 +950.65M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-03 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 2 | ZZ | 0355 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0439 | BLADE 5 +941.6M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0439 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0440 | BLADE 5 +944.6M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0440 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0441 | BLADE 5 +948.1M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0441 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0442 | BLADE 5 +954M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0442 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0443 | BLADE 5 +957.15M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0443 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-2ZZ0444 | BLADE 5 +960M - Decking Plan |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 2 | ZZ | 0444 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0507 | STALL MEZZANINE & ADAPTABLE THEATRE +917.5M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-27 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0507 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0508 | FIRST CIRCLE & ADAPTABLE THEATRE +921M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-27 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0508 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0509 | SECOND CIRCLE & LOFT +928M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-04 |  | QP.E.ST.GEN.GEN.1470 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0509 | Structural | JINGGONG | LOD400 |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0510 | SKY GARDEN +935.85M |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-18 |  | QP.E.ST.GEN.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0510 | Structural | JINGGONG | LOD400 |  |  |  | 2026-02-09
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0511 | ENLARGED PLAN - BLADE FOUNDATION A |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0511 | Structural | JINGGONG | LOD400 |  |  |  | 2026-02-09
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0512 | ENLARGED PLAN - BLADE FOUNDATION B |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0512 | Structural | JINGGONG | LOD400 |  |  |  | 2026-02-09
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0513 | Royal Majlis |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0513 | Structural | JINGGONG | LOD400 |  |  |  | 2027-01-06
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0514 | Royal Majlis |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0514 | Structural | JINGGONG | LOD400 |  |  |  | 2027-01-06
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0515 | Royal Majlis |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0515 | Structural | JINGGONG | LOD400 |  |  |  | 2027-01-06
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0516 | Royal Majlis |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0516 | Structural | JINGGONG | LOD400 |  |  |  | 2027-01-06
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0517 | ENLARGED PLAN - B3 PROMENADE |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0517 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0518 | ENLARGED PLAN - B2 SERVICE A |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0518 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0519 | ENLARGED PLAN - B2 SERVICE B |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0519 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0520 | ENLARGED PLAN - AMPHITHEATRE BOTTOM SLAB |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0520 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0521 | ENLARGED PLAN - B1 SERVICE A |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0521 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0522 | ENLARGED PLAN - B1 SERVICE B |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0522 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0651 | BACKSTAGE DRESSING AREA - ANCHOR BOLTS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-02 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0651 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0526 | ENLARGED PLAN - AMPHITHEATRE MID SLAB |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0526 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0527 | ENLARGED PLAN - LOBBY MEZZANINE |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-04 |  | QP.E.ST.GEN.GEN.1660 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0527 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0528 | ENLARGED PLAN - STALLS & ADAPTABLE THEATRE |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-13 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0528 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0529 | ENLARGED PLAN - L3 MEZZANINE & ADAPTABLE THEATRE |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-13 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0529 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0530 | ENLARGED PLAN - 1ST CIRCLE & ADAPTABLE THEATRE |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-13 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0530 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0531 | ENLARGED PLAN - 1ST CIRCLE & ADAPTABLE THEATRE UPPER BALCONIES |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-13 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0531 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0532 | ENLARGED PLAN - LOFT A |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-28 |  | QP.E.ST.GEN.GEN.1520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0532 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0533 | ENLARGED PLAN - LOFT B |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-28 |  | QP.E.ST.GEN.GEN.1520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0533 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0534 | LOFT & SKY GARDEN - TABLES AND DETAILS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-28 |  | QP.E.ST.GEN.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0534 | Structural | JINGGONG | LOD400 |  |  |  | 2026-02-09
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0535 | ENLARGED PLAN - REHEARSAL AND FLYTOWER ROOF |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-18 |  | QP.E.ST.GEN.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0535 | Structural | JINGGONG | LOD400 |  |  |  | 2026-02-09
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0536 | ENLARGED PLAN - L5.5 LOFT MEP |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-04 |  | QP.E.ST.GEN.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0536 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0537 | ENLARGED PLAN - STAGE ROOF |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-27 |  | QP.E.ST.GEN.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0537 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0538 | ENLARGED PLAN - SLAB AT LEVEL +939.150 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-23 |  | QP.E.ST.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0538 | Structural | JINGGONG | LOD400 |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0539 | ENLARGED PLAN - SKY GARDEN A |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-03-22 |  | QP.E.ST.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0539 | Structural | JINGGONG | LOD400 |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0540 | ENLARGED PLAN - SKY GARDEN B |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-03-22 |  | QP.E.ST.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0540 | Structural | JINGGONG | LOD400 |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0541 | ENLARGED PLAN - ROYAL MAJLIS |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-04-17 |  | QP.E.ST.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0541 | Structural | JINGGONG | LOD400 |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0542 | GUARD ROOM AND RMU DETAILS |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-04-17 |  | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0542 | Structural | JINGGONG | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0543 | LINK BRIDGE #1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0543 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0544 | LINK BRIDGE #2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-08 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0544 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0545 | LINK BRIDGE #3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-02 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0545 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0546 | LINK BRIDGE #4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-02 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0546 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0547 | LINK BRIDGE #5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-03-22 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0547 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0548 | LINK BRIDGE #6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-03-22 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0548 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0549 | LINK BRIDGE #7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-03-22 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0549 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0550 | LINK BRIDGE #8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-03-22 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0550 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0551 | TRUSS BELOW AUDITORIUM - ANCHOR BOLT DETAILS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-31 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0551 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0552 | TRUSS BELOW AUDITORIUM - UPPER SLAB |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-31 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0552 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0553 | TRUSS BELOW AUDITORIUM - DOWN SLAB |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-31 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0553 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0554 | LINK BRIDGE #12 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-04-08 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0554 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0555 | LINK BRIDGE #13 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-04-08 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0555 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0556 | PT CATWALK BRIDGE DETAILS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-12-04 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0556 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0557 | HELIX STAIR PLANS AND ELEVATIONS |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-23 |  | QP.E.ST.GEN.GEN.1570 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0557 | Structural | JINGGONG | LOD400 |  |  |  | 2026-12-05
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0101 | BLADE 2 -CORE ELEV -01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0101 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0102 | BLADE 2 -CORE ELEV -02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0102 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0103 | BLADE 2 -CORE ELEV -03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0103 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0104 | BLADE 2 -CORE ELEV -04 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0104 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0105 | BLADE 2 -CORE ELEV -05 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0105 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0106 | BLADE 2 -CORE ELEV -06 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0106 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0107 | BLADE 2 -SIDE ELEV -01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0107 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0108 | BLADE 2 -SIDE ELEV -02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0108 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0109 | BLADE 2 -SIDE ELEV -03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0109 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0110 | BLADE 2 -SIDE ELEV -04 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0110 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0111 | BLADE 2 -FEATURE STAIR-01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0111 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0112 | BLADE 2 -FEATURE STAIR-02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0112 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0113 | BLADE 2 -FEATURE STAIR-03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.2200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0113 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0114 | BLADE 2 -FLOOR SLABS 3D VIEWS |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0114 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0115 | BLADE 2 -OVERALL FRAMING KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0115 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-1ZZ0116 | BLADE 2 -CORE/FAÇADE/FLOOR FRAMING KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | ZZ | 0116 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0222 | BLADE 3 -OVERALL FRAMING KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-06 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0222 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1ZZ0223 | BLADE 3 -CORE/FAÇADE/FLOOR FRAMING KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-06 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | ZZ | 0223 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0315 | BLADE 4 - ELEVATIONS A (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0315 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0316 | BLADE 4 - ELEVATIONS B (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0316 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0317 | BLADE 4 - ELEVATIONS C (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0317 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0318 | BLADE 4 - ELEVATIONS D (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0318 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0319 | BLADE 4 - ELEVATIONS E (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0319 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0320 | BLADE 4 - ELEVATIONS F (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0320 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0321 | BLADE 4 - ELEVATIONS G (BATCH 2.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1210 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0321 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0322 | BLADE 4 -FEATURE STAIR-01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0322 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0323 | BLADE 4 -FEATURE STAIR-02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0323 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0324 | BLADE 4 -FLOOR SLABS 3D VIEWS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0324 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0325 | BLADE 4 -OVERALL FRAMING KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0325 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0326 | BLADE 4 -CORE/FAÇADE/FLOOR FRAMING KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0326 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-1ZZ0327 | BLADE 4 -FLOOR MINI BLADE FRAMING KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | ZZ | 0327 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0414 | BLADE 5 -CORE ELEV -02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0414 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0415 | BLADE 5 -CORE ELEV -03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0415 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0416 | BLADE 5 -CORE ELEV -04 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0416 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0417 | BLADE 5 -CORE ELEV -05 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0417 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0418 | BLADE 5 -CORE ELEV -06 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0418 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0419 | BLADE 5 -SIDE ELEV -01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0419 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0420 | BLADE 5 -SIDE ELEV -02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0420 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0421 | BLADE 5 -SIDE ELEV -03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0421 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0422 | BLADE 5 -SIDE ELEV -04 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0422 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0423 | BLADE 5 -FEATURE STAIR-01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0423 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0424 | BLADE 5 -FLOOR SLABS 3D VIEWS |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0424 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0425 | BLADE 5 -OVERALL FRAMING KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0425 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-1ZZ0426 | BLADE 5 -CORE/FAÇADE/FLOOR FRAMING KEY |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | ZZ | 0426 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0551 | TRUSS BELOW AUDITORIUM - SECTION SHEET 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-31 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0551 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0552 | TRUSS BELOW AUDITORIUM - SECTION SHEET 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-31 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0552 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0553 | TRUSS BELOW AUDITORIUM - SECTION SHEET 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-31 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0553 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0554 | TRUSS BELOW AUDITORIUM - SECTION SHEET 4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-31 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0554 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0511 | ADAPTABLE THEATRE - SECTION 03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-13 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0511 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0512 | ADAPTABLE THEATRE - SECTION 04 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-13 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0512 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0513 | ADAPTABLE THEATRE - SECTION 05 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-13 |  | QP.E.ST.GEN.GEN.1560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0513 | Structural | JINGGONG | LOD400 |  |  |  | 2026-09-30
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0651 | BACKSTAGE DRESSING AREA - SECTIONS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-27 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0651 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0024 | BLADE 1 -Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-16 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0024 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0025 | BLADE 1 -Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-16 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0025 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0026 | BLADE 1 -Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-16 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0026 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0027 | BLADE 1 -Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-16 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0027 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0028 | BLADE 1 -Details-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-16 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0028 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0029 | BLADE 1 -Details-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-16 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0029 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0030 | BLADE 1 -Details-7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-16 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0030 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0031 | BLADE 1 -Details-8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-16 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0031 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0032 | BLADE 1 -Details-9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-16 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0032 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-5ZZ0033 | BLADE 1 -Details-10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-16 |  | QP.E.ST.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 5 | ZZ | 0033 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0115 | BLADE 2 -Details-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0115 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0116 | BLADE 2 -Details-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0116 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0117 | BLADE 2 -Details-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0117 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0118 | BLADE 2 -Details-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0118 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0119 | BLADE 2 -Details-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0119 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0120 | BLADE 2 -Details-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0120 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0121 | BLADE 2 -Details-7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0121 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0122 | BLADE 2 -Details-8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0122 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0123 | BLADE 2 -Details-9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0123 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0124 | BLADE 2 -Details-10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0124 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0125 | BLADE 2 -Details-11 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0125 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0126 | BLADE 2 -Details-12 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0126 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0127 | BLADE 2 -Details-13 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0127 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0128 | BLADE 2 -Details-14 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0128 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0129 | BLADE 2 -Details-15 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0129 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0130 | BLADE 2 -Details-16 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0130 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0131 | BLADE 2 -Details-17 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0131 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0132 | BLADE 2 -Details-18 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0132 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0133 | BLADE 2 -Details-19 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0133 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0134 | BLADE 2 -Details-20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0134 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0135 | BLADE 2 -Details-21 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0135 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD02-5ZZ0136 | BLADE 2 -Details-22 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1400 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 5 | ZZ | 0136 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0299 | BLADE 3 - Details-46 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0299 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-5ZZ0300 | BLADE 3 - Details-47 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-02-04 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 5 | ZZ | 0300 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0350 | BLADE 4 - Details-23 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0350 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0351 | BLADE 4 - Details-24 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0351 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0352 | BLADE 4 - Details-25 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0352 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0353 | BLADE 4 - Details-26 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0353 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0354 | BLADE 4 - Details-27 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0354 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0355 | BLADE 4 - Details-28 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0355 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0356 | BLADE 4 - Details-29 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0356 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0357 | BLADE 4 - Details-30 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0357 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0358 | BLADE 4 - Details-31 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0358 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0359 | BLADE 4 - Details-32 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0359 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0360 | BLADE 4 - Details-33 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0360 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0361 | BLADE 4 - Details-34 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0361 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0362 | BLADE 4 - Details-35 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0362 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0363 | BLADE 4 - Details-36 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0363 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0364 | BLADE 4 - Details-37 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0364 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0365 | BLADE 4 - Details-38 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0365 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0366 | BLADE 4 - Details-39 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0366 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0367 | BLADE 4 - Details-40 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0367 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0368 | BLADE 4 - Details-41 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0368 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0369 | BLADE 4 - Details-42 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0369 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0370 | BLADE 4 - Details-43 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0370 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0371 | BLADE 4 - Details-44 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0371 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0372 | BLADE 4 - Details-45 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0372 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0373 | BLADE 4 - Details-46 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0373 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0374 | BLADE 4 - Details-47 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0374 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0375 | BLADE 4 - Details-48 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0375 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0376 | BLADE 4 - Details-49 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0376 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0377 | BLADE 4 - Details-50 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0377 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0378 | BLADE 4 - Details-51 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0378 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0379 | BLADE 4 - Details-52 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0379 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0380 | BLADE 4 - Details-53 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0380 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0381 | BLADE 4 - Details-54 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0381 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0382 | BLADE 4 - Details-55 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0382 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0383 | BLADE 4 - Details-56 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0383 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0384 | BLADE 4 - Details-57 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0384 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0385 | BLADE 4 - Details-58 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0385 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0386 | BLADE 4 - Details-59 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0386 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0387 | BLADE 4 - Details-60 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0387 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0388 | BLADE 4 - Details-61 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0388 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0389 | BLADE 4 - Details-62 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0389 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0390 | BLADE 4 - Details-63 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0390 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0391 | BLADE 4 - Details-64 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0391 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0392 | BLADE 4 - Details-65 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0392 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0393 | BLADE 4 - Details-66 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0393 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0394 | BLADE 4 - Details-67 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0394 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0395 | BLADE 4 - Details-68 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0395 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0396 | BLADE 4 - Details-69 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0396 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0397 | BLADE 4 - Details-70 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0397 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0398 | BLADE 4 - Details-71 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0398 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0399 | BLADE 4 - Details-72 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0399 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD04-5ZZ0400 | BLADE 4 - Details-73 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-03 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 5 | ZZ | 0400 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0482 | BLADE 5 - Details-62 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0482 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0483 | BLADE 5 - Details-63 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0483 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0484 | BLADE 5 - Details-64 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0484 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0485 | BLADE 5 - Details-65 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0485 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0486 | BLADE 5 - Details-66 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0486 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0487 | BLADE 5 - Details-67 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0487 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0488 | BLADE 5 - Details-68 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0488 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0489 | BLADE 5 - Details-69 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0489 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0490 | BLADE 5 - Details-70 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0490 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0491 | BLADE 5 - Details-71 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0491 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0492 | BLADE 5 - Details-72 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0492 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0493 | BLADE 5 - Details-73 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0493 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0494 | BLADE 5 - Details-74 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0494 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0495 | BLADE 5 - Details-75 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0495 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0496 | BLADE 5 - Details-76 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0496 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0497 | BLADE 5 - Details-77 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0497 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0498 | BLADE 5 - Details-78 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0498 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0499 | BLADE 5 - Details-79 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0499 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-BLAD05-5ZZ0500 | BLADE 5 - Details-80 |  |  | Tekla | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 5 | ZZ | 0500 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0551 | TRUSS BELOW AUDITORIUM - ANCHOR BOLT DETAILS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-31 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0551 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0552 | TRUSS BELOW AUDITORIUM - TYPICAL DETAILS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-31 |  | QP.E.ST.GEN.GEN.1610 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0552 | Structural | JINGGONG | LOD400 |  |  |  | 2026-11-02
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0651 | BACKSTAGE DRESSING AREA - ANCHOR BOLT DETAILS SHEET 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-27 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0651 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0652 | BACKSTAGE DRESSING AREA - ANCHOR BOLT DETAILS SHEET 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-27 |  | QP.E.ST.GEN.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0652 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0653 | BACKSTAGE DRESSING AREA - ANCHOR BOLT DETAILS SHEET 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-27 |  | QP.E.ST.GEN.GEN.1540 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0653 | Structural | JINGGONG | LOD400 |  |  |  | 2026-08-27
QF01012-NES-C04519-SDW-STL-00-CENT01-1ZZ9013 | STEEL FRAMING SECTIONS (B3~B1) (2/2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-02 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04519 | SDW | STL | 00 | CENT01 | 1 | ZZ | 9013 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04519-SDW-STL-00-CENT01-1ZZ9014 | KEY PLAN FOR SHEAR STEEL PLATES FROM (B3~B1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-02 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04519 | SDW | STL | 00 | CENT01 | 1 | ZZ | 9014 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-CAL-STL-00-BLAD03-000002 | Calculation Of Blade 3 Column Bottom Embed Pin Connection |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD03 | 0 | 00 | 002 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-CAL-STL-00-BLAD03-000004 | Calculation for Connection Design of Temporary Struts of Blade 03 - Batch1.1 and 1.2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD03 | 0 | 00 | 004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD04-000004 | Calculation for Connection Design of Temporary Struts of Blade 04 - Batch1.1 and 1.2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD04 | 0 | 00 | 004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD05-000005 | Calculation for Connection Design of Temporary Struts of Blade 05 - Batch1.1 and 1.2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD05 | 0 | 00 | 005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-Z00000-000014 | Calculation for Batch 1.1 Steel Structure of Truss below side and backstage (CB) |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 014 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-Z00000-000015 | Calculation for Blade 01 & 02 Temporary Support Tower |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 015 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD03-000001 | Blade 3-Batch 1.1-Steel Connections Calculation |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD03 | 0 | 00 | 001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-Z00000-000003 | Calculation for Erection Phases Analysis Design Report - Jinggong |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD04-000002 | Calculation Of Blade 4 Column Bottom Embed with Pin Connection |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD04 | 0 | 00 | 002 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-CAL-STL-00-Z00000-000001 | Calculation of Blade3&4&5 column bottom embed with pin connection, Appendix 1. Calculation Sheet of Pin of Embeds & Appendix 2. Calculation Results of Blade 3, 4, 5 Embeds |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 001 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-CAL-STL-00-Z00000-000004 | Calculation Report for QPAC Blade 5 Temporary Support Tower |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD05-000001 | Calculation of Blade 5 Batch 1.1 Steel Structure Connection |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD05 | 0 | 00 | 001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD05-000002 | Calculations and Drawings - Blade 5 Temporary Support Towers. |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-10-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD05 | 0 | 00 | 002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-Z00000-000002 | Calculation of Erection Phase Analysis, Pre-Camber Strategy and Locked-In Forces |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD04-000001 | Calculation for Blade 4-Batch 1.1-Steel Connections |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD04 | 0 | 00 | 001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD03-000003 | Calculation for Blade 3 Batch 1.2 Steel Connection |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD03 | 0 | 00 | 003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD04-000003 | Calculation for Blade 4 Batch 1.2 Steel Connection |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD04 | 0 | 00 | 003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD05-000003 | Calculation for Blade 5 Batch 1.2 Steel Connection |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD05 | 0 | 00 | 003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD01-000001 | Calculation of Blade 1 Column Bottom Embed with Pin Connection |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD01 | 0 | 00 | 001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-CAL-STL-00-Z00000-000011 | Supplementary Calculation for Steel Member Cutting at Blade 5 Temporary Towers Due To Clash with Rebars |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 011 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-Z00000-000012 | Supplementary Calculation of Bed Jig Footings for Temporary Towers Assembly |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 012 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-BLAD02-000001 | Calculation Of Blade 2 Column Bottom Embed with Pin Connection |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD02 | 0 | 00 | 001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-CAL-STL-00-BLAD05-000004 | Calculation for Blade 5 Batch 2 Steel Connection |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD05 | 0 | 00 | 004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-CAL-STL-00-BLAD03-000005 | Calculation for Blade 3 Batch 2.1 Steel Connection |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | BLAD03 | 0 | 00 | 005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0208 | BLADE 1-Welding Details-sheet 01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0208 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0209 | BLADE 1-Welding Details-sheet 02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0209 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0210 | BLADE 1-Welding Details-sheet 03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0210 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0211 | BLADE 1-Welding Details-sheet 04 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0211 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0212 | BLADE 1-Welding Details-sheet 05 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0212 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0213 | BLADE 1-Welding Details-sheet 06 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0213 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0214 | BLADE 1-Welding Details-sheet 07 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0214 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0215 | BLADE 1-Welding Details-sheet 08 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0215 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0216 | BLADE 1-Welding Details-sheet 09 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0216 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0217 | BLADE 1-Welding Details-sheet 10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0217 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0218 | BLADE 1-Welding Details-sheet 11 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0218 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0219 | BLADE 1-Welding Details-sheet 12 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0219 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0220 | BLADE 1-Welding Details-sheet 13 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0220 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0226 | BLADE 2-Welding Details-sheet 01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0226 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0227 | BLADE 2-Welding Details-sheet 02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0227 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0228 | BLADE 2-Welding Details-sheet 03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0228 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0229 | BLADE 2-Welding Details-sheet 04 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0229 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0230 | BLADE 2-Welding Details-sheet 05 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0230 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0231 | BLADE 2-Welding Details-sheet 06 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0231 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0232 | BLADE 2-Welding Details-sheet 07 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0232 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0233 | BLADE 2-Welding Details-sheet 08 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0233 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0234 | BLADE 2-Welding Details-sheet 09 |  |  | Tekla | .dwg,.pdf | 1:100 | 2025-12-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0234 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0163 | BLADE 3-Welding Details-sheet 19 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0163 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0164 | BLADE 3-Welding Details-sheet 20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0164 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0165 | BLADE 3-Welding Details-sheet 21 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0165 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0166 | BLADE 3-Welding Details-sheet 22 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0166 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0167 | BLADE 3-Welding Details-sheet 23 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0167 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0168 | BLADE 3-Welding Details-sheet 24 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0168 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0169 | BLADE 3-Welding Details-sheet 25 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0169 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0170 | BLADE 3-Welding Details-sheet 26 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0170 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0171 | BLADE 3-Welding Details-sheet 27 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0171 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0172 | BLADE 3-Welding Details-sheet 28 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0172 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0173 | BLADE 3-Welding Details-sheet 29 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0173 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0174 | BLADE 3-Welding Details-sheet 30 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0174 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0175 | BLADE 3-Welding Details-sheet 31 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0175 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0176 | BLADE 3-Welding Details-sheet 32 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0176 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0177 | BLADE 3-Welding Details-sheet 33 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0177 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0178 | BLADE 3-Welding Details-sheet 34 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0178 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0179 | BLADE 3-Welding Details-sheet 35 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0179 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0180 | BLADE 3-Welding Details-sheet 36 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0180 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0181 | BLADE 3-Welding Details-sheet 37 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0181 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0182 | BLADE 3-Welding Details-sheet 38 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0182 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0183 | BLADE 3-Welding Details-sheet 39 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0183 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0184 | BLADE 3-Welding Details-sheet 40 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0184 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0185 | BLADE 3-Welding Details-sheet 41 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0185 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0186 | BLADE 3-Welding Details-sheet 42 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0186 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0187 | BLADE 3-Welding Details-sheet 43 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0187 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0188 | BLADE 3-Welding Details-sheet 44 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0188 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0010 | BLADE 3 -Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0010 | Structural | JINGGONG | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-REP-STL-00-Z00000-000002 | Inspection Release Note - IRN 001-PL - Steel Structure - Mfr. Jinggong |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | REP | STL | 00 | Z00000 | 0 | 00 | 002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-REP-STL-00-Z00000-000003 | Inspection Release Note - IRN 002-PL - Steel Structure - Mfr. Jinggong |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | REP | STL | 00 | Z00000 | 0 | 00 | 003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-REP-STL-00-Z00000-000005 | Inspection Release Note - IRN 001-TX - Steel Structure - Mfr. Jinggong |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | REP | STL | 00 | Z00000 | 0 | 00 | 005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-REP-STL-00-Z00000-000006 | Inspection Release Note - IRN 002-TX - Steel Structure - Mfr. Jinggong |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | REP | STL | 00 | Z00000 | 0 | 00 | 006 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-REP-STL-00-Z00000-000007 | Inspection Release Note - IRN PR-002-PJ - Steel Structure - Mfr. Jinggong |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | REP | STL | 00 | Z00000 | 0 | 00 | 007 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-REP-STL-00-Z00000-000008 | Inspection Release Note - IRN TM-001-PJ - Steel Structure - Mfr. Jinggong |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | REP | STL | 00 | Z00000 | 0 | 00 | 008 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-REP-STL-00-Z00000-000009 | Inspection Release Note - IRN TM-002-PJ - Steel Structure - Mfr. Jinggong |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | REP | STL | 00 | Z00000 | 0 | 00 | 009 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-REP-STL-00-Z00000-000010 | Inspection Release Note - IRN TM-003-PJ - Steel Structure - Mfr. Jinggong |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | REP | STL | 00 | Z00000 | 0 | 00 | 010 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001001 | LAYOUT PLAN FOR ANCHOR BOLT-BS1-1~4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001002 | LAYOUT PLAN FOR ANCHOR BOLT-BS1-1~4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001003 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001004 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001005 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001006 | LADDER LAYOUT PLAN FOR BS1-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1006 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001007 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1007 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001008 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1008 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001009 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1009 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001010 | LADDER LAYOUT PLAN FOR BS1-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1010 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001011 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1011 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001012 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1012 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001013 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1013 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001014 | LADDER LAYOUT PLAN FOR BS1-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1014 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001015 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1015 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001016 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1016 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001017 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS1-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1017 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD01-1001018 | LADDER LAYOUT PLAN FOR BS1-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD01 | 1 | 00 | 1018 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002001 | LAYOUT PLAN FOR ANCHOR BOLT-BS2-1~4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002002 | LAYOUT PLAN FOR ANCHOR BOLT-BS2-1~4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002003 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002004 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002005 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002006 | LADDER LAYOUT PLAN FOR BS2-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2006 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002007 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2007 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002008 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2008 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002009 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2009 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002010 | LADDER LAYOUT PLAN FOR BS2-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2010 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002011 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2011 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002012 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2012 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002013 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2013 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002014 | LADDER LAYOUT PLAN FOR BS2-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2014 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002015 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2015 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002016 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2016 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002017 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS2-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2017 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002018 | LADDER LAYOUT PLAN FOR BS2-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2018 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002019 | CONNENTION DETAIL-1 FOR (BS1-1,BS1-2,BS2-1,BS2-2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2019 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD02-1002020 | CONNENTION DETAIL-2 FOR (BS1-3,BS1-4,BS2-3,BS2-4) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD02 | 1 | 00 | 2020 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003001 | LAYOUT PLAN FOR ANCHOR BOLT-BS3-1~6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003002 | LAYOUT SECTION FOR ANCHOR BOLT-BS3-1~6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003003 | LAYOUT DETAIL FOR ANCHOR BOLT-BS3-1~6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003004 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003005 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003006 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3006 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003007 | LADDER LAYOUT PLAN FOR BS3-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3007 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003008 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3008 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003009 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3009 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003010 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3010 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003011 | LADDER LAYOUT PLAN FOR BS3-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3011 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003012 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3012 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003013 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3013 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003014 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3014 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003015 | LADDER LAYOUT PLAN FOR BS3-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3015 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003016 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3016 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003017 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3017 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003018 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3018 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003019 | LADDER LAYOUT PLAN FOR BS3-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3019 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003020 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3020 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003021 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3021 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003022 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3022 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003023 | LADDER LAYOUT PLAN FOR BS3-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3023 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003024 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3024 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003025 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3025 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003026 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS3-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3026 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD03-1003027 | LADDER LAYOUT PLAN FOR BS3-6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD03 | 1 | 00 | 3027 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004001 | LAYOUT PLAN FOR ANCHOR BOLT-BS4-1~4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004002 | LAYOUT SECTION FOR ANCHOR BOLT-BS4-1~4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004003 | LAYOUT DETAIL FOR ANCHOR BOLT-BS4-1~4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004004 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004005 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004006 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4006 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004007 | LADDER LAYOUT PLAN FOR BS4-1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4007 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004008 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4008 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004009 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4009 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004010 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4010 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004011 | LADDER LAYOUT PLAN FOR BS4-2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4011 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004012 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4012 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004013 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4013 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004014 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4014 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004015 | LADDER LAYOUT PLAN FOR BS4-3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4015 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004016 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4016 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004017 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4017 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004018 | LAYOUT PLAN FOR TEMPORARY SUPPORT-BS4-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4018 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004019 | LADDER LAYOUT PLAN FOR BS4-4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4019 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004020 | CONNENTION DETAIL-1 FOR (BS3-1,BS3-2,BS4-1,BS4-2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4020 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD04-1004021 | CONNENTION DETAIL-2 FOR (BS3-3,BS3-4,BS3-5,BS3-6,BS4-3,BS4-4) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-09 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD04 | 1 | 00 | 4021 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005001 | LAYOUT PLAN FOR ANCHOR BOLT-BS5-1a, BS5-1b,BS5-2a,BS5-2b |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005002 | Layout plan for temporary support-BS5-1a |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005003 | Layout plan for temporary support-BS5-1a |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005004 | Ladder layout plan for BS5-1a |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005005 | Layout plan for temporary support-BS5-1b |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005006 | Layout plan for temporary support-BS5-1b |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5006 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005007 | Ladder layout plan for BS5-1b |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5007 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005008 | Layout plan for temporary support-BS5-2a |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5008 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005009 | Layout plan for temporary support-BS5-2a |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5009 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005010 | Ladder layout plan for BS5-2a |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5010 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005011 | Layout plan for temporary support-BS5-2b |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5011 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005012 | Layout plan for temporary support-BS5-2b |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5012 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005013 | Ladder layout plan for BS5-2b |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5013 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-BLAD05-1005014 | Detail (1) for temporary support-BLADE 5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-05 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | BLAD05 | 1 | 00 | 5014 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-1006001 | LAYOUT PLAN FOR ANCHOR BOLT-LS15,LS16 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6001 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006002 | LAYOUT PLAN FOR ANCHOR BOLT-LS17 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6002 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006003 | LAYOUT PLAN FOR ANCHOR BOLT-LS18 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6003 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006004 | LAYOUT PLAN FOR ANCHOR BOLT-LS19 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6004 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006005 | LAYOUT PLAN FOR ANCHOR BOLT-LS20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006006 | Layout plan for temporary support-LS19 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6006 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006007 | Layout plan for temporary support-LS19 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6007 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006008 | Ladder layout plan for LS19 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6008 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006009 | Layout plan for temporary support-LS20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6009 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006010 | Layout plan for temporary support-LS20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6010 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006011 | Ladder layout plan for LS20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6011 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006031 | Layout plan for temporary support-LS15 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6031 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006032 | Layout plan for temporary support-LS15 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6032 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006033 | Ladder layout plan for LS15 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6033 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006034 | Layout plan for temporary support-LS16 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6034 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006035 | Layout plan for temporary support-LS16 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6035 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006036 | Ladder layout plan for LS16 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6036 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006037 | Layout plan for temporary support-LS17 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6037 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006038 | Layout plan for temporary support-LS17 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6038 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006039 | Ladder layout plan for LS17 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6039 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006040 | Layout plan for temporary support-LS18 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6040 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006041 | Layout plan for temporary support-LS18 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6041 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006042 | Ladder layout plan for LS18 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6042 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006043 | Detail (1) for temporary support-LS15~20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6043 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1006044 | Detail (2) for temporary support-LS15~20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-11-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | 00 | 6044 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0605 | L1 LOBBY & PLAZA - SECTIONS SHEET 5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0605 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0606 | L1 LOBBY & PLAZA - SECTIONS SHEET 6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0606 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0607 | L1 LOBBY & PLAZA - SECTIONS SHEET 7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0607 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0608 | L1 LOBBY & PLAZA - SECTIONS SHEET 8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0608 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0609 | L1 LOBBY & PLAZA - SECTIONS SHEET 9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0609 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0610 | L1 LOBBY & PLAZA - SECTIONS SHEET 10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0610 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0611 | L1M LOBBY & PLAZA - SECTIONS SHEET 11 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0611 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0607 | L1 LOBBY & PLAZA - ANCHOR BOLTS SHEET 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0607 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0608 | L1 LOBBY & PLAZA - ANCHOR BOLTS SHEET 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0608 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0609 | L1 LOBBY & PLAZA - ANCHOR BOLTS SHEET 4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0609 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0610 | L1 MEZZANINE LOBBY & PLAZA - ANCHOR BOLTS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-04-27 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0610 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0618 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 18 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0618 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0619 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 19 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0619 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0620 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0620 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0621 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 21 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0621 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0622 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 22 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0622 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0623 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 23 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0623 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0624 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 24 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0624 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0625 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 25 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0625 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0626 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 26 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0626 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0627 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 27 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0627 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0628 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 28 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0628 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0629 | L1 MEZZANINE LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 29 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0629 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0630 | L1 MEZZANINE LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 30 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0630 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0008 | BLADE 5 - Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0008 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0009 | BLADE 5 - Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0009 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0011 | BLADE 3 - Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0011 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0012 | BLADE 3 - Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0012 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0013 | BLADE 3 - Welding Details |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0013 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0014 | BLADE 4 - WELDING DETAILS (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0014 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0015 | BLADE 4 - WELDING DETAILS (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0015 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0016 | BLADE 4 - WELDING DETAILS (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0016 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0017 | BLADE 4 - WELDING DETAILS (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0017 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0018 | BLADE 4 - WELDING DETAILS (BATCH 1.1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0018 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0051 | BLADE 3-Welding Details-sheet 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0051 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0052 | BLADE 3-Welding Details-sheet 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0052 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0053 | BLADE 3-Welding Details-sheet 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0053 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0054 | BLADE 3-Welding Details-sheet 4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0054 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0055 | BLADE 3-Welding Details-sheet 5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0055 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0056 | BLADE 3-Welding Details-sheet 6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0056 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0057 | BLADE 3-Welding Details-sheet 7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0057 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0058 | BLADE 3-Welding Details-sheet 8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0058 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0059 | BLADE 3-Welding Details-sheet 9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0059 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0060 | BLADE 3-Welding Details-sheet 10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0060 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0061 | BLADE 3-Welding Details-sheet 11 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0061 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0062 | BLADE 3-Welding Details-sheet 12 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0062 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0063 | BLADE 3-Welding Details-sheet 13 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0063 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0064 | BLADE 3-Welding Details-sheet 14 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0064 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0065 | BLADE 3-Welding Details-sheet 15 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0065 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0066 | BLADE 3-Welding Details-sheet 16 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0066 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0067 | BLADE 3-Welding Details-sheet 17 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1050 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0067 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0068 | BLADE 5 - Welding Details -sheet 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0068 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0069 | BLADE 5 - Welding Details -sheet 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0069 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0070 | BLADE 5 - Welding Details -sheet 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0070 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0071 | BLADE 5 - Welding Details -sheet 4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0071 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0072 | BLADE 5 - Welding Details -sheet 5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0072 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0073 | BLADE 5 - Welding Details -sheet 6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0073 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0074 | BLADE 5 - Welding Details -sheet 7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0074 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0075 | BLADE 5 - Welding Details -sheet 8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0075 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0076 | BLADE 5 - Welding Details -sheet 9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0076 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0077 | BLADE 5 - Welding Details -sheet 10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0077 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0078 | BLADE 5 - Welding Details -sheet 11 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0078 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0079 | BLADE 5 - Welding Details -sheet 12 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0079 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0080 | BLADE 5 - Welding Details -sheet 13 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0080 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0081 | BLADE 5 - Welding Details -sheet 14 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0081 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0082 | BLADE 5 - Welding Details -sheet 15 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0082 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0083 | BLADE 5 - Welding Details -sheet 16 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0083 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0084 | BLADE 5 - Welding Details -sheet 17 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0084 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0085 | BLADE 4 - Welding Detail-Sheet 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0085 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0086 | BLADE 4 - Welding Detail-Sheet 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0086 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0087 | BLADE 4 - Welding Detail-Sheet 3 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0087 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0088 | BLADE 4 - Welding Detail-Sheet 4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0088 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0089 | BLADE 4 - Welding Detail-Sheet 5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0089 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0090 | BLADE 4 - Welding Detail-Sheet 6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0090 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0091 | BLADE 4 - Welding Detail-Sheet 7 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0091 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0092 | BLADE 4 - Welding Detail-Sheet 8 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0092 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0093 | BLADE 4 - Welding Detail-Sheet 9 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0093 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0094 | BLADE 4 - Welding Detail-Sheet 10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0094 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0095 | BLADE 4 - Welding Detail-Sheet 11 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0095 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0096 | BLADE 4 - Welding Detail-Sheet 12 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0096 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0097 | BLADE 4 - Welding Detail-Sheet 13 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0097 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0098 | BLADE 4 - Welding Detail-Sheet 14 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0098 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0099 | BLADE 4 - Welding Detail-Sheet 15 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0099 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0100 | BLADE 4 - Welding Detail-Sheet 16 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0100 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0101 | BLADE 4 - Welding Detail-Sheet 17 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0101 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0102 | BLADE 4 - Welding Detail-Sheet 18 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0102 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0103 | BLADE 4 - Welding Detail-Sheet 19 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0103 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0104 | BLADE 4 - Welding Detail-Sheet 20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0104 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0105 | BLADE 4 - Welding Detail-Sheet 21 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0105 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0107 | LOBBY & PLAZA-Welding Details-sheet 01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0107 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0108 | LOBBY & PLAZA-Welding Details-sheet 02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0108 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0109 | BLADE 5-Welding Details-sheet 18 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0109 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0110 | BLADE 5-Welding Details-sheet 19 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0110 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0111 | BLADE 5-Welding Details-sheet 20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0111 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0112 | BLADE 5-Welding Details-sheet 21 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0112 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0113 | BLADE 5-Welding Details-sheet 22 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0113 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0114 | BLADE 5-Welding Details-sheet 23 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0114 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0115 | BLADE 5-Welding Details-sheet 24 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0115 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0116 | BLADE 5-Welding Details-sheet 25 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0116 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0117 | BLADE 5-Welding Details-sheet 26 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0117 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0118 | BLADE 5-Welding Details-sheet 27 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0118 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0119 | BLADE 5-Welding Details-sheet 28 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0119 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0120 | BLADE 5-Welding Details-sheet 29 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0120 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0121 | BLADE 5-Welding Details-sheet 30 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0121 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0122 | BLADE 5-Welding Details-sheet 31 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0122 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0123 | BLADE 5-Welding Details-sheet 32 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0123 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0124 | TRUSS BELOW SIDE AND BACK STAGE-sheet 01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0124 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0125 | TRUSS BELOW SIDE AND BACK STAGE-sheet 02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0125 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0126 | TRUSS BELOW SIDE AND BACK STAGE-sheet 03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0126 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0127 | TRUSS BELOW SIDE AND BACK STAGE-sheet 04 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0127 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0128 | TRUSS BELOW SIDE AND BACK STAGE-sheet 05 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0128 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0129 | TRUSS BELOW SIDE AND BACK STAGE-sheet 06 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0129 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0130 | TRUSS BELOW SIDE AND BACK STAGE-sheet 07 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0130 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0131 | TRUSS BELOW SIDE AND BACK STAGE-sheet 08 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0131 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0132 | TRUSS BELOW SIDE AND BACK STAGE-sheet 09 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0132 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0133 | TRUSS BELOW SIDE AND BACK STAGE-sheet 10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0133 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0134 | BLADE 4-Welding Details-sheet 22 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0134 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0135 | BLADE 4-Welding Details-sheet 23 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0135 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0136 | BLADE 4-Welding Details-sheet 24 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0136 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0137 | BLADE 4-Welding Details-sheet 25 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0137 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0138 | BLADE 4-Welding Details-sheet 26 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0138 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0139 | BLADE 4-Welding Details-sheet 27 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0139 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0140 | BLADE 4-Welding Details-sheet 28 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0140 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0141 | BLADE 4-Welding Details-sheet 29 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0141 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0142 | BLADE 4-Welding Details-sheet 30 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0142 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0143 | BLADE 4-Welding Details-sheet 31 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0143 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0144 | BLADE 4-Welding Details-sheet 32 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0144 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0145 | BLADE 4-Welding Details-sheet 33 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0145 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0146 | BLADE 4-Welding Details-sheet 34 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0146 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0147 | BLADE 4-Welding Details-sheet 35 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0147 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0148 | BLADE 4-Welding Details-sheet 36 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0148 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0149 | BLADE 4-Welding Details-sheet 37 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0149 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0150 | BLADE 4-Welding Details-sheet 38 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0150 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0151 | BLADE 4-Welding Details-sheet 39 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0151 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0152 | BLADE 4-Welding Details-sheet 40 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0152 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0153 | BLADE 4-Welding Details-sheet 41 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0153 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0154 | BLADE 4-Welding Details-sheet 42 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0154 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0155 | BLADE 4-Welding Details-sheet 43 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0155 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0156 | BLADE 4-Welding Details-sheet 44 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0156 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0157 | BLADE 4-Welding Details-sheet 45 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0157 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0158 | BLADE 4-Welding Details-sheet 46 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0158 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0159 | BLADE 4-Welding Details-sheet 47 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0159 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0160 | BLADE 4-Welding Details-sheet 48 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0160 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0161 | BLADE 4-Welding Details-sheet 49 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0161 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0162 | BLADE 4-Welding Details-sheet 50 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0162 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0237 | BLADE 5-Welding Details-sheet 35 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0237 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0250 | BLADE 5-Welding Details-sheet 48 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0250 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0251 | BLADE 5-Welding Details-sheet 49 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0251 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0252 | BLADE 5-Welding Details-sheet 50 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1190 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0252 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0271 | BLADE 3-Welding Details-sheet 45 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0271 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0272 | BLADE 3-Welding Details-sheet 46 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0272 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0273 | BLADE 3-Welding Details-sheet 47 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0273 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0274 | BLADE 3-Welding Details-sheet 48 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0274 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0275 | BLADE 3-Welding Details-sheet 49 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0275 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0276 | BLADE 3-Welding Details-sheet 50 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0276 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0277 | BLADE 3-Welding Details-sheet 51 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0277 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0278 | BLADE 3-Welding Details-sheet 52 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0278 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0279 | BLADE 3-Welding Details-sheet 53 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0279 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0280 | BLADE 3-Welding Details-sheet 54 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0280 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0281 | BLADE 3-Welding Details-sheet 55 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0281 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0282 | BLADE 3-Welding Details-sheet 56 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0282 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0283 | BLADE 3-Welding Details-sheet 57 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0283 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0284 | BLADE 3-Welding Details-sheet 58 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0284 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0285 | BLADE 3-Welding Details-sheet 59 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0285 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0286 | BLADE 3-Welding Details-sheet 60 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0286 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0287 | BLADE 3-Welding Details-sheet 61 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0287 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0288 | BLADE 3-Welding Details-sheet 62 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0288 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0289 | BLADE 3-Welding Details-sheet 63 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0289 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0290 | BLADE 3-Welding Details-sheet 64 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0290 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0291 | BLADE 3-Welding Details-sheet 65 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0291 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0292 | BLADE 3-Welding Details-sheet 66 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0292 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0293 | BLADE 3-Welding Details-sheet 67 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0293 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0294 | BLADE 3-Welding Details-sheet 68 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0294 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0295 | BLADE 3-Welding Details-sheet 69 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0295 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0296 | BLADE 3-Welding Details-sheet 70 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0296 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0297 | BLADE 3-Welding Details-sheet 71 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0297 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0298 | BLADE 3-Welding Details-sheet 72 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0298 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0299 | BLADE 3-Welding Details-sheet 73 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0299 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0300 | BLADE 3-Welding Details-sheet 74 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0300 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0301 | BLADE 3-Welding Details-sheet 75 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0301 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0302 | BLADE 3-Welding Details-sheet 76 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0302 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0303 | BLADE 3-Welding Details-sheet 77 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0303 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0304 | BLADE 3-Welding Details-sheet 78 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0304 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0305 | BLADE 3-Welding Details-sheet 79 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0305 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0306 | BLADE 3-Welding Details-sheet 80 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0306 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0307 | BLADE 3-Welding Details-sheet 81 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0307 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0308 | BLADE 3-Welding Details-sheet 82 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0308 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0309 | BLADE 3-Welding Details-sheet 83 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0309 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0310 | BLADE 3-Welding Details-sheet 84 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0310 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0311 | BLADE 3-Welding Details-sheet 85 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0311 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0312 | BLADE 3-Welding Details-sheet 86 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0312 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0313 | BLADE 3-Welding Details-sheet 87 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0313 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0314 | BLADE 3-Welding Details-sheet 88 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0314 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0315 | BLADE 3-Welding Details-sheet 89 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0315 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0316 | BLADE 3-Welding Details-sheet 90 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0316 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0317 | BLADE 3-Welding Details-sheet 91 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0317 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0318 | BLADE 3-Welding Details-sheet 92 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0318 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0319 | BLADE 3-Welding Details-sheet 93 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0319 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0320 | BLADE 3-Welding Details-sheet 94 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0320 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0321 | BLADE 3-Welding Details-sheet 95 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-19 |  | QP.E.ST.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0321 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-CAL-STL-00-Z00000-000005 | LOFT-Temporary Towers Base connections design report-LS15 to LS20 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-13 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 005 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-CAL-STL-00-Z00000-000007 | Calculation report of bed JIG for temporary tower |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-17 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 007 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-CAL-STL-00-Z00000-000008 | Calculation of Central Block Batch 2.1 Embedded Parts |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-30 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 008 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-CAL-STL-00-Z00000-000009 | Calculation Report for QPAC Blade 3 & 4 Temporary Support Tower |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-24 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 009 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-Z00000-000010 | Calculation Report for Construction Joints at shear walls CJ1-CJ2-CJ3-CJ4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-05-31 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 010 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-CAL-STL-00-Z00000-000013 | Supplemented Calculation-3 of Bed Jig for All of Temporary Towers |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-15 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 013 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18
QF01012-NES-C04518-CAL-STL-00-Z00000-000016 | Calculation Report for Dogging Plate of QPAC Blade5 -Batch 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-07-30 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 016 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-CAL-STL-00-Z00000-000017 | Calculation Report of Lifting Lug of Core Segment of Blade 1-5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-02 |  | QP.E.ST.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 017 | Structural | JINGGONG | LOD400 |  |  |  | 2026-07-26
QF01012-NES-C04518-CAL-STL-00-Z00000-000019 | Calculation Report of Dogging Plate for Blade Core Frame Ground Assembly |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-19 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 019 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-Z00000-000020 | Calculation Report for the Hook of Safety Nets |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-19 |  | QP.E.ST.GEN.GEN.1090 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 020 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-Z00000-000021 | Calculation of Central Block Batch 1.2 Steel Structure Connection |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 021 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-CAL-STL-00-Z00000-000022 | Calculation of Central Block Batch 2.2 Embedded Parts |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 022 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-CAL-STL-00-Z00000-000023 | Calculation of Central Block Batch 2.3 Frame for Balconies |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 023 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-CAL-STL-00-Z00000-000024 | Calculation of Central Block Batch 2.4 PT Catwalk Bridge |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 024 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-CAL-STL-00-Z00000-000025 | Calculation Report for QPAC Blade Floor Beam and Column Lifted with Lug |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-29 |  | QP.E.ST.GEN.GEN.1070 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 00 | 025 | Structural | JINGGONG | LOD400 |  |  |  | 2026-03-19
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0521 | FRAME FOR BALCONIES - ANCHOR BOLT SECTIONS SHEET 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0521 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0522 | FRAME FOR BALCONIES - ANCHOR BOLT SECTIONS SHEET 2 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0522 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-1ZZ0571 | PT CATWALK BRIDGE - ANCHOR BOLT SECTIONS SHEET 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 1 | ZZ | 0571 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0523 | DOWN BALCONIES - ANCHOR BOLT LAYOUT PLAN |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0523 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0524 | UPPER BALCONIES - ANCHOR BOLT LAYOUT PLAN |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0524 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0571 | PT CATWALK BRIDGE - 3D VIEW |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0571 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0572 | PT CATWALK BRIDGE - KEY PLAN |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0572 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0573 | PT CATWALK BRIDGE - ANCHOR BOLT LAYOUT PLAN |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0573 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0652 | BACKSTAGE DRESSING AREA - KEY PLAN |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0652 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-2ZZ0653 | BACKSTAGE DRESSING AREA - ANCHOR BOLTS |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 2 | ZZ | 0653 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0553 | TRUSS BELOW AUDITORIUM - TYPICAL DETAILS (1) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0553 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0554 | TRUSS BELOW AUDITORIUM - TYPICAL DETAILS (2) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0554 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0555 | TRUSS BELOW AUDITORIUM - TYPICAL DETAILS (3) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0555 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0556 | TRUSS BELOW AUDITORIUM - TYPICAL DETAILS (4) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0556 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0557 | TRUSS BELOW AUDITORIUM - TYPICAL DETAILS (5) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0557 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0558 | TRUSS BELOW AUDITORIUM - TYPICAL DETAILS (6) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0558 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0559 | TRUSS BELOW AUDITORIUM - TYPICAL DETAILS (7) |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0559 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0571 | PT CATWALK BRIDGE - ANCHOR BOLT DETAILS SHEET 1 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0571 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0631 | L1 LOBBY & PLAZA - ANCHOR BOLT DETAILS SHEET 25 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-30 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0631 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0654 | BACKSTAGE DRESSING AREA - ANCHOR BOLT DETAILS SHEET 4 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0654 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0655 | BACKSTAGE DRESSING AREA - ANCHOR BOLT DETAILS SHEET 5 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0655 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-CENT01-5ZZ0656 | BACKSTAGE DRESSING AREA - ANCHOR BOLT DETAILS SHEET 6 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | CENT01 | 5 | ZZ | 0656 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0203 | BACKSTAGE DRESSING AREA-Welding Details-sheet 01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0203 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0204 | BACKSTAGE DRESSING AREA-Welding Details-sheet 02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0204 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0205 | BACKSTAGE DRESSING AREA-Welding Details-sheet 03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0205 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0221 | Truss below Auditorium (CB)-weld sheet 01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0221 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0222 | Truss below Auditorium (CB)-weld sheet 02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0222 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0223 | Truss below Auditorium (CB)-weld sheet 03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0223 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0224 | Truss below Auditorium (CB)-weld sheet 04 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0224 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0225 | Truss below Auditorium (CB)-weld sheet 05 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0225 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0323 | Truss below Auditorium (CB)-weld sheet 06 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0323 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0324 | Truss below Auditorium (CB)-weld sheet 07 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0324 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0325 | Truss below Auditorium (CB)-weld sheet 08 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0325 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0326 | Truss below Auditorium (CB)-weld sheet 09 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0326 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0327 | Truss below Auditorium (CB)-weld sheet 10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0327 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0328 | Truss below Auditorium (CB)-weld sheet 11 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0328 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0329 | Truss below Auditorium (CB)-weld sheet 12 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1010 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0329 | Structural | JINGGONG | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0365 | BACKSTAGE DRESSING AREA-Welding Details-sheet 04 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0365 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0366 | BACKSTAGE DRESSING AREA-Welding Details-sheet 05 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0366 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0367 | BACKSTAGE DRESSING AREA-Welding Details-sheet 06 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0367 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0368 | FRAME FOR BALCONIES-Welding Details-sheet 01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0368 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0369 | FRAME FOR BALCONIES-Welding Details-sheet 02 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0369 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0370 | FRAME FOR BALCONIES-Welding Details-sheet 03 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0370 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0371 | FRAME FOR BALCONIES-Welding Details-sheet 04 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0371 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0372 | FRAME FOR BALCONIES-Welding Details-sheet 05 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0372 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0373 | FRAME FOR BALCONIES-Welding Details-sheet 06 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0373 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0374 | FRAME FOR BALCONIES-Welding Details-sheet 07 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0374 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0375 | FRAME FOR BALCONIES-Welding Details-sheet 08 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0375 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0376 | FRAME FOR BALCONIES-Welding Details-sheet 09 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0376 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0377 | FRAME FOR BALCONIES-Welding Details-sheet 10 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0377 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-SDW-STL-00-Z00000-0ZZ0378 | PT CATWALK BRIDGE-Welding Details-sheet 01 |  |  | Tekla | .dwg,.pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STL | 00 | Z00000 | 0 | ZZ | 0378 | Structural | JINGGONG | LOD400 |  |  |  | 2026-04-15
QF01012-NES-C04518-CAL-STL-00-Z00000-000018 | Supplemented Calculation-2 of Bed Jig for All of Temporary Towers |  |  | Tekla | pdf | 1:100 | 2026-08-25 |  | QP.E.ST.GEN.GEN.1340 | FI_60_25 | QF01012 | NES | C04518 | CAL | STL | 00 | Z00000 | 0 | 0 | 0018 | Structural | JINGGONG | LOD400 |  |  |  | 2026-05-18

## Baseline
1 | 2 | 3 | 4 | 5 | 6 | 7 | Package | Activity Code | Activity | Original Duration | Start | Finish
Shop Drawings | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Shop Drawings ¦ Mobilization | QP.M.GN.GEN.GEN.1400 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Shop Drawings ¦ Mobilization ¦ Tower Crane Foundation - Concrete Works | QP.M.GN.GEN.GEN.1470 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Blades Below Loft | QP.M.GN.GEN.GEN.1540 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Loft | QP.M.GN.GEN.GEN.1560 | Submittal | 12 | 2026-08-29 | 2026-09-10
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Above Loft | QP.M.GN.GEN.GEN.1580 | Submittal | 12 | 2026-10-01 | 2026-10-14
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works | QP.E.CV.MBL.GEN.3460 | Submittal | 28 | 2025-10-11 | 2025-11-11
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works Outside Core Area | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works Outside Core Area | QP.E.CV.MBL.GEN.3540 | Submittal | 14 | 2025-11-12 | 2025-11-27
Shop Drawings | Civil | Blades | Blade 1 | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 1 | QP.E.CV.BL1.GEN.1060 | Submittal | 28 | 2026-02-21 | 2026-03-28
Shop Drawings | Civil | Blades | Blade 2 | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 2 | QP.E.CV.BL2.GEN.1060 | Submittal | 28 | 2026-01-19 | 2026-02-19
Shop Drawings | Civil | Blades | Blade 3 | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 3 | QP.E.CV.BL3.GEN.1060 | Submittal | 28 | 2025-12-17 | 2026-01-18
Shop Drawings | Civil | Blades | Blade 4 | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 4 | QP.E.CV.BL4.GEN.1060 | Submittal | 28 | 2025-12-03 | 2026-01-04
Shop Drawings | Civil | Blades | Blade 5 | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 5 | QP.E.CV.BL5.GEN.1060 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Civil | Parking | Parking | Parking | Parking | Parking | Shop Drawings ¦ Civil ¦ Parking | QP.E.CV.PAR.GEN.1000 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - Foundation Works Core Area | QP.E.CV.MBL.GEN.3000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 03 +887.750M | QP.E.CV.MBL.GEN.3030 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - SOG | QP.E.CV.MBL.GEN.3640 | Submittal | 14 | 2026-03-16 | 2026-04-02
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 02 - Foundation Works Outside Core Area | QP.E.CV.MBL.GEN.3020 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 02 +893.5M | QP.E.CV.MBL.GEN.3070 | Submittal | 21 | 2026-02-18 | 2026-03-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 01 +900.5M | QP.E.CV.MBL.GEN.3100 | Submittal | 28 | 2026-03-16 | 2026-04-19
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01- LOBBY LEVEL +905M | QP.E.CV.MBL.GEN.3120 | Submittal | 25 | 2026-04-20 | 2026-05-18
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01 - MEZZANINE +909M | QP.E.CV.MBL.GEN.3140 | Submittal | 15 | 2026-05-19 | 2026-06-08
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3180 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3380 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3220 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3400 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3240 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3420 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3260 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3440 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | QP.E.CV.MBL.GEN.3280 | Submittal | 25 | 2026-10-08 | 2026-11-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | QP.E.CV.MBL.GEN.3300 | Submittal | 28 | 2027-03-13 | 2027-04-13
Shop Drawings | Concrete | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Premium Theatre Concrete Works | QP.E.CV.MBL.GEN.3150 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Amphitheatre Concrete Works | QP.E.CV.MBL.GEN.3200 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Premium Theater | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Premium Theater | QP.E.CV.MBL.GEN.3660 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Loft and Adaptable Theatre | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Loft and Adaptable Theatre | QP.E.CV.MBL.GEN.3700 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Fly Tower | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Fly Tower | QP.E.CV.MBL.GEN.3710 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Lobby & Plaza | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Lobby & Plaza | QP.E.CV.MBL.GEN.3680 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Royal Majlis | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Royal Majlis | QP.E.CV.MBL.GEN.3740 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Foundation | QP.E.CV.BL1.GEN.1000 | Submittal | 25 | 2026-02-25 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL1.GEN.1040 | Submittal | 25 | 2026-03-29 | 2026-04-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL1.GEN.1080 | Submittal | 18 | 2026-05-12 | 2026-06-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL1.GEN.1020 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL1.GEN.1120 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL1.GEN.1100 | Submittal | 28 | 2026-10-27 | 2026-11-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Foundation | QP.E.CV.BL2.GEN.1000 | Submittal | 21 | 2026-03-02 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL2.GEN.1040 | Submittal | 21 | 2026-03-10 | 2026-04-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL2.GEN.1080 | Submittal | 18 | 2026-04-21 | 2026-05-11
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL2.GEN.1020 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL2.GEN.1140 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL2.GEN.1120 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Foundation | QP.E.CV.BL3.GEN.1000 | Submittal | 21 | 2026-02-07 | 2026-03-03
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Steel Composite Slab Including Embedded items Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Steel Composite Slab Including Embedded items Below Loft | QP.E.CV.BL3.GEN.1030 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL3.GEN.1080 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL3.GEN.1020 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Foundation | QP.E.CV.BL4.GEN.1000 | Submittal | 28 | 2026-01-05 | 2026-02-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL4.GEN.1030 | Submittal | 28 | 2026-02-24 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL4.GEN.1080 | Submittal | 15 | 2026-03-31 | 2026-04-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL4.GEN.1020 | Submittal | 28 | 2026-04-18 | 2026-05-19
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL4.GEN.1100 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL4.GEN.1120 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Foundation | QP.E.CV.BL5.GEN.1000 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL5.GEN.1030 | Submittal | 28 | 2026-03-23 | 2026-04-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL5.GEN.1080 | Submittal | 18 | 2026-03-31 | 2026-04-20
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL5.GEN.1020 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL5.GEN.1100 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL5.GEN.1120 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Foundation Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Foundation Including Embedded items | QP.E.CV.PAR.GEN.1020 | Submittal | 28 | 2027-04-28 | 2027-06-03
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Structural Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Structural Concrete Works Including Embedded items | QP.E.CV.PAR.GEN.1040 | Submittal | 28 | 2027-06-19 | 2027-07-20
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Below Loft | QP.E.ST.GEN.GEN.1090 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1100 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1110 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1050 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1060 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1070 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 3,4,5 | QP.E.ST.GEN.GEN.1000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | QP.E.ST.GEN.GEN.1010 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Truss below Auditorium, Side and Back Stage | QP.E.ST.GEN.GEN.2120 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1220 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1230 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1200 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1210 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1190 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Embedded part - Main Building Above Level 5 | QP.E.ST.GEN.GEN.1040 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Premium Theater - Frame Balconies and Back Stage Dressing | QP.E.ST.GEN.GEN.2140 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Loft and adaptable Theatre | QP.E.ST.GEN.GEN.1340 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1390 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1400 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1310 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1320 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1330 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1470 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ Truss above Auditorium Incl. Metal Deck | QP.E.ST.GEN.GEN.2100 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Temporay Tower ROYAL MAJLIS and Blades above loft | QP.E.ST.GEN.GEN.1490 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2160 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1520 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Truss above Flytower | QP.E.ST.GEN.GEN.2180 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1540 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ Blade 2 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2200 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ Adaptable Theatre Incl. Metal Deck | QP.E.ST.GEN.GEN.1560 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.2220 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Loft Truss and Infilled Beam North Side Incl. Metal Deck | QP.E.ST.GEN.GEN.1610 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1600 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Lobby and Plaza Incl. Metal Deck | QP.E.ST.GEN.GEN.1660 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Frame for Mezzanine | QP.E.ST.GEN.GEN.1670 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Link Bridge and Helix Stair | QP.E.ST.GEN.GEN.1570 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1680 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | Shop Drawings ¦ Structural Steel ¦ Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck ¦ ROYAL MAJLIS | QP.E.ST.GEN.GEN.1640 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1090 | Submittal | 21 | 2026-03-26 | 2026-04-19
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1120 | Submittal | 21 | 2026-09-15 | 2026-10-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Wall Cladding | QP.E.AF.MBL.GEN.4440 | Submittal | 21 | 2026-10-11 | 2026-11-03
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1100 | Submittal | 21 | 2026-11-04 | 2026-11-28
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ FFE | QP.E.AF.MBL.GEN.5260 | Submittal | 21 | 2026-11-29 | 2026-12-22
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1170 | Submittal | 21 | 2026-04-20 | 2026-05-13
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1200 | Submittal | 20 | 2026-11-04 | 2026-11-26
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5700 | Submittal | 21 | 2026-11-28 | 2026-12-21
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1180 | Submittal | 21 | 2026-12-23 | 2027-01-16
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ FFE | QP.E.AF.MBL.GEN.5280 | Submittal | 21 | 2027-01-17 | 2027-02-09
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1220 | Submittal | 21 | 2026-05-14 | 2026-06-10
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1250 | Submittal | 28 | 2026-11-28 | 2026-12-29
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5720 | Submittal | 21 | 2026-12-30 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1230 | Submittal | 21 | 2027-01-24 | 2027-02-16
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ FFE | QP.E.AF.MBL.GEN.5300 | Submittal | 21 | 2027-02-17 | 2027-03-16
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1310 | Submittal | 21 | 2026-06-11 | 2026-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1340 | Submittal | 28 | 2026-12-30 | 2027-01-31
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5800 | Submittal | 21 | 2027-02-01 | 2027-02-25
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1320 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ FFE | QP.E.AF.MBL.GEN.5320 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1400 | Submittal | 21 | 2026-07-06 | 2026-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1430 | Submittal | 20 | 2027-02-01 | 2027-02-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5740 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1410 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ FFE | QP.E.AF.MBL.GEN.5340 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1000 | Submittal | 21 | 2026-07-30 | 2026-08-23
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1030 | Submittal | 20 | 2027-02-25 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5760 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1010 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ FFE | QP.E.AF.MBL.GEN.5360 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1490 | Submittal | 21 | 2026-08-24 | 2026-09-16
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1520 | Submittal | 20 | 2027-03-23 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5820 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1500 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ FFE | QP.E.AF.MBL.GEN.5380 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1580 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1610 | Submittal | 20 | 2027-04-15 | 2027-05-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5840 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1590 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ FFE | QP.E.AF.MBL.GEN.5400 | Submittal | 21 | 2027-07-06 | 2027-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1670 | Submittal | 21 | 2026-12-20 | 2027-01-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1700 | Submittal | 20 | 2027-05-23 | 2027-06-14
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5860 | Submittal | 28 | 2027-06-15 | 2027-07-17
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1680 | Submittal | 28 | 2027-07-18 | 2027-08-18
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ FFE | QP.E.AF.MBL.GEN.5420 | Submittal | 28 | 2027-07-31 | 2027-08-31
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1760 | Submittal | 21 | 2027-01-19 | 2027-02-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1790 | Submittal | 21 | 2027-05-23 | 2027-06-15
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5880 | Submittal | 21 | 2027-07-18 | 2027-08-10
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1770 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ FFE | QP.E.AF.MBL.GEN.5440 | Submittal | 21 | 2027-09-01 | 2027-09-26
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1880 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1910 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5900 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1890 | Submittal | 21 | 2027-09-13 | 2027-10-07
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ FFE | QP.E.AF.MBL.GEN.5460 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1800 | Submittal | 21 | 2027-04-22 | 2027-05-20
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1830 | Submittal | 21 | 2027-07-25 | 2027-08-17
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5920 | Submittal | 21 | 2027-08-25 | 2027-09-18
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1810 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ FFE | QP.E.AF.MBL.GEN.5480 | Submittal | 21 | 2027-10-11 | 2027-11-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1110 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1140 | Submittal | 21 | 2027-05-31 | 2027-06-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1120 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1370 | Submittal | 21 | 2027-03-01 | 2027-03-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1360 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Wall Cladding | QP.E.AF.BL1.GEN.5940 | Submittal | 21 | 2027-07-19 | 2027-08-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1340 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1650 | Submittal | 21 | 2027-06-14 | 2027-07-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1680 | Submittal | 14 | 2027-09-01 | 2027-09-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1660 | Submittal | 21 | 2027-11-18 | 2027-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1080 | Submittal | 21 | 2027-05-26 | 2027-06-19
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1110 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Wall Cladding | QP.E.AF.BL2.GEN.5960 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1090 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1580 | Submittal | 21 | 2027-07-04 | 2027-07-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1610 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1590 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1670 | Submittal | 21 | 2027-07-28 | 2027-08-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1700 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1680 | Submittal | 14 | 2028-01-18 | 2028-02-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1000 | Submittal | 24 | 2026-11-15 | 2026-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1030 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL3.GEN.5980 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1010 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1340 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1370 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1350 | Submittal | 21 | 2027-12-22 | 2028-01-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1210 | Submittal | 24 | 2026-12-27 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1240 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL4.GEN.6000 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1220 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1820 | Submittal | 21 | 2027-04-24 | 2027-05-22
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1850 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1830 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1730 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1760 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1740 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.2280 | Submittal | 24 | 2027-02-07 | 2027-03-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.2340 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.2300 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1130 | Submittal | 21 | 2027-03-22 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1160 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1140 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1500 | Submittal | 28 | 2027-06-29 | 2027-07-31
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1530 | Submittal | 21 | 2027-10-10 | 2027-11-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Wall Cladding | QP.E.AF.BL5.GEN.6020 | Submittal | 21 | 2027-12-16 | 2028-01-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1510 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1000 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1020 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Doors / Openings | QP.E.AF.PAR.GEN.1010 | Submittal | 28 | 2027-12-22 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Specialities | QP.E.AF.MBL.GEN.5160 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1030 | Submittal | 28 | 2027-10-16 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1050 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Doors / Openings | QP.E.AF.PAR.GEN.1040 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Specialities | QP.E.AF.MBL.GEN.5200 | Submittal | 21 | 2028-01-09 | 2028-02-01
Shop Drawings | Architecture and Fitouts | Amphitheatre | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4040 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Architecture and Fitouts | Amphitheatre | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.4070 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Amphitheatre | Wall Cladding | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Wall Cladding | QP.E.AF.MBL.GEN.6040 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | Architecture and Fitouts | Amphitheatre | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4050 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | Shop Drawings ¦ External Building Works (Guard House, SEC Room) | QP.E.EX.GEN.GEN.1270 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Main Building | QP.E.AF.MBL.GEN.6060 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 5 | Water Proofing - Roof - Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 5 | QP.E.AF.BL5.GEN.6180 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 4 | Water Proofing - Roof - Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 4 | QP.E.AF.BL4.GEN.6160 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 3 | Water Proofing - Roof - Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 3 | QP.E.AF.BL3.GEN.6140 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 1 | Water Proofing - Roof - Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 1 | QP.E.AF.BL1.GEN.6100 | Submittal | 21 | 2027-12-09 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 2 | Water Proofing - Roof - Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 2 | QP.E.AF.BL2.GEN.6120 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Wet Areas | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Wet Areas ¦ Main Building | QP.E.AF.MBL.GEN.4400 | Submittal | 21 | 2027-08-08 | 2027-08-31
Shop Drawings | Specialist Systems | Doors/ Openings | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Main Building | QP.E.AF.MBL.GEN.1140 | Submittal | 20 | 2027-06-29 | 2027-07-21
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.1130 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 2 | QP.E.AF.BL2.GEN.1100 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.1020 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.1230 | Submittal | 21 | 2027-08-16 | 2027-09-08
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.2320 | Submittal | 21 | 2027-09-09 | 2027-10-04
Shop Drawings | Specialist Systems | Doors/ Openings | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Amphitheatre | QP.E.AF.MBL.GEN.4060 | Submittal | 28 | 2027-11-13 | 2027-12-14
Shop Drawings | Specialist Systems | Conveying System | Waste Management | Waste Management | Waste Management | Waste Management | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Waste Management | QP.E.CY.GEN.GEN.1280 | Submittal | 14 | 2027-12-02 | 2027-12-18
Shop Drawings | Specialist Systems | Conveying System | Escalators | Escalators | Escalators | Escalators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Escalators | QP.E.CY.GEN.GEN.1040 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | Specialist Systems | Conveying System | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | QP.E.CY.GEN.GEN.1020 | Submittal | 28 | 2026-10-22 | 2026-11-23
Shop Drawings | Specialist Systems | Conveying System | Truck Elevators | Truck Elevators | Truck Elevators | Truck Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Truck Elevators | QP.E.CY.GEN.GEN.1000 | Submittal | 28 | 2026-09-19 | 2026-10-21
Shop Drawings | Specialist Systems | Conveying System | Inclined Elevators | Inclined Elevators | Inclined Elevators | Inclined Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Inclined Elevators | QP.E.CY.GEN.GEN.1050 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Main Building | QP.E.CY.GEN.GEN.1090 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 1 | QP.E.CY.GEN.GEN.1130 | Submittal | 28 | 2027-10-17 | 2027-11-17
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 2 | QP.E.CY.GEN.GEN.1170 | Submittal | 28 | 2027-09-13 | 2027-10-16
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 3 | Balde 3 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 3 | QP.E.CY.GEN.GEN.1210 | Submittal | 28 | 2027-06-07 | 2027-07-08
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 4 | QP.E.CY.GEN.GEN.1110 | Submittal | 28 | 2027-07-10 | 2027-08-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 5 | Balde 5 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 5 | QP.E.CY.GEN.GEN.1150 | Submittal | 28 | 2027-08-11 | 2027-09-12
Shop Drawings | Specialist Systems | Joinery Works | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Main Building | QP.E.AF.MBL.GEN.5540 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.6120 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.6160 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.6180 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.6200 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Shop Drawings ¦ Specialist Systems ¦ Kitchen and Laundary | QP.E.AF.MBL.GEN.5500 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Specialist Systems | Water Features | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Specialist Systems ¦ Water Features | QP.E.AF.MBL.GEN.6100 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Mechanical | QP.E.ME.MBL.GEN.6780 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical | QP.E.ME.MBL.GEN.6800 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6840 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical | QP.E.ME.MBL.GEN.6850 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6860 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical | QP.E.ME.MBL.GEN.6870 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Mechanical | QP.E.ME.MBL.GEN.6900 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical | QP.E.ME.MBL.GEN.6910 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Mechanical | QP.E.ME.MBL.GEN.6940 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical | QP.E.ME.MBL.GEN.6950 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Mechanical | QP.E.ME.MBL.GEN.6980 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Electrical | QP.E.ME.MBL.GEN.6990 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Mechanical | QP.E.ME.MBL.GEN.7020 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical | QP.E.ME.MBL.GEN.7030 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7060 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical | QP.E.ME.MBL.GEN.7070 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7100 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical | QP.E.ME.MBL.GEN.7110 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Mechanical | QP.E.ME.MBL.GEN.7140 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical | QP.E.ME.MBL.GEN.7150 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Mechanical | QP.E.ME.MBL.GEN.7180 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Electrical | QP.E.ME.MBL.GEN.7190 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Mechanical | QP.E.ME.MBL.GEN.7220 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical | QP.E.ME.MBL.GEN.7230 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1320 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1330 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1340 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1350 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ ICT Containment | QP.E.ME.MBL.GEN.1360 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1420 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1430 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1440 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1450 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1460 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1740 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1750 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1760 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1770 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1780 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1590 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1600 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1610 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1620 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.1630 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2040 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2050 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2060 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2070 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ ICT Containment | QP.E.ME.MBL.GEN.2080 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2240 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2250 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2260 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2270 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ ICT Containment | QP.E.ME.MBL.GEN.2280 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2440 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2450 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2460 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2470 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.2480 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2640 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2650 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2660 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2670 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2680 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2850 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2860 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2870 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2880 | Submittal | 28 | 2026-12-08 | 2027-01-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2890 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3070 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3080 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3090 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3100 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ ICT Containment | QP.E.ME.MBL.GEN.3110 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3290 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3300 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3310 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3320 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ ICT Containment | QP.E.ME.MBL.GEN.3330 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3500 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3510 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3520 | Submittal | 28 | 2026-12-23 | 2027-01-24
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3530 | Submittal | 28 | 2027-02-11 | 2027-03-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ ICT Containment | QP.E.ME.MBL.GEN.3540 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.MBL.GEN.5000 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.MBL.GEN.5040 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.MBL.GEN.5060 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.MBL.GEN.5080 | Submittal | 28 | 2027-03-07 | 2027-04-10
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.MBL.GEN.7280 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.MBL.GEN.7300 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.MBL.GEN.7320 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.MBL.GEN.7260 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.MBL.GEN.7340 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | LPG System | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ LPG System | QP.E.ME.MBL.GEN.5100 | Submittal | 21 | 2027-09-22 | 2027-10-17
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.MBL.GEN.7360 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Fire Suppression | QP.E.ME.CBR.GEN.1000 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Plumbing | Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Plumbing | QP.E.ME.CBR.GEN.1011 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ LPG System | QP.E.ME.CBR.GEN.1055 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.CBR.GEN.1022 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Electrical | QP.E.ME.CBR.GEN.1033 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ ELV (Low Current System) | QP.E.ME.CBR.GEN.1044 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.MBL.GEN.7380 | Submittal | 28 | 2027-12-09 | 2028-01-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Diesel | Diesel | Diesel | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Diesel | QP.E.ME.MBL.GEN.7420 | Submittal | 21 | 2028-02-01 | 2028-02-26
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Water Features | Water Features | Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Water Features | QP.E.ME.MBL.GEN.7440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M | QP.E.ME.MBL.GEN.6520 | Submittal | 28 | 2026-06-14 | 2026-07-15
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Grey Water Treatment/ Sewage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Grey Water Treatment/ Sewage | QP.E.ME.MBL.GEN.1050 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Stromwater/ Drainage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Stromwater/ Drainage | QP.E.ME.MBL.GEN.1060 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1040 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M | QP.E.ME.MBL.GEN.6540 | Submittal | 28 | 2026-07-16 | 2026-08-17
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ AHU Room | QP.E.ME.MBL.GEN.1160 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Transformer/ Switchgear/ Panel Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Transformer/ Switchgear/ Panel Room | QP.E.ME.MBL.GEN.1240 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Generator Room/ Diesel Tank | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Generator Room/ Diesel Tank | QP.E.ME.MBL.GEN.1250 | Submittal | 14 | 2026-10-05 | 2026-10-20
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | ETS/ CWP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ ETS/ CWP Room | QP.E.ME.MBL.GEN.1170 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1030 | Submittal | 14 | 2026-09-24 | 2026-10-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1290 | Submittal | 28 | 2026-09-01 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M | QP.E.ME.MBL.GEN.6560 | Submittal | 14 | 2026-08-18 | 2026-09-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1020 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Domestic Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Domestic Water | QP.E.ME.MBL.GEN.1010 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Fire Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Fire Water | QP.E.ME.MBL.GEN.1000 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1280 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 LOBBY LEVEL +905.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 LOBBY LEVEL +905.00M | QP.E.ME.MBL.GEN.6640 | Submittal | 21 | 2026-09-03 | 2026-09-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 UPEER LOBBY LEVEL MEZZANINE +909M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M | QP.E.ME.MBL.GEN.6660 | Submittal | 21 | 2026-09-29 | 2026-10-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L2 THEATRE STALLS +913M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L2 THEATRE STALLS +913M | QP.E.ME.MBL.GEN.6680 | Submittal | 21 | 2026-10-24 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | QP.E.ME.MBL.GEN.6700 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | QP.E.ME.MBL.GEN.6720 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 SECOND CIRCLE AND LOFT +928.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 SECOND CIRCLE AND LOFT +928.00M | QP.E.ME.MBL.GEN.6740 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M | QP.E.ME.MBL.GEN.5540 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - AHU Room | QP.E.ME.MBL.GEN.1180 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Makeup Air Unit and Ecology | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Makeup Air Unit and Ecology | QP.E.ME.MBL.GEN.1190 | Submittal | 14 | 2027-01-06 | 2027-01-21
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Sky Garden Irrigation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Sky Garden Irrigation | QP.E.ME.MBL.GEN.1070 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L6 SKY GARDEN +935.85M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L6 SKY GARDEN +935.85M | QP.E.ME.MBL.GEN.6760 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M | QP.E.ME.MBL.GEN.6580 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | Plant Room - Fan Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M ¦ Plant Room - Fan Room | QP.E.ME.MBL.GEN.6600 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Kitchen and Laundry | Kitchen and Laundry | Kitchen and Laundry | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Kitchen and Laundry | QP.E.ME.MBL.GEN.7400 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | MEP | Panels | Panels | Panels | Panels | Panels | Shop Drawings ¦ MEP ¦ Panels | QP.E.ME.MBL.GEN.6510 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Mechanical | QP.E.ME.BL1.GEN.3720 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical | QP.E.ME.BL1.GEN.3740 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL1.GEN.3760 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL1.GEN.3780 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Mechanical | QP.E.ME.BL1.GEN.3800 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical | QP.E.ME.BL1.GEN.3820 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1020 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1030 | Submittal | 21 | 2027-02-25 | 2027-03-23
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1040 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1050 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ ICT Containment | QP.E.ME.BL1.GEN.1060 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL1.GEN.2940 | Submittal | 21 | 2027-04-11 | 2027-05-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.2950 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.2960 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.2970 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL1.GEN.2980 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1510 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1520 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1530 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1540 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ ICT Containment | QP.E.ME.BL1.GEN.1550 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.BL1.GEN.3280 | Submittal | 21 | 2027-08-30 | 2027-09-22
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL1.GEN.3320 | Submittal | 21 | 2027-10-07 | 2027-10-31
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL1.GEN.3340 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL1.GEN.3360 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL1.GEN.3580 | Submittal | 21 | 2027-11-15 | 2027-12-08
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL1.GEN.3600 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL1.GEN.3620 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL1.GEN.3680 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL1.GEN.3640 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL1.GEN.3660 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3480 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL1.GEN.1000 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL1.GEN.3700 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3400 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical | QP.E.ME.BL2.GEN.3420 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL2.GEN.3440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL2.GEN.3460 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3480 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical | QP.E.ME.BL2.GEN.3500 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1020 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1030 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1040 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1050 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.1060 | Submittal | 21 | 2027-04-18 | 2027-05-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1910 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1920 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1930 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1940 | Submittal | 21 | 2027-04-29 | 2027-05-27
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL2.GEN.1950 | Submittal | 21 | 2027-05-12 | 2027-06-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.2110 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.2120 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.2130 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.2140 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.2150 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL2.GEN.3160 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL2.GEN.3200 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL2.GEN.3220 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL2.GEN.3240 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL2.GEN.3260 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL2.GEN.3280 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL2.GEN.3300 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL2.GEN.3380 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL2.GEN.3320 | Submittal | 28 | 2027-11-22 | 2027-12-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL2.GEN.3340 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3500 | Submittal | 14 | 2028-02-17 | 2028-03-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL2.GEN.1000 | Submittal | 16 | 2028-02-17 | 2028-03-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL2.GEN.3360 | Submittal | 14 | 2028-04-09 | 2028-04-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Mechanical | QP.E.ME.BL3.GEN.3640 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical | QP.E.ME.BL3.GEN.3660 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical | QP.E.ME.BL3.GEN.3700 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Mechanical | QP.E.ME.BL3.GEN.3680 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1020 | Submittal | 21 | 2026-06-17 | 2026-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.1030 | Submittal | 21 | 2026-07-12 | 2026-08-04
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1040 | Submittal | 21 | 2026-08-05 | 2026-08-29
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1050 | Submittal | 21 | 2026-08-30 | 2026-09-22
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ ICT Containment | QP.E.ME.BL3.GEN.1060 | Submittal | 21 | 2026-10-07 | 2026-10-31
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1790 | Submittal | 21 | 2026-12-31 | 2027-01-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.3280 | Submittal | 21 | 2027-01-25 | 2027-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1810 | Submittal | 21 | 2027-02-18 | 2027-03-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1820 | Submittal | 21 | 2027-03-18 | 2027-04-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ ICT Containment | QP.E.ME.BL3.GEN.1830 | Submittal | 21 | 2027-04-12 | 2027-05-05
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL3.GEN.3400 | Submittal | 21 | 2027-06-23 | 2027-07-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL3.GEN.3440 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL3.GEN.3460 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL3.GEN.3480 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL3.GEN.3500 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL3.GEN.3540 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL3.GEN.3560 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL3.GEN.3620 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL3.GEN.3600 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL3.GEN.3580 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3520 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL3.GEN.1000 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL3.GEN.3520 | Submittal | 14 | 2028-04-04 | 2028-04-19
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Mechanical | QP.E.ME.BL4.GEN.6010 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical | QP.E.ME.BL4.GEN.6030 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Mechanical | QP.E.ME.BL4.GEN.6050 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Electrical | QP.E.ME.BL4.GEN.6070 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Mechanical | QP.E.ME.BL4.GEN.6090 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical | QP.E.ME.BL4.GEN.6110 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Fire Suppression | QP.E.ME.BL4.GEN.2110 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2120 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2130 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2140 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ ICT Containment | QP.E.ME.BL4.GEN.2150 | Submittal | 21 | 2026-11-01 | 2026-11-24
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2910 | Submittal | 21 | 2026-12-05 | 2026-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.5550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2930 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2940 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ ICT Containment | QP.E.ME.BL4.GEN.2950 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2810 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2820 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2830 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2840 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ ICT Containment | QP.E.ME.BL4.GEN.2850 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL4.GEN.5770 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL4.GEN.5810 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL4.GEN.5830 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL4.GEN.5850 | Submittal | 21 | 2027-09-29 | 2027-10-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL4.GEN.5870 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL4.GEN.5930 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL4.GEN.5950 | Submittal | 21 | 2027-12-05 | 2027-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL4.GEN.5890 | Submittal | 21 | 2028-01-12 | 2028-02-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL4.GEN.5970 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL4.GEN.5990 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3540 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL4.GEN.3110 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL4.GEN.5910 | Submittal | 14 | 2028-04-02 | 2028-04-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Mechanical | QP.E.ME.BL5.GEN.3040 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical | QP.E.ME.BL5.GEN.3060 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL5.GEN.3080 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL5.GEN.3100 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Mechanical | QP.E.ME.BL5.GEN.3120 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical | QP.E.ME.BL5.GEN.3140 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1020 | Submittal | 21 | 2026-10-29 | 2026-11-22
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1030 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1040 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1050 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ ICT Containment | QP.E.ME.BL5.GEN.1060 | Submittal | 21 | 2026-11-25 | 2026-12-19
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1560 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1570 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1580 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL5.GEN.1590 | Submittal | 21 | 2027-04-10 | 2027-05-03
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1750 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1760 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1770 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1780 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ ICT Containment | QP.E.ME.BL5.GEN.1790 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL5.GEN.2800 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL5.GEN.2840 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL5.GEN.2860 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL5.GEN.2880 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL5.GEN.3020 | Submittal | 14 | 2027-10-24 | 2027-11-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL5.GEN.2900 | Submittal | 14 | 2027-12-01 | 2027-12-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL5.GEN.2920 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL5.GEN.3000 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL5.GEN.2940 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL5.GEN.2960 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3560 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL5.GEN.1000 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL5.GEN.2980 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Mechanical | QP.E.ME.PAR.GEN.1459 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Electrical | QP.E.ME.PAR.GEN.1479 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Mechanical | QP.E.ME.PAR.GEN.1499 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Electrical | QP.E.ME.PAR.GEN.1519 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Fire Suppression | QP.E.ME.PAR.GEN.1000 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1011 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1022 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1033 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ ICT Containment | QP.E.ME.PAR.GEN.1044 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Fire Suppression | QP.E.ME.PAR.GEN.1055 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1066 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1077 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1088 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ ICT Containment | QP.E.ME.PAR.GEN.1099 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.PAR.GEN.1219 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.PAR.GEN.1259 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.PAR.GEN.1279 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.PAR.GEN.1299 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.PAR.GEN.1419 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.PAR.GEN.1319 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.PAR.GEN.1339 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.PAR.GEN.1439 | Submittal | 14 | 2028-02-07 | 2028-02-23
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.PAR.GEN.1359 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.PAR.GEN.1379 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.PAR.GEN.1399 | Submittal | 14 | 2028-03-09 | 2028-03-25
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3600 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3610 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3620 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.4430 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4440 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.4450 | Submittal | 14 | 2027-12-18 | 2028-01-02
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3960 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3970 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3980 | Submittal | 14 | 2028-01-01 | 2028-01-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Fire Suppression | QP.E.ME.MBL.GEN.3930 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3940 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Electrical | QP.E.ME.MBL.GEN.3950 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Fire Suppression | QP.E.ME.MBL.GEN.3810 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3820 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Electrical | QP.E.ME.MBL.GEN.3830 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4400 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4410 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4420 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4340 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4350 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4360 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4520 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4530 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4540 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4640 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4650 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4660 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3870 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3880 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3890 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3840 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3850 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3860 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.4550 | Submittal | 21 | 2028-02-08 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4560 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.4570 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 3, 4 & 5 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 3, 4 & 5 | QP.E.FA.GEN.GEN.1460 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 1 & 2 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 1 & 2 | QP.E.FA.GEN.GEN.2180 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Loft and Lobby | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Loft and Lobby | QP.E.FA.GEN.GEN.2140 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | QP.E.FA.GEN.GEN.2160 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Blades | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Blades | QP.E.FA.GEN.GEN.1820 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Lobby and Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Lobby and Loft | QP.E.FA.GEN.GEN.1770 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Above Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Above Loft | QP.E.FA.GEN.GEN.1780 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Blades | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Blades | QP.E.FA.GEN.GEN.1890 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Main Building | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Main Building | QP.E.FA.GEN.GEN.2230 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Facade | Facade | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 1 | QP.E.FA.GEN.GEN.1920 | Submittal | 28 | 2026-09-29 | 2026-10-31
Shop Drawings | Facade | Facade | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 2 | QP.E.FA.GEN.GEN.1930 | Submittal | 28 | 2026-08-26 | 2026-09-28
Shop Drawings | Facade | Facade | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 3 | QP.E.FA.GEN.GEN.1940 | Submittal | 28 | 2026-05-17 | 2026-06-21
Shop Drawings | Facade | Facade | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 4 | QP.E.FA.GEN.GEN.1950 | Submittal | 28 | 2026-06-22 | 2026-07-23
Shop Drawings | Facade | Facade | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 5 | QP.E.FA.GEN.GEN.1960 | Submittal | 28 | 2026-07-25 | 2026-08-25
Shop Drawings | Facade | Facade | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Facade ¦ Amphitheatre | QP.E.FA.GEN.GEN.2240 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Lobby | Lobby | Lobby | Lobby | Shop Drawings ¦ Facade ¦ Lobby | QP.E.FA.GEN.GEN.2090 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | Loft | Loft | Loft | Loft | Shop Drawings ¦ Facade ¦ Loft | QP.E.FA.GEN.GEN.2100 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Above Loft | Above Loft | Above Loft | Above Loft | Shop Drawings ¦ Facade ¦ Above Loft | QP.E.FA.GEN.GEN.1910 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | Link Bridges | Link Bridges | Link Bridges | Link Bridges | Shop Drawings ¦ Facade ¦ Link Bridges | QP.E.FA.GEN.GEN.2050 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Facade | Facade | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Shop Drawings ¦ Facade ¦ Facade Lighting Fixtures | QP.E.FA.GEN.GEN.1450 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | GRC Cladding | GRC Cladding | GRC Cladding | GRC Cladding | Shop Drawings ¦ Facade ¦ GRC Cladding | QP.E.FA.GEN.GEN.1390 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 1 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 1 | QP.E.CV.MBL.GEN.3060 | Submittal | 28 | 2026-08-06 | 2026-09-07
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 2 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 2 | QP.E.CV.MBL.GEN.3560 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 3 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 3 | QP.E.CV.MBL.GEN.3580 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 4 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 4 | QP.E.CV.MBL.GEN.3600 | Submittal | 28 | 2027-01-03 | 2027-02-03
Shop Drawings | External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Shop Drawings ¦ External Works ¦ Waterproofing for External Works | QP.E.EX.GEN.GEN.1040 | Submittal | 28 | 2026-06-25 | 2026-07-27
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Excavation | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Excavation | QP.E.CV.MBL.GEN.3320 | Submittal | 28 | 2027-01-06 | 2027-02-07
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Blinding Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Blinding Including Embedded Items | QP.E.CV.MBL.GEN.3500 | Submittal | 28 | 2027-02-23 | 2027-03-29
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Foundation Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Foundation Including Embedded Items | QP.E.CV.MBL.GEN.3480 | Submittal | 28 | 2027-04-13 | 2027-05-19
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Structural Concrete Works Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Structural Concrete Works Including Embedded Items | QP.E.CV.MBL.GEN.3520 | Submittal | 28 | 2027-06-03 | 2027-07-05
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4000 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Finishing | Finishing | Finishing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Finishing | QP.E.AF.MBL.GEN.4030 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4010 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Doors / Openings | QP.E.AF.MBL.GEN.4020 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Fire Suppression | QP.E.ME.MBL.GEN.1690 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Plumbing | Plumbing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Plumbing | QP.E.ME.MBL.GEN.1700 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.1710 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Electrical | Electrical | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Electrical | QP.E.ME.MBL.GEN.1720 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ ELV (Low Current System) | QP.E.ME.MBL.GEN.1730 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | External Utilities | Irrigation Works | Irrigation Works | Irrigation Works | Irrigation Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ Irrigation Works | QP.E.EX.GEN.GEN.1090 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Drainage Works | External Drainage Works | External Drainage Works | External Drainage Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Drainage Works | QP.E.EX.GEN.GEN.1110 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Lighting Works | External Lighting Works | External Lighting Works | External Lighting Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Lighting Works | QP.E.EX.GEN.GEN.1170 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | External Utilities | Low Current | Low Current | Low Current | Low Current | Shop Drawings ¦ External Works ¦ External Utilities ¦ Low Current | QP.E.EX.GEN.GEN.1100 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Shop Drawings ¦ External Works ¦ Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 | Submittal | 14 | 2027-08-07 | 2027-08-22
Shop Drawings | External Works | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Shop Drawings ¦ External Works ¦ Water and Environment | QP.E.EX.GEN.GEN.1220 | Submittal | 21 | 2026-11-23 | 2026-12-16
Shop Drawings | External Works | External Fixtures | External Fixtures | External Fixtures | External Fixtures | External Fixtures | Shop Drawings ¦ External Works ¦ External Fixtures | QP.E.EX.GEN.GEN.1260 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | External Works | LPG System | LPG System | LPG System | LPG System | LPG System | Shop Drawings ¦ External Works ¦ LPG System | QP.E.EX.GEN.GEN.1300 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Fit-out | Fit-out | Fit-out | Fit-out | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Fit-out | QP.C.PS.GEN.GEN.2590 | Submittal | 110 | 2026-07-30 | 2026-12-06
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Stage Engineering | Stage Engineering | Stage Engineering | Stage Engineering | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Stage Engineering | QP.C.PS.GEN.GEN.2560 | Submittal | 110 | 2026-12-07 | 2027-04-17
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | AV / Broadcast | AV / Broadcast | AV / Broadcast | AV / Broadcast | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ AV / Broadcast | QP.C.PS.GEN.GEN.1200 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ Technology (ICT) | QP.C.PS.GEN.GEN.1810 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Control Systems | Control Systems | Control Systems | Control Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Control Systems | QP.C.PS.GEN.GEN.1880 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Lighting Systems | Lighting Systems | Lighting Systems | Lighting Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Lighting Systems | QP.C.PS.GEN.GEN.1850 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Conveying System Finishes | QP.C.PS.GEN.GEN.2120 | Submittal | 150 | 2027-06-07 | 2027-11-29
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | HVAC System | HVAC System | HVAC System | HVAC System | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ HVAC System | QP.C.PS.GEN.GEN.2100 | Submittal | 90 | 2027-11-01 | 2028-02-13
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | ID Finishes | ID Finishes | ID Finishes | ID Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ ID Finishes | QP.C.PS.GEN.GEN.1930 | Submittal | 90 | 2027-07-18 | 2027-10-31
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Water Features | QP.C.PS.GEN.GEN.1960 | Submittal | 120 | 2027-02-16 | 2027-07-13
Shop Drawings | Provisional Sums | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | Shop Drawings ¦ Provisional Sums ¦ PS5 - Signage and Wayfinding | QP.C.PS.GEN.GEN.2140 | Submittal | 60 | 2028-07-29 | 2028-10-07
Shop Drawings | Provisional Sums | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | Shop Drawings ¦ Provisional Sums ¦ PS6 - Soft Landscaping | QP.C.PS.GEN.GEN.2180 | Submittal | 160 | 2027-08-30 | 2028-03-08
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Concrete Superstructure | QP.C.PS.GEN.GEN.2360 | Submittal | 30 | 2028-06-08 | 2028-07-12
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Foundation | Foundation | Foundation | Foundation | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Foundation | QP.C.PS.GEN.GEN.2260 | Submittal | 30 | 2028-05-01 | 2028-06-07
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Landscape | Landscape | Landscape | Landscape | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Landscape | QP.C.PS.GEN.GEN.2320 | Submittal | 30 | 2028-07-31 | 2028-09-03
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Promenade Bridge MEP | QP.C.PS.GEN.GEN.2340 | Submittal | 30 | 2028-06-26 | 2028-07-30
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Technology (ICT) | QP.C.PS.GEN.GEN.2400 | Submittal | 150 | 2027-04-11 | 2027-10-07
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Traffic & Car Parking | QP.C.PS.GEN.GEN.2500 | Submittal | 150 | 2027-07-12 | 2028-01-03

## Picklists
| #VALUE! |  | Numbering System Document - Metadata Mapping
DOCUMENT NUMBERING DROPDOWN ATTRIBUTES | [18 empty] | QIC GENERAL DROPDOWN ATTRIBUTES
FIELD 01 - PROJECT CODE |  | FIELD 02 - ORIGINATOR |  | FIELD 03 - CONTRACT REFERENCE |  | FIELD 04 - DOCUMENT TYPES |  | FIELD 05 - DISCIPLINE |  | FIELD 06 - AREA/ZONE |  | FIELD 07 - VENUE/BUILDING |  | FIELD 08 - SERIAL NUMBER |  |  |  |  | DOCUMENT DETAILS |  |  | SUITABILITY STATUS |  | NAP GENERAL DROPDOWN ATTRIBUTES
Ab. 01 | 1 - Project Name | Ab. 02 | 2 - Originator Name | Ab. 03 | 3 - Contract Reference | Ab. 04 | 4 - Document Type | Ab. 05 | 5 - Discipline | Ab. 06 | 6 - Area/Zone | Ab. 07 | 7 - Venue/Building | Ab. 08A | 8A - Drawing Type | Ab. 08B | 8B - Level | 8C - Sequence Number | Authoring Software | File/Exchange Format | Scope Area | Code | Status | Scale | Classification ID | Classification | Corporate Discipline | Author
QF01012 | Qiddaya Performing Arts Center | NES | Nesma and Partners | C04518 | Contract Number | AGD | Agenda | ACO | Acoustic | 00 | Overall | Z00000 | Overall | 0 | General (General Notes, Abbreviations, Legends, Single Line Diagrams, General Detail) | 00 | Non-Specific ( For Blade ) | 4 Digit Sequence Number For Drawings/Models | Revit | .rvt | Design Management | S0 (WIP) | Initial status or WIP | NTS | FI_60_25 | Drawing | Architectural | Nesma & Partners
[6 empty] | AVV | Agreed Value of Variation | ADM | Administration | 01 | Zone Sheet 1 | CENT01 | Center Block | 1 | Elevations (Vertical View) | B1 | Basement 1 - Parking A +900.50 | 3 Digit Sequence Number For Documents | Civil3D | .nwc | Architecture / LDC | S1 (Shared) | Suitable for Coordination | AS INDICATED | FI_90_75 | Schedule or table | Electrical | JINGGONG
[6 empty] | ASB | As Built | ARC | Architectural | 02 | Zone Sheet 2 | GARD01 | Guard House | 2 | Plans (Overall, Horizontal View, Floor Plan, Ceiling Plan, Site Plan, Loading Plan) | B2 | Basement 2 - Service +893.50 |  | MicrosoftWord | .nwd | Landscape | S2 (Shared) | Suitable for Information | 1:1 | FI_60_53 | Model | Façade | ALUTEC
[6 empty] | AUR | Audit Report | ADT | Area Development | 03 | Zone Sheet 3 | BLAD01 | Blade 01 | 3 | Sections (Sectional View, Wall Section, Riser) | B3 | Basement 3 - Promenade +887.750 |  | MicrosoftExcel | .ifc | Interior Design | S3 (Shared) | Suitable for Review and Comment | 1:2 | FI_60_15 | Clash Rendition | Fire & Life Safety | AFCO
[6 empty] | BOQ | Bill of Quantities | ASM | Assets Management | 04 | Zone Sheet 4 | BLAD02 | Blade 02 | 4 | Large-scale Views (Enlarged Details) (Plans, Elevations, Stair Sections, etc) | FL | Foundation level |  | Navisworks | .pdf | Signage & Wayfinding | S4 (Shared) | Suitable for Review and Authorisation | 1:5 | FI_40_10 | Calculations | Interior Design | DOKA
[6 empty] | BEP | BIM Execution Plan | AVL | Audio Visual | 05 | Zone Sheet 5 | BLAD03 | Blade 03 | 5 | Details (Any detail view, such as Wall / Floor / Manhole Detail, etc) | L1 | Lobby Level +905.0 |  | inDesign | .jpg | Public Interaction & Activation | S5 (Shared) | Suitable for Review and Acceptance | 1:10 | FI_90_72 | Report | Infrastructure | RAWABI
[6 empty] | BIM | BIM Model | AUV | Audio/Video | 06 | Zone Sheet 6 | BLAD04 | Blade 04 | 6 | Schedules and Diagrams | L2 | Theater Stalls +913.0 |  | Inviso | .xls | Structure | A1 (Published) | Authorised and Accepted-Concept Design | 1:20 | FI_10_90 | Transmittal | Landscape | FALLPROTEC
[6 empty] | BRF | Brief | BRG | Bridges | 07 | Zone Sheet 7 | BLAD05 | Blade 05 | 7 | Combination of different views | L3 | Stalles Mezz & AD Theater +917.5 |  | JPG | .xer | Geotechnical Engineering | A2 (Published) | Authorised and Accepted-Schematic Design 100% | 1:25 | FI_90_47 | Log | Mechanical | TKE
[6 empty] | BUD | Budget | BRC | Broadcast | 08 | Zone Sheet 8 | MBLAD1 | Mini Blade 01 | 8 | User-Defined (For types that do not fall in other categories) | L4 | First Circle & AD Theater +921.0 |  | Recap | .dwf | Civil Engineering | A3 (Published) | Authorised and Accepted-Detailed Design 100% | 1:50 | FI_80_50 | Method statement | Structural | Subcontractor - Unassigned
[6 empty] | CAL | Calculation | BIM | Building Information Modelling | 09 | Zone Sheet 9 | MBLAD4 | Mini Blade 04 | 9 | 3D Representation (Isometric, Perspectives, Photographes) | L5 | Second Circle & Loft |  | Rhino | .dwg | MEP Engineering | A4 (Published) | Authorised and Accepted-Tender | 1:100 | FI_90_64 | Plan |  | Provisional Sum
[6 empty] | CER | Certificate | BMS | Building Management System | 10 | Zone Sheet 10 | SECE01 | SEC Room |  |  | L6 | SKY Garden +935.85 |  | Sketchup | .bcf | Fire & Life Safety | A5 (Published) | Authorised and Accepted-IFC | 1:150 |  |  |  | NAP PMO
[6 empty] | COR | Change Order | CWC | Chilled Water / Cooling | 11 | Zone Sheet 11 | PARK01 | Parking Building |  |  | L8 | Royal Majlis +948.10M |  | Autocad | .3ds | Pitch Design & Sports Playing Surfaces | A6 (Published) | Authorised and Accepted-Construction (Shop Drawing) | 1:200 |  |  |  | Sana Al-Jazerah
[6 empty] | CRA | Change Request Authorization | CIV | Civil | 12 | Zone Sheet 12 |  |  |  |  | M1 | Mez Upper Lobby +909.0 |  | ArcGIS | .skp | Specialist Lighting (Services and Systems) | A7 (Published) | Authorised and Accepted-As Built | 1:250
[6 empty] | CDT | Clash Detection Report | CPM | Contracts & Procurement | 13 | Zone Sheet 13 |  |  |  |  | M2 | Mez Loft MEP +931.10 |  |  | .docx | Acoustics | A8(Published) | Authorised and Accepted-In Use | 1:300
[6 empty] | CLM | Claim | CIN | Controls & Instrumentation | 14 | Zone Sheet 14 |  |  |  |  | RL | Roof Level |  |  | .rvt,.nwd,.ifc | AV / Broadcast |  |  | 1:350
[6 empty] | CIN | Client Instruction | CRE | Creative Designer | 15 | Zone Sheet 15 |  |  |  |  | ZZ | Overall |  |  | .nwc,.nwd,.ifc | Security |  |  | 1:500
[6 empty] | CRS | Comments Resolution Sheet | CDM | Crowd Management | 16 | Zone Sheet 16 | [8 empty] | .dwg,.nwc,.ifc | Vertical Transport
[6 empty] | CON | Contract | CUL | Culvert | 17 | Zone Sheet 17 | [8 empty] | .docx,.pdf | Facade & Roof Envelope
[6 empty] | COS | Cost Estimate | DRN | Drainage | 18 | Zone Sheet 18 | [8 empty] | .xer,.pdf | Crowd Modelling / Pedestrian Flow
[6 empty] | DAB | Dashboard | ELP | Earthing & Lighting Protection | 19 | Zone Sheet 19 | [8 empty] | .xls,.pdf | Sustainability
[6 empty] | DOA | Delegation of Authority | ELE | Electrical | 20 | Zone Sheet 20 | [8 empty] | .msp,.pdf | Accessibility
[6 empty] | DES | Design | ELC | Electrical Containment | 21 | Zone Sheet 21 | [8 empty] | .dwg,.pdf | Architect of Record
[6 empty] | MTX | Distribution Matrix | ENV | Environmental | 22 | Zone Sheet 22 | [8 empty] | .indd | Food & Beverage & Operations
[6 empty] | DSS | Dossier | EQP | Equipment | 23 | Zone Sheet 23 | [8 empty] | .pdf, .indd | Utilities, Roads & Infrastructure
[6 empty] | DRW | Drawing | FAC | Facade | 24 | Zone Sheet 24 | [8 empty] | .rvt,.nwc,.ifc | Traffic & Car Parking
[6 empty] | ENI | Engineer Instruction | FED | Federated | 25 | Zone Sheet 25 | [8 empty] | .gdb | Technology (ICT)
[6 empty] | EXP | Expenses | FIN | Finance | 26 | Zone Sheet 26 | [9 empty] | Sports & Specialist Lighting
[6 empty] | HOC | Handover Certificate | FAE | Fire Alarm & Emergency Lighting | 27 | Zone Sheet 27 | [9 empty] | BMS & Access Control
[6 empty] | IRT | Incident Report | FLS | Fire Life Safety | 28 | Zone Sheet 28 | [9 empty] | Waste Management
[6 empty] | ITP | Inspection & Test Plan | FPR | Fire Protection | [11 empty] | Health & Safety in Design
[6 empty] | INS | Instruction | FFE | Furniture Fixture & Equipment | [11 empty] | Wind
[6 empty] | IAB | Insurance and Bonds | GEN | General
[6 empty] | INV | Invoice | GIS | Geospatial Information System
[6 empty] | LAR | Laydown Area Access Request | GEH | Geotechnical & Hydraulics
[6 empty] | LTR | Letter | GRA | Graphics
[6 empty] | LIC | License | HSE | Health and Safety
[6 empty] | LST | List | EHV | High Voltage
[6 empty] | MAN | Manual | HVC | HVAC
[6 empty] | MPL | Master Plan | ICT | Information & Communication Technology
[6 empty] | MAR | Material Approval Request | INF | Infrastructure
[6 empty] | MIR | Material Inspection Request | INS | Installation
[6 empty] | MST | Method Statement | ITS | Intelligent Transportation System
[6 empty] | MOM | Minutes of Meeting | INT | Interior Design
[6 empty] | MIX | Mix Design | IRR | Irrigation
[6 empty] | MOD | Model | KNL | Kitchen & Laundry
[6 empty] | MRP | Monthly Report | LSE | Landscape
[6 empty] | NOC | No Objection Certificate | ELL | Lighting
[6 empty] | NCR | Non-Conformance Report | LTC | Lighting Control
[6 empty] | NDA | Non-Disclosure Agreement | ELV | Low Voltage
[6 empty] | NTC | Notice | LPG | LPG
[6 empty] | OMM | Operation & Maintenance Manual | MAR | Marine Engineering
[6 empty] | ORC | Organizational Chart | MPL | Master Planning
[6 empty] | OTR | Overtime Request | MEC | Mechanical
[6 empty] | PAP | Payment Application | EMV | Medium Voltage
[6 empty] | PYC | Payment Certificate | MEP | MEPF
[6 empty] | PRM | Permit | NTD | Non-Technical Document
[6 empty] | PAF | Personnel Approval Form | OSE | Operating Supplies and Equipment
[6 empty] | PIV | Photographs, Images & Videos | OTH | Others
[6 empty] | PLN | Plan | PLB | Plumbing
[6 empty] | PLT | Plant | PTW | Potable Water
[6 empty] | PPG | Policy & Procedure | PJC | Project Control
[6 empty] | PQS | Prequalification Submittal | QMS | Quality Management
[6 empty] | PRE | Presentation | RID | Rides
[6 empty] | PRO | Procedure | ERL | Road Lighting
[6 empty] | PEP | Project Execution Plan | RKW | Rockwork
[6 empty] | PRS | Proposal | SEC | Security System
[6 empty] | POR | Purchase Order | SEW | Sewage
[6 empty] | REG | Register | SHW | Show
[6 empty] | REP | Report | SGN | Signage / Wayfinding
[6 empty] | RFC | Request For Change | ESP | Small Power
[6 empty] | RSM | Resume | SSC | Smart City
[6 empty] | SVR | Safety Violation Report | SPL | Specialist Lighting
[6 empty] | SMP | Sample | SWD | Storm Water Drainage
[6 empty] | SCH | Schedule | STR | Structural
[6 empty] | SDW | Shop Drawing | SUR | Surveying / Mapping
[6 empty] | SIN | Site Instruction | SUS | Sustainability
[6 empty] | SOR | Site Observation Report | TEL | Telecommunication
[6 empty] | SPE | Specification | TNC | Testing/Commissioning
[6 empty] | STD | Standard | TFC | Traffic System
[6 empty] | SFA | Statement of Final Account | UTI | Utilities
[6 empty] | STR | Strategy | VNT | Ventilation Ductwork
[6 empty] | TOC | Taking Over Certificate | VTR | Vertical Transportation
[6 empty] | TOR | Task Order | VES | Voice Evacuation
[6 empty] | TEM | Template | WSM | Waste Management
[6 empty] | TDC | Tender Document | WTR | Water
[6 empty] | TRP | Test Report | CTV | CCTV System
[6 empty] | TMS | Time Sheet | ACS | Access Control System
[6 empty] | VOR | Variation Order | EFL | Facade Lighting
[6 empty] | WAR | Warranty / Guarantees | DES | Diesel
[6 empty] | WRP | Weekly Report | SMK | Smoke Ductwork
[6 empty] | WIR | Work Inspection Request | STL | Steel Structure
[6 empty] | RLM | RedLine Mark Drawing | FWR | Formwork
[6 empty] | MDP | Master Information Delivery Plan | ELS | Emergency Lighting system
[6 empty] | TDP | Task Information Delivery Plan | EBW | Electrical Builder Works
[8 empty] | MBW | Mechanical Builder Works
[8 empty] | EBC | Electrical Busway
[8 empty] | WFT | Water Features
[8 empty] | LOG | Logistics