## TIDP_Sheet
TASK INFORMATION DELIVERY PLAN (TIDP)
CLIENT | Qiddiya | #VALUE!
PROJECT | Qiddiya Performing Arts Center (QPAC)
ORGANISATION | Nesma & Partners
DISCIPLINE | Façade
APPROVER | BSBG
DATE CREATED
DATE LAST UPDATED
REVISION NUMBER | 00
DOCUMENT REFERENCE | QF01012-NES-C04518-TDP-XXX-00-000000-000001
This document shall be populated and kept up-to-date by the task team | [10 empty] | REFER TO THE FILE NAMING CONVENTION IN THE BIM EXECUTION PLAN | [10 empty] | DATA EXCHANGE #01 | [5 empty] | DATA EXCHANGE #02
[11 empty] | DOC REFERENCE GENERATOR | [10 empty] | STAGE: | CONSTRUCTION |  |  |  |  | STAGE: | HAND OVER
[22 empty] | PROGRAMME REF: | [5 empty] | PROGRAMME REF:
[5 empty] | EXCHANGE FORMATS | [5 empty] | FIELD 01 | FIELD 02 | FIELD 03 | FIELD 04 | FIELD 05 | FIELD 06 | FIELD 07 | FIELD 08 |  |  |  |  | LEVEL OF INFORMATION NEED | [5 empty] | LEVEL OF INFORMATION NEED
DOCUMENT NUMBER | DOCUMENT TITLE | EXTRACTED FROM MODEL | SCOPE AREA | AUTHORING SOFTWARE | EXCHANGE FORMAT | SCALE | DELIVERY MILESTONE | PACKAGE NAME | ACTIVITY ID | CLASSIFICATION CODE | PROJECT | ORIGINATOR | CONTRACT | DOCUMENT TYPE | DISCIPLINE | AREA/ZONE | VENUE/BUILDING | DRAWING TYPE | LEVEL | SEQUENCE NUMBER | CORPORATE DISCIPLINE | 01-AUTHOR | 01-GEOMETRICAL | 01-NON GEOMETRICAL | 01-DURATION (DAYS) | 01-PREDECESSOR | 01-EXCHANGE DATE | 02-AUTHOR | 02-GEOMETRICAL | 02-NON GEOMETRICAL | 02-DURATION (DAYS) | 02-PREDECESSOR | 02-EXCHANGE DATE
QF01012-NES-C04518-CAL-FAC-00-Z00000-000004 | GS-1A Preliminary Concept Design Calculation |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-05-18 |  | QP.E.FA.GEN.GEN.2050 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 004 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-000005 | CL-1A Preliminary Concept Design Calculations |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-08 |  | QP.E.FA.GEN.GEN.1820 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 005 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-000006 | GS-2A Preliminary Concept Design Calculation |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-06-11 |  | QP.E.FA.GEN.GEN.2090 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 006 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-CAL-FAC-00-Z00000-000007 | CL-1D PRELIMINARY CONCEPT DESIGN CALCULATIONS |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-05-18 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 007 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-CAL-FAC-00-Z00000-000008 | BL-01 PRELIMINARY DESIGN VERIFICATION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-12 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 008 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-CAL-FAC-00-Z00000-000009 | GS-3A PRELIMINARY CONCEPT DESIGN CALCULATIONS |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-08-12 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 009 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-CAL-FAC-00-Z00000-000010 | GS-2B PRELIMINARY CONCEPT DESIGN CALCULATIONS |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-08-12 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 010 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-CAL-FAC-00-Z00000-000011 | GS-2C PRELIMINARY CONCEPT DESIGN CALCULATIONS |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-08-12 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 011 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-CAL-FAC-00-Z00000-000012 | GS-3C PRELIMINARY CONCEPT DESIGN CALCULATIONS |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-06-07 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 012 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-CAL-FAC-00-Z00000-000013 | CL-1B PRELIMINARY CONCEPT DESIGN CALCULATIONS |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-06-07 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 013 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000596 | BRIDGES_CONCEPT_REPORT |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0596 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000597 | BLADES_CL1_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-24 |  | QP.E.FA.GEN.GEN.1820 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0597 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000598 | BLADES_GS1_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-24 |  | QP.E.FA.GEN.GEN.1820 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0598 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000599 | BLADES_CL4_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-20 |  | QP.E.FA.GEN.GEN.1820 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0599 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000600 | BLADES_SC1_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-14 |  | QP.E.FA.GEN.GEN.1820 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0600 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000601 | BLADES_CL3_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.1820 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0601 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000602 | BLADES_GS3_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-12 |  | QP.E.FA.GEN.GEN.1820 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0602 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000603 | LOBBY_GS2_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-12 |  | QP.E.FA.GEN.GEN.2090 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0603 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000604 | LOBBY_GS3_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-12 |  | QP.E.FA.GEN.GEN.2090 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0604 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000605 | LOBBY_CL4_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0605 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000606 | LOBBY_CL5_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0606 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000607 | LOFT_CL1_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-09 |  | QP.E.FA.GEN.GEN.2100 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0607 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000608 | LOFT_CL2_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-30 |  | QP.E.FA.GEN.GEN.2100 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0608 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000609 | LOFT_GS3_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-12 |  | QP.E.FA.GEN.GEN.2100 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0609 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000610 | SKY_GARDEN_CL1_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-09 |  | QP.E.FA.GEN.GEN.1910 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0610 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000611 | SKY_GARDEN_GS3_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-12 |  | QP.E.FA.GEN.GEN.1910 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0611 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000612 | ROYAL_MAJLIS_CL1_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0612 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000613 | ROYAL_MAJLIS_CL2_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0613 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000614 | ROYAL_MAJLIS_CL4_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0614 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000615 | ROYAL_MAJLIS_GS3_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0615 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000616 | ROYAL_MAJLIST_SC1_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0616 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000617 | BRIDGE_BR1_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0617 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000618 | BRIDGE_BR2_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0618 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000619 | BRIDGE_BR3_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0619 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000620 | BRIDGE_BR4_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0620 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000621 | BRIDGE_BR5_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0621 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000622 | BRIDGE_BR6_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0622 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000623 | BLADES_THERMAL_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-02-09 |  | QP.E.FA.GEN.GEN.1820 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0623 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000624 | LOBBY_THERMAL_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-12 |  | QP.E.FA.GEN.GEN.2090 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0624 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000625 | LOFT_THERMAL_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-30 |  | QP.E.FA.GEN.GEN.2100 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0625 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000626 | SKY_GARDEN_THERMAL_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-30 |  | QP.E.FA.GEN.GEN.1910 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0626 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-REP-FAC-00-Z00000-000004 | GS-1A Preliminary Concept Design Report |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-06-15 |  | QP.E.FA.GEN.GEN.2100 | FI_40_10 | QF01012 | NES | C04518 | REP | FAC | 00 | Z00000 | 0 | 00 | 004 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-REP-FAC-00-Z00000-000006 | GS-2A Preliminary Concept Design Report |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-03 |  | QP.E.FA.GEN.GEN.1820 | FI_40_10 | QF01012 | NES | C04518 | REP | FAC | 00 | Z00000 | 0 | 00 | 006 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-REP-FAC-00-Z00000-8000589 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_90_72 | QF01012 | NES | C04518 | REP | FAC | 00 | Z00000 | 8 | 00 | 0589 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-REP-FAC-00-Z00000-8000590 | BASIS_OF_DESIGN_REPORT |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-05-18 |  | QP.E.FA.GEN.GEN.1820 | FI_90_72 | QF01012 | NES | C04518 | REP | FAC | 00 | Z00000 | 8 | 00 | 0590 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-REP-FAC-00-Z00000-8000591 | BLADES_CONCEPT_REPORT |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-05-18 |  | QP.E.FA.GEN.GEN.1820 | FI_90_72 | QF01012 | NES | C04518 | REP | FAC | 00 | Z00000 | 8 | 00 | 0591 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-REP-FAC-00-Z00000-8000592 | LOBBY_CONCEPT_REPORT |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_90_72 | QF01012 | NES | C04518 | REP | FAC | 00 | Z00000 | 8 | 00 | 0592 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-REP-FAC-00-Z00000-8000593 | LOFT_CONCEPT_REPORT |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-09 |  | QP.E.FA.GEN.GEN.2100 | FI_90_72 | QF01012 | NES | C04518 | REP | FAC | 00 | Z00000 | 8 | 00 | 0593 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-REP-FAC-00-Z00000-8000594 | SKY_GARDEN_CONCEPT_REPORT |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-30 |  | QP.E.FA.GEN.GEN.1910 | FI_90_72 | QF01012 | NES | C04518 | REP | FAC | 00 | Z00000 | 8 | 00 | 0594 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-REP-FAC-00-Z00000-8000595 | ROYAL MAJLIS_CONCEPT_REPORT |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1820 | FI_90_72 | QF01012 | NES | C04518 | REP | FAC | 00 | Z00000 | 8 | 00 | 0595 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-FAC-00-BLAD01-1ZZ0106 | BRIDGE6_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 1 | ZZ | 0106 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-BLAD01-1ZZ0107 | BLADE1_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 1 | ZZ | 0107 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-1ZZ0108 | BLADE1_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 1 | ZZ | 0108 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-1ZZ0109 | BLADE1_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 1 | ZZ | 0109 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-1ZZ0110 | BLADE1_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 1 | ZZ | 0110 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-1ZZ0111 | BLADE1_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 1 | ZZ | 0111 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0001 | BLADE1_PLAN | find |  | Rhino | .dwg,.pdf | 1:100 | 2026-10-31 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0001 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0002 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0002 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0003 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0003 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0004 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0004 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0005 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0005 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0006 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0006 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0007 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0007 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0008 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0008 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0009 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0009 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0010 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0010 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0011 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0011 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0012 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0012 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0013 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0013 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-2ZZ0014 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 2 | ZZ | 0014 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD01-5ZZ0629 | LOBBY_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.1820 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 5 | ZZ | 0629 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-FAC-00-BLAD01-5ZZ0630 | VMU 01 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 5 | ZZ | 0630 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD01-5ZZ0631 | VMU 01 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 5 | ZZ | 0631 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD01-5ZZ0632 | VMU 01 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD01 | 5 | ZZ | 0632 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD02-1ZZ0112 | BLADE1_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 1 | ZZ | 0112 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD02-1ZZ0113 | BLADE2_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 1 | ZZ | 0113 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-1ZZ0114 | BLADE2_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 1 | ZZ | 0114 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-1ZZ0115 | BLADE2_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 1 | ZZ | 0115 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-1ZZ0116 | BLADE2_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 1 | ZZ | 0116 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-1ZZ0117 | BLADE2_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 1 | ZZ | 0117 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-2ZZ0015 | BLADE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 2 | ZZ | 0015 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-BLAD02-2ZZ0016 | BLADE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 2 | ZZ | 0016 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-2ZZ0017 | BLADE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 2 | ZZ | 0017 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-2ZZ0018 | BLADE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 2 | ZZ | 0018 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-2ZZ0019 | BLADE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 2 | ZZ | 0019 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-2ZZ0020 | BLADE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 2 | ZZ | 0020 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-2ZZ0021 | BLADE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 2 | ZZ | 0021 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-2ZZ0022 | BLADE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 2 | ZZ | 0022 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-2ZZ0023 | BLADE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 2 | ZZ | 0023 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-2ZZ0024 | BLADE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 2 | ZZ | 0024 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-2ZZ0025 | BLADE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 2 | ZZ | 0025 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD02-5ZZ0633 | VMU 01 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 5 | ZZ | 0633 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD02-5ZZ0634 | VMU 01 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 5 | ZZ | 0634 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD02-5ZZ0635 | VMU 01 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 5 | ZZ | 0635 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD02-5ZZ0636 | VMU 01 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 5 | ZZ | 0636 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD03-1ZZ0118 | BLADE2_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 1 | ZZ | 0118 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD03-1ZZ0119 | BLADE3_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 1 | ZZ | 0119 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD03-1ZZ0120 | BLADE3_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 1 | ZZ | 0120 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD03-1ZZ0121 | BLADE3_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 1 | ZZ | 0121 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD03-2ZZ0026 | BLADE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 2 | ZZ | 0026 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-BLAD03-2ZZ0027 | BLADE3_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 2 | ZZ | 0027 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD03-2ZZ0028 | BLADE3_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 2 | ZZ | 0028 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD03-2ZZ0029 | BLADE3_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 2 | ZZ | 0029 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD03-2ZZ0030 | BLADE3_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 2 | ZZ | 0030 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD03-2ZZ0031 | BLADE3_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 2 | ZZ | 0031 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD03-2ZZ0032 | BLADE3_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 2 | ZZ | 0032 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD03-2ZZ0033 | BLADE3_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 2 | ZZ | 0033 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD03-2ZZ0034 | BLADE3_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 2 | ZZ | 0034 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD03-5ZZ0637 | VMU 01 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 5 | ZZ | 0637 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD03-5ZZ0638 | VMU 01 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 5 | ZZ | 0638 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD03-5ZZ0639 | VMU 01 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 5 | ZZ | 0639 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD03-5ZZ0640 | VMU 03 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 5 | ZZ | 0640 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD04-1ZZ0122 | BLADE3_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 1 | ZZ | 0122 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD04-1ZZ0123 | BLADE4_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 1 | ZZ | 0123 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-1ZZ0124 | BLADE4_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 1 | ZZ | 0124 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-1ZZ0125 | BLADE4_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 1 | ZZ | 0125 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-1ZZ0126 | BLADE4_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 1 | ZZ | 0126 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-1ZZ0127 | BLADE4_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 1 | ZZ | 0127 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0035 | BLADE3_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0035 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0036 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0036 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0037 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0037 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0038 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0038 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0039 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0039 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0040 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0040 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0041 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0041 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0042 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0042 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0043 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0043 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0044 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0044 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0045 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0045 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0046 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0046 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0047 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0047 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0048 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0048 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ0049 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 0049 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD04-5ZZ0641 | VMU 03 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 5 | ZZ | 0641 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD04-5ZZ0642 | VMU 03 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 5 | ZZ | 0642 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD04-5ZZ0643 | VMU 03 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 5 | ZZ | 0643 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD04-5ZZ0644 | VMU 03 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 5 | ZZ | 0644 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD05-1ZZ0128 | BLADE4_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 1 | ZZ | 0128 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD05-1ZZ0129 | BLADE5_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 1 | ZZ | 0129 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-1ZZ0130 | BLADE5_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 1 | ZZ | 0130 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-1ZZ0131 | BLADE5_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 1 | ZZ | 0131 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-1ZZ0132 | BLADE5_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 1 | ZZ | 0132 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-1ZZ0133 | BLADE5_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 1 | ZZ | 0133 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-2ZZ0050 | BLADE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 2 | ZZ | 0050 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-BLAD05-2ZZ0051 | BLADE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 2 | ZZ | 0051 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-2ZZ0052 | BLADE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 2 | ZZ | 0052 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-2ZZ0053 | BLADE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 2 | ZZ | 0053 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-2ZZ0054 | BLADE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 2 | ZZ | 0054 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-2ZZ0055 | BLADE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 2 | ZZ | 0055 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-2ZZ0056 | BLADE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 2 | ZZ | 0056 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-2ZZ0057 | BLADE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 2 | ZZ | 0057 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-2ZZ0058 | BLADE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 2 | ZZ | 0058 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-2ZZ0059 | BLADE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 2 | ZZ | 0059 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-2ZZ0060 | BLADE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 2 | ZZ | 0060 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-BLAD05-5ZZ0645 | VMU 03 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 5 | ZZ | 0645 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD05-5ZZ0646 | VMU 03 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 5 | ZZ | 0646 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD05-5ZZ0647 | VMU 04 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 5 | ZZ | 0647 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-BLAD05-5ZZ0648 | VMU 04 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD05 | 5 | ZZ | 0648 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0134 | BLADE5_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0134 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0135 | LOBBY_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0135 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0136 | LOBBY_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0136 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0137 | LOBBY_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0137 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0138 | LOFT_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0138 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0139 | LOFT_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0139 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0140 | LOFT_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0140 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0141 | LOFT_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0141 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0142 | LOFT_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0142 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0143 | LOFT_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0143 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0144 | LOFT_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0144 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0145 | LOFT_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0145 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0146 | LOFT_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0146 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0147 | LOFT_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0147 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0148 | SKY_GARDEN_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0148 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0149 | SKY_GARDEN_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0149 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0150 | SKY_GARDEN_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0150 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0151 | SKY_GARDEN_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0151 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0152 | SKY_GARDEN_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0152 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0153 | SKY_GARDEN_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0153 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0154 | SKY_GARDEN_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0154 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0155 | SKY_GARDEN_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0155 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0156 | ROYLA_MAJLIS__ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0156 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0157 | ROYLA_MAJLIS__ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0157 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0158 | ROYLA_MAJLIS__ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0158 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0159 | ROYLA_MAJLIS__ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0159 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0160 | ROYLA_MAJLIS__ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0160 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0161 | ROYLA_MAJLIS__ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0161 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0162 | ROYLA_MAJLIS__ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0162 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0163 | ROYLA_MAJLIS__ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0163 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0164 | BRIDGE1_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0164 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0165 | BRIDGE1_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0165 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0166 | BRIDGE1_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0166 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0167 | BRIDGE1_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0167 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0168 | BRIDGE2_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0168 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0169 | BRIDGE2_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0169 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0170 | BRIDGE2_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0170 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0171 | BRIDGE2_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0171 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0172 | BRIDGE3_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0172 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0173 | BRIDGE3_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0173 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0174 | BRIDGE3_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0174 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0175 | BRIDGE3_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0175 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0176 | BRIDGE4_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0176 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0177 | BRIDGE4_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0177 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0178 | BRIDGE4_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0178 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0179 | BRIDGE4_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0179 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0180 | BRIDGE5_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0180 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0181 | BRIDGE5_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0181 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0182 | BRIDGE5_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0182 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0183 | BRIDGE5_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0183 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0184 | BRIDGE6_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0184 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0185 | BRIDGE6_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0185 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0186 | BRIDGE6_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0186 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0628 | BRIDGES_THERMAL_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_40_10 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0628 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-1ZZ0689 | VMU 10 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-28 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 1 | ZZ | 0689 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0061 | BLADE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0061 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0062 | LOBBY_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0062 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0063 | LOBBY_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0063 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0064 | LOBBY_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0064 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0065 | LOBBY_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0065 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0066 | LOBBY_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0066 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0067 | LOBBY_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0067 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0068 | LOBBY_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0068 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0069 | LOBBY_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0069 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0070 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0070 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0071 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0071 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0072 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0072 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0073 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0073 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0074 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0074 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0075 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0075 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0076 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0076 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0077 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0077 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0078 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0078 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0079 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0079 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0080 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0080 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0081 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0081 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0082 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0082 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0083 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0083 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0084 | LOFT_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0084 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0085 | SKY_GARDEN_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0085 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0086 | SKY_GARDEN_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0086 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0087 | SKY_GARDEN_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0087 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0088 | SKY_GARDEN_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0088 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0089 | SKY_GARDEN_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0089 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0090 | ROYLA_MAJLIS_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0090 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0091 | ROYLA_MAJLIS_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0091 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0092 | ROYLA_MAJLIS_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0092 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0093 | ROYLA_MAJLIS_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0093 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0094 | ROYLA_MAJLIS_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0094 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0095 | BRIDGE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0095 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0096 | BRIDGE1_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0096 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0097 | BRIDGE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0097 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0098 | BRIDGE2_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0098 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0099 | BRIDGE3_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0099 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0100 | BRIDGE3_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0100 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0101 | BRIDGE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0101 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0102 | BRIDGE4_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0102 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0103 | BRIDGE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0103 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0104 | BRIDGE5_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0104 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-2ZZ0105 | BRIDGE6_PLAN |  |  | Rhino | .dwg,.pdf | 1:100 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 2 | ZZ | 0105 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-300004 | FACADE CL-1B - SS CHEVRON INCLINED BLADES HORIZONTAL SECTION DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-06-07 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 004 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000099 | FACADE GS-2B - GLAZING LOBBY -SKYLIGHT PROPOSED DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-08-12 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0099 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000100 | FACADE GS-2C - GLAZING LOBBY BRIDGE VERTICAL SECTION DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-08-12 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0100 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000117 | FACADE GS-2B - GLAZING LOBBY -SKYLIGHT PROPOSED DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-08-12 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0117 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000118 | FACADE GS-2C - GLAZING LOBBY BRIDGE VERTICAL SECTION DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-08-12 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0118 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000119 | FACADE GS-2C - GLAZING LOBBY BRIDGE VERTICAL SECTION DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-08-12 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0119 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000120 | FACADE GS-2C - GLAZING LOBBY BRIDGE VERTICAL SECTION DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-08-12 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0120 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000370 | WIRE FRAMING MODEL AND CALCULATION -03-BLASDES |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-15 |  | QP.E.FA.GEN.GEN.1820 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0370 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000371 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0371 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000372 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0372 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000373 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0373 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000374 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0374 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000375 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0375 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000376 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0376 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000377 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0377 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000378 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0378 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000379 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0379 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000380 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0380 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000381 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0381 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000382 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0382 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000383 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0383 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000384 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0384 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000385 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0385 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000386 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0386 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000387 | LOBBY_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0387 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000388 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0388 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000389 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0389 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000390 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0390 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000391 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0391 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000392 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0392 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000393 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0393 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000394 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0394 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000395 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0395 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000396 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0396 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000397 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0397 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000398 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0398 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000399 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0399 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000400 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0400 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000401 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0401 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000402 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0402 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000403 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0403 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000404 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0404 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000405 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0405 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000406 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0406 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000407 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0407 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000408 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0408 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000409 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0409 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000410 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0410 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000411 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0411 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000412 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0412 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000413 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0413 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000414 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0414 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000415 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0415 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000416 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0416 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000417 | LOBBY_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-18 |  | QP.E.FA.GEN.GEN.2090 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0417 | Façade | ALUTEC | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000418 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0418 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000419 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0419 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000420 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0420 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000421 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0421 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000422 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0422 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000423 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0423 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000424 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0424 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000425 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0425 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000426 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0426 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000427 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0427 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000428 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0428 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000429 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0429 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000430 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0430 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000431 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0431 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000432 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0432 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000433 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0433 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000434 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0434 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000435 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0435 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000436 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0436 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000437 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0437 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000438 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0438 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000439 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0439 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000440 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0440 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000441 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0441 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000442 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0442 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000443 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0443 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000444 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0444 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000445 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0445 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000446 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0446 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000447 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0447 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000448 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0448 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000449 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0449 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000450 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0450 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000451 | LOFT_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0451 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000452 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0452 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000453 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0453 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000454 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0454 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000455 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0455 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000456 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0456 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000457 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0457 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000458 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0458 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000459 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0459 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000460 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0460 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000461 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0461 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000462 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0462 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000463 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0463 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000464 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0464 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000465 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0465 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000466 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0466 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000467 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0467 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000468 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0468 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000469 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0469 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000470 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0470 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000471 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0471 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000472 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0472 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000473 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0473 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000474 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0474 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000475 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0475 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000476 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0476 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000477 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0477 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000478 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0478 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000479 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0479 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000480 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0480 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000481 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0481 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000482 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0482 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000483 | LOFT_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-06-02 |  | QP.E.FA.GEN.GEN.2100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0483 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000484 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0484 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000485 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0485 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000486 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0486 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000487 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0487 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000488 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0488 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000489 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0489 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000490 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0490 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000491 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0491 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000492 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0492 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000493 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0493 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000494 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0494 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000495 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0495 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000496 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0496 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000497 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0497 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000498 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0498 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000499 | SKY_GARDEN_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0499 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000500 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0500 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000501 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0501 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000502 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0502 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000503 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0503 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000504 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0504 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000505 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0505 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000506 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0506 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000507 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0507 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000508 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0508 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000509 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0509 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000510 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0510 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000511 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0511 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000512 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0512 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000513 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0513 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000514 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0514 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000515 | SKY_GARDEN_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-08-25 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0515 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000516 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0516 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000517 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0517 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000518 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0518 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000519 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0519 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000520 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0520 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000521 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0521 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000522 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0522 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000523 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0523 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000524 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0524 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000525 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0525 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000526 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0526 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000527 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0527 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000528 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0528 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000529 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0529 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000530 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0530 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000531 | ROYLA_MAJLIS_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0531 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000532 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0532 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000533 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0533 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000534 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0534 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000535 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0535 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000536 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0536 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000537 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0537 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000538 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0538 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000539 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0539 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000540 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0540 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000541 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0541 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000542 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0542 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000543 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0543 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000544 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0544 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000545 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0545 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000546 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0546 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000547 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0547 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000548 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0548 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000549 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0549 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-300055 | FACADE CL-1B - SS CHEVRON INCLINED BLADES VERTICAL SECTION DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-06-07 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 055 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000550 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0550 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000551 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0551 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000552 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0552 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000553 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0553 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000554 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0554 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000555 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0555 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000556 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0556 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000557 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0557 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000558 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0558 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000559 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0559 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000560 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0560 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000561 | ROYLA_MAJLIS_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-10-06 |  | QP.E.FA.GEN.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0561 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000562 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0562 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000563 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0563 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000564 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0564 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000565 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0565 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000566 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0566 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000567 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0567 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000568 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0568 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000569 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0569 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000570 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0570 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000571 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0571 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000572 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0572 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000573 | BRIDGE_VERTICAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0573 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000574 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0574 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000575 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0575 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000576 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0576 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000577 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0577 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000578 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0578 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000579 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0579 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000580 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0580 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000581 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0581 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000582 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0582 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000583 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0583 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000584 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0584 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000585 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0585 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000586 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0586 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000587 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0587 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000588 | BRIDGE_HORIZONTAL_SECTION |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0588 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-CENT01-300147 | FACADE GS-3C - GLAZING INFILL BLADE CORE HORIZONTAL SECTION DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-06-07 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 147 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-300182 | FACADE GS-3C - GLAZING INFILL BLADE CORE VERTICAL SECTION DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-06-07 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 182 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000003 | FACADE CL-1D - SS CHEVRON UNINSULATED INCLINED BLADES HORIZONTAL SECTION DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-05-18 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0003 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000054 | FACADE CL-1D - SS CHEVRON UNINSULATED INCLINED BLADES VERTICAL SECTION DETAIL |  |  | Rhino | .dwg,.pdf | 1:100 | 2026-05-18 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0054 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000187 | BRIDGE6_ELEVATION |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-12-29 |  | QP.E.FA.GEN.GEN.2050 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0187 | Façade | ALUTEC | LOD400 |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000188 | BLADE-01 SECTION DETAILS -01 |  |  | Rhino | .dwg,.pdf | 1:50 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0188 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000189 | BLADE-01 SECTION DETAILS -02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0189 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000190 | BLADE-01 SECTION DETAILS -03 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0190 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000191 | BLADE-01 SECTION DETAILS -04 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0191 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000192 | BLADE-01 SECTION DETAILS -05 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0192 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000193 | BLADE-01 SECTION DETAILS -06 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0193 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000194 | BLADE-01 SECTION DETAILS -07 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0194 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000195 | BLADE-01 SECTION DETAILS -08 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0195 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000196 | BLADE-01 SECTION DETAILS -09 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0196 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000197 | BLADE-01 SECTION DETAILS -10 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0197 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000198 | BLADE-01 SECTION DETAILS -11 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0198 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000199 | BLADE-01 SECTION DETAILS -12 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0199 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000200 | BLADE-01 SECTION DETAILS -13 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0200 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000201 | BLADE-01 SECTION DETAILS -14 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0201 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000202 | BLADE-01 SECTION DETAILS -15 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0202 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000203 | BLADE-01 SECTION DETAILS -16 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0203 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000204 | BLADE-01 SECTION DETAILS -17 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0204 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000205 | BLADE-01 SECTION DETAILS -18 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0205 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000206 | BLADE-01 SECTION DETAILS -19 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0206 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000207 | BLADE-01 SECTION DETAILS -20 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0207 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000208 | BLADE-01 SECTION DETAILS -21 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0208 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000209 | BLADE-01 SECTION DETAILS -22 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0209 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000210 | BLADE-01 SECTION DETAILS -23 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0210 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000211 | BLADE-01 SECTION DETAILS -24 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0211 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000212 | BLADE-01 SECTION DETAILS -25 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0212 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000213 | BLADE-01 SECTION DETAILS -26 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0213 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000214 | BLADE-01 SECTION DETAILS -27 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-01-27 |  | QP.E.FA.GEN.GEN.1920 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0214 | Façade | ALUTEC | LOD400 |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000215 | BLADE-02 SECTION DETAILS -01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0215 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000216 | BLADE-02 SECTION DETAILS -02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0216 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000217 | BLADE-02 SECTION DETAILS -03 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0217 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000218 | BLADE-02 SECTION DETAILS -04 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0218 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000219 | BLADE-02 SECTION DETAILS -05 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0219 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000220 | BLADE-02 SECTION DETAILS -06 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0220 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000221 | BLADE-02 SECTION DETAILS -07 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0221 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000222 | BLADE-02 SECTION DETAILS -08 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0222 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000223 | BLADE-02 SECTION DETAILS -09 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0223 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000224 | BLADE-02 SECTION DETAILS -10 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0224 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000225 | BLADE-02 SECTION DETAILS -11 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0225 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000226 | BLADE-02 SECTION DETAILS -12 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0226 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000227 | BLADE-02 SECTION DETAILS -13 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0227 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000228 | BLADE-02 SECTION DETAILS -14 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0228 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000229 | BLADE-02 SECTION DETAILS -15 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0229 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000230 | BLADE-02 SECTION DETAILS -16 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0230 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000231 | BLADE-02 SECTION DETAILS -17 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0231 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000232 | BLADE-02 SECTION DETAILS -18 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0232 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000233 | BLADE-02 SECTION DETAILS -19 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0233 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000234 | BLADE-02 SECTION DETAILS -20 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0234 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000235 | BLADE-02 SECTION DETAILS -21 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0235 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000236 | BLADE-02 SECTION DETAILS -22 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0236 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000237 | BLADE-02 SECTION DETAILS -23 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0237 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000238 | BLADE-02 SECTION DETAILS -24 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0238 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000239 | BLADE-02 SECTION DETAILS -25 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0239 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000240 | BLADE-02 SECTION DETAILS -26 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0240 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000241 | BLADE-02 SECTION DETAILS -27 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-30 |  | QP.E.FA.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0241 | Façade | ALUTEC | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000242 | BLADE-03 SECTION DETAILS -01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0242 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000243 | BLADE-03 SECTION DETAILS -02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0243 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000244 | BLADE-03 SECTION DETAILS -03 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0244 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000245 | BLADE-03 SECTION DETAILS -04 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0245 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000246 | BLADE-03 SECTION DETAILS -05 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0246 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000247 | BLADE-03 SECTION DETAILS -06 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0247 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000248 | BLADE-03 SECTION DETAILS -07 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0248 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000249 | BLADE-03 SECTION DETAILS -08 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0249 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000250 | BLADE-03 SECTION DETAILS -09 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0250 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000251 | BLADE-03 SECTION DETAILS -10 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0251 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000252 | BLADE-03 SECTION DETAILS -11 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0252 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000253 | BLADE-03 SECTION DETAILS -12 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0253 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000254 | BLADE-03 SECTION DETAILS -13 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0254 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000255 | BLADE-03 SECTION DETAILS -14 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0255 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000256 | BLADE-03 SECTION DETAILS -15 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0256 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000257 | BLADE-03 SECTION DETAILS -16 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0257 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000258 | BLADE-03 SECTION DETAILS -17 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0258 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000259 | BLADE-03 SECTION DETAILS -18 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0259 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000260 | BLADE-03 SECTION DETAILS -19 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0260 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000261 | BLADE-03 SECTION DETAILS -20 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0261 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000262 | BLADE-03 SECTION DETAILS -21 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0262 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000263 | BLADE-03 SECTION DETAILS -22 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0263 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000264 | BLADE-03 SECTION DETAILS -23 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0264 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000265 | BLADE-03 SECTION DETAILS -24 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0265 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000266 | BLADE-03 SECTION DETAILS -25 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0266 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000267 | BLADE-03 SECTION DETAILS -26 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0267 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000268 | BLADE-03 SECTION DETAILS -27 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-11-04 |  | QP.E.FA.GEN.GEN.1940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0268 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-21
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000269 | BLADE-04 SECTION DETAILS -01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0269 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000270 | BLADE-04 SECTION DETAILS -02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0270 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000271 | BLADE-04 SECTION DETAILS -03 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0271 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000272 | BLADE-04 SECTION DETAILS -04 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0272 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000273 | BLADE-04 SECTION DETAILS -05 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0273 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000274 | BLADE-04 SECTION DETAILS -06 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0274 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000275 | BLADE-04 SECTION DETAILS -07 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0275 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000276 | BLADE-04 SECTION DETAILS -08 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0276 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000277 | BLADE-04 SECTION DETAILS -09 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0277 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000278 | BLADE-04 SECTION DETAILS -10 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0278 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000279 | BLADE-04 SECTION DETAILS -11 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0279 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000280 | BLADE-04 SECTION DETAILS -12 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0280 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000281 | BLADE-04 SECTION DETAILS -13 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0281 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000282 | BLADE-04 SECTION DETAILS -14 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0282 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000283 | BLADE-04 SECTION DETAILS -15 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0283 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000284 | BLADE-04 SECTION DETAILS -16 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0284 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000285 | BLADE-04 SECTION DETAILS -17 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0285 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000286 | BLADE-04 SECTION DETAILS -18 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0286 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000287 | BLADE-04 SECTION DETAILS -19 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0287 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000288 | BLADE-04 SECTION DETAILS -20 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0288 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000289 | BLADE-04 SECTION DETAILS -21 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0289 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000290 | BLADE-04 SECTION DETAILS -22 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0290 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000291 | BLADE-04 SECTION DETAILS -23 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0291 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000292 | BLADE-04 SECTION DETAILS -24 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0292 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000293 | BLADE-04 SECTION DETAILS -25 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0293 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000294 | BLADE-04 SECTION DETAILS -26 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0294 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000295 | BLADE-04 SECTION DETAILS -27 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-12-02 |  | QP.E.FA.GEN.GEN.1950 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0295 | Façade | ALUTEC | LOD400 |  |  |  | 2026-07-23
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000296 | BLADE-05 SECTION DETAILS -01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0296 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000297 | BLADE-05 SECTION DETAILS -02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0297 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000298 | BLADE-05 SECTION DETAILS -03 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0298 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000299 | BLADE-05 SECTION DETAILS -04 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0299 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000300 | BLADE-05 SECTION DETAILS -05 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0300 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000301 | BLADE-05 SECTION DETAILS -06 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0301 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000302 | BLADE-05 SECTION DETAILS -07 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0302 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000303 | BLADE-05 SECTION DETAILS -08 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0303 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000304 | BLADE-05 SECTION DETAILS -09 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0304 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000305 | BLADE-05 SECTION DETAILS -10 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0305 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000306 | BLADE-05 SECTION DETAILS -11 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0306 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000307 | BLADE-05 SECTION DETAILS -12 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0307 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000308 | BLADE-05 SECTION DETAILS -13 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0308 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000309 | BLADE-05 SECTION DETAILS -14 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0309 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000310 | BLADE-05 SECTION DETAILS -15 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0310 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000311 | BLADE-05 SECTION DETAILS -16 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0311 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000312 | BLADE-05 SECTION DETAILS -17 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0312 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000313 | BLADE-05 SECTION DETAILS -18 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0313 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000314 | BLADE-05 SECTION DETAILS -19 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0314 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000315 | BLADE-05 SECTION DETAILS -20 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0315 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000316 | BLADE-05 SECTION DETAILS -21 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0316 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000317 | BLADE-05 SECTION DETAILS -22 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0317 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000318 | BLADE-05 SECTION DETAILS -23 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0318 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000319 | BLADE-05 SECTION DETAILS -24 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0319 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000320 | BLADE-05 SECTION DETAILS -25 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0320 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000321 | BLADE-05 SECTION DETAILS -26 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0321 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000322 | BLADE-05 SECTION DETAILS -27 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0322 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000323 | BLADE-05 SECTION DETAILS 28 |  |  | Rhino | .dwg,.pdf | 1:25 | 2027-02-24 |  | QP.E.FA.GEN.GEN.1960 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0323 | Façade | ALUTEC | LOD400 |  |  |  | 2026-08-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000324 | FAÇADE SYSTEM-01-FOR BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0324 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000325 | FAÇADE SYSTEM-01-FOR BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0325 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000326 | FAÇADE SYSTEM-02-FOR BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0326 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000327 | FAÇADE SYSTEM-02-FOR BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0327 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000328 | FAÇADE SYSTEM-03-FOR BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0328 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000329 | FAÇADE SYSTEM-03-FOR BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0329 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000330 | FAÇADE SYSTEM-04-FOR BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0330 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000331 | FAÇADE SYSTEM-04-FOR BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0331 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000332 | FAÇADE SYSTEM-05-FOR BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0332 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000333 | FAÇADE SYSTEM-05-FOR BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0333 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000334 | FAÇADE SYSTEM-06-FOR BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0334 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000335 | FAÇADE SYSTEM-06-FOR BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-01-15 |  | QP.E.FA.GEN.GEN.1460 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0335 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000336 | FAÇADE SYSTEM-01-FOR-NON-BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0336 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000337 | FAÇADE SYSTEM-01-FOR NON-BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0337 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000338 | FAÇADE SYSTEM-02-FOR NON-BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0338 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000339 | FAÇADE SYSTEM-02-FOR NON-BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0339 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000340 | FAÇADE SYSTEM-03-FOR NON-BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0340 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000341 | FAÇADE SYSTEM-03-FOR NON-BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0341 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000342 | FAÇADE SYSTEM-04-FOR NON-BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0342 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000343 | FAÇADE SYSTEM-04-FOR NON-BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0343 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000344 | FAÇADE SYSTEM-05-FOR NON-BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0344 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000345 | FAÇADE SYSTEM-05-FOR NON-BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0345 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000346 | FAÇADE SYSTEM-06-FOR NON-BLADES SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0346 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000347 | FAÇADE SYSTEM-06-FOR NON-BLADES SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-04-27 |  | QP.E.FA.GEN.GEN.2160 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0347 | Façade | ALUTEC | LOD400 |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000348 | FAÇADE SYSTEM-01-COMMON SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0348 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000349 | FAÇADE SYSTEM-01-COMMON SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0349 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000350 | FAÇADE SYSTEM-02-COMMON SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0350 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000351 | FAÇADE SYSTEM-02-COMMON SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0351 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000352 | FAÇADE SYSTEM-03-COMMON SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0352 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000353 | FAÇADE SYSTEM-03-COMMON SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0353 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000354 | FAÇADE SYSTEM-04-COMMON SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0354 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000355 | FAÇADE SYSTEM-04-COMMON SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0355 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000356 | FAÇADE SYSTEM-05-COMMON SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0356 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000357 | FAÇADE SYSTEM-05-COMMON SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0357 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000358 | FAÇADE SYSTEM-06-COMMON SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0358 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000359 | FAÇADE SYSTEM-06-COMMON SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0359 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000360 | FAÇADE SYSTEM-07-COMMON SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0360 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000361 | FAÇADE SYSTEM-07-COMMON SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0361 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000362 | FAÇADE SYSTEM-08-COMMON SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0362 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000363 | FAÇADE SYSTEM-08-COMMON SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0363 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000364 | FAÇADE SYSTEM-09-COMMON SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0364 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000365 | FAÇADE SYSTEM-09-COMMON SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0365 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000366 | FAÇADE SYSTEM-10-COMMON SHEET-01 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0366 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000367 | FAÇADE SYSTEM-10-COMMON SHEET-02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-03-25 |  | QP.E.FA.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0367 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000368 | WIRE FRAMING MODEL AND CALCULATION -01-NON BLADES |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-07-27 |  | QP.E.FA.GEN.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0368 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000369 | WIRE FRAMING MODEL AND CALCULATION -02 |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0369 | Façade | ALUTEC | LOD400 |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0649 | VMU 04 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0649 | Façade | ALUTEC | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0650 | VMU 04 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0650 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0651 | VMU 04 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0651 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0652 | VMU 04 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0652 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0653 | VMU 04 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-25 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0653 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0654 | VMU 05 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0654 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0655 | VMU 05 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0655 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0656 | VMU 05 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0656 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0657 | VMU 05 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0657 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0658 | VMU 05 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0658 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0659 | VMU 05 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0659 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0660 | VMU 06 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0660 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0661 | VMU 06 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0661 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0662 | VMU 06 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0662 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0663 | VMU 06 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0663 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0664 | VMU 06 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0664 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0665 | VMU 06 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0665 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0666 | VMU 06 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-30 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0666 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0667 | VMU 07 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-03 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0667 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0668 | VMU 07 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-03 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0668 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0669 | VMU 07 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-03 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0669 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0670 | VMU 07 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-03 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0670 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0671 | VMU 07 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-03 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0671 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0672 | VMU 07 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-03 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0672 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0673 | VMU 08 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-31 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0673 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0674 | VMU 08 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-31 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0674 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0675 | VMU 08 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-31 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0675 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0676 | VMU 08 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-31 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0676 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0677 | VMU 08 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-31 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0677 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0678 | VMU 09 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-10 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0678 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0679 | VMU 09 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-10 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0679 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0680 | VMU 09 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-10 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0680 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0681 | VMU 09 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-10 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0681 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0682 | VMU 09 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-10 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0682 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0683 | VMU 09 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-09-10 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0683 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0684 | VMU 10 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-28 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0684 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0685 | VMU 10 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-28 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0685 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0686 | VMU 10 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-28 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0686 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0687 | VMU 10 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-28 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0687 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-5ZZ0688 | VMU 10 Shop Drawings |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-08-28 |  | QP.E.FA.GEN.GEN.2230 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 5 | ZZ | 0688 | Façade | ALUTEC | LOD400 |  |  |  | 2026-06-16
QF01012-NES-C04518-CAL-FAC-00-Z00000-000014 | Calculation for Embed Blade Preliminary | [5 empty] | 2026-07-28 10:12 |  | QP.E.FA.GEN.GEN.1910 |  | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 014 | Façade | ALUTEC |  |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-000015 | CL-04A Preliminary Design Calculations | [5 empty] | 2026-04-25 18:57 |  | QP.E.FA.GEN.GEN.1910 |  | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 015 | Façade | ALUTEC |  |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-000016 | VMU 4 Structural Calculation | [5 empty] | 2026-07-11 10:03 |  | QP.E.FA.GEN.GEN.1910 |  | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 016 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-000017 | GS-03E Preliminary Concept Design Calculations | [5 empty] | 2026-07-14 09:44 |  | QP.E.FA.GEN.GEN.1910 |  | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 017 | Façade | ALUTEC |  |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-000018 | SC-01B Preliminary Concept Design Calculations | [5 empty] | 2026-07-14 10:29 |  | QP.E.FA.GEN.GEN.1910 |  | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 018 | Façade | ALUTEC |  |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-000019 | CL-02A Preliminary Design Calculation | [5 empty] | 2026-07-30 16:31 |  | QP.E.FA.GEN.GEN.1910 |  | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 019 | Façade | ALUTEC |  |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-000020 | CL-02B Preliminary Design Calculation | [5 empty] | 2026-07-30 17:31 |  | QP.E.FA.GEN.GEN.1910 |  | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 020 | Façade | ALUTEC |  |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-000022 | Blade 3 Embed Design Calculation | [5 empty] | 2026-08-02 15:37 |  | QP.E.FA.GEN.GEN.1910 |  | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 0 | 00 | 022 | Façade | ALUTEC |  |  |  |  | 2027-05-23
QF01012-NES-C04518-CAL-FAC-00-Z00000-8000627 | SIGNATURE_RESTAURANT_THERMAL_CALC |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-10-05 |  | QP.E.FA.GEN.GEN.1820 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAC | 00 | Z00000 | 8 | 00 | 0627 | Façade | ALUTEC | LOD400 |  |  |  | 2025-12-14
QF01012-NES-C04518-REP-FAC-00-Z00000-000005 | CI-1A Preliminary Concept Design Report |  |  | Rhino | .dwg,.pdf | 1:25 | 2026-02-15 18:51 |  | QP.E.FA.GEN.GEN.1910 | FI_40_10 | QF01012 | NES | C04518 | REP | FAC | 00 | Z00000 | 0 | 00 | 005 | Façade | ALUTEC | LOD400 |  |  |  | 2027-05-23
QF01012-NES-C04518-REP-FAC-00-Z00000-000008 | Blade 1,3 and 5 Facade Weight | [5 empty] | 2026-05-18 11:25 |  | QP.E.FA.GEN.GEN.1910 |  | QF01012 | NES | C04518 | REP | FAC | 00 | Z00000 | 0 | 00 | 008 | Façade | ALUTEC |  |  |  |  | 2027-05-23
QF01012-NES-C04518-SDW-FAC-00-BLAD02-5ZZ0900 | LINEAR_LIGHTING_VISUAL_MOCKUP BLACK_CUT_INSIDE_CORNER | [5 empty] | 2026-10-05 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 5 | ZZ | 0900 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-BLAD02-5ZZ0901 | LINEAR_LIGHTING_VISUAL_MOCKUP BLACK_CUT_LIGHTING_CHANNEL | [5 empty] | 2026-10-05 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 5 | ZZ | 0901 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-BLAD02-5ZZ0902 | LINEAR_LIGHTING_VISUAL_MOCKUP GLAZING_CHANNEL | [5 empty] | 2026-10-05 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 5 | ZZ | 0902 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-BLAD02-5ZZ0903 | LINEAR_LIGHTING_VISUAL_MOCKUP BLADE_ROOF_CORNER PAGE 1 OF 2 | [5 empty] | 2026-10-05 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 5 | ZZ | 0903 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-BLAD02-5ZZ0904 | LINEAR_LIGHTING_VISUAL_MOCKUP BLADE_GLAZING_CORNER | [5 empty] | 2026-10-05 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD02 | 5 | ZZ | 0904 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-BLAD03-2ZZ0037 | BLADE 3 EMBED LAYOUT | [5 empty] | 2026-12-08 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD03 | 2 | ZZ | 0037 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-BLAD04-2ZZ9001 | BLADE 4 EMBED LAYOUT | [5 empty] | 2026-12-08 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | BLAD04 | 2 | ZZ | 9001 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000004 | FACADE CL-1B - SS CHEVRON INCLINED BLADES CORE HORIZONTAL SECTION DETAIL | [5 empty] | 2026-02-28 13:26 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0004 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000005 | FACADE CL-4A - ALUMINIUM CLADDING BLACK CUTS HORIZONTAL SECTION DETAIL | [5 empty] | 2026-04-25 19:01 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0005 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000008 | FACADE CL-1B - SS CHEVRON INCLINED BLADES CORE HORIZONTAL SECTION DETAIL | [5 empty] | 2026-06-07 15:03 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0008 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000055 | FACADE CL-1B - SS CHEVRON INCLINED BLADES CORE VERTICAL SECTION DETAIL | [5 empty] | 2026-02-28 13:26 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0055 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000056 | FACADE CL-4A - ALUMINIUM CLADDING BLACK CUTS VERTICAL SECTION DETAIL | [5 empty] | 2026-04-25 19:01 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0056 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000069 | FACADE CL-4A - ALUMINIUM CLADDING BLACK CUTS VERTICAL SECTION DETAIL | [5 empty] | 2026-04-25 19:01 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0069 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000070 | FACADE CL-4A - ALUMINIUM CLADDING STEEL BUILD-UP BRACKET & STEEL STRUCTURE VERTICAL SECTION DETAIL | [5 empty] | 2026-04-25 19:01 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0070 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000071 | FACADE CL-4A - SS CHEVRON INCLINED BLADES ALUMINUM FRAMING DETAILS | [5 empty] | 2026-04-25 19:01 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0071 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000072 | FACADE CL-4A - SS CHEVRON INCLINED BLADES ALUMINUM PANEL SUBFRAME DETAILS | [5 empty] | 2026-04-25 19:01 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0072 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000073 | FACADE CL-4A - ALUMINIUM CLADDING BLACK CUTS STEEL FRAMING DETAILS | [5 empty] | 2026-04-25 19:01 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0073 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000146 | FACADE GS-3A - GLAZING INFILL HORIZONTAL DETAIL | [5 empty] | 2026-05-17 12:32 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0146 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000180 | FACADE BL-01 - GLASS BALUSTRADE VERTICAL SECTION DETAIL | [5 empty] | 2026-05-17 10:34 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0180 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-CENT01-3000181 | FACADE GS-3A - GLAZING INFILL VERTICAL DETAIL | [5 empty] | 2026-05-17 12:32 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | CENT01 | 3 | 00 | 0181 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-2ZZ0050 | GENERAL MATERIAL SPECEFICATION | [5 empty] | 2026-12-08 |  | QP.E.FA.GEN.GEN.2160 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 2 | ZZ | 0050 | Façade | ALUTEC |  |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000001 | FACADE GS-1A - GLAZING CHEVRON INCLINED BLADES HORIZONTAL SECTION DETAIL | [5 empty] | 2026-04-25 17:53 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0001 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000002 | FACADE CL-1A - SS CHEVRON INCLINED BLADES HORIZONTAL SECTION DETAIL | [5 empty] | 2026-06-04 10:01 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0002 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000006 | FACADE CL-1D - SS CHEVRON UNINSULATED INCLINED BLADES GENERAL MATERIAL SPECIFICATION | [5 empty] | 2026-05-17 13:09 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0006 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000009 | FACADE SC-1B - ALUMINIUM PERFORATED CLADDING BLACK CUTS HORIZONTAL SECTION DETAIL | [5 empty] | 2026-07-14 10:23 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0009 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000010 | FACADE GS-3E - GLAZING INFILL BASEMENT HORIZONTAL DETAIL | [5 empty] | 2026-07-14 09:31 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0010 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000051 | FACADE GS-1A - GLAZING CHEVRON INCLINED BLADES VERTICAL SECTION DETAIL | [5 empty] | 2026-04-25 17:53 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0051 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000052 | FACADE GS-1A - GLAZING CHEVRON INCLINED BLADES VERTICAL SECTION DETAIL | [5 empty] | 2026-04-25 17:53 |  | QP.E.FA.GEN.GEN.1920 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0052 | Façade | ALUTEC |  |  |  |  | 2026-10-31
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000053 | FACADE CL-1A - SS CHEVRON INCLINED BLADES VERTICAL SECTION DETAIL | [5 empty] | 2026-06-04 10:01 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0053 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000057 | FACADE GS-1A - GLAZING CHEVRON INCLINED BLADES TYPICAL FRAMING LAYOUT | [5 empty] | 2026-04-25 17:53 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0057 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000058 | FACADE GS-1A - GLAZING CHEVRON INCLINED BLADES MOVEMENT DETAIL | [5 empty] | 2026-04-25 17:53 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0058 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000059 | FACADE GS-1A - GLAZING CHEVRON STEEL BUILD-UP INWARD INCLINATION VERTICAL SECTION DETAIL | [5 empty] | 2026-04-25 17:53 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0059 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000060 | FACADE GS-1A - GLAZING CHEVRON STEEL BUILD-UP INWARD INCLINATION MOVEMENT DETAIL | [5 empty] | 2026-04-25 17:53 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0060 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000061 | FACADE CL-1A - SS CHEVRON INCLINED BLADES ALUMINUM FRAMING DETAILS | [5 empty] | 2026-04-25 19:56 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0061 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000062 | FACADE CL-1A - SS CHEVRON INCLINED BLADES ALUMINUM PANEL SUBFRAME DETAILS | [5 empty] | 2026-04-25 19:56 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0062 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000063 | FACADE CL-1A - SS CHEVRON INCLINED BLADES STEEL FRAMING DETAILS | [5 empty] | 2026-04-25 19:56 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0063 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000064 | FACADE CL-1A - SS CHEVRON INCLINED BLADES HORIZONTAL SECTION DETAIL | [5 empty] | 2026-04-25 19:56 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0064 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000065 | FACADE CL-1D - SS CHEVRON UNINSULATED INCLINED BLADES HORIZONTAL SECTION DETAIL | [5 empty] | 2026-05-17 13:09 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0065 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000066 | FACADE GS-1A - GLAZING CHEVRON STEEL BUILD-UP MULLION HORIZONTAL SECTION DETAIL | [5 empty] | 2026-04-25 17:53 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0066 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000067 | FACADE GS-1A - GLAZING CHEVRON STEEL BUILD-UP MULLION INWARD INCLINATION ELEVATION, PLAN, & CONNECTION DETAIL | [5 empty] | 2026-04-25 17:53 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0067 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000068 | FACADE GS-1A - GLAZING CHEVRON STEEL BUILD-UP MULLION INWARD INCLINATION ELEVATION, PLAN, & CONNECTION DETAIL | [5 empty] | 2026-04-25 17:53 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0068 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000074 | FACADE GS-1A - GLAZING CHEVRON INCLINED BLADES GENERAL MATERIAL SPECIFICATION | [5 empty] | 2026-04-28 10:07 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0074 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000075 | FACADE CL-1A - SS CHEVRON INCLINED BLADES GENERAL MATERIAL SPECIFICATION | [5 empty] | 2026-06-04 10:01 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0075 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000076 | FACADE SC-1B - ALUMINIUM PERFORATED CLADDING BLACK CUTS VERTICAL SECTION DETAIL | [5 empty] | 2026-07-14 10:23 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0076 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000077 | FACADE GS-3E - GLAZING INFILL BASEMENT VERTICAL DETAIL | [5 empty] | 2026-07-14 09:31 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0077 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000098 | FACADE GS-2A - GLAZING LOBBY VERTICAL CURTAIN WALL HORIZONTAL SECTION DETAIL | [5 empty] | 2026-05-17 11:50 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0098 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000101 | FACADE GS-2A - GLAZING LOBBY VERTICAL CURTAIN WALL VERTICAL SECTION DETAIL | [5 empty] | 2026-05-17 11:50 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0101 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000102 | FACADE GS-2A - GLAZING LOBBY VERTICAL CURTAIN WALL VERTICAL SECTION DETAIL | [5 empty] | 2026-05-17 11:50 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0102 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000116 | FACADE GS-2A - GLAZING LOBBY VERTICAL CURTAIN WALL VERTICAL SECTION DETAIL | [5 empty] | 2026-05-17 11:50 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0116 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000183 | FACADE CL-2A - SS ROOF LOFT + RM + PT VERTICAL SECTION DETAIL | [5 empty] | 2026-07-30 16:09 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0183 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000184 | FACADE CL-2A - SS ROOF LOFT + RM + PT VERTICAL SECTION DETAIL | [5 empty] | 2026-07-30 16:09 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0184 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000185 | FACADE CL-2B - SS ROOF LOFT + RM + PT VERTICAL SECTION DETAIL | [5 empty] | 2026-07-30 16:38 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0185 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3000186 | FACADE CL-2B - SS ROOF LOFT + RM + PT VERTICAL SECTION DETAIL | [5 empty] | 2026-07-30 16:38 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 0186 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3009001 | BLADE4 PLAN EMBED DETAILS | [5 empty] | 2026-07-28 09:46 |  | QP.E.FA.GEN.GEN.2050 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 9001 | Façade | ALUTEC |  |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-Z00000-3009002 | BLADE4 PLAN EMBED DETAILS | [5 empty] | 2026-07-28 09:46 |  | QP.E.FA.GEN.GEN.2050 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 9002 | Façade | ALUTEC |  |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-Z00000-3009003 | BLADE4 PLAN EMBED DETAILS | [5 empty] | 2026-07-28 09:46 |  | QP.E.FA.GEN.GEN.2050 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 9003 | Façade | ALUTEC |  |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-Z00000-3009004 | BLADE4 PLAN EMBED DETAILS | [5 empty] | 2026-07-28 09:46 |  | QP.E.FA.GEN.GEN.2050 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 9004 | Façade | ALUTEC |  |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-Z00000-3009005 | BLADE4 PLAN EMBED DETAILS | [5 empty] | 2026-07-28 09:46 |  | QP.E.FA.GEN.GEN.2050 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 9005 | Façade | ALUTEC |  |  |  |  | 2027-03-14
QF01012-NES-C04518-SDW-FAC-00-Z00000-3009006 | "BLADE 4 EMBED GENERAL MATERIAL SPECIFICATION" | [5 empty] | 2026-07-28 09:46 |  | QP.E.FA.GEN.GEN.2160 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 9006 | Façade | ALUTEC |  |  |  |  | 2026-04-27
QF01012-NES-C04518-SDW-FAC-00-Z00000-3009007 | EMBED DETAILS | [5 empty] | 2026-08-02 15:18 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 9007 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3009008 | EMBED DETAILS | [5 empty] | 2026-08-02 15:18 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 9008 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3009009 | EMBED DETAILS | [5 empty] | 2026-08-02 15:18 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 9009 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3009010 | EMBED DETAILS | [5 empty] | 2026-08-02 15:18 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 9010 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-SDW-FAC-00-Z00000-3009011 | EMBED DETAILS | [5 empty] | 2026-08-02 15:18 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | SDW | FAC | 00 | Z00000 | 3 | 00 | 9011 | Façade | ALUTEC |  |  |  |  | 2026-06-16
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0401 | VMU 4 - LOBBY Glazing GS-02B Partial Plan & Elevation | [5 empty] | 2026-07-25 |  | QP.E.FA.GEN.GEN.2050 |  | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0401 | Façade | ALUTEC |  |  |  |  | 2027-03-14
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0402 | VMU 4 - LOBBY Glazing GS-02B Section Details | [5 empty] | 2026-07-25 |  | QP.E.FA.GEN.GEN.2230 |  | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0402 | Façade | ALUTEC |  |  |  |  | 2026-06-16

## Baseline (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | Package | Activity Code | Activity | Original Duration | Start | Finish
Shop Drawings | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Shop Drawings ¦ Mobilization | QP.M.GN.GEN.GEN.1400 | Submittal | 12 | 2025-10-18 | 2025-10-30
Shop Drawings | Mobilization | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Shop Drawings ¦ Mobilization ¦ Tower Crane Foundation - Concrete Works | QP.M.GN.GEN.GEN.1470 | Submittal | 12 | 2025-10-18 | 2025-10-30
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Blades Below Loft | QP.M.GN.GEN.GEN.1540 | Submittal | 12 | 2026-01-08 | 2026-01-21
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Loft | QP.M.GN.GEN.GEN.1560 | Submittal | 12 | 2026-06-20 | 2026-07-02
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Above Loft | QP.M.GN.GEN.GEN.1580 | Submittal | 12 | 2026-07-22 | 2026-08-04
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works | QP.E.CV.MBL.GEN.3460 | Submittal | 7 | 2025-11-04 | 2025-11-11
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works Outside Core Area | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works Outside Core Area | QP.E.CV.MBL.GEN.3540 | Submittal | 14 | 2025-11-12 | 2025-11-27
Shop Drawings | Civil | Blades | Blade 1 | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 1 | QP.E.CV.BL1.GEN.1060 | Submittal | 25 | 2025-12-07 | 2026-01-04
Shop Drawings | Civil | Blades | Blade 2 | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 2 | QP.E.CV.BL2.GEN.1060 | Submittal | 25 | 2025-12-14 | 2026-01-11
Shop Drawings | Civil | Blades | Blade 3 | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 3 | QP.E.CV.BL3.GEN.1060 | Submittal | 25 | 2025-11-30 | 2025-12-28
Shop Drawings | Civil | Blades | Blade 4 | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 4 | QP.E.CV.BL4.GEN.1060 | Submittal | 25 | 2025-11-23 | 2025-12-21
Shop Drawings | Civil | Blades | Blade 5 | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 5 | QP.E.CV.BL5.GEN.1060 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Civil | Parking | Parking | Parking | Parking | Parking | Shop Drawings ¦ Civil ¦ Parking | QP.E.CV.PAR.GEN.1000 | Submittal | 21 | 2027-03-04 | 2027-03-30
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - Foundation Works Core Area | QP.E.CV.MBL.GEN.3000 | Submittal | 28 | 2025-11-18 | 2025-12-20
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 03 +887.750M | QP.E.CV.MBL.GEN.3030 | Submittal | 28 | 2025-12-21 | 2026-01-21
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - SOG | QP.E.CV.MBL.GEN.3640 | Submittal | 14 | 2026-01-06 | 2026-01-21
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 02 - Foundation Works Outside Core Area | QP.E.CV.MBL.GEN.3020 | Submittal | 14 | 2025-12-21 | 2026-01-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 02 +893.5M | QP.E.CV.MBL.GEN.3070 | Submittal | 28 | 2025-12-21 | 2026-01-21
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 01 +900.5M | QP.E.CV.MBL.GEN.3100 | Submittal | 28 | 2026-01-22 | 2026-02-24
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01- LOBBY LEVEL +905M | QP.E.CV.MBL.GEN.3120 | Submittal | 25 | 2026-02-25 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01 - MEZZANINE +909M | QP.E.CV.MBL.GEN.3140 | Submittal | 15 | 2026-03-29 | 2026-04-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3180 | Submittal | 25 | 2026-04-15 | 2026-05-13
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3380 | Submittal | 25 | 2026-04-15 | 2026-05-13
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3220 | Submittal | 25 | 2026-05-14 | 2026-06-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3400 | Submittal | 25 | 2026-05-14 | 2026-06-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3240 | Submittal | 25 | 2026-06-16 | 2026-07-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3420 | Submittal | 25 | 2026-06-16 | 2026-07-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3260 | Submittal | 25 | 2026-07-15 | 2026-08-12
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3440 | Submittal | 25 | 2026-07-15 | 2026-08-12
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | QP.E.CV.MBL.GEN.3280 | Submittal | 25 | 2026-08-13 | 2026-09-10
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | QP.E.CV.MBL.GEN.3300 | Submittal | 28 | 2027-01-17 | 2027-02-17
Shop Drawings | Concrete | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Premium Theatre Concrete Works | QP.E.CV.MBL.GEN.3150 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | Concrete | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Amphitheatre Concrete Works | QP.E.CV.MBL.GEN.3200 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Premium Theater | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Premium Theater | QP.E.CV.MBL.GEN.3660 | Submittal | 28 | 2026-01-08 | 2026-02-09
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Loft and Adaptable Theatre | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Loft and Adaptable Theatre | QP.E.CV.MBL.GEN.3700 | Submittal | 28 | 2026-03-08 | 2026-04-11
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Fly Tower | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Fly Tower | QP.E.CV.MBL.GEN.3710 | Submittal | 28 | 2026-04-26 | 2026-05-31
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Lobby & Plaza | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Lobby & Plaza | QP.E.CV.MBL.GEN.3680 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Royal Majlis | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Royal Majlis | QP.E.CV.MBL.GEN.3740 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Foundation | QP.E.CV.BL1.GEN.1000 | Submittal | 25 | 2025-12-07 | 2026-01-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL1.GEN.1040 | Submittal | 28 | 2026-01-08 | 2026-02-09
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL1.GEN.1080 | Submittal | 18 | 2026-03-26 | 2026-04-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL1.GEN.1020 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL1.GEN.1120 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL1.GEN.1100 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Foundation | QP.E.CV.BL2.GEN.1000 | Submittal | 25 | 2025-12-14 | 2026-01-11
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL2.GEN.1040 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL2.GEN.1080 | Submittal | 18 | 2026-03-03 | 2026-03-25
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL2.GEN.1020 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL2.GEN.1140 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL2.GEN.1120 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Foundation | QP.E.CV.BL3.GEN.1000 | Submittal | 25 | 2025-11-30 | 2025-12-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Steel Composite Slab Including Embedded items Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Steel Composite Slab Including Embedded items Below Loft | QP.E.CV.BL3.GEN.1030 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL3.GEN.1080 | Submittal | 18 | 2025-12-29 | 2026-01-18
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL3.GEN.1020 | Submittal | 28 | 2026-01-31 | 2026-03-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Foundation | QP.E.CV.BL4.GEN.1000 | Submittal | 25 | 2025-11-23 | 2025-12-21
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL4.GEN.1030 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL4.GEN.1080 | Submittal | 18 | 2026-01-19 | 2026-02-08
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL4.GEN.1020 | Submittal | 28 | 2026-02-09 | 2026-03-14
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL4.GEN.1100 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL4.GEN.1120 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Foundation | QP.E.CV.BL5.GEN.1000 | Submittal | 25 | 2025-11-16 | 2025-12-14
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL5.GEN.1030 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL5.GEN.1080 | Submittal | 18 | 2026-02-09 | 2026-03-02
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL5.GEN.1020 | Submittal | 28 | 2026-03-03 | 2026-04-06
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL5.GEN.1100 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL5.GEN.1120 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Foundation Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Foundation Including Embedded items | QP.E.CV.PAR.GEN.1020 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Structural Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Structural Concrete Works Including Embedded items | QP.E.CV.PAR.GEN.1040 | Submittal | 28 | 2027-06-05 | 2027-07-06
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Below Loft | QP.E.ST.GEN.GEN.1090 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1100 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1110 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1050 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1060 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1070 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 3,4,5 | QP.E.ST.GEN.GEN.1000 | Submittal | 21 | 2025-11-12 | 2025-12-06
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | QP.E.ST.GEN.GEN.1010 | Submittal | 21 | 2025-11-12 | 2025-12-06
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Truss below Auditorium, Side and Back Stage | QP.E.ST.GEN.GEN.2120 | Submittal | 21 | 2025-12-15 | 2026-01-07
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1220 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1230 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1200 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1210 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1190 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Embedded part - Main Building Above Level 5 | QP.E.ST.GEN.GEN.1040 | Submittal | 21 | 2025-12-07 | 2025-12-30
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Premium Theater - Frame Balconies and Back Stage Dressing | QP.E.ST.GEN.GEN.2140 | Submittal | 21 | 2026-01-08 | 2026-02-01
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Loft and adaptable Theatre | QP.E.ST.GEN.GEN.1340 | Submittal | 28 | 2026-01-22 | 2026-02-24
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1390 | Submittal | 28 | 2026-02-02 | 2026-03-07
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1400 | Submittal | 28 | 2026-02-02 | 2026-03-07
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1310 | Submittal | 28 | 2026-02-02 | 2026-03-07
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1320 | Submittal | 28 | 2026-02-02 | 2026-03-07
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1330 | Submittal | 28 | 2026-02-02 | 2026-03-07
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1470 | Submittal | 28 | 2026-03-08 | 2026-04-11
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ Truss above Auditorium Incl. Metal Deck | QP.E.ST.GEN.GEN.2100 | Submittal | 28 | 2026-03-08 | 2026-04-11
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Temporay Tower ROYAL MAJLIS and Blades above loft | QP.E.ST.GEN.GEN.1490 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2160 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1520 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Truss above Flytower | QP.E.ST.GEN.GEN.2180 | Submittal | 28 | 2026-04-12 | 2026-05-13
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1540 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ Blade 2 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2200 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ Adaptable Theatre Incl. Metal Deck | QP.E.ST.GEN.GEN.1560 | Submittal | 28 | 2026-06-20 | 2026-07-21
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.2220 | Submittal | 28 | 2026-06-20 | 2026-07-21
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Loft Truss and Infilled Beam North Side Incl. Metal Deck | QP.E.ST.GEN.GEN.1610 | Submittal | 28 | 2026-07-22 | 2026-08-23
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1600 | Submittal | 28 | 2026-07-22 | 2026-08-23
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Lobby and Plaza Incl. Metal Deck | QP.E.ST.GEN.GEN.1660 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Frame for Mezzanine | QP.E.ST.GEN.GEN.1670 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Link Bridge and Helix Stair | QP.E.ST.GEN.GEN.1570 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1680 | Submittal | 28 | 2026-09-27 | 2026-10-28
Shop Drawings | Structural Steel | Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | Shop Drawings ¦ Structural Steel ¦ Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck ¦ ROYAL MAJLIS | QP.E.ST.GEN.GEN.1640 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1090 | Submittal | 21 | 2026-03-29 | 2026-04-21
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1120 | Submittal | 21 | 2026-08-15 | 2026-09-07
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Wall Cladding | QP.E.AF.MBL.GEN.4440 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1100 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ FFE | QP.E.AF.MBL.GEN.5260 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1170 | Submittal | 21 | 2026-04-22 | 2026-05-16
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1200 | Submittal | 21 | 2026-09-08 | 2026-10-03
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5700 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1180 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ FFE | QP.E.AF.MBL.GEN.5280 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1220 | Submittal | 21 | 2026-05-17 | 2026-06-13
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1250 | Submittal | 21 | 2026-10-04 | 2026-10-27
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5720 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1230 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ FFE | QP.E.AF.MBL.GEN.5300 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1310 | Submittal | 21 | 2026-06-14 | 2026-07-07
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1340 | Submittal | 21 | 2026-10-28 | 2026-11-21
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5800 | Submittal | 21 | 2027-01-19 | 2027-02-11
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1320 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ FFE | QP.E.AF.MBL.GEN.5320 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1400 | Submittal | 21 | 2026-07-08 | 2026-08-01
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1430 | Submittal | 21 | 2026-11-22 | 2026-12-15
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5740 | Submittal | 21 | 2027-02-13 | 2027-03-09
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1410 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ FFE | QP.E.AF.MBL.GEN.5340 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1000 | Submittal | 21 | 2026-08-02 | 2026-08-25
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1030 | Submittal | 21 | 2026-12-16 | 2027-01-09
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5760 | Submittal | 21 | 2027-02-13 | 2027-03-09
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1010 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ FFE | QP.E.AF.MBL.GEN.5360 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1490 | Submittal | 21 | 2026-08-26 | 2026-09-19
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1520 | Submittal | 21 | 2027-01-10 | 2027-02-02
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5820 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1500 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ FFE | QP.E.AF.MBL.GEN.5380 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1580 | Submittal | 21 | 2026-09-20 | 2026-10-14
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1610 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5840 | Submittal | 21 | 2027-05-01 | 2027-05-29
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1590 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ FFE | QP.E.AF.MBL.GEN.5400 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1670 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1700 | Submittal | 28 | 2027-04-18 | 2027-05-24
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5860 | Submittal | 28 | 2027-05-30 | 2027-06-30
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1680 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ FFE | QP.E.AF.MBL.GEN.5420 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1760 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1790 | Submittal | 21 | 2027-05-25 | 2027-06-17
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5880 | Submittal | 21 | 2027-07-01 | 2027-07-25
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1770 | Submittal | 21 | 2027-07-12 | 2027-08-04
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ FFE | QP.E.AF.MBL.GEN.5440 | Submittal | 21 | 2027-07-12 | 2027-08-04
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1880 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1910 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5900 | Submittal | 21 | 2027-07-26 | 2027-08-18
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1890 | Submittal | 21 | 2027-08-05 | 2027-08-29
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ FFE | QP.E.AF.MBL.GEN.5460 | Submittal | 21 | 2027-08-05 | 2027-08-29
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1800 | Submittal | 21 | 2027-03-31 | 2027-04-24
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1830 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5920 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1810 | Submittal | 21 | 2027-08-30 | 2027-09-22
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ FFE | QP.E.AF.MBL.GEN.5480 | Submittal | 21 | 2027-09-15 | 2027-10-10
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1110 | Submittal | 28 | 2026-11-12 | 2026-12-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1140 | Submittal | 28 | 2027-04-05 | 2027-05-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1120 | Submittal | 28 | 2027-02-13 | 2027-03-20
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1370 | Submittal | 28 | 2026-12-15 | 2027-01-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1360 | Submittal | 28 | 2027-05-08 | 2027-06-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Wall Cladding | QP.E.AF.BL1.GEN.5940 | Submittal | 28 | 2027-05-30 | 2027-06-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1340 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1650 | Submittal | 28 | 2027-01-17 | 2027-02-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1680 | Submittal | 28 | 2027-06-14 | 2027-07-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1660 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1080 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1110 | Submittal | 28 | 2027-03-03 | 2027-04-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Wall Cladding | QP.E.AF.BL2.GEN.5960 | Submittal | 28 | 2027-03-21 | 2027-04-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1090 | Submittal | 28 | 2027-03-21 | 2027-04-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1580 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1610 | Submittal | 28 | 2027-04-18 | 2027-05-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1590 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1670 | Submittal | 28 | 2027-01-28 | 2027-03-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1700 | Submittal | 28 | 2027-05-25 | 2027-06-26
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1680 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1000 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1030 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL3.GEN.5980 | Submittal | 28 | 2027-04-22 | 2027-05-29
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1010 | Submittal | 28 | 2027-04-22 | 2027-05-29
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1340 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1370 | Submittal | 28 | 2027-04-18 | 2027-05-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1350 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1210 | Submittal | 28 | 2026-07-20 | 2026-08-20
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1240 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL4.GEN.6000 | Submittal | 28 | 2027-09-15 | 2027-10-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1220 | Submittal | 28 | 2027-04-22 | 2027-05-29
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1820 | Submittal | 21 | 2026-10-24 | 2026-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1850 | Submittal | 21 | 2027-04-26 | 2027-05-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1830 | Submittal | 21 | 2027-06-09 | 2027-07-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1730 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1760 | Submittal | 28 | 2027-05-25 | 2027-06-26
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1740 | Submittal | 28 | 2027-07-04 | 2027-08-04
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.2280 | Submittal | 28 | 2026-08-22 | 2026-09-22
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.2340 | Submittal | 28 | 2026-09-24 | 2026-10-26
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.2300 | Submittal | 28 | 2027-05-30 | 2027-06-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1130 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1160 | Submittal | 21 | 2027-05-25 | 2027-06-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1140 | Submittal | 21 | 2027-07-01 | 2027-07-25
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1500 | Submittal | 28 | 2027-01-13 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1530 | Submittal | 28 | 2027-07-04 | 2027-08-04
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Wall Cladding | QP.E.AF.BL5.GEN.6020 | Submittal | 28 | 2027-09-15 | 2027-10-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1510 | Submittal | 28 | 2027-07-26 | 2027-08-26
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1000 | Submittal | 28 | 2027-07-21 | 2027-08-22
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1020 | Submittal | 21 | 2027-08-23 | 2027-09-15
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Doors / Openings | QP.E.AF.PAR.GEN.1010 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Specialities | QP.E.AF.MBL.GEN.5160 | Submittal | 21 | 2027-10-19 | 2027-11-11
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1030 | Submittal | 28 | 2027-09-08 | 2027-10-11
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1050 | Submittal | 21 | 2027-10-12 | 2027-11-04
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Doors / Openings | QP.E.AF.PAR.GEN.1040 | Submittal | 21 | 2027-10-12 | 2027-11-04
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Specialities | QP.E.AF.MBL.GEN.5200 | Submittal | 21 | 2027-11-13 | 2027-12-06
Shop Drawings | Architecture and Fitouts | Amphitheatre | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4040 | Submittal | 28 | 2027-08-23 | 2027-09-25
Shop Drawings | Architecture and Fitouts | Amphitheatre | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.4070 | Submittal | 21 | 2027-09-26 | 2027-10-19
Shop Drawings | Architecture and Fitouts | Amphitheatre | Wall Cladding | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Wall Cladding | QP.E.AF.MBL.GEN.6040 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Amphitheatre | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4050 | Submittal | 21 | 2027-10-20 | 2027-11-13
Shop Drawings | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | Shop Drawings ¦ External Building Works (Guard House, SEC Room) | QP.E.EX.GEN.GEN.1270 | Submittal | 28 | 2027-02-11 | 2027-03-18
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Main Building | QP.E.AF.MBL.GEN.6060 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 5 | Water Proofing - Roof - Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 5 | QP.E.AF.BL5.GEN.6180 | Submittal | 21 | 2027-05-25 | 2027-06-17
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 4 | Water Proofing - Roof - Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 4 | QP.E.AF.BL4.GEN.6160 | Submittal | 21 | 2027-04-26 | 2027-05-24
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 3 | Water Proofing - Roof - Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 3 | QP.E.AF.BL3.GEN.6140 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 1 | Water Proofing - Roof - Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 1 | QP.E.AF.BL1.GEN.6100 | Submittal | 21 | 2027-05-08 | 2027-06-05
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 2 | Water Proofing - Roof - Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 2 | QP.E.AF.BL2.GEN.6120 | Submittal | 21 | 2027-04-18 | 2027-05-11
Shop Drawings | Specialist Systems | Waterproofing | Wet Areas | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Wet Areas ¦ Main Building | QP.E.AF.MBL.GEN.4400 | Submittal | 21 | 2026-04-30 | 2026-05-24
Shop Drawings | Specialist Systems | Doors/ Openings | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Main Building | QP.E.AF.MBL.GEN.1140 | Submittal | 28 | 2027-01-24 | 2027-02-25
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.1130 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 2 | QP.E.AF.BL2.GEN.1100 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.1020 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.1230 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.2320 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Doors/ Openings | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Amphitheatre | QP.E.AF.MBL.GEN.4060 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Specialist Systems | Conveying System | Waste Management | Waste Management | Waste Management | Waste Management | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Waste Management | QP.E.CY.GEN.GEN.1280 | Submittal | 21 | 2027-06-26 | 2027-07-19
Shop Drawings | Specialist Systems | Conveying System | Escalators | Escalators | Escalators | Escalators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Escalators | QP.E.CY.GEN.GEN.1040 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Specialist Systems | Conveying System | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | QP.E.CY.GEN.GEN.1020 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | Specialist Systems | Conveying System | Truck Elevators | Truck Elevators | Truck Elevators | Truck Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Truck Elevators | QP.E.CY.GEN.GEN.1000 | Submittal | 28 | 2026-06-16 | 2026-07-18
Shop Drawings | Specialist Systems | Conveying System | Inclined Elevators | Inclined Elevators | Inclined Elevators | Inclined Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Inclined Elevators | QP.E.CY.GEN.GEN.1050 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | Specialist Systems | Conveying System | BMU | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Main Building | QP.E.CY.GEN.GEN.1090 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 1 | QP.E.CY.GEN.GEN.1130 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 2 | QP.E.CY.GEN.GEN.1170 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 3 | Balde 3 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 3 | QP.E.CY.GEN.GEN.1210 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 4 | QP.E.CY.GEN.GEN.1110 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 5 | Balde 5 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 5 | QP.E.CY.GEN.GEN.1150 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | Specialist Systems | Joinery Works | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Main Building | QP.E.AF.MBL.GEN.5540 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.6120 | Submittal | 21 | 2027-06-14 | 2027-07-07
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.6160 | Submittal | 21 | 2027-05-25 | 2027-06-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.6180 | Submittal | 21 | 2027-05-25 | 2027-06-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.6200 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | Specialist Systems | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Shop Drawings ¦ Specialist Systems ¦ Kitchen and Laundary | QP.E.AF.MBL.GEN.5500 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | Specialist Systems | Water Features | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Specialist Systems ¦ Water Features | QP.E.AF.MBL.GEN.6100 | Submittal | 21 | 2026-09-13 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Mechanical | QP.E.ME.MBL.GEN.6780 | Submittal | 18 | 2026-01-06 | 2026-01-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical | QP.E.ME.MBL.GEN.6800 | Submittal | 18 | 2026-01-06 | 2026-01-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6840 | Submittal | 18 | 2026-01-06 | 2026-01-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical | QP.E.ME.MBL.GEN.6850 | Submittal | 18 | 2026-01-06 | 2026-01-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6860 | Submittal | 18 | 2026-02-03 | 2026-02-24
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical | QP.E.ME.MBL.GEN.6870 | Submittal | 18 | 2026-02-03 | 2026-02-24
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Mechanical | QP.E.ME.MBL.GEN.6900 | Submittal | 18 | 2026-03-05 | 2026-03-28
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical | QP.E.ME.MBL.GEN.6910 | Submittal | 18 | 2026-03-05 | 2026-03-28
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Mechanical | QP.E.ME.MBL.GEN.6940 | Submittal | 18 | 2026-03-29 | 2026-04-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical | QP.E.ME.MBL.GEN.6950 | Submittal | 18 | 2026-03-29 | 2026-04-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Mechanical | QP.E.ME.MBL.GEN.6980 | Submittal | 18 | 2026-04-23 | 2026-05-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Electrical | QP.E.ME.MBL.GEN.6990 | Submittal | 18 | 2026-04-23 | 2026-05-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Mechanical | QP.E.ME.MBL.GEN.7020 | Submittal | 18 | 2026-05-23 | 2026-06-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical | QP.E.ME.MBL.GEN.7030 | Submittal | 18 | 2026-05-23 | 2026-06-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7060 | Submittal | 18 | 2026-06-24 | 2026-07-14
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical | QP.E.ME.MBL.GEN.7070 | Submittal | 18 | 2026-06-24 | 2026-07-14
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7100 | Submittal | 18 | 2026-07-23 | 2026-08-12
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical | QP.E.ME.MBL.GEN.7110 | Submittal | 18 | 2026-07-23 | 2026-08-12
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Mechanical | QP.E.ME.MBL.GEN.7140 | Submittal | 18 | 2026-08-22 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical | QP.E.ME.MBL.GEN.7150 | Submittal | 18 | 2026-08-22 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Mechanical | QP.E.ME.MBL.GEN.7180 | Submittal | 18 | 2026-08-22 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Electrical | QP.E.ME.MBL.GEN.7190 | Submittal | 18 | 2026-08-22 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Mechanical | QP.E.ME.MBL.GEN.7220 | Submittal | 18 | 2026-09-12 | 2026-10-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical | QP.E.ME.MBL.GEN.7230 | Submittal | 18 | 2026-09-12 | 2026-10-03
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1320 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1330 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1340 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1350 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ ICT Containment | QP.E.ME.MBL.GEN.1360 | Submittal | 28 | 2026-03-29 | 2026-04-29
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1420 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1430 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1440 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1450 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1460 | Submittal | 28 | 2026-04-30 | 2026-06-04
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1740 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1750 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1760 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1770 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1780 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1590 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1600 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1610 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1620 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.1630 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2040 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2050 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2060 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2070 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ ICT Containment | QP.E.ME.MBL.GEN.2080 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2240 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2250 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2260 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2270 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ ICT Containment | QP.E.ME.MBL.GEN.2280 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2440 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2450 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2460 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2470 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.2480 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2640 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2650 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2660 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2670 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2680 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2850 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2860 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2870 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2880 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2890 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3070 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3080 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3090 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3100 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ ICT Containment | QP.E.ME.MBL.GEN.3110 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3290 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3300 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3310 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3320 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ ICT Containment | QP.E.ME.MBL.GEN.3330 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3500 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3510 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3520 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3530 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ ICT Containment | QP.E.ME.MBL.GEN.3540 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.MBL.GEN.5000 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.MBL.GEN.5040 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.MBL.GEN.5060 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.MBL.GEN.5080 | Submittal | 28 | 2027-05-19 | 2027-06-20
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.MBL.GEN.7280 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.MBL.GEN.7300 | Submittal | 28 | 2027-05-19 | 2027-06-20
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.MBL.GEN.7320 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.MBL.GEN.7260 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.MBL.GEN.7340 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | LPG System | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ LPG System | QP.E.ME.MBL.GEN.5100 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.MBL.GEN.7360 | Submittal | 28 | 2027-07-24 | 2027-08-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Fire Suppression | QP.E.ME.CBR.GEN.1000 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Plumbing | Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Plumbing | QP.E.ME.CBR.GEN.1011 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ LPG System | QP.E.ME.CBR.GEN.1055 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.CBR.GEN.1022 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Electrical | QP.E.ME.CBR.GEN.1033 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ ELV (Low Current System) | QP.E.ME.CBR.GEN.1044 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.MBL.GEN.7380 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Diesel | Diesel | Diesel | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Diesel | QP.E.ME.MBL.GEN.7420 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Water Features | Water Features | Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Water Features | QP.E.ME.MBL.GEN.7440 | Submittal | 28 | 2027-06-26 | 2027-07-27
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M | QP.E.ME.MBL.GEN.6520 | Submittal | 14 | 2026-11-17 | 2026-12-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Grey Water Treatment/ Sewage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Grey Water Treatment/ Sewage | QP.E.ME.MBL.GEN.1050 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Stromwater/ Drainage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Stromwater/ Drainage | QP.E.ME.MBL.GEN.1060 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1040 | Submittal | 21 | 2026-12-03 | 2026-12-27
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M | QP.E.ME.MBL.GEN.6540 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ AHU Room | QP.E.ME.MBL.GEN.1160 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Transformer/ Switchgear/ Panel Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Transformer/ Switchgear/ Panel Room | QP.E.ME.MBL.GEN.1240 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Generator Room/ Diesel Tank | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Generator Room/ Diesel Tank | QP.E.ME.MBL.GEN.1250 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | ETS/ CWP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ ETS/ CWP Room | QP.E.ME.MBL.GEN.1170 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1030 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1290 | Submittal | 14 | 2026-12-03 | 2026-12-19
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M | QP.E.ME.MBL.GEN.6560 | Submittal | 14 | 2026-12-20 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1020 | Submittal | 14 | 2026-12-20 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Domestic Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Domestic Water | QP.E.ME.MBL.GEN.1010 | Submittal | 14 | 2026-12-20 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Fire Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Fire Water | QP.E.ME.MBL.GEN.1000 | Submittal | 14 | 2026-12-20 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1280 | Submittal | 14 | 2026-12-20 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 LOBBY LEVEL +905.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 LOBBY LEVEL +905.00M | QP.E.ME.MBL.GEN.6640 | Submittal | 14 | 2027-01-05 | 2027-01-20
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 UPEER LOBBY LEVEL MEZZANINE +909M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M | QP.E.ME.MBL.GEN.6660 | Submittal | 14 | 2027-01-21 | 2027-02-06
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L2 THEATRE STALLS +913M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L2 THEATRE STALLS +913M | QP.E.ME.MBL.GEN.6680 | Submittal | 14 | 2027-02-07 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | QP.E.ME.MBL.GEN.6700 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | QP.E.ME.MBL.GEN.6720 | Submittal | 14 | 2027-03-15 | 2027-03-30
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 SECOND CIRCLE AND LOFT +928.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 SECOND CIRCLE AND LOFT +928.00M | QP.E.ME.MBL.GEN.6740 | Submittal | 14 | 2027-03-31 | 2027-04-15
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M | QP.E.ME.MBL.GEN.5540 | Submittal | 14 | 2027-04-17 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - AHU Room | QP.E.ME.MBL.GEN.1180 | Submittal | 14 | 2027-05-03 | 2027-05-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Makeup Air Unit and Ecology | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Makeup Air Unit and Ecology | QP.E.ME.MBL.GEN.1190 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Sky Garden Irrigation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Sky Garden Irrigation | QP.E.ME.MBL.GEN.1070 | Submittal | 14 | 2027-04-17 | 2027-05-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L6 SKY GARDEN +935.85M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L6 SKY GARDEN +935.85M | QP.E.ME.MBL.GEN.6760 | Submittal | 14 | 2027-05-03 | 2027-05-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M | QP.E.ME.MBL.GEN.6580 | Submittal | 14 | 2027-05-24 | 2027-06-08
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | Plant Room - Fan Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M ¦ Plant Room - Fan Room | QP.E.ME.MBL.GEN.6600 | Submittal | 28 | 2027-05-24 | 2027-06-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Kitchen and Laundry | Kitchen and Laundry | Kitchen and Laundry | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Kitchen and Laundry | QP.E.ME.MBL.GEN.7400 | Submittal | 28 | 2027-08-14 | 2027-09-14
Shop Drawings | MEP | Panels | Panels | Panels | Panels | Panels | Shop Drawings ¦ MEP ¦ Panels | QP.E.ME.MBL.GEN.6510 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Mechanical | QP.E.ME.BL1.GEN.3720 | Submittal | 18 | 2026-02-10 | 2026-03-03
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical | QP.E.ME.BL1.GEN.3740 | Submittal | 18 | 2026-02-10 | 2026-03-03
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL1.GEN.3760 | Submittal | 28 | 2026-09-27 | 2026-10-28
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL1.GEN.3780 | Submittal | 28 | 2026-09-27 | 2026-10-28
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Mechanical | QP.E.ME.BL1.GEN.3800 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical | QP.E.ME.BL1.GEN.3820 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1020 | Submittal | 28 | 2026-11-12 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1030 | Submittal | 28 | 2026-08-12 | 2026-09-13
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1040 | Submittal | 28 | 2026-08-12 | 2026-09-13
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1050 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ ICT Containment | QP.E.ME.BL1.GEN.1060 | Submittal | 28 | 2026-10-15 | 2026-11-16
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL1.GEN.2940 | Submittal | 28 | 2026-12-29 | 2027-01-30
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.2950 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.2960 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.2970 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL1.GEN.2980 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1510 | Submittal | 28 | 2027-02-14 | 2027-03-21
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1520 | Submittal | 28 | 2027-02-04 | 2027-03-09
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1530 | Submittal | 28 | 2027-03-13 | 2027-04-13
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1540 | Submittal | 28 | 2027-02-04 | 2027-03-09
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ ICT Containment | QP.E.ME.BL1.GEN.1550 | Submittal | 28 | 2027-02-04 | 2027-03-09
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.BL1.GEN.3280 | Submittal | 28 | 2027-04-05 | 2027-05-06
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL1.GEN.3320 | Submittal | 28 | 2027-05-08 | 2027-06-13
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL1.GEN.3340 | Submittal | 28 | 2027-06-14 | 2027-07-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL1.GEN.3360 | Submittal | 28 | 2027-07-17 | 2027-08-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL1.GEN.3580 | Submittal | 28 | 2027-06-14 | 2027-07-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL1.GEN.3600 | Submittal | 28 | 2027-09-01 | 2027-10-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL1.GEN.3620 | Submittal | 28 | 2027-10-05 | 2027-11-06
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL1.GEN.3680 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL1.GEN.3640 | Submittal | 28 | 2027-09-01 | 2027-10-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL1.GEN.3660 | Submittal | 28 | 2027-10-05 | 2027-11-06
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3480 | Submittal | 21 | 2027-11-07 | 2027-11-30
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL1.GEN.1000 | Submittal | 21 | 2027-11-07 | 2027-11-30
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL1.GEN.3700 | Submittal | 28 | 2027-07-17 | 2027-08-17
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3400 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical | QP.E.ME.BL2.GEN.3420 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL2.GEN.3440 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL2.GEN.3460 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3480 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical | QP.E.ME.BL2.GEN.3500 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1020 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1030 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1040 | Submittal | 28 | 2026-08-24 | 2026-09-26
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1050 | Submittal | 28 | 2026-05-30 | 2026-06-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.1060 | Submittal | 28 | 2026-11-17 | 2026-12-19
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1910 | Submittal | 28 | 2026-12-27 | 2027-01-27
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1920 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1930 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1940 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL2.GEN.1950 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.2110 | Submittal | 28 | 2027-01-28 | 2027-03-02
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.2120 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.2130 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.2140 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.2150 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL2.GEN.3160 | Submittal | 28 | 2027-03-03 | 2027-04-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL2.GEN.3200 | Submittal | 28 | 2027-04-07 | 2027-05-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL2.GEN.3220 | Submittal | 28 | 2027-05-10 | 2027-06-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL2.GEN.3240 | Submittal | 28 | 2027-06-16 | 2027-07-18
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL2.GEN.3260 | Submittal | 28 | 2027-05-10 | 2027-06-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL2.GEN.3280 | Submittal | 28 | 2027-07-19 | 2027-08-19
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL2.GEN.3300 | Submittal | 28 | 2027-08-21 | 2027-09-21
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL2.GEN.3380 | Submittal | 28 | 2027-04-07 | 2027-05-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL2.GEN.3320 | Submittal | 28 | 2027-07-19 | 2027-08-19
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL2.GEN.3340 | Submittal | 28 | 2027-08-21 | 2027-09-21
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3500 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL2.GEN.1000 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL2.GEN.3360 | Submittal | 28 | 2027-06-16 | 2027-07-18
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Mechanical | QP.E.ME.BL3.GEN.3640 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical | QP.E.ME.BL3.GEN.3660 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical | QP.E.ME.BL3.GEN.3700 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Mechanical | QP.E.ME.BL3.GEN.3680 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1020 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.1030 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1040 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1050 | Submittal | 28 | 2026-04-09 | 2026-05-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ ICT Containment | QP.E.ME.BL3.GEN.1060 | Submittal | 28 | 2026-07-08 | 2026-08-09
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1790 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.3280 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1810 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1820 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ ICT Containment | QP.E.ME.BL3.GEN.1830 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL3.GEN.3400 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL3.GEN.3440 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL3.GEN.3460 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL3.GEN.3480 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL3.GEN.3500 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL3.GEN.3540 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL3.GEN.3560 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL3.GEN.3620 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL3.GEN.3600 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL3.GEN.3580 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3520 | Submittal | 21 | 2027-08-28 | 2027-09-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL3.GEN.1000 | Submittal | 21 | 2027-09-21 | 2027-10-16
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL3.GEN.3520 | Submittal | 28 | 2027-10-17 | 2027-11-17
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Mechanical | QP.E.ME.BL4.GEN.6010 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical | QP.E.ME.BL4.GEN.6030 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Mechanical | QP.E.ME.BL4.GEN.6050 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Electrical | QP.E.ME.BL4.GEN.6070 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Mechanical | QP.E.ME.BL4.GEN.6090 | Submittal | 28 | 2026-06-20 | 2026-07-21
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical | QP.E.ME.BL4.GEN.6110 | Submittal | 28 | 2026-06-20 | 2026-07-21
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Fire Suppression | QP.E.ME.BL4.GEN.2110 | Submittal | 28 | 2026-07-20 | 2026-08-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2120 | Submittal | 28 | 2026-07-20 | 2026-08-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2130 | Submittal | 28 | 2026-07-20 | 2026-08-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2140 | Submittal | 28 | 2026-04-21 | 2026-05-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ ICT Containment | QP.E.ME.BL4.GEN.2150 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2910 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.5550 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2930 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2940 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ ICT Containment | QP.E.ME.BL4.GEN.2950 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2810 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2820 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2830 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2840 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ ICT Containment | QP.E.ME.BL4.GEN.2850 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL4.GEN.5770 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL4.GEN.5810 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL4.GEN.5830 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL4.GEN.5850 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL4.GEN.5870 | Submittal | 28 | 2027-05-03 | 2027-06-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL4.GEN.5930 | Submittal | 28 | 2027-07-12 | 2027-08-12
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL4.GEN.5950 | Submittal | 28 | 2027-08-14 | 2027-09-14
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL4.GEN.5890 | Submittal | 28 | 2027-03-31 | 2027-05-02
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL4.GEN.5970 | Submittal | 28 | 2027-07-26 | 2027-08-26
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL4.GEN.5990 | Submittal | 28 | 2027-08-28 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3540 | Submittal | 21 | 2027-09-11 | 2027-10-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL4.GEN.3110 | Submittal | 21 | 2027-09-11 | 2027-10-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL4.GEN.5910 | Submittal | 28 | 2027-06-09 | 2027-07-11
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Mechanical | QP.E.ME.BL5.GEN.3040 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical | QP.E.ME.BL5.GEN.3060 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL5.GEN.3080 | Submittal | 21 | 2026-05-14 | 2026-06-10
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL5.GEN.3100 | Submittal | 28 | 2026-05-14 | 2026-06-18
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Mechanical | QP.E.ME.BL5.GEN.3120 | Submittal | 28 | 2026-06-11 | 2026-07-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical | QP.E.ME.BL5.GEN.3140 | Submittal | 28 | 2026-06-20 | 2026-07-21
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1020 | Submittal | 28 | 2026-08-01 | 2026-09-01
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1030 | Submittal | 28 | 2026-08-01 | 2026-09-01
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1040 | Submittal | 28 | 2026-08-01 | 2026-09-01
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1050 | Submittal | 28 | 2026-05-03 | 2026-06-07
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ ICT Containment | QP.E.ME.BL5.GEN.1060 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1550 | Submittal | 21 | 2026-12-20 | 2027-01-12
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1560 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1570 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1580 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL5.GEN.1590 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1750 | Submittal | 28 | 2027-01-13 | 2027-02-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1760 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1770 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1780 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ ICT Containment | QP.E.ME.BL5.GEN.1790 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL5.GEN.2800 | Submittal | 28 | 2027-02-15 | 2027-03-22
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL5.GEN.2840 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL5.GEN.2860 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL5.GEN.2880 | Submittal | 28 | 2027-06-01 | 2027-07-03
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL5.GEN.3020 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL5.GEN.2900 | Submittal | 28 | 2027-07-04 | 2027-08-04
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL5.GEN.2920 | Submittal | 28 | 2027-08-05 | 2027-09-06
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL5.GEN.3000 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL5.GEN.2940 | Submittal | 28 | 2027-07-04 | 2027-08-04
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL5.GEN.2960 | Submittal | 28 | 2027-08-05 | 2027-09-06
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3560 | Submittal | 28 | 2027-09-07 | 2027-10-10
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL5.GEN.1000 | Submittal | 28 | 2027-09-07 | 2027-10-10
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL5.GEN.2980 | Submittal | 28 | 2027-06-01 | 2027-07-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Mechanical | QP.E.ME.PAR.GEN.1459 | Submittal | 21 | 2027-05-22 | 2027-06-14
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Electrical | QP.E.ME.PAR.GEN.1479 | Submittal | 21 | 2027-05-22 | 2027-06-14
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Mechanical | QP.E.ME.PAR.GEN.1499 | Submittal | 21 | 2027-05-22 | 2027-06-14
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Electrical | QP.E.ME.PAR.GEN.1519 | Submittal | 21 | 2027-05-22 | 2027-06-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Fire Suppression | QP.E.ME.PAR.GEN.1000 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1011 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1022 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1033 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ ICT Containment | QP.E.ME.PAR.GEN.1044 | Submittal | 21 | 2027-07-21 | 2027-08-14
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Fire Suppression | QP.E.ME.PAR.GEN.1055 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1066 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1077 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1088 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ ICT Containment | QP.E.ME.PAR.GEN.1099 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.PAR.GEN.1219 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.PAR.GEN.1259 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.PAR.GEN.1279 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.PAR.GEN.1299 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.PAR.GEN.1419 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.PAR.GEN.1319 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.PAR.GEN.1339 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.PAR.GEN.1439 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.PAR.GEN.1359 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.PAR.GEN.1379 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Parking | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.PAR.GEN.1399 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3600 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3610 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3620 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.4430 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4440 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.4450 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3960 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3970 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3980 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Fire Suppression | QP.E.ME.MBL.GEN.3930 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3940 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Electrical | QP.E.ME.MBL.GEN.3950 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Fire Suppression | QP.E.ME.MBL.GEN.3810 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3820 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Electrical | QP.E.ME.MBL.GEN.3830 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4400 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4410 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4420 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4340 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4350 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4360 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4520 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4530 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4540 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4640 | Submittal | 21 | 2027-06-01 | 2027-06-24
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4650 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4660 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3870 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3880 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3890 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3840 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3850 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3860 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.4550 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4560 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.4570 | Submittal | 21 | 2027-05-03 | 2027-05-31
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 3, 4 & 5 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 3, 4 & 5 | QP.E.FA.GEN.GEN.1460 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 1 & 2 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 1 & 2 | QP.E.FA.GEN.GEN.2180 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Loft and Lobby | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Loft and Lobby | QP.E.FA.GEN.GEN.2140 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | QP.E.FA.GEN.GEN.2160 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Blades | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Blades | QP.E.FA.GEN.GEN.1820 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Lobby and Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Lobby and Loft | QP.E.FA.GEN.GEN.1770 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Above Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Above Loft | QP.E.FA.GEN.GEN.1780 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Blades | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Blades | QP.E.FA.GEN.GEN.1890 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Main Building | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Main Building | QP.E.FA.GEN.GEN.2230 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Facade | Facade | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 1 | QP.E.FA.GEN.GEN.1920 | Submittal | 28 | 2026-09-29 | 2026-10-31
Shop Drawings | Facade | Facade | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 2 | QP.E.FA.GEN.GEN.1930 | Submittal | 28 | 2026-08-26 | 2026-09-28
Shop Drawings | Facade | Facade | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 3 | QP.E.FA.GEN.GEN.1940 | Submittal | 28 | 2026-05-17 | 2026-06-21
Shop Drawings | Facade | Facade | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 4 | QP.E.FA.GEN.GEN.1950 | Submittal | 28 | 2026-06-22 | 2026-07-23
Shop Drawings | Facade | Facade | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 5 | QP.E.FA.GEN.GEN.1960 | Submittal | 28 | 2026-07-25 | 2026-08-25
Shop Drawings | Facade | Facade | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Facade ¦ Amphitheatre | QP.E.FA.GEN.GEN.2240 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Lobby | Lobby | Lobby | Lobby | Shop Drawings ¦ Facade ¦ Lobby | QP.E.FA.GEN.GEN.2090 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | Loft | Loft | Loft | Loft | Shop Drawings ¦ Facade ¦ Loft | QP.E.FA.GEN.GEN.2100 | Submittal | 28 | 2027-02-07 | 2027-03-14
Shop Drawings | Facade | Facade | Above Loft | Above Loft | Above Loft | Above Loft | Shop Drawings ¦ Facade ¦ Above Loft | QP.E.FA.GEN.GEN.1910 | Submittal | 28 | 2027-04-17 | 2027-05-23
Shop Drawings | Facade | Facade | Link Bridges | Link Bridges | Link Bridges | Link Bridges | Shop Drawings ¦ Facade ¦ Link Bridges | QP.E.FA.GEN.GEN.2050 | Submittal | 28 | 2027-02-07 | 2027-03-14
Shop Drawings | Facade | Facade | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Shop Drawings ¦ Facade ¦ Facade Lighting Fixtures | QP.E.FA.GEN.GEN.1450 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | GRC Cladding | GRC Cladding | GRC Cladding | GRC Cladding | Shop Drawings ¦ Facade ¦ GRC Cladding | QP.E.FA.GEN.GEN.1390 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 1 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 1 | QP.E.CV.MBL.GEN.3060 | Submittal | 28 | 2026-06-16 | 2026-07-18
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 2 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 2 | QP.E.CV.MBL.GEN.3560 | Submittal | 28 | 2026-08-19 | 2026-09-20
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 3 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 3 | QP.E.CV.MBL.GEN.3580 | Submittal | 28 | 2026-09-21 | 2026-10-24
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 4 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 4 | QP.E.CV.MBL.GEN.3600 | Submittal | 28 | 2026-10-25 | 2026-11-25
Shop Drawings | External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Shop Drawings ¦ External Works ¦ Waterproofing for External Works | QP.E.EX.GEN.GEN.1040 | Submittal | 28 | 2026-06-25 | 2026-07-27
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Excavation | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Excavation | QP.E.CV.MBL.GEN.3320 | Submittal | 15 | 2027-03-31 | 2027-04-17
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Blinding Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Blinding Including Embedded Items | QP.E.CV.MBL.GEN.3500 | Submittal | 15 | 2027-04-18 | 2027-05-04
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Foundation Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Foundation Including Embedded Items | QP.E.CV.MBL.GEN.3480 | Submittal | 28 | 2027-05-05 | 2027-06-10
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Structural Concrete Works Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Structural Concrete Works Including Embedded Items | QP.E.CV.MBL.GEN.3520 | Submittal | 28 | 2027-06-12 | 2027-07-13
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4000 | Submittal | 28 | 2027-07-14 | 2027-08-15
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Finishing | Finishing | Finishing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Finishing | QP.E.AF.MBL.GEN.4030 | Submittal | 21 | 2027-02-10 | 2027-03-07
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4010 | Submittal | 21 | 2027-01-17 | 2027-02-09
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Doors / Openings | QP.E.AF.MBL.GEN.4020 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Fire Suppression | QP.E.ME.MBL.GEN.1690 | Submittal | 21 | 2027-07-14 | 2027-08-07
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Plumbing | Plumbing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Plumbing | QP.E.ME.MBL.GEN.1700 | Submittal | 21 | 2027-07-14 | 2027-08-07
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.1710 | Submittal | 21 | 2027-07-14 | 2027-08-07
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Electrical | Electrical | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Electrical | QP.E.ME.MBL.GEN.1720 | Submittal | 21 | 2027-07-14 | 2027-08-07
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ ELV (Low Current System) | QP.E.ME.MBL.GEN.1730 | Submittal | 21 | 2027-07-14 | 2027-08-07
Shop Drawings | External Works | External Utilities | Irrigation Works | Irrigation Works | Irrigation Works | Irrigation Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ Irrigation Works | QP.E.EX.GEN.GEN.1090 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | External Works | External Utilities | External Drainage Works | External Drainage Works | External Drainage Works | External Drainage Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Drainage Works | QP.E.EX.GEN.GEN.1110 | Submittal | 28 | 2026-12-20 | 2027-01-20
Shop Drawings | External Works | External Utilities | External Lighting Works | External Lighting Works | External Lighting Works | External Lighting Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Lighting Works | QP.E.EX.GEN.GEN.1170 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | External Works | External Utilities | Low Current | Low Current | Low Current | Low Current | Shop Drawings ¦ External Works ¦ External Utilities ¦ Low Current | QP.E.EX.GEN.GEN.1100 | Submittal | 28 | 2027-02-24 | 2027-03-30
Shop Drawings | External Works | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Shop Drawings ¦ External Works ¦ Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 | Submittal | 28 | 2026-08-11 | 2026-09-12
Shop Drawings | External Works | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Shop Drawings ¦ External Works ¦ Water and Environment | QP.E.EX.GEN.GEN.1220 | Submittal | 21 | 2026-09-13 | 2026-10-07
Shop Drawings | External Works | External Fixtures | External Fixtures | External Fixtures | External Fixtures | External Fixtures | Shop Drawings ¦ External Works ¦ External Fixtures | QP.E.EX.GEN.GEN.1260 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | External Works | LPG System | LPG System | LPG System | LPG System | LPG System | Shop Drawings ¦ External Works ¦ LPG System | QP.E.EX.GEN.GEN.1300 | Submittal | 28 | 2027-01-21 | 2027-02-23

## Picklists (hidden)
| #VALUE! |  | Numbering System Document - Metadata Mapping
DOCUMENT NUMBERING DROPDOWN ATTRIBUTES | [18 empty] | QIC GENERAL DROPDOWN ATTRIBUTES
FIELD 01 - PROJECT CODE |  | FIELD 02 - ORIGINATOR |  | FIELD 03 - CONTRACT REFERENCE |  | FIELD 04 - DOCUMENT TYPES |  | FIELD 05 - DISCIPLINE |  | FIELD 06 - AREA/ZONE |  | FIELD 07 - VENUE/BUILDING |  | FIELD 08 - SERIAL NUMBER |  |  |  |  | DOCUMENT DETAILS |  |  | SUITABILITY STATUS |  | NAP GENERAL DROPDOWN ATTRIBUTES
Ab. 01 | 1 - Project Name | Ab. 02 | 2 - Originator Name | Ab. 03 | 3 - Contract Reference | Ab. 04 | 4 - Document Type | Ab. 05 | 5 - Discipline | Ab. 06 | 6 - Area/Zone | Ab. 07 | 7 - Venue/Building | Ab. 08A | 8A - Drawing Type | Ab. 08B | 8B - Level | 8C - Sequence Number | Authoring Software | File/Exchange Format | Scope Area | Code | Status | Scale | Classification ID | Classification | Corporate Discipline | Author
QF01012 | Qiddaya Performing Arts Center | NES | Nesma and Partners | C04518 | Contract Number | AGD | Agenda | ACO | Acoustic | 00 | Overall | Z00000 | Overall | 0 | General (General Notes, Abbreviations, Legends, Single Line Diagrams, General Detail) | 00 | Non-Specific ( For Blade ) | 4 Digit Sequence Number For Drawings/Models | Revit | .rvt | Design Management | S0 (WIP) | Initial status or WIP | NTS | FI_60_25 | Drawing | Architectural | Nesma & Partners
[6 empty] | AVV | Agreed Value of Variation | ADM | Administration | 01 | Zone Sheet 1 | CENT01 | Center Block | 1 | Elevations (Vertical View) | B1 | Basement 1 - Parking A +900.50 | 3 Digit Sequence Number For Documents | Civil3D | .nwc | Architecture / LDC | S1 (Shared) | Suitable for Coordination | AS INDICATED | FI_90_75 | Schedule or table | Electrical | GINGGONG
[6 empty] | ASB | As Built | ARC | Architectural | 02 | Zone Sheet 2 | GARD01 | Guard House | 2 | Plans (Overall, Horizontal View, Floor Plan, Ceiling Plan, Site Plan, Loading Plan) | B2 | Basement 2 - Service +893.50 |  | MicrosoftWord | .nwd | Landscape | S2 (Shared) | Suitable for Information | 1:1 | FI_60_53 | Model | Façade | ALUTEC
[6 empty] | AUR | Audit Report | ADT | Area Development | 03 | Zone Sheet 3 | BLAD01 | Blade 01 | 3 | Sections (Sectional View, Wall Section, Riser) | B3 | Basement 3 - Promenade +887.750 |  | MicrosoftExcel | .ifc | Interior Design | S3 (Shared) | Suitable for Review and Comment | 1:2 | FI_60_15 | Clash Rendition | Fire & Life Safety | AFCO
[6 empty] | BOQ | Bill of Quantities | ASM | Assets Management | 04 | Zone Sheet 4 | BLAD02 | Blade 02 | 4 | Large-scale Views (Enlarged Details) (Plans, Elevations, Stair Sections, etc) | FL | Foundation level |  | Navisworks | .pdf | Signage & Wayfinding | S4 (Shared) | Suitable for Review and Authorisation | 1:5 | FI_40_10 | Calculations | Interior Design | DOKA
[6 empty] | BEP | BIM Execution Plan | AVL | Audio Visual | 05 | Zone Sheet 5 | BLAD03 | Blade 03 | 5 | Details (Any detail view, such as Wall / Floor / Manhole Detail, etc) | L1 | Lobby Level +905.0 |  | inDesign | .jpg | Public Interaction & Activation | S5 (Shared) | Suitable for Review and Acceptance | 1:10 | FI_90_72 | Report | Infrastructure | RAWABI
[6 empty] | BIM | BIM Model | AUV | Audio/Video | 06 | Zone Sheet 6 | BLAD04 | Blade 04 | 6 | Schedules and Diagrams | L2 | Theater Stalls +913.0 |  | Inviso | .xls | Structure | A1 (Published) | Authorised and Accepted-Concept Design | 1:20 | FI_10_90 | Transmittal | Landscape | Subcontractor - Façade Lighting
[6 empty] | BRF | Brief | BRG | Bridges | 07 | Zone Sheet 7 | BLAD05 | Blade 05 | 7 | Combination of different views | L3 | Stalles Mezz & AD Theater +917.5 |  | JPG | .xer | Geotechnical Engineering | A2 (Published) | Authorised and Accepted-Schematic Design 100% | 1:25 | FI_90_47 | Log | Mechanical | Subcontractor - AR / Vertical Transportation
[6 empty] | BUD | Budget | BRC | Broadcast | 08 | Zone Sheet 8 | MBLAD1 | Mini Blade 01 | 8 | User-Defined (For types that do not fall in other categories) | L4 | First Circle & AD Theater +921.0 |  | Recap | .dwf | Civil Engineering | A3 (Published) | Authorised and Accepted-Detailed Design 100% | 1:50 | FI_80_50 | Method statement | Structural | Subcontractor - Unassigned
[6 empty] | CAL | Calculation | BIM | Building Information Modelling | 09 | Zone Sheet 9 | MBLAD4 | Mini Blade 04 | 9 | 3D Representation (Isometric, Perspectives, Photographes) | L5 | Second Circle & Loft |  | Rhino | .dwg | MEP Engineering | A4 (Published) | Authorised and Accepted-Tender | 1:100 | FI_90_64 | Plan
[6 empty] | CER | Certificate | BMS | Building Management System | 10 | Zone Sheet 10 | SECE001 | SEC Room |  |  | L6 | SKY Garden +935.85 |  | Sketchup | .bcf | Fire & Life Safety | A5 (Published) | Authorised and Accepted-IFC | 1:150
[6 empty] | COR | Change Order | CWC | Chilled Water / Cooling | 11 | Zone Sheet 11 | PARK01 | Parking Building |  |  | L8 | Royal Majlis +948.10M |  | Autocad | .3ds | Pitch Design & Sports Playing Surfaces | A6 (Published) | Authorised and Accepted-Construction (Shop Drawing) | 1:200
[6 empty] | CRA | Change Request Authorization | CIV | Civil | 12 | Zone Sheet 12 |  |  |  |  | M1 | Mez Upper Lobby +909.0 |  | ArcGIS | .skp | Specialist Lighting (Services and Systems) | A7 (Published) | Authorised and Accepted-As Built | 1:250
[6 empty] | CDT | Clash Detection Report | CPM | Contracts & Procurement | 13 | Zone Sheet 13 |  |  |  |  | M2 | Mez Loft MEP +931.10 |  |  | .docx | Acoustics | A8(Published) | Authorised and Accepted-In Use | 1:300
[6 empty] | CLM | Claim | CIN | Controls & Instrumentation | 14 | Zone Sheet 14 |  |  |  |  | RL | Roof Level |  |  | .rvt,.nwd,.ifc | AV / Broadcast |  |  | 1:350
[6 empty] | CIN | Client Instruction | CRE | Creative Designer | 15 | Zone Sheet 15 |  |  |  |  | ZZ | Overall |  |  | .nwc,.nwd,.ifc | Security |  |  | 1:500
[6 empty] | CRS | Comments Resolution Sheet | CDM | Crowd Management | 16 | Zone Sheet 16 | [8 empty] | .dwg,.nwc,.ifc | Vertical Transport
[6 empty] | CON | Contract | CUL | Culvert | 17 | Zone Sheet 17 | [8 empty] | .docx,.pdf | Facade & Roof Envelope
[6 empty] | COS | Cost Estimate | DRN | Drainage | 18 | Zone Sheet 18 | [8 empty] | .xer,.pdf | Crowd Modelling / Pedestrian Flow
[6 empty] | DAB | Dashboard | ELP | Earthing & Lighting Protection | 19 | Zone Sheet 19 | [8 empty] | .xls,.pdf | Sustainability
[6 empty] | DOA | Delegation of Authority | ELE | Electrical | 20 | Zone Sheet 20 | [8 empty] | .msp,.pdf | Accessibility
[6 empty] | DES | Design | ELC | Electrical Containment | 21 | Zone Sheet 21 | [8 empty] | .dwg,.pdf | Architect of Record
[6 empty] | MTX | Distribution Matrix | ENV | Environmental | 22 | Zone Sheet 22 | [8 empty] | .indd | Food & Beverage & Operations
[6 empty] | DSS | Dossier | EQP | Equipment | 23 | Zone Sheet 23 | [8 empty] | .pdf, .indd | Utilities, Roads & Infrastructure
[6 empty] | DRW | Drawing | FAC | Facade | 24 | Zone Sheet 24 | [8 empty] | .rvt,.nwc,.ifc | Traffic & Car Parking
[6 empty] | ENI | Engineer Instruction | FED | Federated | 25 | Zone Sheet 25 | [8 empty] | .gdb | Technology (ICT)
[6 empty] | EXP | Expenses | FIN | Finance | 26 | Zone Sheet 26 | [9 empty] | Sports & Specialist Lighting
[6 empty] | HOC | Handover Certificate | FAE | Fire Alarm & Emergency Lighting | 27 | Zone Sheet 27 | [9 empty] | BMS & Access Control
[6 empty] | IRT | Incident Report | FLS | Fire Life Safety | 28 | Zone Sheet 28 | [9 empty] | Waste Management
[6 empty] | ITP | Inspection & Test Plan | FPR | Fire Protection | [11 empty] | Health & Safety in Design
[6 empty] | INS | Instruction | FFE | Furniture Fixture & Equipment | [11 empty] | Wind
[6 empty] | IAB | Insurance and Bonds | GEN | General
[6 empty] | INV | Invoice | GIS | Geospatial Information System
[6 empty] | LAR | Laydown Area Access Request | GEH | Geotechnical & Hydraulics
[6 empty] | LTR | Letter | GRA | Graphics
[6 empty] | LIC | License | HSE | Health and Safety
[6 empty] | LST | List | EHV | High Voltage
[6 empty] | MAN | Manual | HVC | HVAC
[6 empty] | MPL | Master Plan | ICT | Information & Communication Technology
[6 empty] | MAR | Material Approval Request | INF | Infrastructure
[6 empty] | MIR | Material Inspection Request | INS | Installation
[6 empty] | MST | Method Statement | ITS | Intelligent Transportation System
[6 empty] | MOM | Minutes of Meeting | INT | Interior Design
[6 empty] | MIX | Mix Design | IRR | Irrigation
[6 empty] | MOD | Model | KNL | Kitchen & Laundry
[6 empty] | MRP | Monthly Report | LSE | Landscape
[6 empty] | NOC | No Objection Certificate | ELL | Lighting
[6 empty] | NCR | Non-Conformance Report | LTC | Lighting Control
[6 empty] | NDA | Non-Disclosure Agreement | ELV | Low Voltage
[6 empty] | NTC | Notice | LPG | LPG
[6 empty] | OMM | Operation & Maintenance Manual | MAR | Marine Engineering
[6 empty] | ORC | Organizational Chart | MPL | Master Planning
[6 empty] | OTR | Overtime Request | MEC | Mechanical
[6 empty] | PAP | Payment Application | EMV | Medium Voltage
[6 empty] | PYC | Payment Certificate | MEP | MEPF
[6 empty] | PRM | Permit | NTD | Non-Technical Document
[6 empty] | PAF | Personnel Approval Form | OSE | Operating Supplies and Equipment
[6 empty] | PIV | Photographs, Images & Videos | OTH | Others
[6 empty] | PLN | Plan | PLB | Plumbing
[6 empty] | PLT | Plant | PTW | Potable Water
[6 empty] | PPG | Policy & Procedure | PJC | Project Control
[6 empty] | PQS | Prequalification Submittal | QMS | Quality Management
[6 empty] | PRE | Presentation | RID | Rides
[6 empty] | PRO | Procedure | ERL | Road Lighting
[6 empty] | PEP | Project Execution Plan | RKW | Rockwork
[6 empty] | PRS | Proposal | SEC | Security System
[6 empty] | POR | Purchase Order | SEW | Sewage
[6 empty] | REG | Register | SHW | Show
[6 empty] | REP | Report | SGN | Signage / Wayfinding
[6 empty] | RFC | Request For Change | ESP | Small Power
[6 empty] | RSM | Resume | SSC | Smart City
[6 empty] | SVR | Safety Violation Report | SPL | Specialist Lighting
[6 empty] | SMP | Sample | SWD | Storm Water Drainage
[6 empty] | SCH | Schedule | STR | Structural
[6 empty] | SDW | Shop Drawing | SUR | Surveying / Mapping
[6 empty] | SIN | Site Instruction | SUS | Sustainability
[6 empty] | SOR | Site Observation Report | TEL | Telecommunication
[6 empty] | SPE | Specification | TNC | Testing/Commissioning
[6 empty] | STD | Standard | TFC | Traffic System
[6 empty] | SFA | Statement of Final Account | UTI | Utilities
[6 empty] | STR | Strategy | VNT | Ventilation Ductwork
[6 empty] | TOC | Taking Over Certificate | VTR | Vertical Transportation
[6 empty] | TOR | Task Order | VES | Voice Evacuation
[6 empty] | TEM | Template | WSM | Waste Management
[6 empty] | TDC | Tender Document | WTR | Water
[6 empty] | TRP | Test Report | CTV | CCTV System
[6 empty] | TMS | Time Sheet | ACS | Access Control System
[6 empty] | VOR | Variation Order | EFL | Facade Lighting
[6 empty] | WAR | Warranty / Guarantees | DES | Diesel
[6 empty] | WRP | Weekly Report | SMK | Smoke Ductwork
[6 empty] | WIR | Work Inspection Request | STL | Steel Structure
[6 empty] | RLM | RedLine Mark Drawing | FWR | Formwork
[6 empty] | MDP | Master Information Delivery Plan | ELS | Emergency Lighting system
[6 empty] | TDP | Task Information Delivery Plan | EBW | Electrical Builder Works
[8 empty] | MBW | Mechanical Builder Works
[8 empty] | EBC | Electrical Busway