## TIDP_Sheet
TASK INFORMATION DELIVERY PLAN (TIDP)
CLIENT | Qiddiya | #VALUE!
PROJECT | Qiddiya Performing Arts Center (QPAC)
ORGANISATION | Nesma & Partners
DISCIPLINE | Electrical
APPROVER | BSBG
DATE CREATED
DATE LAST UPDATED
REVISION NUMBER | 00
DOCUMENT REFERENCE | QF01012-NES-C04518-TDP-XXX-00-000000-000001
This document shall be populated and kept up-to-date by the task team | [10 empty] | REFER TO THE FILE NAMING CONVENTION IN THE BIM EXECUTION PLAN | [10 empty] | DATA EXCHANGE #01 | [5 empty] | DATA EXCHANGE #02
[11 empty] | DOC REFERENCE GENERATOR | [10 empty] | STAGE: | CONSTRUCTION |  |  |  |  | STAGE: | HAND OVER
[22 empty] | PROGRAMME REF: | [5 empty] | PROGRAMME REF:
[5 empty] | EXCHANGE FORMATS | [5 empty] | FIELD 01 | FIELD 02 | FIELD 03 | FIELD 04 | FIELD 05 | FIELD 06 | FIELD 07 | FIELD 08 |  |  |  |  | LEVEL OF INFORMATION NEED | [5 empty] | LEVEL OF INFORMATION NEED
DOCUMENT NUMBER | DOCUMENT TITLE | EXTRACTED FROM MODEL | SCOPE AREA | AUTHORING SOFTWARE | EXCHANGE FORMAT | SCALE | DELIVERY MILESTONE | PACKAGE NAME | ACTIVITY ID | CLASSIFICATION CODE | PROJECT | ORIGINATOR | CONTRACT | DOCUMENT TYPE | DISCIPLINE | AREA/ZONE | VENUE/BUILDING | DRAWING TYPE | LEVEL | SEQUENCE NUMBER | CORPORATE DISCIPLINE | 01-AUTHOR | 01-GEOMETRICAL | 01-NON GEOMETRICAL | 01-DURATION (DAYS) | 01-PREDECESSOR | 01-EXCHANGE DATE | 02-AUTHOR | 02-GEOMETRICAL | 02-NON GEOMETRICAL | 02-DURATION (DAYS) | 02-PREDECESSOR | 02-EXCHANGE DATE
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ5992 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 5992 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ5993 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 5993 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ5994 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 5994 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ5995 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 5995 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ5996 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 5996 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ5997 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 5997 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ5998 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 5998 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ5999 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 5999 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6000 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6000 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6001 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6001 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6002 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6002 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6003 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6003 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6004 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6004 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6005 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6005 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6006 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6006 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6007 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6007 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6008 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6008 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6009 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6009 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6010 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6010 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6011 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6011 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6012 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6012 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6013 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6013 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6014 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6014 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6015 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6015 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6016 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6016 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6017 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6017 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6018 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6018 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6019 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6019 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6020 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6020 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6021 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6021 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6022 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6022 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6023 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6023 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6024 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6024 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6025 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6025 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6026 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6026 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6027 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6027 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6028 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6028 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6029 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6029 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6030 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6030 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6031 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6031 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6032 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6032 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6033 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6033 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6034 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6034 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6035 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6035 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6036 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6036 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6037 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6037 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6038 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6038 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6039 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6039 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6040 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6040 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6041 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6041 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6042 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6042 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6043 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6043 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6044 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6044 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6045 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6045 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6046 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6046 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6047 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6047 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6048 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6048 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6049 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6049 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6050 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6050 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6051 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6051 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6052 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6052 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6053 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6053 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6054 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6054 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6055 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6055 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6056 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6056 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6057 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6057 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6058 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6058 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6059 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6059 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6060 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6060 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6061 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6061 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6062 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6062 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6063 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6063 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6064 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6064 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6065 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6065 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6066 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6066 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6067 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6067 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6068 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6068 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6069 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6069 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6070 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6070 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6071 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6071 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6072 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6072 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6073 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6073 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6115 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6115 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6116 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6116 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6117 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6117 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6118 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6118 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6119 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6119 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6120 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6120 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6121 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6121 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6122 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6122 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6123 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6123 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6124 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6124 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6125 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6125 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6126 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6126 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6127 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6127 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6128 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6128 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6129 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6129 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6130 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6130 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6131 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6131 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6132 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6132 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6133 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6133 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6134 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6134 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6135 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6135 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6136 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6136 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6137 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6137 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6138 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6138 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6139 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6139 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6140 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6140 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6141 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6141 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6142 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6142 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6143 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6143 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6144 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6144 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6145 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6145 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6146 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6146 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6147 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6147 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6148 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6148 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6149 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6149 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6150 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6150 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6151 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6151 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6152 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6152 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6153 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6153 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6154 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6154 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6155 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2560 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6155 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-04-17
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6404 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6404 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6405 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6405 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6406 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6406 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6407 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6407 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6408 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6408 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6409 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6409 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6410 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6410 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6411 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6411 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6412 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6412 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6413 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6413 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6414 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6414 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6415 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6415 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6416 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6416 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6417 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6417 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6418 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6418 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6419 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6419 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6420 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6420 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6421 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6421 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6422 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6422 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6423 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6423 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6424 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6424 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6425 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6425 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6426 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6426 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6427 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6427 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6428 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6428 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6429 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6429 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6430 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6430 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6431 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6431 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6432 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6432 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6433 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6433 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6434 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6434 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6435 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6435 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6436 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6436 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6437 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6437 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6438 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6438 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6439 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6439 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6440 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6440 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6441 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6441 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6442 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6442 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-AVL-00-Z00000-2ZZ6443 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 2 | ZZ | 6443 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6444 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6444 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6445 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6445 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6446 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6446 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6447 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6447 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6448 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6448 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6449 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6449 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6450 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6450 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6451 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6451 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6452 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6452 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6453 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6453 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6454 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6454 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6455 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6455 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6456 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6456 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6457 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6457 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6458 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6458 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6459 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6459 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6460 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6460 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6461 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6461 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6462 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6462 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6463 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6463 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6464 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6464 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6465 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6465 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6466 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6466 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6467 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6467 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6468 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6468 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6469 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6469 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6470 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6470 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6471 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6471 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6472 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6472 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6473 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6473 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6474 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6474 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6475 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6475 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6476 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6476 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6477 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6477 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6478 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6478 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6479 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6479 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6480 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6480 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6481 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6481 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6482 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6482 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6483 | PS2 - IT/AV & SPECIALIST MEDIA (EXCLUDE THEATRE FOH AREAS) |  |  | Revit | .dwg,.pdf |  |  | PS.2 | QP.C.PS.GEN.GEN.1200 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6483 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-07-31
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5177 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5177 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5178 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5178 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5179 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5179 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5180 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5180 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5181 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5181 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5182 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5182 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5183 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5183 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5184 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5184 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5185 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5185 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5186 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5186 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5187 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5187 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5188 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5188 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5189 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5189 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5190 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5190 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5191 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5191 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5192 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5192 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5193 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5193 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5194 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5194 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5195 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5195 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5196 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5196 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5197 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5197 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5198 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5198 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5199 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5199 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5200 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5200 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5201 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5201 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5202 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5202 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5203 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5203 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5204 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5204 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5205 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5205 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5206 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5206 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5207 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5207 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5208 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5208 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5209 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5209 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5210 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5210 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5211 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5211 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5212 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5212 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5213 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5213 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5214 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5214 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5215 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5215 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5216 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5216 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5217 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5217 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5218 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5218 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5219 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5219 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5220 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5220 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5221 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5221 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5222 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5222 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5223 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5223 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5224 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5224 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5225 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5225 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5226 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5226 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6484 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6484 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6485 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6485 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6486 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6486 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6487 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6487 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6488 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6488 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6489 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6489 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6490 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6490 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6491 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6491 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6492 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6492 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6493 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6493 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6494 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6494 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6495 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6495 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6496 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6496 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6497 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6497 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6498 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6498 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6499 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6499 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6500 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6500 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6501 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6501 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6502 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6502 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6503 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6503 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6504 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6504 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6505 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6505 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6506 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6506 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6507 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6507 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6508 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6508 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6509 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6509 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6510 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6510 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6511 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6511 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6512 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6512 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6513 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6513 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6514 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6514 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6515 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6515 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6516 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6516 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6517 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6517 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6518 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6518 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6519 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6519 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6520 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6520 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6521 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6521 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6522 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6522 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6523 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6523 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6524 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6524 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6525 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6525 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6526 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6526 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6527 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6527 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6528 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6528 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6529 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6529 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6530 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6530 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6531 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6531 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6532 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6532 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-SPL-00-Z00000-2ZZ6533 | PS3-SPECIALIST LIGHTING (@ FOH AREA) |  |  | Revit | .dwg,.pdf |  |  | PS.3 | QP.C.PS.GEN.GEN.1850 | FI_60_25 | QF01012 | NES | C04518 | SDW | SPL | 00 | Z00000 | 2 | ZZ | 6533 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6534 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6534 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6535 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6535 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6536 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6536 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6537 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6537 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6538 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6538 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6539 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6539 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6540 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6540 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6541 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6541 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6542 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6542 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6543 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6543 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6544 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6544 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6545 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6545 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6546 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6546 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6547 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6547 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6548 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6548 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6549 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6549 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6550 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6550 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6551 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6551 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6552 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6552 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6553 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6553 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6554 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6554 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6555 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6555 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6556 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6556 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6557 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6557 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6558 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6558 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6559 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6559 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6560 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6560 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6561 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6561 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6562 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6562 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6563 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6563 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6564 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6564 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6565 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6565 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6566 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6566 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6567 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6567 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6568 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6568 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6569 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6569 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6570 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6570 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6571 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6571 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6572 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6572 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6573 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6573 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6574 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6574 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6575 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6575 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6576 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6576 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6577 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6577 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6578 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6578 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6579 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6579 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6580 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6580 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6581 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6581 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6582 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6582 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6583 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6583 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6584 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6584 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6585 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6585 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6586 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6586 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6587 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6587 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6588 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6588 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6589 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6589 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6590 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6590 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6591 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6591 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6592 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6592 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6593 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6593 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6594 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6594 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6595 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6595 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6596 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6596 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6597 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6597 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6598 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6598 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6599 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6599 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6600 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6600 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6601 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6601 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6602 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6602 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6603 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6603 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6604 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6604 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6605 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6605 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6606 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6606 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6607 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6607 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6608 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6608 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6609 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6609 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6610 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6610 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6611 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6611 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6612 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6612 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6613 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6613 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6614 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6614 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6615 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6615 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6616 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6616 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6617 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6617 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6618 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6618 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6619 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6619 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6620 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6620 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6621 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6621 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6622 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6622 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6623 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6623 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6624 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6624 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6625 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6625 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6626 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6626 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6627 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6627 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6628 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6628 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6629 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6629 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6630 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6630 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6631 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6631 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6632 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6632 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6633 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.2120 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6633 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-11-29
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5802 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5802 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5803 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5803 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5804 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5804 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5805 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5805 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5806 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5806 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5807 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5807 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5808 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5808 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5809 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5809 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5810 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5810 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5811 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5811 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5812 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5812 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5813 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5813 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5814 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5814 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5815 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5815 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5816 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5816 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5817 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5817 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5818 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5818 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5819 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5819 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5820 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5820 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5821 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5821 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5822 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5822 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5823 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5823 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5824 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5824 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5825 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5825 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5826 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5826 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5827 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5827 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5828 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5828 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5829 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5829 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5830 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5830 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5831 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5831 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5832 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5832 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5833 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5833 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5834 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5834 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5835 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5835 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5836 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5836 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5837 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5837 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5838 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5838 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5839 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5839 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5840 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5840 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5841 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5841 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5842 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5842 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5843 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5843 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5844 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5844 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5845 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5845 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5846 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5846 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5847 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5847 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5848 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5848 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5849 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5849 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5850 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5850 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5851 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5851 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5852 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5852 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5853 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5853 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5854 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5854 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5855 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5855 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5856 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5856 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5857 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5857 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5858 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5858 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5859 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5859 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5860 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5860 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5861 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5861 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5862 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5862 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5863 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5863 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5864 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5864 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5865 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5865 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5866 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5866 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5867 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5867 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5868 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5868 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5869 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5869 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5870 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5870 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5871 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5871 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5872 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5872 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5873 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5873 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5874 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5874 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5875 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5875 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5876 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5876 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5877 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5877 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5878 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5878 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5879 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5879 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5880 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5880 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5881 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5881 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5882 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5882 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5883 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5883 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5884 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5884 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5885 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5885 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5886 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5886 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5887 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5887 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5888 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5888 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5889 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5889 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5890 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5890 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5891 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5891 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5892 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5892 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5893 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5893 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5894 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5894 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5895 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5895 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5896 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5896 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5897 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5897 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5898 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5898 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5899 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5899 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5900 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5900 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ5901 | PS5- SIGNAGE & WAYFIDING |  |  | Revit | .dwg,.pdf |  |  | PS.5 | QP.C.PS.GEN.GEN.2140 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 5901 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6681 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6681 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6682 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6682 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6683 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6683 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6684 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6684 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6685 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6685 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6686 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6686 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6687 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6687 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6688 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6688 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6689 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6689 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6690 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6690 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6691 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6691 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6692 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6692 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6693 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6693 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6694 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6694 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6695 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6695 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6696 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6696 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6697 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6697 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6698 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6698 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6699 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6699 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6700 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6700 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6701 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6701 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6702 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6702 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6703 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6703 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6704 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6704 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6705 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6705 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6706 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6706 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6707 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6707 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6708 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6708 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6709 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6709 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ICT-00-Z00000-2ZZ6710 | PS7 - PROMENADE BRIDGE |  |  | Revit | .dwg,.pdf |  |  | PS.7 | QP.C.PS.GEN.GEN.2340 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 2 | ZZ | 6710 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-07-30
QF01012-NES-C04518-SDW-ELE-00-Z00000-2ZZ6721 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 2 | ZZ | 6721 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6722 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6722 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6723 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6723 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6724 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6724 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6725 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6725 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6726 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6726 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6727 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6727 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6728 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6728 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6729 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6729 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6730 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6730 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6731 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6731 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6732 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6732 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6733 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6733 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6734 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6734 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6735 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6735 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6736 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6736 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6737 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6737 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6738 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6738 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6739 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6739 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ6740 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 6740 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6741 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6741 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6742 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6742 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6743 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6743 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6744 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6744 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6745 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6745 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6746 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6746 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6747 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6747 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6748 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6748 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6749 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6749 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6750 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6750 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6751 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6751 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6752 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6752 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6753 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6753 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6754 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6754 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6755 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6755 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6756 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6756 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6757 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6757 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6758 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6758 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6759 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6759 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6760 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6760 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6761 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6761 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6762 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6762 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6763 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6763 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6764 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6764 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6765 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6765 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6766 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6766 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6767 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6767 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6768 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6768 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6769 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6769 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ICT-00-Z00000-6ZZ6770 | PS8-SECURITY EQUIPMENT |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 6 | ZZ | 6770 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6890 | TRAFFIC SYSTEM OVERALL SITE PLAN |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2400 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6890 | Electrical | Provisional Sum | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6891 | PS8-SECURITY EQUIPMENT (TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN ) |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6891 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6892 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 01 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6892 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6893 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 02 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6893 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6894 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 03 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6894 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6895 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 04 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6895 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6896 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 05 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6896 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6897 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 06 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6897 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6898 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 07 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6898 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6899 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 08 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6899 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6900 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 09 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6900 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6901 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 10 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6901 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6902 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 11 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6902 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6903 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 12 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6903 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6904 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 13 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6904 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6905 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 14 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6905 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6906 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 15 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6906 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6907 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 16 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6907 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6908 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 17 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6908 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6909 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 18 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6909 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6910 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 19 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6910 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6911 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 20 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6911 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6912 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 21 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6912 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6913 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 22 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6913 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6914 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 23 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6914 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6915 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 24 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6915 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6916 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 25 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6916 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6917 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 26 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6917 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6918 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 27 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6918 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6919 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 28 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6919 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6920 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 29 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6920 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6921 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 30 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6921 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6922 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 31 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6922 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6923 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 32 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6923 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6924 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 33 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6924 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03
QF01012-NES-C04518-SDW-TFC-00-Z00000-2ZZ6925 | PS8-SECURITY EQUIPMENT -TRAFFIC & CAR PARKING SYSTEM PARTIAL SITE PLAN - SHEET 34 |  |  | Revit | .dwg,.pdf |  |  | PS.8 | QP.C.PS.GEN.GEN.2500 | FI_60_25 | QF01012 | NES | C04518 | SDW | TFC | 00 | Z00000 | 2 | ZZ | 6925 | Electrical | Provisional Sum | LOD400 |  |  |  | 2028-01-03

## Baseline (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | Package | Activity Code | Activity | Original Duration | Start | Finish
Shop Drawings | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Shop Drawings ¦ Mobilization | QP.M.GN.GEN.GEN.1400 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Shop Drawings ¦ Mobilization ¦ Tower Crane Foundation - Concrete Works | QP.M.GN.GEN.GEN.1470 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Blades Below Loft | QP.M.GN.GEN.GEN.1540 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Loft | QP.M.GN.GEN.GEN.1560 | Submittal | 12 | 2026-08-29 | 2026-09-10
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Above Loft | QP.M.GN.GEN.GEN.1580 | Submittal | 12 | 2026-10-01 | 2026-10-14
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works | QP.E.CV.MBL.GEN.3460 | Submittal | 28 | 2025-10-11 | 2025-11-11
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works Outside Core Area | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works Outside Core Area | QP.E.CV.MBL.GEN.3540 | Submittal | 14 | 2025-11-12 | 2025-11-27
Shop Drawings | Civil | Blades | Blade 1 | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 1 | QP.E.CV.BL1.GEN.1060 | Submittal | 28 | 2026-02-21 | 2026-03-28
Shop Drawings | Civil | Blades | Blade 2 | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 2 | QP.E.CV.BL2.GEN.1060 | Submittal | 28 | 2026-01-19 | 2026-02-19
Shop Drawings | Civil | Blades | Blade 3 | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 3 | QP.E.CV.BL3.GEN.1060 | Submittal | 28 | 2025-12-17 | 2026-01-18
Shop Drawings | Civil | Blades | Blade 4 | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 4 | QP.E.CV.BL4.GEN.1060 | Submittal | 28 | 2025-12-03 | 2026-01-04
Shop Drawings | Civil | Blades | Blade 5 | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 5 | QP.E.CV.BL5.GEN.1060 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Civil | Parking | Parking | Parking | Parking | Parking | Shop Drawings ¦ Civil ¦ Parking | QP.E.CV.PAR.GEN.1000 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - Foundation Works Core Area | QP.E.CV.MBL.GEN.3000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 03 +887.750M | QP.E.CV.MBL.GEN.3030 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - SOG | QP.E.CV.MBL.GEN.3640 | Submittal | 14 | 2026-03-16 | 2026-04-02
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 02 - Foundation Works Outside Core Area | QP.E.CV.MBL.GEN.3020 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 02 +893.5M | QP.E.CV.MBL.GEN.3070 | Submittal | 21 | 2026-02-18 | 2026-03-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 01 +900.5M | QP.E.CV.MBL.GEN.3100 | Submittal | 28 | 2026-03-16 | 2026-04-19
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01- LOBBY LEVEL +905M | QP.E.CV.MBL.GEN.3120 | Submittal | 25 | 2026-04-20 | 2026-05-18
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01 - MEZZANINE +909M | QP.E.CV.MBL.GEN.3140 | Submittal | 15 | 2026-05-19 | 2026-06-08
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3180 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3380 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3220 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3400 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3240 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3420 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3260 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3440 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | QP.E.CV.MBL.GEN.3280 | Submittal | 25 | 2026-10-08 | 2026-11-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | QP.E.CV.MBL.GEN.3300 | Submittal | 28 | 2027-03-13 | 2027-04-13
Shop Drawings | Concrete | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Premium Theatre Concrete Works | QP.E.CV.MBL.GEN.3150 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Amphitheatre Concrete Works | QP.E.CV.MBL.GEN.3200 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Premium Theater | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Premium Theater | QP.E.CV.MBL.GEN.3660 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Loft and Adaptable Theatre | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Loft and Adaptable Theatre | QP.E.CV.MBL.GEN.3700 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Fly Tower | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Fly Tower | QP.E.CV.MBL.GEN.3710 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Lobby & Plaza | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Lobby & Plaza | QP.E.CV.MBL.GEN.3680 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Royal Majlis | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Royal Majlis | QP.E.CV.MBL.GEN.3740 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Foundation | QP.E.CV.BL1.GEN.1000 | Submittal | 25 | 2026-02-25 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL1.GEN.1040 | Submittal | 25 | 2026-03-29 | 2026-04-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL1.GEN.1080 | Submittal | 18 | 2026-05-12 | 2026-06-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL1.GEN.1020 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL1.GEN.1120 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL1.GEN.1100 | Submittal | 28 | 2026-10-27 | 2026-11-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Foundation | QP.E.CV.BL2.GEN.1000 | Submittal | 21 | 2026-03-02 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL2.GEN.1040 | Submittal | 21 | 2026-03-10 | 2026-04-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL2.GEN.1080 | Submittal | 18 | 2026-04-21 | 2026-05-11
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL2.GEN.1020 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL2.GEN.1140 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL2.GEN.1120 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Foundation | QP.E.CV.BL3.GEN.1000 | Submittal | 21 | 2026-02-07 | 2026-03-03
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Steel Composite Slab Including Embedded items Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Steel Composite Slab Including Embedded items Below Loft | QP.E.CV.BL3.GEN.1030 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL3.GEN.1080 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL3.GEN.1020 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Foundation | QP.E.CV.BL4.GEN.1000 | Submittal | 28 | 2026-01-05 | 2026-02-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL4.GEN.1030 | Submittal | 28 | 2026-02-24 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL4.GEN.1080 | Submittal | 15 | 2026-03-31 | 2026-04-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL4.GEN.1020 | Submittal | 28 | 2026-04-18 | 2026-05-19
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL4.GEN.1100 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL4.GEN.1120 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Foundation | QP.E.CV.BL5.GEN.1000 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL5.GEN.1030 | Submittal | 28 | 2026-03-23 | 2026-04-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL5.GEN.1080 | Submittal | 18 | 2026-03-31 | 2026-04-20
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL5.GEN.1020 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL5.GEN.1100 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL5.GEN.1120 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Foundation Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Foundation Including Embedded items | QP.E.CV.PAR.GEN.1020 | Submittal | 28 | 2027-04-28 | 2027-06-03
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Structural Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Structural Concrete Works Including Embedded items | QP.E.CV.PAR.GEN.1040 | Submittal | 28 | 2027-06-19 | 2027-07-20
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Below Loft | QP.E.ST.GEN.GEN.1090 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1100 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1110 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1050 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1060 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1070 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 3,4,5 | QP.E.ST.GEN.GEN.1000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | QP.E.ST.GEN.GEN.1010 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Truss below Auditorium, Side and Back Stage | QP.E.ST.GEN.GEN.2120 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1220 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1230 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1200 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1210 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1190 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Embedded part - Main Building Above Level 5 | QP.E.ST.GEN.GEN.1040 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Premium Theater - Frame Balconies and Back Stage Dressing | QP.E.ST.GEN.GEN.2140 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Loft and adaptable Theatre | QP.E.ST.GEN.GEN.1340 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1390 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1400 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1310 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1320 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1330 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1470 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ Truss above Auditorium Incl. Metal Deck | QP.E.ST.GEN.GEN.2100 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Temporay Tower ROYAL MAJLIS and Blades above loft | QP.E.ST.GEN.GEN.1490 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2160 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1520 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Truss above Flytower | QP.E.ST.GEN.GEN.2180 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1540 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ Blade 2 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2200 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ Adaptable Theatre Incl. Metal Deck | QP.E.ST.GEN.GEN.1560 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.2220 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Loft Truss and Infilled Beam North Side Incl. Metal Deck | QP.E.ST.GEN.GEN.1610 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1600 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Lobby and Plaza Incl. Metal Deck | QP.E.ST.GEN.GEN.1660 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Frame for Mezzanine | QP.E.ST.GEN.GEN.1670 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Link Bridge and Helix Stair | QP.E.ST.GEN.GEN.1570 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1680 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | Shop Drawings ¦ Structural Steel ¦ Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck ¦ ROYAL MAJLIS | QP.E.ST.GEN.GEN.1640 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1090 | Submittal | 21 | 2026-03-26 | 2026-04-19
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1120 | Submittal | 21 | 2026-09-15 | 2026-10-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Wall Cladding | QP.E.AF.MBL.GEN.4440 | Submittal | 21 | 2026-10-11 | 2026-11-03
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1100 | Submittal | 21 | 2026-11-04 | 2026-11-28
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ FFE | QP.E.AF.MBL.GEN.5260 | Submittal | 21 | 2026-11-29 | 2026-12-22
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1170 | Submittal | 21 | 2026-04-20 | 2026-05-13
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1200 | Submittal | 20 | 2026-11-04 | 2026-11-26
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5700 | Submittal | 21 | 2026-11-28 | 2026-12-21
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1180 | Submittal | 21 | 2026-12-23 | 2027-01-16
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ FFE | QP.E.AF.MBL.GEN.5280 | Submittal | 21 | 2027-01-17 | 2027-02-09
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1220 | Submittal | 21 | 2026-05-14 | 2026-06-10
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1250 | Submittal | 28 | 2026-11-28 | 2026-12-29
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5720 | Submittal | 21 | 2026-12-30 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1230 | Submittal | 21 | 2027-01-24 | 2027-02-16
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ FFE | QP.E.AF.MBL.GEN.5300 | Submittal | 21 | 2027-02-17 | 2027-03-16
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1310 | Submittal | 21 | 2026-06-11 | 2026-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1340 | Submittal | 28 | 2026-12-30 | 2027-01-31
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5800 | Submittal | 21 | 2027-02-01 | 2027-02-25
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1320 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ FFE | QP.E.AF.MBL.GEN.5320 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1400 | Submittal | 21 | 2026-07-06 | 2026-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1430 | Submittal | 20 | 2027-02-01 | 2027-02-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5740 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1410 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ FFE | QP.E.AF.MBL.GEN.5340 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1000 | Submittal | 21 | 2026-07-30 | 2026-08-23
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1030 | Submittal | 20 | 2027-02-25 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5760 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1010 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ FFE | QP.E.AF.MBL.GEN.5360 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1490 | Submittal | 21 | 2026-08-24 | 2026-09-16
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1520 | Submittal | 20 | 2027-03-23 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5820 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1500 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ FFE | QP.E.AF.MBL.GEN.5380 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1580 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1610 | Submittal | 20 | 2027-04-15 | 2027-05-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5840 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1590 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ FFE | QP.E.AF.MBL.GEN.5400 | Submittal | 21 | 2027-07-06 | 2027-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1670 | Submittal | 21 | 2026-12-20 | 2027-01-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1700 | Submittal | 20 | 2027-05-23 | 2027-06-14
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5860 | Submittal | 28 | 2027-06-15 | 2027-07-17
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1680 | Submittal | 28 | 2027-07-18 | 2027-08-18
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ FFE | QP.E.AF.MBL.GEN.5420 | Submittal | 28 | 2027-07-31 | 2027-08-31
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1760 | Submittal | 21 | 2027-01-19 | 2027-02-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1790 | Submittal | 21 | 2027-05-23 | 2027-06-15
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5880 | Submittal | 21 | 2027-07-18 | 2027-08-10
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1770 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ FFE | QP.E.AF.MBL.GEN.5440 | Submittal | 21 | 2027-09-01 | 2027-09-26
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1880 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1910 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5900 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1890 | Submittal | 21 | 2027-09-13 | 2027-10-07
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ FFE | QP.E.AF.MBL.GEN.5460 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1800 | Submittal | 21 | 2027-04-22 | 2027-05-20
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1830 | Submittal | 21 | 2027-07-25 | 2027-08-17
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5920 | Submittal | 21 | 2027-08-25 | 2027-09-18
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1810 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ FFE | QP.E.AF.MBL.GEN.5480 | Submittal | 21 | 2027-10-11 | 2027-11-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1110 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1140 | Submittal | 21 | 2027-05-31 | 2027-06-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1120 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1370 | Submittal | 21 | 2027-03-01 | 2027-03-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1360 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Wall Cladding | QP.E.AF.BL1.GEN.5940 | Submittal | 21 | 2027-07-19 | 2027-08-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1340 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1650 | Submittal | 21 | 2027-06-14 | 2027-07-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1680 | Submittal | 14 | 2027-09-01 | 2027-09-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1660 | Submittal | 21 | 2027-11-18 | 2027-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1080 | Submittal | 21 | 2027-05-26 | 2027-06-19
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1110 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Wall Cladding | QP.E.AF.BL2.GEN.5960 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1090 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1580 | Submittal | 21 | 2027-07-04 | 2027-07-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1610 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1590 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1670 | Submittal | 21 | 2027-07-28 | 2027-08-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1700 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1680 | Submittal | 14 | 2028-01-18 | 2028-02-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1000 | Submittal | 24 | 2026-11-15 | 2026-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1030 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL3.GEN.5980 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1010 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1340 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1370 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1350 | Submittal | 21 | 2027-12-22 | 2028-01-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1210 | Submittal | 24 | 2026-12-27 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1240 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL4.GEN.6000 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1220 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1820 | Submittal | 21 | 2027-04-24 | 2027-05-22
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1850 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1830 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1730 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1760 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1740 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.2280 | Submittal | 24 | 2027-02-07 | 2027-03-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.2340 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.2300 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1130 | Submittal | 21 | 2027-03-22 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1160 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1140 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1500 | Submittal | 28 | 2027-06-29 | 2027-07-31
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1530 | Submittal | 21 | 2027-10-10 | 2027-11-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Wall Cladding | QP.E.AF.BL5.GEN.6020 | Submittal | 21 | 2027-12-16 | 2028-01-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1510 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1000 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1020 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Doors / Openings | QP.E.AF.PAR.GEN.1010 | Submittal | 28 | 2027-12-22 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Specialities | QP.E.AF.MBL.GEN.5160 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1030 | Submittal | 28 | 2027-10-16 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1050 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Doors / Openings | QP.E.AF.PAR.GEN.1040 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Specialities | QP.E.AF.MBL.GEN.5200 | Submittal | 21 | 2028-01-09 | 2028-02-01
Shop Drawings | Architecture and Fitouts | Amphitheatre | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4040 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Architecture and Fitouts | Amphitheatre | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.4070 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Amphitheatre | Wall Cladding | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Wall Cladding | QP.E.AF.MBL.GEN.6040 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | Architecture and Fitouts | Amphitheatre | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4050 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | Shop Drawings ¦ External Building Works (Guard House, SEC Room) | QP.E.EX.GEN.GEN.1270 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Main Building | QP.E.AF.MBL.GEN.6060 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 5 | Water Proofing - Roof - Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 5 | QP.E.AF.BL5.GEN.6180 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 4 | Water Proofing - Roof - Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 4 | QP.E.AF.BL4.GEN.6160 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 3 | Water Proofing - Roof - Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 3 | QP.E.AF.BL3.GEN.6140 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 1 | Water Proofing - Roof - Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 1 | QP.E.AF.BL1.GEN.6100 | Submittal | 21 | 2027-12-09 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 2 | Water Proofing - Roof - Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 2 | QP.E.AF.BL2.GEN.6120 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Wet Areas | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Wet Areas ¦ Main Building | QP.E.AF.MBL.GEN.4400 | Submittal | 21 | 2027-08-08 | 2027-08-31
Shop Drawings | Specialist Systems | Doors/ Openings | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Main Building | QP.E.AF.MBL.GEN.1140 | Submittal | 20 | 2027-06-29 | 2027-07-21
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.1130 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 2 | QP.E.AF.BL2.GEN.1100 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.1020 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.1230 | Submittal | 21 | 2027-08-16 | 2027-09-08
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.2320 | Submittal | 21 | 2027-09-09 | 2027-10-04
Shop Drawings | Specialist Systems | Doors/ Openings | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Amphitheatre | QP.E.AF.MBL.GEN.4060 | Submittal | 28 | 2027-11-13 | 2027-12-14
Shop Drawings | Specialist Systems | Conveying System | Waste Management | Waste Management | Waste Management | Waste Management | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Waste Management | QP.E.CY.GEN.GEN.1280 | Submittal | 14 | 2027-12-02 | 2027-12-18
Shop Drawings | Specialist Systems | Conveying System | Escalators | Escalators | Escalators | Escalators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Escalators | QP.E.CY.GEN.GEN.1040 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | Specialist Systems | Conveying System | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | QP.E.CY.GEN.GEN.1020 | Submittal | 28 | 2026-10-22 | 2026-11-23
Shop Drawings | Specialist Systems | Conveying System | Truck Elevators | Truck Elevators | Truck Elevators | Truck Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Truck Elevators | QP.E.CY.GEN.GEN.1000 | Submittal | 28 | 2026-09-19 | 2026-10-21
Shop Drawings | Specialist Systems | Conveying System | Inclined Elevators | Inclined Elevators | Inclined Elevators | Inclined Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Inclined Elevators | QP.E.CY.GEN.GEN.1050 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Main Building | QP.E.CY.GEN.GEN.1090 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 1 | QP.E.CY.GEN.GEN.1130 | Submittal | 28 | 2027-10-17 | 2027-11-17
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 2 | QP.E.CY.GEN.GEN.1170 | Submittal | 28 | 2027-09-13 | 2027-10-16
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 3 | Balde 3 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 3 | QP.E.CY.GEN.GEN.1210 | Submittal | 28 | 2027-06-07 | 2027-07-08
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 4 | QP.E.CY.GEN.GEN.1110 | Submittal | 28 | 2027-07-10 | 2027-08-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 5 | Balde 5 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 5 | QP.E.CY.GEN.GEN.1150 | Submittal | 28 | 2027-08-11 | 2027-09-12
Shop Drawings | Specialist Systems | Joinery Works | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Main Building | QP.E.AF.MBL.GEN.5540 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.6120 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.6160 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.6180 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.6200 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Shop Drawings ¦ Specialist Systems ¦ Kitchen and Laundary | QP.E.AF.MBL.GEN.5500 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Specialist Systems | Water Features | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Specialist Systems ¦ Water Features | QP.E.AF.MBL.GEN.6100 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Mechanical | QP.E.ME.MBL.GEN.6780 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical | QP.E.ME.MBL.GEN.6800 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6840 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical | QP.E.ME.MBL.GEN.6850 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6860 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical | QP.E.ME.MBL.GEN.6870 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Mechanical | QP.E.ME.MBL.GEN.6900 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical | QP.E.ME.MBL.GEN.6910 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Mechanical | QP.E.ME.MBL.GEN.6940 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical | QP.E.ME.MBL.GEN.6950 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Mechanical | QP.E.ME.MBL.GEN.6980 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Electrical | QP.E.ME.MBL.GEN.6990 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Mechanical | QP.E.ME.MBL.GEN.7020 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical | QP.E.ME.MBL.GEN.7030 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7060 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical | QP.E.ME.MBL.GEN.7070 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7100 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical | QP.E.ME.MBL.GEN.7110 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Mechanical | QP.E.ME.MBL.GEN.7140 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical | QP.E.ME.MBL.GEN.7150 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Mechanical | QP.E.ME.MBL.GEN.7180 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Electrical | QP.E.ME.MBL.GEN.7190 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Mechanical | QP.E.ME.MBL.GEN.7220 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical | QP.E.ME.MBL.GEN.7230 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1320 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1330 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1340 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1350 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ ICT Containment | QP.E.ME.MBL.GEN.1360 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1420 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1430 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1440 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1450 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1460 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1740 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1750 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1760 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1770 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1780 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1590 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1600 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1610 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1620 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.1630 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2040 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2050 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2060 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2070 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ ICT Containment | QP.E.ME.MBL.GEN.2080 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2240 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2250 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2260 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2270 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ ICT Containment | QP.E.ME.MBL.GEN.2280 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2440 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2450 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2460 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2470 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.2480 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2640 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2650 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2660 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2670 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2680 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2850 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2860 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2870 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2880 | Submittal | 28 | 2026-12-08 | 2027-01-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2890 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3070 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3080 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3090 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3100 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ ICT Containment | QP.E.ME.MBL.GEN.3110 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3290 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3300 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3310 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3320 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ ICT Containment | QP.E.ME.MBL.GEN.3330 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3500 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3510 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3520 | Submittal | 28 | 2026-12-23 | 2027-01-24
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3530 | Submittal | 28 | 2027-02-11 | 2027-03-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ ICT Containment | QP.E.ME.MBL.GEN.3540 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.MBL.GEN.5000 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.MBL.GEN.5040 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.MBL.GEN.5060 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.MBL.GEN.5080 | Submittal | 28 | 2027-03-07 | 2027-04-10
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.MBL.GEN.7280 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.MBL.GEN.7300 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.MBL.GEN.7320 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.MBL.GEN.7260 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.MBL.GEN.7340 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | LPG System | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ LPG System | QP.E.ME.MBL.GEN.5100 | Submittal | 21 | 2027-09-22 | 2027-10-17
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.MBL.GEN.7360 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Fire Suppression | QP.E.ME.CBR.GEN.1000 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Plumbing | Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Plumbing | QP.E.ME.CBR.GEN.1011 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ LPG System | QP.E.ME.CBR.GEN.1055 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.CBR.GEN.1022 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Electrical | QP.E.ME.CBR.GEN.1033 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ ELV (Low Current System) | QP.E.ME.CBR.GEN.1044 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.MBL.GEN.7380 | Submittal | 28 | 2027-12-09 | 2028-01-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Diesel | Diesel | Diesel | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Diesel | QP.E.ME.MBL.GEN.7420 | Submittal | 21 | 2028-02-01 | 2028-02-26
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Water Features | Water Features | Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Water Features | QP.E.ME.MBL.GEN.7440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M | QP.E.ME.MBL.GEN.6520 | Submittal | 28 | 2026-06-14 | 2026-07-15
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Grey Water Treatment/ Sewage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Grey Water Treatment/ Sewage | QP.E.ME.MBL.GEN.1050 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Stromwater/ Drainage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Stromwater/ Drainage | QP.E.ME.MBL.GEN.1060 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1040 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M | QP.E.ME.MBL.GEN.6540 | Submittal | 28 | 2026-07-16 | 2026-08-17
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ AHU Room | QP.E.ME.MBL.GEN.1160 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Transformer/ Switchgear/ Panel Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Transformer/ Switchgear/ Panel Room | QP.E.ME.MBL.GEN.1240 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Generator Room/ Diesel Tank | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Generator Room/ Diesel Tank | QP.E.ME.MBL.GEN.1250 | Submittal | 14 | 2026-10-05 | 2026-10-20
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | ETS/ CWP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ ETS/ CWP Room | QP.E.ME.MBL.GEN.1170 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1030 | Submittal | 14 | 2026-09-24 | 2026-10-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1290 | Submittal | 28 | 2026-09-01 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M | QP.E.ME.MBL.GEN.6560 | Submittal | 14 | 2026-08-18 | 2026-09-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1020 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Domestic Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Domestic Water | QP.E.ME.MBL.GEN.1010 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Fire Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Fire Water | QP.E.ME.MBL.GEN.1000 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1280 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 LOBBY LEVEL +905.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 LOBBY LEVEL +905.00M | QP.E.ME.MBL.GEN.6640 | Submittal | 21 | 2026-09-03 | 2026-09-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 UPEER LOBBY LEVEL MEZZANINE +909M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M | QP.E.ME.MBL.GEN.6660 | Submittal | 21 | 2026-09-29 | 2026-10-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L2 THEATRE STALLS +913M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L2 THEATRE STALLS +913M | QP.E.ME.MBL.GEN.6680 | Submittal | 21 | 2026-10-24 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | QP.E.ME.MBL.GEN.6700 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | QP.E.ME.MBL.GEN.6720 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 SECOND CIRCLE AND LOFT +928.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 SECOND CIRCLE AND LOFT +928.00M | QP.E.ME.MBL.GEN.6740 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M | QP.E.ME.MBL.GEN.5540 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - AHU Room | QP.E.ME.MBL.GEN.1180 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Makeup Air Unit and Ecology | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Makeup Air Unit and Ecology | QP.E.ME.MBL.GEN.1190 | Submittal | 14 | 2027-01-06 | 2027-01-21
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Sky Garden Irrigation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Sky Garden Irrigation | QP.E.ME.MBL.GEN.1070 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L6 SKY GARDEN +935.85M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L6 SKY GARDEN +935.85M | QP.E.ME.MBL.GEN.6760 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M | QP.E.ME.MBL.GEN.6580 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | Plant Room - Fan Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M ¦ Plant Room - Fan Room | QP.E.ME.MBL.GEN.6600 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Kitchen and Laundry | Kitchen and Laundry | Kitchen and Laundry | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Kitchen and Laundry | QP.E.ME.MBL.GEN.7400 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | MEP | Panels | Panels | Panels | Panels | Panels | Shop Drawings ¦ MEP ¦ Panels | QP.E.ME.MBL.GEN.6510 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Mechanical | QP.E.ME.BL1.GEN.3720 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical | QP.E.ME.BL1.GEN.3740 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL1.GEN.3760 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL1.GEN.3780 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Mechanical | QP.E.ME.BL1.GEN.3800 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical | QP.E.ME.BL1.GEN.3820 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1020 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1030 | Submittal | 21 | 2027-02-25 | 2027-03-23
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1040 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1050 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ ICT Containment | QP.E.ME.BL1.GEN.1060 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL1.GEN.2940 | Submittal | 21 | 2027-04-11 | 2027-05-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.2950 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.2960 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.2970 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL1.GEN.2980 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1510 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1520 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1530 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1540 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ ICT Containment | QP.E.ME.BL1.GEN.1550 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.BL1.GEN.3280 | Submittal | 21 | 2027-08-30 | 2027-09-22
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL1.GEN.3320 | Submittal | 21 | 2027-10-07 | 2027-10-31
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL1.GEN.3340 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL1.GEN.3360 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL1.GEN.3580 | Submittal | 21 | 2027-11-15 | 2027-12-08
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL1.GEN.3600 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL1.GEN.3620 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL1.GEN.3680 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL1.GEN.3640 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL1.GEN.3660 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3480 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL1.GEN.1000 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL1.GEN.3700 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3400 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical | QP.E.ME.BL2.GEN.3420 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL2.GEN.3440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL2.GEN.3460 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3480 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical | QP.E.ME.BL2.GEN.3500 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1020 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1030 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1040 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1050 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.1060 | Submittal | 21 | 2027-04-18 | 2027-05-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1910 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1920 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1930 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1940 | Submittal | 21 | 2027-04-29 | 2027-05-27
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL2.GEN.1950 | Submittal | 21 | 2027-05-12 | 2027-06-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.2110 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.2120 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.2130 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.2140 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.2150 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL2.GEN.3160 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL2.GEN.3200 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL2.GEN.3220 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL2.GEN.3240 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL2.GEN.3260 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL2.GEN.3280 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL2.GEN.3300 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL2.GEN.3380 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL2.GEN.3320 | Submittal | 28 | 2027-11-22 | 2027-12-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL2.GEN.3340 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3500 | Submittal | 14 | 2028-02-17 | 2028-03-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL2.GEN.1000 | Submittal | 16 | 2028-02-17 | 2028-03-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL2.GEN.3360 | Submittal | 14 | 2028-04-09 | 2028-04-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Mechanical | QP.E.ME.BL3.GEN.3640 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical | QP.E.ME.BL3.GEN.3660 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical | QP.E.ME.BL3.GEN.3700 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Mechanical | QP.E.ME.BL3.GEN.3680 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1020 | Submittal | 21 | 2026-06-17 | 2026-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.1030 | Submittal | 21 | 2026-07-12 | 2026-08-04
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1040 | Submittal | 21 | 2026-08-05 | 2026-08-29
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1050 | Submittal | 21 | 2026-08-30 | 2026-09-22
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ ICT Containment | QP.E.ME.BL3.GEN.1060 | Submittal | 21 | 2026-10-07 | 2026-10-31
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1790 | Submittal | 21 | 2026-12-31 | 2027-01-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.3280 | Submittal | 21 | 2027-01-25 | 2027-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1810 | Submittal | 21 | 2027-02-18 | 2027-03-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1820 | Submittal | 21 | 2027-03-18 | 2027-04-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ ICT Containment | QP.E.ME.BL3.GEN.1830 | Submittal | 21 | 2027-04-12 | 2027-05-05
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL3.GEN.3400 | Submittal | 21 | 2027-06-23 | 2027-07-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL3.GEN.3440 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL3.GEN.3460 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL3.GEN.3480 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL3.GEN.3500 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL3.GEN.3540 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL3.GEN.3560 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL3.GEN.3620 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL3.GEN.3600 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL3.GEN.3580 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3520 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL3.GEN.1000 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL3.GEN.3520 | Submittal | 14 | 2028-04-04 | 2028-04-19
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Mechanical | QP.E.ME.BL4.GEN.6010 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical | QP.E.ME.BL4.GEN.6030 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Mechanical | QP.E.ME.BL4.GEN.6050 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Electrical | QP.E.ME.BL4.GEN.6070 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Mechanical | QP.E.ME.BL4.GEN.6090 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical | QP.E.ME.BL4.GEN.6110 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Fire Suppression | QP.E.ME.BL4.GEN.2110 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2120 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2130 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2140 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ ICT Containment | QP.E.ME.BL4.GEN.2150 | Submittal | 21 | 2026-11-01 | 2026-11-24
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2910 | Submittal | 21 | 2026-12-05 | 2026-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.5550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2930 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2940 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ ICT Containment | QP.E.ME.BL4.GEN.2950 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2810 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2820 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2830 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2840 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ ICT Containment | QP.E.ME.BL4.GEN.2850 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL4.GEN.5770 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL4.GEN.5810 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL4.GEN.5830 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL4.GEN.5850 | Submittal | 21 | 2027-09-29 | 2027-10-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL4.GEN.5870 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL4.GEN.5930 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL4.GEN.5950 | Submittal | 21 | 2027-12-05 | 2027-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL4.GEN.5890 | Submittal | 21 | 2028-01-12 | 2028-02-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL4.GEN.5970 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL4.GEN.5990 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3540 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL4.GEN.3110 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL4.GEN.5910 | Submittal | 14 | 2028-04-02 | 2028-04-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Mechanical | QP.E.ME.BL5.GEN.3040 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical | QP.E.ME.BL5.GEN.3060 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL5.GEN.3080 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL5.GEN.3100 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Mechanical | QP.E.ME.BL5.GEN.3120 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical | QP.E.ME.BL5.GEN.3140 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1020 | Submittal | 21 | 2026-10-29 | 2026-11-22
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1030 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1040 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1050 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ ICT Containment | QP.E.ME.BL5.GEN.1060 | Submittal | 21 | 2026-11-25 | 2026-12-19
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1560 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1570 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1580 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL5.GEN.1590 | Submittal | 21 | 2027-04-10 | 2027-05-03
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1750 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1760 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1770 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1780 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ ICT Containment | QP.E.ME.BL5.GEN.1790 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL5.GEN.2800 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL5.GEN.2840 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL5.GEN.2860 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL5.GEN.2880 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL5.GEN.3020 | Submittal | 14 | 2027-10-24 | 2027-11-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL5.GEN.2900 | Submittal | 14 | 2027-12-01 | 2027-12-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL5.GEN.2920 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL5.GEN.3000 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL5.GEN.2940 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL5.GEN.2960 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3560 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL5.GEN.1000 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL5.GEN.2980 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Mechanical | QP.E.ME.PAR.GEN.1459 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Electrical | QP.E.ME.PAR.GEN.1479 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Mechanical | QP.E.ME.PAR.GEN.1499 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Electrical | QP.E.ME.PAR.GEN.1519 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Fire Suppression | QP.E.ME.PAR.GEN.1000 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1011 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1022 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1033 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ ICT Containment | QP.E.ME.PAR.GEN.1044 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Fire Suppression | QP.E.ME.PAR.GEN.1055 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1066 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1077 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1088 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ ICT Containment | QP.E.ME.PAR.GEN.1099 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.PAR.GEN.1219 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.PAR.GEN.1259 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.PAR.GEN.1279 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.PAR.GEN.1299 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.PAR.GEN.1419 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.PAR.GEN.1319 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.PAR.GEN.1339 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.PAR.GEN.1439 | Submittal | 14 | 2028-02-07 | 2028-02-23
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.PAR.GEN.1359 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.PAR.GEN.1379 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.PAR.GEN.1399 | Submittal | 14 | 2028-03-09 | 2028-03-25
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3600 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3610 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3620 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.4430 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4440 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.4450 | Submittal | 14 | 2027-12-18 | 2028-01-02
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3960 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3970 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3980 | Submittal | 14 | 2028-01-01 | 2028-01-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Fire Suppression | QP.E.ME.MBL.GEN.3930 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3940 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Electrical | QP.E.ME.MBL.GEN.3950 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Fire Suppression | QP.E.ME.MBL.GEN.3810 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3820 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Electrical | QP.E.ME.MBL.GEN.3830 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4400 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4410 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4420 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4340 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4350 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4360 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4520 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4530 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4540 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4640 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4650 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4660 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3870 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3880 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3890 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3840 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3850 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3860 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.4550 | Submittal | 21 | 2028-02-08 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4560 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.4570 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 3, 4 & 5 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 3, 4 & 5 | QP.E.FA.GEN.GEN.1460 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 1 & 2 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 1 & 2 | QP.E.FA.GEN.GEN.2180 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Loft and Lobby | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Loft and Lobby | QP.E.FA.GEN.GEN.2140 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | QP.E.FA.GEN.GEN.2160 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Blades | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Blades | QP.E.FA.GEN.GEN.1820 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Lobby and Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Lobby and Loft | QP.E.FA.GEN.GEN.1770 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Above Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Above Loft | QP.E.FA.GEN.GEN.1780 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Blades | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Blades | QP.E.FA.GEN.GEN.1890 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Main Building | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Main Building | QP.E.FA.GEN.GEN.2230 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Facade | Facade | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 1 | QP.E.FA.GEN.GEN.1920 | Submittal | 28 | 2026-09-29 | 2026-10-31
Shop Drawings | Facade | Facade | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 2 | QP.E.FA.GEN.GEN.1930 | Submittal | 28 | 2026-08-26 | 2026-09-28
Shop Drawings | Facade | Facade | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 3 | QP.E.FA.GEN.GEN.1940 | Submittal | 28 | 2026-05-17 | 2026-06-21
Shop Drawings | Facade | Facade | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 4 | QP.E.FA.GEN.GEN.1950 | Submittal | 28 | 2026-06-22 | 2026-07-23
Shop Drawings | Facade | Facade | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 5 | QP.E.FA.GEN.GEN.1960 | Submittal | 28 | 2026-07-25 | 2026-08-25
Shop Drawings | Facade | Facade | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Facade ¦ Amphitheatre | QP.E.FA.GEN.GEN.2240 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Lobby | Lobby | Lobby | Lobby | Shop Drawings ¦ Facade ¦ Lobby | QP.E.FA.GEN.GEN.2090 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | Loft | Loft | Loft | Loft | Shop Drawings ¦ Facade ¦ Loft | QP.E.FA.GEN.GEN.2100 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Above Loft | Above Loft | Above Loft | Above Loft | Shop Drawings ¦ Facade ¦ Above Loft | QP.E.FA.GEN.GEN.1910 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | Link Bridges | Link Bridges | Link Bridges | Link Bridges | Shop Drawings ¦ Facade ¦ Link Bridges | QP.E.FA.GEN.GEN.2050 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Facade | Facade | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Shop Drawings ¦ Facade ¦ Facade Lighting Fixtures | QP.E.FA.GEN.GEN.1450 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | GRC Cladding | GRC Cladding | GRC Cladding | GRC Cladding | Shop Drawings ¦ Facade ¦ GRC Cladding | QP.E.FA.GEN.GEN.1390 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 1 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 1 | QP.E.CV.MBL.GEN.3060 | Submittal | 28 | 2026-08-06 | 2026-09-07
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 2 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 2 | QP.E.CV.MBL.GEN.3560 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 3 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 3 | QP.E.CV.MBL.GEN.3580 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 4 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 4 | QP.E.CV.MBL.GEN.3600 | Submittal | 28 | 2027-01-03 | 2027-02-03
Shop Drawings | External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Shop Drawings ¦ External Works ¦ Waterproofing for External Works | QP.E.EX.GEN.GEN.1040 | Submittal | 28 | 2026-06-25 | 2026-07-27
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Excavation | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Excavation | QP.E.CV.MBL.GEN.3320 | Submittal | 28 | 2027-01-06 | 2027-02-07
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Blinding Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Blinding Including Embedded Items | QP.E.CV.MBL.GEN.3500 | Submittal | 28 | 2027-02-23 | 2027-03-29
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Foundation Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Foundation Including Embedded Items | QP.E.CV.MBL.GEN.3480 | Submittal | 28 | 2027-04-13 | 2027-05-19
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Structural Concrete Works Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Structural Concrete Works Including Embedded Items | QP.E.CV.MBL.GEN.3520 | Submittal | 28 | 2027-06-03 | 2027-07-05
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4000 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Finishing | Finishing | Finishing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Finishing | QP.E.AF.MBL.GEN.4030 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4010 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Doors / Openings | QP.E.AF.MBL.GEN.4020 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Fire Suppression | QP.E.ME.MBL.GEN.1690 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Plumbing | Plumbing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Plumbing | QP.E.ME.MBL.GEN.1700 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.1710 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Electrical | Electrical | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Electrical | QP.E.ME.MBL.GEN.1720 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ ELV (Low Current System) | QP.E.ME.MBL.GEN.1730 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | External Utilities | Irrigation Works | Irrigation Works | Irrigation Works | Irrigation Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ Irrigation Works | QP.E.EX.GEN.GEN.1090 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Drainage Works | External Drainage Works | External Drainage Works | External Drainage Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Drainage Works | QP.E.EX.GEN.GEN.1110 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Lighting Works | External Lighting Works | External Lighting Works | External Lighting Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Lighting Works | QP.E.EX.GEN.GEN.1170 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | External Utilities | Low Current | Low Current | Low Current | Low Current | Shop Drawings ¦ External Works ¦ External Utilities ¦ Low Current | QP.E.EX.GEN.GEN.1100 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Shop Drawings ¦ External Works ¦ Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 | Submittal | 14 | 2027-08-07 | 2027-08-22
Shop Drawings | External Works | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Shop Drawings ¦ External Works ¦ Water and Environment | QP.E.EX.GEN.GEN.1220 | Submittal | 21 | 2026-11-23 | 2026-12-16
Shop Drawings | External Works | External Fixtures | External Fixtures | External Fixtures | External Fixtures | External Fixtures | Shop Drawings ¦ External Works ¦ External Fixtures | QP.E.EX.GEN.GEN.1260 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | External Works | LPG System | LPG System | LPG System | LPG System | LPG System | Shop Drawings ¦ External Works ¦ LPG System | QP.E.EX.GEN.GEN.1300 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Fit-out | Fit-out | Fit-out | Fit-out | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Fit-out | QP.C.PS.GEN.GEN.2590 | Submittal | 110 | 2026-07-30 | 2026-12-06
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Stage Engineering | Stage Engineering | Stage Engineering | Stage Engineering | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Stage Engineering | QP.C.PS.GEN.GEN.2560 | Submittal | 110 | 2026-12-07 | 2027-04-17
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | AV / Broadcast | AV / Broadcast | AV / Broadcast | AV / Broadcast | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ AV / Broadcast | QP.C.PS.GEN.GEN.1200 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ Technology (ICT) | QP.C.PS.GEN.GEN.1810 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Control Systems | Control Systems | Control Systems | Control Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Control Systems | QP.C.PS.GEN.GEN.1880 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Lighting Systems | Lighting Systems | Lighting Systems | Lighting Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Lighting Systems | QP.C.PS.GEN.GEN.1850 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Conveying System Finishes | QP.C.PS.GEN.GEN.2120 | Submittal | 150 | 2027-06-07 | 2027-11-29
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | HVAC System | HVAC System | HVAC System | HVAC System | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ HVAC System | QP.C.PS.GEN.GEN.2100 | Submittal | 90 | 2027-11-01 | 2028-02-13
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | ID Finishes | ID Finishes | ID Finishes | ID Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ ID Finishes | QP.C.PS.GEN.GEN.1930 | Submittal | 90 | 2027-07-18 | 2027-10-31
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Water Features | QP.C.PS.GEN.GEN.1960 | Submittal | 120 | 2027-02-16 | 2027-07-13
Shop Drawings | Provisional Sums | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | Shop Drawings ¦ Provisional Sums ¦ PS5 - Signage and Wayfinding | QP.C.PS.GEN.GEN.2140 | Submittal | 60 | 2028-07-29 | 2028-10-07
Shop Drawings | Provisional Sums | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | Shop Drawings ¦ Provisional Sums ¦ PS6 - Soft Landscaping | QP.C.PS.GEN.GEN.2180 | Submittal | 160 | 2027-08-30 | 2028-03-08
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Concrete Superstructure | QP.C.PS.GEN.GEN.2360 | Submittal | 30 | 2028-06-08 | 2028-07-12
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Foundation | Foundation | Foundation | Foundation | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Foundation | QP.C.PS.GEN.GEN.2260 | Submittal | 30 | 2028-05-01 | 2028-06-07
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Landscape | Landscape | Landscape | Landscape | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Landscape | QP.C.PS.GEN.GEN.2320 | Submittal | 30 | 2028-07-31 | 2028-09-03
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Promenade Bridge MEP | QP.C.PS.GEN.GEN.2340 | Submittal | 30 | 2028-06-26 | 2028-07-30
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Technology (ICT) | QP.C.PS.GEN.GEN.2400 | Submittal | 150 | 2027-04-11 | 2027-10-07
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Traffic & Car Parking | QP.C.PS.GEN.GEN.2500 | Submittal | 150 | 2027-07-12 | 2028-01-03

## Picklists
| #VALUE! |  | Numbering System Document - Metadata Mapping
DOCUMENT NUMBERING DROPDOWN ATTRIBUTES | [18 empty] | QIC GENERAL DROPDOWN ATTRIBUTES
FIELD 01 - PROJECT CODE |  | FIELD 02 - ORIGINATOR |  | FIELD 03 - CONTRACT REFERENCE |  | FIELD 04 - DOCUMENT TYPES |  | FIELD 05 - DISCIPLINE |  | FIELD 06 - AREA/ZONE |  | FIELD 07 - VENUE/BUILDING |  | FIELD 08 - SERIAL NUMBER |  |  |  |  | DOCUMENT DETAILS |  |  | SUITABILITY STATUS |  | NAP GENERAL DROPDOWN ATTRIBUTES
Ab. 01 | 1 - Project Name | Ab. 02 | 2 - Originator Name | Ab. 03 | 3 - Contract Reference | Ab. 04 | 4 - Document Type | Ab. 05 | 5 - Discipline | Ab. 06 | 6 - Area/Zone | Ab. 07 | 7 - Venue/Building | Ab. 08A | 8A - Drawing Type | Ab. 08B | 8B - Level | 8C - Sequence Number | Authoring Software | File/Exchange Format | Scope Area | Code | Status | Scale | Classification ID | Classification | Corporate Discipline | Author
QF01012 | Qiddaya Performing Arts Center | NES | Nesma and Partners | C04518 | Contract Number | AGD | Agenda | ACO | Acoustic | 00 | Overall | Z00000 | Overall | 0 | General (General Notes, Abbreviations, Legends, Single Line Diagrams, General Detail) | 00 | Non-Specific ( For Blade ) | 4 Digit Sequence Number For Drawings/Models | Revit | .rvt | Design Management | S0 (WIP) | Initial status or WIP | NTS | FI_60_25 | Drawing | Architectural | Nesma & Partners
[6 empty] | AVV | Agreed Value of Variation | ADM | Administration | 01 | Zone Sheet 1 | CENT01 | Center Block | 1 | Elevations (Vertical View) | B1 | Basement 1 - Parking A +900.50 | 3 Digit Sequence Number For Documents | Civil3D | .nwc | Architecture / LDC | S1 (Shared) | Suitable for Coordination | AS INDICATED | FI_90_75 | Schedule or table | Electrical | GINGGONG
[6 empty] | ASB | As Built | ARC | Architectural | 02 | Zone Sheet 2 | GARD01 | Guard House | 2 | Plans (Overall, Horizontal View, Floor Plan, Ceiling Plan, Site Plan, Loading Plan) | B2 | Basement 2 - Service +893.50 |  | MicrosoftWord | .nwd | Landscape | S2 (Shared) | Suitable for Information | 1:1 | FI_60_53 | Model | Façade | ALUTEC
[6 empty] | AUR | Audit Report | ADT | Area Development | 03 | Zone Sheet 3 | BLAD01 | Blade 01 | 3 | Sections (Sectional View, Wall Section, Riser) | B3 | Basement 3 - Promenade +887.750 |  | MicrosoftExcel | .ifc | Interior Design | S3 (Shared) | Suitable for Review and Comment | 1:2 | FI_60_15 | Clash Rendition | Fire & Life Safety | AFCO
[6 empty] | BOQ | Bill of Quantities | ASM | Assets Management | 04 | Zone Sheet 4 | BLAD02 | Blade 02 | 4 | Large-scale Views (Enlarged Details) (Plans, Elevations, Stair Sections, etc) | FL | Foundation level |  | Navisworks | .pdf | Signage & Wayfinding | S4 (Shared) | Suitable for Review and Authorisation | 1:5 | FI_40_10 | Calculations | Interior Design | DOKA
[6 empty] | BEP | BIM Execution Plan | AVL | Audio Visual | 05 | Zone Sheet 5 | BLAD03 | Blade 03 | 5 | Details (Any detail view, such as Wall / Floor / Manhole Detail, etc) | L1 | Lobby Level +905.0 |  | inDesign | .jpg | Public Interaction & Activation | S5 (Shared) | Suitable for Review and Acceptance | 1:10 | FI_90_72 | Report | Infrastructure | RAWABI
[6 empty] | BIM | BIM Model | AUV | Audio/Video | 06 | Zone Sheet 6 | BLAD04 | Blade 04 | 6 | Schedules and Diagrams | L2 | Theater Stalls +913.0 |  | Inviso | .xls | Structure | A1 (Published) | Authorised and Accepted-Concept Design | 1:20 | FI_10_90 | Transmittal | Landscape | Subcontractor - Façade Lighting
[6 empty] | BRF | Brief | BRG | Bridges | 07 | Zone Sheet 7 | BLAD05 | Blade 05 | 7 | Combination of different views | L3 | Stalles Mezz & AD Theater +917.5 |  | JPG | .xer | Geotechnical Engineering | A2 (Published) | Authorised and Accepted-Schematic Design 100% | 1:25 | FI_90_47 | Log | Mechanical | Subcontractor - AR / Vertical Transportation
[6 empty] | BUD | Budget | BRC | Broadcast | 08 | Zone Sheet 8 | MBLAD1 | Mini Blade 01 | 8 | User-Defined (For types that do not fall in other categories) | L4 | First Circle & AD Theater +921.0 |  | Recap | .dwf | Civil Engineering | A3 (Published) | Authorised and Accepted-Detailed Design 100% | 1:50 | FI_80_50 | Method statement | Structural | Subcontractor - Unassigned
[6 empty] | CAL | Calculation | BIM | Building Information Modelling | 09 | Zone Sheet 9 | MBLAD4 | Mini Blade 04 | 9 | 3D Representation (Isometric, Perspectives, Photographes) | L5 | Second Circle & Loft |  | Rhino | .dwg | MEP Engineering | A4 (Published) | Authorised and Accepted-Tender | 1:100 | FI_90_64 | Plan |  | Provisional Sum
[6 empty] | CER | Certificate | BMS | Building Management System | 10 | Zone Sheet 10 | SECE001 | SEC Room |  |  | L6 | SKY Garden +935.85 |  | Sketchup | .bcf | Fire & Life Safety | A5 (Published) | Authorised and Accepted-IFC | 1:150
[6 empty] | COR | Change Order | CWC | Chilled Water / Cooling | 11 | Zone Sheet 11 | PARK01 | Parking Building |  |  | L8 | Royal Majlis +948.10M |  | Autocad | .3ds | Pitch Design & Sports Playing Surfaces | A6 (Published) | Authorised and Accepted-Construction (Shop Drawing) | 1:200
[6 empty] | CRA | Change Request Authorization | CIV | Civil | 12 | Zone Sheet 12 |  |  |  |  | M1 | Mez Upper Lobby +909.0 |  | ArcGIS | .skp | Specialist Lighting (Services and Systems) | A7 (Published) | Authorised and Accepted-As Built | 1:250
[6 empty] | CDT | Clash Detection Report | CPM | Contracts & Procurement | 13 | Zone Sheet 13 |  |  |  |  | M2 | Mez Loft MEP +931.10 |  |  | .docx | Acoustics | A8(Published) | Authorised and Accepted-In Use | 1:300
[6 empty] | CLM | Claim | CIN | Controls & Instrumentation | 14 | Zone Sheet 14 |  |  |  |  | RL | Roof Level |  |  | .rvt,.nwd,.ifc | AV / Broadcast |  |  | 1:350
[6 empty] | CIN | Client Instruction | CRE | Creative Designer | 15 | Zone Sheet 15 |  |  |  |  | ZZ | Overall |  |  | .nwc,.nwd,.ifc | Security |  |  | 1:500
[6 empty] | CRS | Comments Resolution Sheet | CDM | Crowd Management | 16 | Zone Sheet 16 | [8 empty] | .dwg,.nwc,.ifc | Vertical Transport
[6 empty] | CON | Contract | CUL | Culvert | 17 | Zone Sheet 17 | [8 empty] | .docx,.pdf | Facade & Roof Envelope
[6 empty] | COS | Cost Estimate | DRN | Drainage | 18 | Zone Sheet 18 | [8 empty] | .xer,.pdf | Crowd Modelling / Pedestrian Flow
[6 empty] | DAB | Dashboard | ELP | Earthing & Lighting Protection | 19 | Zone Sheet 19 | [8 empty] | .xls,.pdf | Sustainability
[6 empty] | DOA | Delegation of Authority | ELE | Electrical | 20 | Zone Sheet 20 | [8 empty] | .msp,.pdf | Accessibility
[6 empty] | DES | Design | ELC | Electrical Containment | 21 | Zone Sheet 21 | [8 empty] | .dwg,.pdf | Architect of Record
[6 empty] | MTX | Distribution Matrix | ENV | Environmental | 22 | Zone Sheet 22 | [8 empty] | .indd | Food & Beverage & Operations
[6 empty] | DSS | Dossier | EQP | Equipment | 23 | Zone Sheet 23 | [8 empty] | .pdf, .indd | Utilities, Roads & Infrastructure
[6 empty] | DRW | Drawing | FAC | Facade | 24 | Zone Sheet 24 | [8 empty] | .rvt,.nwc,.ifc | Traffic & Car Parking
[6 empty] | ENI | Engineer Instruction | FED | Federated | 25 | Zone Sheet 25 | [8 empty] | .gdb | Technology (ICT)
[6 empty] | EXP | Expenses | FIN | Finance | 26 | Zone Sheet 26 | [9 empty] | Sports & Specialist Lighting
[6 empty] | HOC | Handover Certificate | FAE | Fire Alarm & Emergency Lighting | 27 | Zone Sheet 27 | [9 empty] | BMS & Access Control
[6 empty] | IRT | Incident Report | FLS | Fire Life Safety | 28 | Zone Sheet 28 | [9 empty] | Waste Management
[6 empty] | ITP | Inspection & Test Plan | FPR | Fire Protection | [11 empty] | Health & Safety in Design
[6 empty] | INS | Instruction | FFE | Furniture Fixture & Equipment | [11 empty] | Wind
[6 empty] | IAB | Insurance and Bonds | GEN | General
[6 empty] | INV | Invoice | GIS | Geospatial Information System
[6 empty] | LAR | Laydown Area Access Request | GEH | Geotechnical & Hydraulics
[6 empty] | LTR | Letter | GRA | Graphics
[6 empty] | LIC | License | HSE | Health and Safety
[6 empty] | LST | List | EHV | High Voltage
[6 empty] | MAN | Manual | HVC | HVAC
[6 empty] | MPL | Master Plan | ICT | Information & Communication Technology
[6 empty] | MAR | Material Approval Request | INF | Infrastructure
[6 empty] | MIR | Material Inspection Request | INS | Installation
[6 empty] | MST | Method Statement | ITS | Intelligent Transportation System
[6 empty] | MOM | Minutes of Meeting | INT | Interior Design
[6 empty] | MIX | Mix Design | IRR | Irrigation
[6 empty] | MOD | Model | KNL | Kitchen & Laundry
[6 empty] | MRP | Monthly Report | LSE | Landscape
[6 empty] | NOC | No Objection Certificate | ELL | Lighting
[6 empty] | NCR | Non-Conformance Report | LTC | Lighting Control
[6 empty] | NDA | Non-Disclosure Agreement | ELV | Low Voltage
[6 empty] | NTC | Notice | LPG | LPG
[6 empty] | OMM | Operation & Maintenance Manual | MAR | Marine Engineering
[6 empty] | ORC | Organizational Chart | MPL | Master Planning
[6 empty] | OTR | Overtime Request | MEC | Mechanical
[6 empty] | PAP | Payment Application | EMV | Medium Voltage
[6 empty] | PYC | Payment Certificate | MEP | MEPF
[6 empty] | PRM | Permit | NTD | Non-Technical Document
[6 empty] | PAF | Personnel Approval Form | OSE | Operating Supplies and Equipment
[6 empty] | PIV | Photographs, Images & Videos | OTH | Others
[6 empty] | PLN | Plan | PLB | Plumbing
[6 empty] | PLT | Plant | PTW | Potable Water
[6 empty] | PPG | Policy & Procedure | PJC | Project Control
[6 empty] | PQS | Prequalification Submittal | QMS | Quality Management
[6 empty] | PRE | Presentation | RID | Rides
[6 empty] | PRO | Procedure | ERL | Road Lighting
[6 empty] | PEP | Project Execution Plan | RKW | Rockwork
[6 empty] | PRS | Proposal | SEC | Security System
[6 empty] | POR | Purchase Order | SEW | Sewage
[6 empty] | REG | Register | SHW | Show
[6 empty] | REP | Report | SGN | Signage / Wayfinding
[6 empty] | RFC | Request For Change | ESP | Small Power
[6 empty] | RSM | Resume | SSC | Smart City
[6 empty] | SVR | Safety Violation Report | SPL | Specialist Lighting
[6 empty] | SMP | Sample | SWD | Storm Water Drainage
[6 empty] | SCH | Schedule | STR | Structural
[6 empty] | SDW | Shop Drawing | SUR | Surveying / Mapping
[6 empty] | SIN | Site Instruction | SUS | Sustainability
[6 empty] | SOR | Site Observation Report | TEL | Telecommunication
[6 empty] | SPE | Specification | TNC | Testing/Commissioning
[6 empty] | STD | Standard | TFC | Traffic System
[6 empty] | SFA | Statement of Final Account | UTI | Utilities
[6 empty] | STR | Strategy | VNT | Ventilation Ductwork
[6 empty] | TOC | Taking Over Certificate | VTR | Vertical Transportation
[6 empty] | TOR | Task Order | VES | Voice Evacuation
[6 empty] | TEM | Template | WSM | Waste Management
[6 empty] | TDC | Tender Document | WTR | Water
[6 empty] | TRP | Test Report | CTV | CCTV System
[6 empty] | TMS | Time Sheet | ACS | Access Control System
[6 empty] | VOR | Variation Order | EFL | Facade Lighting
[6 empty] | WAR | Warranty / Guarantees | DES | Diesel
[6 empty] | WRP | Weekly Report | SMK | Smoke Ductwork
[6 empty] | WIR | Work Inspection Request | STL | Steel Structure
[6 empty] | RLM | RedLine Mark Drawing | FWR | Formwork
[6 empty] | MDP | Master Information Delivery Plan | ELS | Emergency Lighting system
[6 empty] | TDP | Task Information Delivery Plan | EBW | Electrical Builder Works
[8 empty] | MBW | Mechanical Builder Works
[8 empty] | EBC | Electrical Busway