## TIDP_Sheet
TASK INFORMATION DELIVERY PLAN (TIDP)
CLIENT | Qiddiya | #VALUE!
PROJECT | Qiddiya Performing Arts Center (QPAC)
ORGANISATION | Nesma & Partners
DISCIPLINE | Interior Design
APPROVER | BSBG
DATE CREATED
DATE LAST UPDATED
REVISION NUMBER | 00
DOCUMENT REFERENCE | QF01012-NES-C04518-TDP-XXX-00-000000-000001
This document shall be populated and kept up-to-date by the task team | [10 empty] | REFER TO THE FILE NAMING CONVENTION IN THE BIM EXECUTION PLAN | [10 empty] | DATA EXCHANGE #01 | [5 empty] | DATA EXCHANGE #02
[11 empty] | DOC REFERENCE GENERATOR | [10 empty] | STAGE: | CONSTRUCTION |  |  |  |  | STAGE: | HAND OVER
[22 empty] | PROGRAMME REF: | [5 empty] | PROGRAMME REF:
[5 empty] | EXCHANGE FORMATS | [5 empty] | FIELD 01 | FIELD 02 | FIELD 03 | FIELD 04 | FIELD 05 | FIELD 06 | FIELD 07 | FIELD 08 |  |  |  |  | LEVEL OF INFORMATION NEED | [5 empty] | LEVEL OF INFORMATION NEED
DOCUMENT NUMBER | DOCUMENT TITLE | EXTRACTED FROM MODEL | SCOPE AREA | AUTHORING SOFTWARE | EXCHANGE FORMAT | SCALE | DELIVERY MILESTONE | PACKAGE NAME | ACTIVITY ID | CLASSIFICATION CODE | PROJECT | ORIGINATOR | CONTRACT | DOCUMENT TYPE | DISCIPLINE | AREA/ZONE | VENUE/BUILDING | DRAWING TYPE | LEVEL | SEQUENCE NUMBER | CORPORATE DISCIPLINE | 01-AUTHOR | 01-GEOMETRICAL | 01-NON GEOMETRICAL | 01-DURATION (DAYS) | 01-PREDECESSOR | 01-EXCHANGE DATE | 02-AUTHOR | 02-GEOMETRICAL | 02-NON GEOMETRICAL | 02-DURATION (DAYS) | 02-PREDECESSOR | 02-EXCHANGE DATE
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4934 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4934 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4935 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4935 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4936 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4936 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4937 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4937 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4938 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4938 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4939 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4939 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4940 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4940 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4941 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4941 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4942 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4942 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4943 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4943 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4944 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4944 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4945 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4945 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4946 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4946 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4947 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4947 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4948 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4948 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4949 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4949 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4950 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4950 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4951 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4951 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4952 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4952 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4953 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4953 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4954 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4954 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4955 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4955 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4956 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4956 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4957 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4957 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4958 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4958 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4959 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4959 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4960 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4960 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4961 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4961 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4962 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4962 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4963 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4963 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4964 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4964 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4965 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4965 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4966 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4966 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4967 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4967 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4968 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4968 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4969 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4969 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4970 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4970 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4971 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4971 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4972 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4972 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4973 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4973 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4974 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4974 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4975 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4975 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4976 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4976 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4977 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4977 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4978 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4978 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4979 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4979 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4980 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4980 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4981 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4981 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4982 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4982 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4983 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4983 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4984 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4984 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4985 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4985 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4986 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4986 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4987 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4987 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4988 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4988 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4989 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4989 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4990 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4990 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4991 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4991 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4992 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4992 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4993 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4993 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4994 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4994 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4995 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4995 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4996 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4996 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4997 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4997 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4998 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4998 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ4999 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 4999 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5000 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5000 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5001 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5001 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5002 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5002 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5003 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5003 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5004 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5004 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5005 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5005 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5006 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5006 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5007 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5007 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5008 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5008 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5009 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5009 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5010 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5010 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5011 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5011 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5012 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5012 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5013 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5013 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5014 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5014 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5015 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5015 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5016 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5016 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5017 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5017 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5018 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5018 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5019 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5019 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5020 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5020 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5021 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5021 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5022 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5022 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5023 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5023 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5024 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5024 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5025 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5025 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5026 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5026 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5027 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5027 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5028 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5028 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5029 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5029 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5030 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5030 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5031 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5031 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5032 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5032 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5033 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5033 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5034 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5034 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5035 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5035 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5036 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5036 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5037 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5037 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5038 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5038 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5039 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5039 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5040 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5040 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5041 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5041 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5042 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5042 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5043 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5043 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5044 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5044 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5045 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5045 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5046 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5046 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5047 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5047 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5048 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5048 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5049 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5049 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5050 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5050 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5051 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5051 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5052 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5052 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5053 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5053 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5054 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5054 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5055 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5055 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5056 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5056 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5057 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5057 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5058 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5058 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5059 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5059 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5060 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5060 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5061 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5061 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5062 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5062 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5063 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5063 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5064 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5064 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5065 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5065 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5066 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5066 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5067 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5067 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5068 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5068 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5069 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5069 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5070 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5070 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5071 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5071 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5072 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5072 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5073 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5073 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5074 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5074 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5075 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5075 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5076 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5076 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5077 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5077 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5078 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5078 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5079 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5079 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5080 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5080 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5081 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5081 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5082 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5082 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5083 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5083 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5084 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5084 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5085 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5085 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5086 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5086 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5087 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5087 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5088 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5088 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5089 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5089 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5090 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5090 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5091 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5091 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5092 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5092 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5093 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5093 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5094 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5094 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5095 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5095 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5096 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5096 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5097 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5097 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5098 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5098 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5099 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5099 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5100 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5100 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5101 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5101 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5102 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5102 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5103 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5103 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5104 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5104 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5105 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5105 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5106 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5106 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5107 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5107 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5108 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5108 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5109 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5109 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5110 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5110 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5111 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5111 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5112 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5112 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5113 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5113 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5114 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5114 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5115 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5115 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5116 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5116 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5117 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5117 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5118 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5118 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5119 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5119 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5120 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5120 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5121 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5121 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5122 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5122 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5123 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5123 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5124 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5124 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5125 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5125 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5126 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5126 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5127 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5127 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5128 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5128 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5129 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5129 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5130 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5130 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5131 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5131 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5132 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5132 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5133 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5133 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5134 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5134 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5135 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5135 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5136 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5136 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5137 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5137 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5138 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5138 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5139 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5139 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5140 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5140 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5141 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5141 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5142 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5142 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5143 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5143 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5144 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5144 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5145 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5145 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5146 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5146 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5147 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5147 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5148 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5148 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5149 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5149 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5150 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5150 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5151 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5151 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5152 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5152 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5153 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5153 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5154 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5154 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5155 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5155 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5156 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5156 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5157 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5157 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5158 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5158 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5159 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5159 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5160 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5160 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5161 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5161 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5162 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5162 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5163 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5163 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5164 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5164 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5165 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5165 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5166 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5166 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5167 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5167 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5168 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5168 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5169 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5169 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5170 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5170 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5171 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5171 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5172 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5172 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5173 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5173 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5174 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5174 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5175 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5175 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5176 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5176 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6196 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6196 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6197 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6197 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6198 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6198 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6199 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6199 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6200 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6200 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6201 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6201 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6202 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6202 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6203 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6203 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6204 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6204 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6205 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6205 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6206 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6206 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6207 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6207 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6208 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6208 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6209 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6209 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6210 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6210 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6211 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6211 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6212 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6212 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6213 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6213 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6214 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6214 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6215 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6215 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6216 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6216 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6217 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6217 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6218 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6218 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6219 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6219 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6220 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6220 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6221 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6221 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6222 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6222 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6223 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6223 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6224 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6224 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6225 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6225 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6226 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6226 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6227 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6227 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6228 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6228 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6229 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6229 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6230 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6230 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6231 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6231 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6232 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6232 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6233 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6233 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6234 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6234 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6235 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6235 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6236 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6236 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6237 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6237 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6238 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6238 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6239 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6239 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6240 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6240 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6241 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6241 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6242 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6242 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6243 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6243 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6244 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6244 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6245 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6245 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6246 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6246 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6247 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6247 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6248 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6248 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6249 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6249 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6250 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6250 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6251 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6251 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6252 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6252 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6253 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6253 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6254 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6254 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6255 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6255 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6256 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6256 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6257 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6257 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6258 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6258 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6259 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6259 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6260 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6260 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6261 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6261 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6262 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6262 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6263 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6263 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6264 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6264 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6265 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6265 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6266 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6266 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6267 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6267 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6268 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6268 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6269 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6269 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6270 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6270 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6271 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6271 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6272 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6272 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6273 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6273 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6274 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6274 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6275 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6275 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6276 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6276 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6277 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6277 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6278 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6278 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6279 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6279 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6280 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6280 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6281 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6281 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6282 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6282 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6283 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6283 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6284 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6284 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6285 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6285 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6286 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6286 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6287 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6287 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6288 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6288 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6289 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6289 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6290 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6290 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6291 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6291 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6292 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6292 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6293 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6293 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6294 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6294 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6295 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6295 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6296 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6296 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6297 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6297 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6298 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6298 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6299 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6299 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6300 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6300 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6301 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6301 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6302 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6302 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6303 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6303 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6304 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6304 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6305 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6305 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6306 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6306 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6307 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6307 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6308 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6308 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6309 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6309 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6310 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6310 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6311 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6311 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6312 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6312 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6313 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6313 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6314 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6314 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6315 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6315 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6316 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6316 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6317 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6317 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6318 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6318 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6319 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6319 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6320 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6320 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6321 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6321 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6322 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6322 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6323 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6323 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6324 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6324 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6325 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6325 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6326 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6326 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6327 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6327 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6328 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6328 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6329 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6329 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6330 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6330 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6331 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6331 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6332 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6332 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6333 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6333 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6334 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6334 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6335 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6335 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6336 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6336 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6337 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6337 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6338 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6338 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6339 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6339 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6340 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6340 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6341 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6341 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6342 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6342 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6343 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6343 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6344 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6344 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6345 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6345 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6346 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6346 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6347 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6347 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6348 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6348 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6349 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6349 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6350 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6350 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6351 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6351 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6352 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6352 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6353 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6353 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6354 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6354 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6355 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6355 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6356 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6356 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6357 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6357 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6358 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6358 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6359 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6359 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6360 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6360 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6361 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6361 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6362 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6362 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6363 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6363 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6364 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6364 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6365 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6365 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6366 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6366 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6367 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6367 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6368 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6368 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6369 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6369 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6370 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6370 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6371 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6371 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6372 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6372 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6373 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6373 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6374 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6374 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6375 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6375 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6376 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6376 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6377 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6377 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6378 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6378 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6379 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6379 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6380 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6380 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6381 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6381 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6382 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6382 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6383 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6383 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6384 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6384 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6385 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6385 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6386 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6386 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6387 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6387 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6388 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6388 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6389 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6389 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6390 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6390 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6391 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6391 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6392 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6392 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6393 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6393 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6394 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6394 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6395 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6395 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6396 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6396 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6397 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6397 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6398 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6398 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6399 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6399 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6400 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6400 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6401 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6401 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6402 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6402 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-6ZZ6403 | PS1-THEATRE EQUIPMENT & FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.1 | QP.C.PS.GEN.GEN.2590 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 6 | ZZ | 6403 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2026-12-06
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54724 | L2- THEATRE STALLS +913M- SETTING OUT PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4724 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54725 | L2- THEATRE STALLS +913M- SETTING OUT PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4725 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54726 | L2- THEATRE STALLS +913M- SETTING OUT PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4726 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54727 | L2- THEATRE STALLS +913M- SETTING OUT PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4727 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54728 | L2- THEATRE STALLS +913M- SETTING OUT PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4728 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54729 | L2- THEATRE STALLS +913M- SETTING OUT PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4729 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54730 | L2- THEATRE STALLS +913M- SETTING OUT PLAN - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4730 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54731 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- SETTING OUT PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4731 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54732 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- SETTING OUT PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4732 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54733 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- SETTING OUT PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4733 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54734 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- SETTING OUT PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4734 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54735 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- SETTING OUT PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4735 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54736 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- SETTING OUT PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4736 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54737 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- SETTING OUT PLAN - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4737 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54738 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- SETTING OUT PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4738 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54739 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SETTING OUT PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4739 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54740 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- SETTING OUT PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4740 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54741 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - SETTING OUT PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4741 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54742 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- SETTING OUT PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4742 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54743 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- SETTING OUT PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4743 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54744 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- SETTING OUT PLAN - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4744 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54745 | L5- SECOND CIRCLE & LOFT +928M- SETTING OUT PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4745 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54746 | L5- SECOND CIRCLE & LOFT +928M- SETTING OUT PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4746 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54747 | L5- SECOND CIRCLE & LOFT +928M- SETTING OUT PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4747 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54748 | L5- SECOND CIRCLE & LOFT +928M- SETTING OUT PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4748 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54749 | L5- SECOND CIRCLE & LOFT +928M- SETTING OUT PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4749 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54750 | L5- SECOND CIRCLE & LOFT +928M- SETTING OUT PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4750 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54751 | L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4751 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54752 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- SETTING OUT PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4752 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54753 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- SETTING OUT PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4753 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54754 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- SETTING OUT PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4754 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54755 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - SETTING OUT PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4755 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54756 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- SETTING OUT PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4756 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54757 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- SETTING OUT PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4757 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54758 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- SETTING OUT PLAN - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4758 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64759 | L6- SKY GARDEN+935.85M- SETTING OUT PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4759 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64760 | L6- SKY GARDEN +935.85M- SETTING OUT PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4760 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64761 | L6- SKY GARDEN +935.85M- SETTING OUT PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4761 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64762 | L6- SKY GARDEN +935.85M- SETTING OUT PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4762 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64763 | L6- SKY GARDEN +935.85M- SETTING OUT PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4763 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64764 | L6- SKY GARDEN +935.85M- SETTING OUT PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4764 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64765 | L6- SKY GARDEN +935.85M- SETTING OUT PLAN - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4765 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54766 | L2- THEATRE STALLS +913M- BUILDERS WORK- OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4766 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54767 | L2- THEATRE STALLS +913M- BUILDERS WORK- SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4767 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54768 | L2- THEATRE STALLS +913M- BUILDERS WORK- SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4768 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54769 | L2- THEATRE STALLS +913M- BUILDERS WORK- SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4769 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54770 | L2- THEATRE STALLS +913M- BUILDERS WORK- SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4770 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54771 | L2- THEATRE STALLS +913M- BUILDERS WORK- SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4771 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54772 | L2- THEATRE STALLS +913M- BUILDERS WORK- SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4772 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54773 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- BUILDERS WORK- OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4773 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54774 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- BUILDERS WORK- SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4774 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54775 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- BUILDERS WORK- SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4775 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54776 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- BUILDERS WORK- SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4776 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54777 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- BUILDERS WORK- SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4777 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54778 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- BUILDERS WORK- SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4778 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54779 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- BUILDERS WORK- SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4779 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54780 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- BUILDERS WORK- OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4780 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54781 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - BUILDERS WORK- SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4781 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54782 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- BUILDERS WORK- SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4782 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54783 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - BUILDERS WORK- SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4783 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54784 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- BUILDERS WORK- SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4784 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54785 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- BUILDERS WORK- SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4785 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54786 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- BUILDERS WORK- SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4786 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54787 | L5- SECOND CIRCLE & LOFT +928M- BUILDERS WORK- OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4787 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54788 | L5- SECOND CIRCLE & LOFT +928M- BUILDERS WORK- SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4788 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54789 | L5- SECOND CIRCLE & LOFT +928M- BUILDERS WORK- SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4789 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54790 | L5- SECOND CIRCLE & LOFT +928M- BUILDERS WORK- SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4790 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54791 | L5- SECOND CIRCLE & LOFT +928M- BUILDERS WORK- SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4791 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54792 | L5- SECOND CIRCLE & LOFT +928M- BUILDERS WORK- SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4792 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54793 | L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4793 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54794 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- BUILDERS WORK- OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4794 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54795 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- BUILDERS WORK- SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4795 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54796 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- BUILDERS WORK- SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4796 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54797 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - BUILDERS WORK- SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4797 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54798 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- BUILDERS WORK- SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4798 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54799 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- BUILDERS WORK- SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4799 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54800 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- BUILDERS WORK- SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4800 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64801 | L6- SKY GARDEN+935.85M- BUILDERS WORK- OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4801 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64802 | L6- SKY GARDEN +935.85M- BUILDERS WORK- SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4802 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64803 | L6- SKY GARDEN +935.85M- BUILDERS WORK- SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4803 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64804 | L6- SKY GARDEN +935.85M- BUILDERS WORK- SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4804 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64805 | L6- SKY GARDEN +935.85M- BUILDERS WORK- SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4805 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64806 | L6- SKY GARDEN +935.85M- BUILDERS WORK- SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4806 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64807 | L6- SKY GARDEN +935.85M- BUILDERS WORK- SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4807 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54892 | L2- THEATRE STALLS +913M- WALL LINING PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4892 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54893 | L2- THEATRE STALLS +913M- WALL LINING PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4893 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54894 | L2- THEATRE STALLS +913M- WALL LINING PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4894 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54895 | L2- THEATRE STALLS +913M- WALL LINING PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4895 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54896 | L2- THEATRE STALLS +913M- WALL LINING PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4896 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54897 | L2- THEATRE STALLS +913M- WALL LINING PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4897 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54898 | L2- THEATRE STALLS +913M- WALL LINING PLAN - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4898 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54899 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- WALL LINING PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4899 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54900 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- WALL LINING PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4900 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54901 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- WALL LINING PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4901 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54902 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- WALL LINING PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4902 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54903 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- WALL LINING PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4903 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54904 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- WALL LINING PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4904 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54905 | L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M- WALL LINING PLAN - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4905 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54906 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- WALL LINING PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4906 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54907 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - WALL LINING PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4907 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54908 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- WALL LINING PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4908 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54909 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M - WALL LINING PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4909 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54910 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- WALL LINING PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4910 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54911 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- WALL LINING PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4911 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54912 | L4-FIRST CIRCLE & ADAPTIVE THEATRE +921M- WALL LINING PLAN - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4912 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54913 | L5- SECOND CIRCLE & LOFT +928M- WALL LINING PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4913 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54914 | L5- SECOND CIRCLE & LOFT +928M- WALL LINING PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4914 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54915 | L5- SECOND CIRCLE & LOFT +928M- WALL LINING PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4915 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54916 | L5- SECOND CIRCLE & LOFT +928M- WALL LINING PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4916 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54917 | L5- SECOND CIRCLE & LOFT +928M- WALL LINING PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4917 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54918 | L5- SECOND CIRCLE & LOFT +928M- WALL LINING PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4918 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54919 | L5- SECOND CIRCLE & LOFT +928M - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4919 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54920 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- WALL LINING PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4920 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54921 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- WALL LINING PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4921 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54922 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- WALL LINING PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4922 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54923 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M - WALL LINING PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4923 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54924 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- WALL LINING PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4924 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54925 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- WALL LINING PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4925 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L54926 | L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M- WALL LINING PLAN - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L5 | 4926 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64927 | L6- SKY GARDEN+935.85M- WALL LINING PLAN - OVERALL |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4927 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64928 | L6- SKY GARDEN +935.85M- WALL LINING PLAN - SHEET 01 - (01 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4928 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64929 | L6- SKY GARDEN +935.85M- WALL LINING PLAN - SHEET 02 - (02 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4929 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64930 | L6- SKY GARDEN +935.85M- WALL LINING PLAN - SHEET 03 - (03 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4930 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64931 | L6- SKY GARDEN +935.85M- WALL LINING PLAN - SHEET 04 - (04 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4931 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64932 | L6- SKY GARDEN +935.85M- WALL LINING PLAN - SHEET 05 - (05 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4932 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2L64933 | L6- SKY GARDEN +935.85M- WALL LINING PLAN - SHEET 06 - (06 OF 06) |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | L6 | 4933 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5227 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5227 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5228 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5228 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5229 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5229 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5230 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5230 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5231 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5231 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5232 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5232 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5233 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5233 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5234 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5234 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5235 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5235 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5236 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5236 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5237 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5237 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5238 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5238 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5239 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5239 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5240 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5240 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5241 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5241 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5242 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5242 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5243 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5243 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5244 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5244 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5245 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5245 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5246 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5246 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5247 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5247 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5248 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5248 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5249 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5249 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5250 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5250 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5251 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5251 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5252 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5252 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5253 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5253 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5254 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5254 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5255 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5255 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5256 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5256 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5257 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5257 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5258 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5258 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5259 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5259 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5260 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5260 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5261 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5261 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5262 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5262 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5263 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5263 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5264 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5264 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5265 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5265 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5266 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5266 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5267 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5267 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5268 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5268 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5269 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5269 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5270 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5270 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5271 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5271 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5272 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5272 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5273 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5273 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5274 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5274 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5275 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5275 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5276 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5276 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5277 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5277 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5278 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5278 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5279 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5279 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5280 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5280 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5281 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5281 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5282 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5282 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5283 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5283 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5284 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5284 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5285 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5285 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5286 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5286 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5287 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5287 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5288 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5288 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5289 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5289 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5290 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5290 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5291 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5291 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5292 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5292 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5293 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5293 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5294 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5294 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5295 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5295 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5296 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5296 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5297 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5297 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5298 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5298 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5299 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5299 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5300 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5300 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5301 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5301 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5302 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5302 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5303 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5303 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5304 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5304 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5305 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5305 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5306 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5306 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5307 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5307 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5308 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5308 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5309 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5309 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5310 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5310 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5311 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5311 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5312 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5312 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5313 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5313 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5314 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5314 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5315 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5315 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5316 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5316 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5317 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5317 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5318 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5318 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5319 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5319 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5320 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5320 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5321 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5321 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5322 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5322 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5323 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5323 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5324 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5324 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5325 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5325 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5326 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5326 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5327 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5327 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5328 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5328 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5329 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5329 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5330 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5330 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5331 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5331 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5332 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5332 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5333 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5333 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5334 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5334 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5335 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5335 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5336 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5336 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5337 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5337 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5338 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5338 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5339 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5339 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5340 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5340 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5341 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5341 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5342 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5342 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5343 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5343 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5344 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5344 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5345 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5345 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5346 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5346 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5347 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5347 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5348 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5348 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5349 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5349 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5350 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5350 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5351 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5351 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5352 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5352 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5353 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5353 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5354 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5354 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5355 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5355 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5356 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5356 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5357 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5357 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5358 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5358 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5359 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5359 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5360 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5360 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5361 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5361 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5362 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5362 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5363 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5363 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5364 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5364 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5365 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5365 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5366 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5366 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5367 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5367 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5368 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5368 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5369 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5369 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5370 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5370 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5371 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5371 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5372 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5372 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5373 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5373 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5374 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5374 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5375 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5375 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5376 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5376 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5377 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5377 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5378 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5378 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5379 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5379 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5380 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5380 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5381 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5381 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5382 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5382 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5383 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5383 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5384 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5384 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5385 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5385 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5386 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5386 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5387 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5387 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5388 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5388 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5389 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5389 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5390 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5390 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5391 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5391 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5392 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5392 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5393 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5393 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5394 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5394 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5395 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5395 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5396 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5396 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5397 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5397 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5398 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5398 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5399 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5399 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5400 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5400 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5401 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5401 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5402 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5402 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5403 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5403 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5404 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5404 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5405 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5405 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5406 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5406 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5407 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5407 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5408 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5408 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5409 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5409 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5410 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5410 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5411 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5411 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5412 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5412 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5413 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5413 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5414 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5414 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5415 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5415 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5416 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5416 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5417 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5417 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5418 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5418 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5419 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5419 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5420 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5420 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5421 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5421 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5422 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5422 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5423 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5423 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5424 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5424 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5425 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5425 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5426 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5426 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5427 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5427 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5428 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5428 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5429 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5429 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5430 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5430 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5431 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5431 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5432 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5432 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5433 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5433 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5434 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5434 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5435 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5435 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5436 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5436 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5437 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5437 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5438 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5438 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5439 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5439 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5440 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5440 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5441 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5441 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5442 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5442 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5443 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5443 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5444 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5444 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5445 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5445 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5446 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5446 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5447 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5447 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5448 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5448 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5449 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5449 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5450 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5450 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5451 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5451 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5452 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5452 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5453 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5453 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5454 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5454 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5455 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5455 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5456 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5456 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5457 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5457 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5458 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5458 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5459 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5459 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5460 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5460 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5461 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5461 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5462 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5462 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5463 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5463 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5464 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5464 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5465 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5465 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5466 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5466 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5467 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5467 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5468 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5468 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5469 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5469 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5470 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5470 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5471 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5471 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5472 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5472 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5473 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5473 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5474 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5474 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5475 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5475 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5476 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5476 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5477 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5477 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5478 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5478 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5479 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5479 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5480 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5480 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5481 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5481 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5482 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5482 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5483 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5483 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5484 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5484 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5485 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5485 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5486 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5486 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5487 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5487 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5488 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5488 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5489 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5489 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5490 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5490 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5491 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5491 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5492 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5492 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5493 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5493 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5494 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5494 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5495 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5495 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5496 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5496 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5497 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5497 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5498 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5498 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5499 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5499 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5500 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5500 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5501 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5501 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5502 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5502 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5503 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5503 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5504 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5504 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5505 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5505 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5506 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5506 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5507 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5507 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5508 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5508 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5509 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5509 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5510 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5510 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5511 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5511 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5512 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5512 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5513 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5513 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5514 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5514 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5515 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5515 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5516 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5516 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5517 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5517 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5518 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5518 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5519 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5519 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5520 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5520 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5521 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5521 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5522 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5522 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5523 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5523 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5524 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5524 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5525 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5525 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5526 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5526 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5527 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5527 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5528 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5528 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5529 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5529 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5530 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5530 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5531 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5531 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5532 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5532 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5533 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5533 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5534 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5534 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5535 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5535 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5536 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5536 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5537 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5537 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5538 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5538 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5539 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5539 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5540 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5540 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5541 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5541 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5542 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5542 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5543 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5543 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5544 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5544 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5545 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5545 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5546 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5546 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5547 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5547 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5548 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5548 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5549 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5549 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5550 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5550 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5551 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5551 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5552 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5552 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5553 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5553 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5554 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5554 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5555 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5555 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5556 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5556 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5557 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5557 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5558 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5558 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5559 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5559 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5560 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5560 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5561 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5561 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5562 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5562 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5563 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5563 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5564 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5564 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5565 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5565 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5566 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5566 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5567 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5567 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5568 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5568 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5569 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5569 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5570 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5570 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5571 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5571 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5572 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5572 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5573 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5573 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5574 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5574 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5575 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5575 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5576 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5576 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5577 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5577 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5578 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5578 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5579 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5579 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5580 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5580 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5581 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5581 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5582 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5582 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5583 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5583 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5584 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5584 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5585 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5585 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5586 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5586 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5587 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5587 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5588 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5588 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5589 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5589 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5590 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5590 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5591 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5591 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5592 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5592 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5593 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5593 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5594 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5594 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5595 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5595 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5596 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5596 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5597 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5597 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5598 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5598 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5599 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5599 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5600 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5600 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5601 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5601 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5602 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5602 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5603 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5603 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5604 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5604 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5605 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5605 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5606 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5606 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5607 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5607 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5608 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5608 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5609 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5609 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5610 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5610 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5611 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5611 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5612 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5612 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5613 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5613 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5614 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5614 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5615 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5615 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5616 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5616 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5617 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5617 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5618 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5618 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5619 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5619 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5620 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5620 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5621 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5621 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5622 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5622 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5623 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5623 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5624 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5624 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5625 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5625 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5626 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5626 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5627 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5627 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5628 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5628 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5629 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5629 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5630 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5630 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5631 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5631 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5632 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5632 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5633 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5633 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5634 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5634 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5635 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5635 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5636 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5636 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5637 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5637 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5638 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5638 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5639 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5639 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5640 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5640 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5641 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5641 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5642 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5642 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5643 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5643 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5644 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5644 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5645 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5645 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5646 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5646 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5647 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5647 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5648 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5648 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5649 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5649 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5650 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5650 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5651 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5651 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5652 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5652 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5653 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5653 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5654 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5654 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5655 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5655 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5656 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5656 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5657 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5657 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5658 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5658 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5659 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5659 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5660 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5660 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5661 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5661 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5662 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5662 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5663 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5663 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5664 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5664 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5665 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5665 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5666 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5666 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5667 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5667 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5668 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5668 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5669 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5669 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5670 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5670 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5671 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5671 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5672 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5672 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5673 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5673 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5674 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5674 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5675 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5675 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5676 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5676 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5677 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5677 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5678 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5678 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5679 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5679 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5680 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5680 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5681 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5681 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5682 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5682 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5683 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5683 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5684 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5684 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5685 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5685 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5686 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5686 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5687 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5687 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5688 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5688 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5689 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5689 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5690 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5690 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5691 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5691 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5692 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5692 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5693 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5693 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5694 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5694 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5695 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5695 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5696 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5696 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5697 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5697 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5698 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5698 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5699 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5699 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5700 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5700 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5701 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5701 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5702 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5702 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5703 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5703 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5704 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5704 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5705 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5705 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5706 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5706 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5707 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5707 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5708 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5708 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5709 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5709 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5710 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5710 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5711 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5711 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5712 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5712 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5713 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5713 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5714 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5714 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5715 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5715 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5716 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5716 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5717 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5717 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5718 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5718 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5719 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5719 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5720 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5720 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5721 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5721 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5722 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5722 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5723 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5723 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5724 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5724 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5725 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5725 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5726 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5726 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5727 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5727 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5728 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5728 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5729 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5729 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5730 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5730 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5731 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5731 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5732 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5732 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5733 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5733 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5734 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5734 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5735 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5735 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5736 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5736 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5737 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5737 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5738 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5738 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5739 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5739 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5740 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5740 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5741 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5741 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5742 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5742 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5743 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5743 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5744 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5744 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5745 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5745 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5746 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5746 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5747 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5747 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5748 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5748 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5749 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5749 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5750 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5750 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5751 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5751 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5752 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5752 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5753 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5753 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5754 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5754 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5755 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5755 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5756 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5756 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5757 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5757 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5758 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5758 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5759 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5759 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5760 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5760 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5761 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5761 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5762 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5762 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5763 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5763 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5764 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5764 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5765 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5765 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5766 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5766 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5767 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5767 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5768 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5768 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5769 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5769 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5770 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5770 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5771 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5771 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5772 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5772 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5773 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5773 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5774 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5774 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5775 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5775 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5776 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5776 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5777 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5777 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5778 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5778 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5779 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5779 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5780 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5780 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5781 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5781 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5782 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5782 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5783 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5783 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5784 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5784 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5785 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5785 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5786 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5786 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5787 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5787 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5788 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5788 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5789 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5789 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5790 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5790 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5791 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5791 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5792 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5792 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5793 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5793 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5794 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5794 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5795 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5795 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5796 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5796 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5797 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5797 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5798 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5798 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5799 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5799 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5800 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5800 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31
QF01012-NES-C04518-SDW-INT-00-Z00000-2ZZ5801 | PS4-FOH FITOUT |  |  | Revit | .dwg,.pdf |  |  | PS.4 | QP.C.PS.GEN.GEN.1930 | FI_60_25 | QF01012 | NES | C04518 | SDW | INT | 00 | Z00000 | 2 | ZZ | 5801 | Interior Design | Provisional Sum | LOD400 |  |  |  | 2027-10-31

## Baseline (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | Package | Activity Code | Activity | Original Duration | Start | Finish
Shop Drawings | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Shop Drawings ¦ Mobilization | QP.M.GN.GEN.GEN.1400 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Shop Drawings ¦ Mobilization ¦ Tower Crane Foundation - Concrete Works | QP.M.GN.GEN.GEN.1470 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Blades Below Loft | QP.M.GN.GEN.GEN.1540 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Loft | QP.M.GN.GEN.GEN.1560 | Submittal | 12 | 2026-08-29 | 2026-09-10
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Above Loft | QP.M.GN.GEN.GEN.1580 | Submittal | 12 | 2026-10-01 | 2026-10-14
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works | QP.E.CV.MBL.GEN.3460 | Submittal | 28 | 2025-10-11 | 2025-11-11
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works Outside Core Area | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works Outside Core Area | QP.E.CV.MBL.GEN.3540 | Submittal | 14 | 2025-11-12 | 2025-11-27
Shop Drawings | Civil | Blades | Blade 1 | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 1 | QP.E.CV.BL1.GEN.1060 | Submittal | 28 | 2026-02-21 | 2026-03-28
Shop Drawings | Civil | Blades | Blade 2 | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 2 | QP.E.CV.BL2.GEN.1060 | Submittal | 28 | 2026-01-19 | 2026-02-19
Shop Drawings | Civil | Blades | Blade 3 | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 3 | QP.E.CV.BL3.GEN.1060 | Submittal | 28 | 2025-12-17 | 2026-01-18
Shop Drawings | Civil | Blades | Blade 4 | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 4 | QP.E.CV.BL4.GEN.1060 | Submittal | 28 | 2025-12-03 | 2026-01-04
Shop Drawings | Civil | Blades | Blade 5 | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 5 | QP.E.CV.BL5.GEN.1060 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Civil | Parking | Parking | Parking | Parking | Parking | Shop Drawings ¦ Civil ¦ Parking | QP.E.CV.PAR.GEN.1000 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - Foundation Works Core Area | QP.E.CV.MBL.GEN.3000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 03 +887.750M | QP.E.CV.MBL.GEN.3030 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - SOG | QP.E.CV.MBL.GEN.3640 | Submittal | 14 | 2026-03-16 | 2026-04-02
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 02 - Foundation Works Outside Core Area | QP.E.CV.MBL.GEN.3020 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 02 +893.5M | QP.E.CV.MBL.GEN.3070 | Submittal | 21 | 2026-02-18 | 2026-03-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 01 +900.5M | QP.E.CV.MBL.GEN.3100 | Submittal | 28 | 2026-03-16 | 2026-04-19
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01- LOBBY LEVEL +905M | QP.E.CV.MBL.GEN.3120 | Submittal | 25 | 2026-04-20 | 2026-05-18
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01 - MEZZANINE +909M | QP.E.CV.MBL.GEN.3140 | Submittal | 15 | 2026-05-19 | 2026-06-08
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3180 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3380 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3220 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3400 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3240 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3420 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3260 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3440 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | QP.E.CV.MBL.GEN.3280 | Submittal | 25 | 2026-10-08 | 2026-11-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | QP.E.CV.MBL.GEN.3300 | Submittal | 28 | 2027-03-13 | 2027-04-13
Shop Drawings | Concrete | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Premium Theatre Concrete Works | QP.E.CV.MBL.GEN.3150 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Amphitheatre Concrete Works | QP.E.CV.MBL.GEN.3200 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Premium Theater | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Premium Theater | QP.E.CV.MBL.GEN.3660 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Loft and Adaptable Theatre | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Loft and Adaptable Theatre | QP.E.CV.MBL.GEN.3700 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Fly Tower | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Fly Tower | QP.E.CV.MBL.GEN.3710 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Lobby & Plaza | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Lobby & Plaza | QP.E.CV.MBL.GEN.3680 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Royal Majlis | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Royal Majlis | QP.E.CV.MBL.GEN.3740 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Foundation | QP.E.CV.BL1.GEN.1000 | Submittal | 25 | 2026-02-25 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL1.GEN.1040 | Submittal | 25 | 2026-03-29 | 2026-04-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL1.GEN.1080 | Submittal | 18 | 2026-05-12 | 2026-06-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL1.GEN.1020 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL1.GEN.1120 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL1.GEN.1100 | Submittal | 28 | 2026-10-27 | 2026-11-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Foundation | QP.E.CV.BL2.GEN.1000 | Submittal | 21 | 2026-03-02 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL2.GEN.1040 | Submittal | 21 | 2026-03-10 | 2026-04-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL2.GEN.1080 | Submittal | 18 | 2026-04-21 | 2026-05-11
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL2.GEN.1020 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL2.GEN.1140 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL2.GEN.1120 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Foundation | QP.E.CV.BL3.GEN.1000 | Submittal | 21 | 2026-02-07 | 2026-03-03
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Steel Composite Slab Including Embedded items Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Steel Composite Slab Including Embedded items Below Loft | QP.E.CV.BL3.GEN.1030 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL3.GEN.1080 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL3.GEN.1020 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Foundation | QP.E.CV.BL4.GEN.1000 | Submittal | 28 | 2026-01-05 | 2026-02-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL4.GEN.1030 | Submittal | 28 | 2026-02-24 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL4.GEN.1080 | Submittal | 15 | 2026-03-31 | 2026-04-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL4.GEN.1020 | Submittal | 28 | 2026-04-18 | 2026-05-19
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL4.GEN.1100 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL4.GEN.1120 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Foundation | QP.E.CV.BL5.GEN.1000 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL5.GEN.1030 | Submittal | 28 | 2026-03-23 | 2026-04-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL5.GEN.1080 | Submittal | 18 | 2026-03-31 | 2026-04-20
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL5.GEN.1020 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL5.GEN.1100 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL5.GEN.1120 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Foundation Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Foundation Including Embedded items | QP.E.CV.PAR.GEN.1020 | Submittal | 28 | 2027-04-28 | 2027-06-03
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Structural Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Structural Concrete Works Including Embedded items | QP.E.CV.PAR.GEN.1040 | Submittal | 28 | 2027-06-19 | 2027-07-20
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Below Loft | QP.E.ST.GEN.GEN.1090 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1100 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1110 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1050 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1060 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1070 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 3,4,5 | QP.E.ST.GEN.GEN.1000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | QP.E.ST.GEN.GEN.1010 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Truss below Auditorium, Side and Back Stage | QP.E.ST.GEN.GEN.2120 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1220 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1230 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1200 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1210 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1190 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Embedded part - Main Building Above Level 5 | QP.E.ST.GEN.GEN.1040 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Premium Theater - Frame Balconies and Back Stage Dressing | QP.E.ST.GEN.GEN.2140 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Loft and adaptable Theatre | QP.E.ST.GEN.GEN.1340 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1390 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1400 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1310 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1320 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1330 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1470 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ Truss above Auditorium Incl. Metal Deck | QP.E.ST.GEN.GEN.2100 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Temporay Tower ROYAL MAJLIS and Blades above loft | QP.E.ST.GEN.GEN.1490 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2160 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1520 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Truss above Flytower | QP.E.ST.GEN.GEN.2180 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1540 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ Blade 2 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2200 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ Adaptable Theatre Incl. Metal Deck | QP.E.ST.GEN.GEN.1560 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.2220 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Loft Truss and Infilled Beam North Side Incl. Metal Deck | QP.E.ST.GEN.GEN.1610 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1600 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Lobby and Plaza Incl. Metal Deck | QP.E.ST.GEN.GEN.1660 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Frame for Mezzanine | QP.E.ST.GEN.GEN.1670 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Link Bridge and Helix Stair | QP.E.ST.GEN.GEN.1570 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1680 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | Shop Drawings ¦ Structural Steel ¦ Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck ¦ ROYAL MAJLIS | QP.E.ST.GEN.GEN.1640 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1090 | Submittal | 21 | 2026-03-26 | 2026-04-19
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1120 | Submittal | 21 | 2026-09-15 | 2026-10-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Wall Cladding | QP.E.AF.MBL.GEN.4440 | Submittal | 21 | 2026-10-11 | 2026-11-03
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1100 | Submittal | 21 | 2026-11-04 | 2026-11-28
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ FFE | QP.E.AF.MBL.GEN.5260 | Submittal | 21 | 2026-11-29 | 2026-12-22
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1170 | Submittal | 21 | 2026-04-20 | 2026-05-13
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1200 | Submittal | 20 | 2026-11-04 | 2026-11-26
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5700 | Submittal | 21 | 2026-11-28 | 2026-12-21
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1180 | Submittal | 21 | 2026-12-23 | 2027-01-16
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ FFE | QP.E.AF.MBL.GEN.5280 | Submittal | 21 | 2027-01-17 | 2027-02-09
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1220 | Submittal | 21 | 2026-05-14 | 2026-06-10
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1250 | Submittal | 28 | 2026-11-28 | 2026-12-29
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5720 | Submittal | 21 | 2026-12-30 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1230 | Submittal | 21 | 2027-01-24 | 2027-02-16
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ FFE | QP.E.AF.MBL.GEN.5300 | Submittal | 21 | 2027-02-17 | 2027-03-16
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1310 | Submittal | 21 | 2026-06-11 | 2026-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1340 | Submittal | 28 | 2026-12-30 | 2027-01-31
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5800 | Submittal | 21 | 2027-02-01 | 2027-02-25
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1320 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ FFE | QP.E.AF.MBL.GEN.5320 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1400 | Submittal | 21 | 2026-07-06 | 2026-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1430 | Submittal | 20 | 2027-02-01 | 2027-02-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5740 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1410 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ FFE | QP.E.AF.MBL.GEN.5340 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1000 | Submittal | 21 | 2026-07-30 | 2026-08-23
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1030 | Submittal | 20 | 2027-02-25 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5760 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1010 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ FFE | QP.E.AF.MBL.GEN.5360 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1490 | Submittal | 21 | 2026-08-24 | 2026-09-16
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1520 | Submittal | 20 | 2027-03-23 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5820 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1500 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ FFE | QP.E.AF.MBL.GEN.5380 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1580 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1610 | Submittal | 20 | 2027-04-15 | 2027-05-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5840 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1590 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ FFE | QP.E.AF.MBL.GEN.5400 | Submittal | 21 | 2027-07-06 | 2027-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1670 | Submittal | 21 | 2026-12-20 | 2027-01-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1700 | Submittal | 20 | 2027-05-23 | 2027-06-14
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5860 | Submittal | 28 | 2027-06-15 | 2027-07-17
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1680 | Submittal | 28 | 2027-07-18 | 2027-08-18
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ FFE | QP.E.AF.MBL.GEN.5420 | Submittal | 28 | 2027-07-31 | 2027-08-31
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1760 | Submittal | 21 | 2027-01-19 | 2027-02-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1790 | Submittal | 21 | 2027-05-23 | 2027-06-15
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5880 | Submittal | 21 | 2027-07-18 | 2027-08-10
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1770 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ FFE | QP.E.AF.MBL.GEN.5440 | Submittal | 21 | 2027-09-01 | 2027-09-26
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1880 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1910 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5900 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1890 | Submittal | 21 | 2027-09-13 | 2027-10-07
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ FFE | QP.E.AF.MBL.GEN.5460 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1800 | Submittal | 21 | 2027-04-22 | 2027-05-20
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1830 | Submittal | 21 | 2027-07-25 | 2027-08-17
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5920 | Submittal | 21 | 2027-08-25 | 2027-09-18
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1810 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ FFE | QP.E.AF.MBL.GEN.5480 | Submittal | 21 | 2027-10-11 | 2027-11-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1110 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1140 | Submittal | 21 | 2027-05-31 | 2027-06-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1120 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1370 | Submittal | 21 | 2027-03-01 | 2027-03-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1360 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Wall Cladding | QP.E.AF.BL1.GEN.5940 | Submittal | 21 | 2027-07-19 | 2027-08-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1340 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1650 | Submittal | 21 | 2027-06-14 | 2027-07-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1680 | Submittal | 14 | 2027-09-01 | 2027-09-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1660 | Submittal | 21 | 2027-11-18 | 2027-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1080 | Submittal | 21 | 2027-05-26 | 2027-06-19
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1110 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Wall Cladding | QP.E.AF.BL2.GEN.5960 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1090 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1580 | Submittal | 21 | 2027-07-04 | 2027-07-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1610 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1590 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1670 | Submittal | 21 | 2027-07-28 | 2027-08-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1700 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1680 | Submittal | 14 | 2028-01-18 | 2028-02-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1000 | Submittal | 24 | 2026-11-15 | 2026-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1030 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL3.GEN.5980 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1010 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1340 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1370 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1350 | Submittal | 21 | 2027-12-22 | 2028-01-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1210 | Submittal | 24 | 2026-12-27 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1240 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL4.GEN.6000 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1220 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1820 | Submittal | 21 | 2027-04-24 | 2027-05-22
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1850 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1830 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1730 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1760 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1740 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.2280 | Submittal | 24 | 2027-02-07 | 2027-03-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.2340 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.2300 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1130 | Submittal | 21 | 2027-03-22 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1160 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1140 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1500 | Submittal | 28 | 2027-06-29 | 2027-07-31
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1530 | Submittal | 21 | 2027-10-10 | 2027-11-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Wall Cladding | QP.E.AF.BL5.GEN.6020 | Submittal | 21 | 2027-12-16 | 2028-01-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1510 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1000 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1020 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Doors / Openings | QP.E.AF.PAR.GEN.1010 | Submittal | 28 | 2027-12-22 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Specialities | QP.E.AF.MBL.GEN.5160 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1030 | Submittal | 28 | 2027-10-16 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1050 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Doors / Openings | QP.E.AF.PAR.GEN.1040 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Specialities | QP.E.AF.MBL.GEN.5200 | Submittal | 21 | 2028-01-09 | 2028-02-01
Shop Drawings | Architecture and Fitouts | Amphitheatre | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4040 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Architecture and Fitouts | Amphitheatre | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.4070 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Amphitheatre | Wall Cladding | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Wall Cladding | QP.E.AF.MBL.GEN.6040 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | Architecture and Fitouts | Amphitheatre | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4050 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | Shop Drawings ¦ External Building Works (Guard House, SEC Room) | QP.E.EX.GEN.GEN.1270 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Main Building | QP.E.AF.MBL.GEN.6060 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 5 | Water Proofing - Roof - Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 5 | QP.E.AF.BL5.GEN.6180 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 4 | Water Proofing - Roof - Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 4 | QP.E.AF.BL4.GEN.6160 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 3 | Water Proofing - Roof - Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 3 | QP.E.AF.BL3.GEN.6140 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 1 | Water Proofing - Roof - Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 1 | QP.E.AF.BL1.GEN.6100 | Submittal | 21 | 2027-12-09 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 2 | Water Proofing - Roof - Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 2 | QP.E.AF.BL2.GEN.6120 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Wet Areas | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Wet Areas ¦ Main Building | QP.E.AF.MBL.GEN.4400 | Submittal | 21 | 2027-08-08 | 2027-08-31
Shop Drawings | Specialist Systems | Doors/ Openings | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Main Building | QP.E.AF.MBL.GEN.1140 | Submittal | 20 | 2027-06-29 | 2027-07-21
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.1130 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 2 | QP.E.AF.BL2.GEN.1100 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.1020 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.1230 | Submittal | 21 | 2027-08-16 | 2027-09-08
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.2320 | Submittal | 21 | 2027-09-09 | 2027-10-04
Shop Drawings | Specialist Systems | Doors/ Openings | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Amphitheatre | QP.E.AF.MBL.GEN.4060 | Submittal | 28 | 2027-11-13 | 2027-12-14
Shop Drawings | Specialist Systems | Conveying System | Waste Management | Waste Management | Waste Management | Waste Management | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Waste Management | QP.E.CY.GEN.GEN.1280 | Submittal | 14 | 2027-12-02 | 2027-12-18
Shop Drawings | Specialist Systems | Conveying System | Escalators | Escalators | Escalators | Escalators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Escalators | QP.E.CY.GEN.GEN.1040 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | Specialist Systems | Conveying System | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | QP.E.CY.GEN.GEN.1020 | Submittal | 28 | 2026-10-22 | 2026-11-23
Shop Drawings | Specialist Systems | Conveying System | Truck Elevators | Truck Elevators | Truck Elevators | Truck Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Truck Elevators | QP.E.CY.GEN.GEN.1000 | Submittal | 28 | 2026-09-19 | 2026-10-21
Shop Drawings | Specialist Systems | Conveying System | Inclined Elevators | Inclined Elevators | Inclined Elevators | Inclined Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Inclined Elevators | QP.E.CY.GEN.GEN.1050 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Main Building | QP.E.CY.GEN.GEN.1090 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 1 | QP.E.CY.GEN.GEN.1130 | Submittal | 28 | 2027-10-17 | 2027-11-17
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 2 | QP.E.CY.GEN.GEN.1170 | Submittal | 28 | 2027-09-13 | 2027-10-16
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 3 | Balde 3 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 3 | QP.E.CY.GEN.GEN.1210 | Submittal | 28 | 2027-06-07 | 2027-07-08
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 4 | QP.E.CY.GEN.GEN.1110 | Submittal | 28 | 2027-07-10 | 2027-08-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 5 | Balde 5 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 5 | QP.E.CY.GEN.GEN.1150 | Submittal | 28 | 2027-08-11 | 2027-09-12
Shop Drawings | Specialist Systems | Joinery Works | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Main Building | QP.E.AF.MBL.GEN.5540 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.6120 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.6160 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.6180 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.6200 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Shop Drawings ¦ Specialist Systems ¦ Kitchen and Laundary | QP.E.AF.MBL.GEN.5500 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Specialist Systems | Water Features | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Specialist Systems ¦ Water Features | QP.E.AF.MBL.GEN.6100 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Mechanical | QP.E.ME.MBL.GEN.6780 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical | QP.E.ME.MBL.GEN.6800 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6840 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical | QP.E.ME.MBL.GEN.6850 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6860 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical | QP.E.ME.MBL.GEN.6870 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Mechanical | QP.E.ME.MBL.GEN.6900 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical | QP.E.ME.MBL.GEN.6910 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Mechanical | QP.E.ME.MBL.GEN.6940 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical | QP.E.ME.MBL.GEN.6950 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Mechanical | QP.E.ME.MBL.GEN.6980 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Electrical | QP.E.ME.MBL.GEN.6990 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Mechanical | QP.E.ME.MBL.GEN.7020 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical | QP.E.ME.MBL.GEN.7030 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7060 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical | QP.E.ME.MBL.GEN.7070 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7100 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical | QP.E.ME.MBL.GEN.7110 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Mechanical | QP.E.ME.MBL.GEN.7140 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical | QP.E.ME.MBL.GEN.7150 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Mechanical | QP.E.ME.MBL.GEN.7180 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Electrical | QP.E.ME.MBL.GEN.7190 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Mechanical | QP.E.ME.MBL.GEN.7220 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical | QP.E.ME.MBL.GEN.7230 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1320 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1330 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1340 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1350 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ ICT Containment | QP.E.ME.MBL.GEN.1360 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1420 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1430 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1440 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1450 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1460 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1740 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1750 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1760 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1770 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1780 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1590 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1600 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1610 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1620 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.1630 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2040 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2050 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2060 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2070 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ ICT Containment | QP.E.ME.MBL.GEN.2080 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2240 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2250 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2260 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2270 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ ICT Containment | QP.E.ME.MBL.GEN.2280 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2440 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2450 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2460 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2470 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.2480 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2640 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2650 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2660 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2670 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2680 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2850 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2860 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2870 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2880 | Submittal | 28 | 2026-12-08 | 2027-01-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2890 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3070 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3080 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3090 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3100 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ ICT Containment | QP.E.ME.MBL.GEN.3110 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3290 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3300 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3310 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3320 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ ICT Containment | QP.E.ME.MBL.GEN.3330 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3500 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3510 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3520 | Submittal | 28 | 2026-12-23 | 2027-01-24
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3530 | Submittal | 28 | 2027-02-11 | 2027-03-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ ICT Containment | QP.E.ME.MBL.GEN.3540 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.MBL.GEN.5000 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.MBL.GEN.5040 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.MBL.GEN.5060 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.MBL.GEN.5080 | Submittal | 28 | 2027-03-07 | 2027-04-10
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.MBL.GEN.7280 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.MBL.GEN.7300 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.MBL.GEN.7320 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.MBL.GEN.7260 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.MBL.GEN.7340 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | LPG System | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ LPG System | QP.E.ME.MBL.GEN.5100 | Submittal | 21 | 2027-09-22 | 2027-10-17
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.MBL.GEN.7360 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Fire Suppression | QP.E.ME.CBR.GEN.1000 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Plumbing | Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Plumbing | QP.E.ME.CBR.GEN.1011 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ LPG System | QP.E.ME.CBR.GEN.1055 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.CBR.GEN.1022 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Electrical | QP.E.ME.CBR.GEN.1033 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ ELV (Low Current System) | QP.E.ME.CBR.GEN.1044 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.MBL.GEN.7380 | Submittal | 28 | 2027-12-09 | 2028-01-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Diesel | Diesel | Diesel | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Diesel | QP.E.ME.MBL.GEN.7420 | Submittal | 21 | 2028-02-01 | 2028-02-26
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Water Features | Water Features | Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Water Features | QP.E.ME.MBL.GEN.7440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M | QP.E.ME.MBL.GEN.6520 | Submittal | 28 | 2026-06-14 | 2026-07-15
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Grey Water Treatment/ Sewage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Grey Water Treatment/ Sewage | QP.E.ME.MBL.GEN.1050 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Stromwater/ Drainage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Stromwater/ Drainage | QP.E.ME.MBL.GEN.1060 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1040 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M | QP.E.ME.MBL.GEN.6540 | Submittal | 28 | 2026-07-16 | 2026-08-17
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ AHU Room | QP.E.ME.MBL.GEN.1160 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Transformer/ Switchgear/ Panel Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Transformer/ Switchgear/ Panel Room | QP.E.ME.MBL.GEN.1240 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Generator Room/ Diesel Tank | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Generator Room/ Diesel Tank | QP.E.ME.MBL.GEN.1250 | Submittal | 14 | 2026-10-05 | 2026-10-20
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | ETS/ CWP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ ETS/ CWP Room | QP.E.ME.MBL.GEN.1170 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1030 | Submittal | 14 | 2026-09-24 | 2026-10-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1290 | Submittal | 28 | 2026-09-01 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M | QP.E.ME.MBL.GEN.6560 | Submittal | 14 | 2026-08-18 | 2026-09-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1020 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Domestic Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Domestic Water | QP.E.ME.MBL.GEN.1010 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Fire Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Fire Water | QP.E.ME.MBL.GEN.1000 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1280 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 LOBBY LEVEL +905.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 LOBBY LEVEL +905.00M | QP.E.ME.MBL.GEN.6640 | Submittal | 21 | 2026-09-03 | 2026-09-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 UPEER LOBBY LEVEL MEZZANINE +909M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M | QP.E.ME.MBL.GEN.6660 | Submittal | 21 | 2026-09-29 | 2026-10-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L2 THEATRE STALLS +913M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L2 THEATRE STALLS +913M | QP.E.ME.MBL.GEN.6680 | Submittal | 21 | 2026-10-24 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | QP.E.ME.MBL.GEN.6700 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | QP.E.ME.MBL.GEN.6720 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 SECOND CIRCLE AND LOFT +928.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 SECOND CIRCLE AND LOFT +928.00M | QP.E.ME.MBL.GEN.6740 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M | QP.E.ME.MBL.GEN.5540 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - AHU Room | QP.E.ME.MBL.GEN.1180 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Makeup Air Unit and Ecology | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Makeup Air Unit and Ecology | QP.E.ME.MBL.GEN.1190 | Submittal | 14 | 2027-01-06 | 2027-01-21
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Sky Garden Irrigation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Sky Garden Irrigation | QP.E.ME.MBL.GEN.1070 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L6 SKY GARDEN +935.85M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L6 SKY GARDEN +935.85M | QP.E.ME.MBL.GEN.6760 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M | QP.E.ME.MBL.GEN.6580 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | Plant Room - Fan Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M ¦ Plant Room - Fan Room | QP.E.ME.MBL.GEN.6600 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Kitchen and Laundry | Kitchen and Laundry | Kitchen and Laundry | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Kitchen and Laundry | QP.E.ME.MBL.GEN.7400 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | MEP | Panels | Panels | Panels | Panels | Panels | Shop Drawings ¦ MEP ¦ Panels | QP.E.ME.MBL.GEN.6510 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Mechanical | QP.E.ME.BL1.GEN.3720 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical | QP.E.ME.BL1.GEN.3740 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL1.GEN.3760 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL1.GEN.3780 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Mechanical | QP.E.ME.BL1.GEN.3800 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical | QP.E.ME.BL1.GEN.3820 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1020 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1030 | Submittal | 21 | 2027-02-25 | 2027-03-23
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1040 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1050 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ ICT Containment | QP.E.ME.BL1.GEN.1060 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL1.GEN.2940 | Submittal | 21 | 2027-04-11 | 2027-05-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.2950 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.2960 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.2970 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL1.GEN.2980 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1510 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1520 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1530 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1540 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ ICT Containment | QP.E.ME.BL1.GEN.1550 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.BL1.GEN.3280 | Submittal | 21 | 2027-08-30 | 2027-09-22
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL1.GEN.3320 | Submittal | 21 | 2027-10-07 | 2027-10-31
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL1.GEN.3340 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL1.GEN.3360 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL1.GEN.3580 | Submittal | 21 | 2027-11-15 | 2027-12-08
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL1.GEN.3600 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL1.GEN.3620 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL1.GEN.3680 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL1.GEN.3640 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL1.GEN.3660 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3480 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL1.GEN.1000 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL1.GEN.3700 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3400 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical | QP.E.ME.BL2.GEN.3420 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL2.GEN.3440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL2.GEN.3460 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3480 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical | QP.E.ME.BL2.GEN.3500 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1020 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1030 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1040 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1050 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.1060 | Submittal | 21 | 2027-04-18 | 2027-05-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1910 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1920 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1930 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1940 | Submittal | 21 | 2027-04-29 | 2027-05-27
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL2.GEN.1950 | Submittal | 21 | 2027-05-12 | 2027-06-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.2110 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.2120 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.2130 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.2140 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.2150 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL2.GEN.3160 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL2.GEN.3200 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL2.GEN.3220 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL2.GEN.3240 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL2.GEN.3260 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL2.GEN.3280 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL2.GEN.3300 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL2.GEN.3380 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL2.GEN.3320 | Submittal | 28 | 2027-11-22 | 2027-12-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL2.GEN.3340 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3500 | Submittal | 14 | 2028-02-17 | 2028-03-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL2.GEN.1000 | Submittal | 16 | 2028-02-17 | 2028-03-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL2.GEN.3360 | Submittal | 14 | 2028-04-09 | 2028-04-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Mechanical | QP.E.ME.BL3.GEN.3640 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical | QP.E.ME.BL3.GEN.3660 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical | QP.E.ME.BL3.GEN.3700 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Mechanical | QP.E.ME.BL3.GEN.3680 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1020 | Submittal | 21 | 2026-06-17 | 2026-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.1030 | Submittal | 21 | 2026-07-12 | 2026-08-04
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1040 | Submittal | 21 | 2026-08-05 | 2026-08-29
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1050 | Submittal | 21 | 2026-08-30 | 2026-09-22
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ ICT Containment | QP.E.ME.BL3.GEN.1060 | Submittal | 21 | 2026-10-07 | 2026-10-31
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1790 | Submittal | 21 | 2026-12-31 | 2027-01-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.3280 | Submittal | 21 | 2027-01-25 | 2027-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1810 | Submittal | 21 | 2027-02-18 | 2027-03-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1820 | Submittal | 21 | 2027-03-18 | 2027-04-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ ICT Containment | QP.E.ME.BL3.GEN.1830 | Submittal | 21 | 2027-04-12 | 2027-05-05
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL3.GEN.3400 | Submittal | 21 | 2027-06-23 | 2027-07-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL3.GEN.3440 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL3.GEN.3460 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL3.GEN.3480 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL3.GEN.3500 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL3.GEN.3540 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL3.GEN.3560 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL3.GEN.3620 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL3.GEN.3600 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL3.GEN.3580 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3520 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL3.GEN.1000 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL3.GEN.3520 | Submittal | 14 | 2028-04-04 | 2028-04-19
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Mechanical | QP.E.ME.BL4.GEN.6010 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical | QP.E.ME.BL4.GEN.6030 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Mechanical | QP.E.ME.BL4.GEN.6050 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Electrical | QP.E.ME.BL4.GEN.6070 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Mechanical | QP.E.ME.BL4.GEN.6090 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical | QP.E.ME.BL4.GEN.6110 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Fire Suppression | QP.E.ME.BL4.GEN.2110 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2120 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2130 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2140 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ ICT Containment | QP.E.ME.BL4.GEN.2150 | Submittal | 21 | 2026-11-01 | 2026-11-24
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2910 | Submittal | 21 | 2026-12-05 | 2026-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.5550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2930 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2940 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ ICT Containment | QP.E.ME.BL4.GEN.2950 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2810 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2820 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2830 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2840 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ ICT Containment | QP.E.ME.BL4.GEN.2850 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL4.GEN.5770 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL4.GEN.5810 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL4.GEN.5830 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL4.GEN.5850 | Submittal | 21 | 2027-09-29 | 2027-10-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL4.GEN.5870 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL4.GEN.5930 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL4.GEN.5950 | Submittal | 21 | 2027-12-05 | 2027-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL4.GEN.5890 | Submittal | 21 | 2028-01-12 | 2028-02-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL4.GEN.5970 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL4.GEN.5990 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3540 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL4.GEN.3110 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL4.GEN.5910 | Submittal | 14 | 2028-04-02 | 2028-04-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Mechanical | QP.E.ME.BL5.GEN.3040 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical | QP.E.ME.BL5.GEN.3060 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL5.GEN.3080 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL5.GEN.3100 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Mechanical | QP.E.ME.BL5.GEN.3120 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical | QP.E.ME.BL5.GEN.3140 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1020 | Submittal | 21 | 2026-10-29 | 2026-11-22
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1030 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1040 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1050 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ ICT Containment | QP.E.ME.BL5.GEN.1060 | Submittal | 21 | 2026-11-25 | 2026-12-19
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1560 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1570 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1580 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL5.GEN.1590 | Submittal | 21 | 2027-04-10 | 2027-05-03
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1750 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1760 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1770 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1780 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ ICT Containment | QP.E.ME.BL5.GEN.1790 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL5.GEN.2800 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL5.GEN.2840 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL5.GEN.2860 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL5.GEN.2880 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL5.GEN.3020 | Submittal | 14 | 2027-10-24 | 2027-11-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL5.GEN.2900 | Submittal | 14 | 2027-12-01 | 2027-12-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL5.GEN.2920 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL5.GEN.3000 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL5.GEN.2940 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL5.GEN.2960 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3560 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL5.GEN.1000 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL5.GEN.2980 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Mechanical | QP.E.ME.PAR.GEN.1459 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Electrical | QP.E.ME.PAR.GEN.1479 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Mechanical | QP.E.ME.PAR.GEN.1499 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Electrical | QP.E.ME.PAR.GEN.1519 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Fire Suppression | QP.E.ME.PAR.GEN.1000 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1011 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1022 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1033 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ ICT Containment | QP.E.ME.PAR.GEN.1044 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Fire Suppression | QP.E.ME.PAR.GEN.1055 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1066 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1077 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1088 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ ICT Containment | QP.E.ME.PAR.GEN.1099 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.PAR.GEN.1219 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.PAR.GEN.1259 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.PAR.GEN.1279 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.PAR.GEN.1299 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.PAR.GEN.1419 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.PAR.GEN.1319 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.PAR.GEN.1339 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.PAR.GEN.1439 | Submittal | 14 | 2028-02-07 | 2028-02-23
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.PAR.GEN.1359 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.PAR.GEN.1379 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.PAR.GEN.1399 | Submittal | 14 | 2028-03-09 | 2028-03-25
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3600 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3610 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3620 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.4430 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4440 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.4450 | Submittal | 14 | 2027-12-18 | 2028-01-02
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3960 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3970 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3980 | Submittal | 14 | 2028-01-01 | 2028-01-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Fire Suppression | QP.E.ME.MBL.GEN.3930 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3940 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Electrical | QP.E.ME.MBL.GEN.3950 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Fire Suppression | QP.E.ME.MBL.GEN.3810 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3820 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Electrical | QP.E.ME.MBL.GEN.3830 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4400 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4410 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4420 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4340 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4350 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4360 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4520 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4530 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4540 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4640 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4650 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4660 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3870 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3880 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3890 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3840 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3850 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3860 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.4550 | Submittal | 21 | 2028-02-08 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4560 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.4570 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 3, 4 & 5 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 3, 4 & 5 | QP.E.FA.GEN.GEN.1460 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 1 & 2 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 1 & 2 | QP.E.FA.GEN.GEN.2180 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Loft and Lobby | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Loft and Lobby | QP.E.FA.GEN.GEN.2140 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | QP.E.FA.GEN.GEN.2160 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Blades | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Blades | QP.E.FA.GEN.GEN.1820 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Lobby and Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Lobby and Loft | QP.E.FA.GEN.GEN.1770 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Above Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Above Loft | QP.E.FA.GEN.GEN.1780 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Blades | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Blades | QP.E.FA.GEN.GEN.1890 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Main Building | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Main Building | QP.E.FA.GEN.GEN.2230 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Facade | Facade | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 1 | QP.E.FA.GEN.GEN.1920 | Submittal | 28 | 2026-09-29 | 2026-10-31
Shop Drawings | Facade | Facade | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 2 | QP.E.FA.GEN.GEN.1930 | Submittal | 28 | 2026-08-26 | 2026-09-28
Shop Drawings | Facade | Facade | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 3 | QP.E.FA.GEN.GEN.1940 | Submittal | 28 | 2026-05-17 | 2026-06-21
Shop Drawings | Facade | Facade | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 4 | QP.E.FA.GEN.GEN.1950 | Submittal | 28 | 2026-06-22 | 2026-07-23
Shop Drawings | Facade | Facade | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 5 | QP.E.FA.GEN.GEN.1960 | Submittal | 28 | 2026-07-25 | 2026-08-25
Shop Drawings | Facade | Facade | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Facade ¦ Amphitheatre | QP.E.FA.GEN.GEN.2240 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Lobby | Lobby | Lobby | Lobby | Shop Drawings ¦ Facade ¦ Lobby | QP.E.FA.GEN.GEN.2090 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | Loft | Loft | Loft | Loft | Shop Drawings ¦ Facade ¦ Loft | QP.E.FA.GEN.GEN.2100 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Above Loft | Above Loft | Above Loft | Above Loft | Shop Drawings ¦ Facade ¦ Above Loft | QP.E.FA.GEN.GEN.1910 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | Link Bridges | Link Bridges | Link Bridges | Link Bridges | Shop Drawings ¦ Facade ¦ Link Bridges | QP.E.FA.GEN.GEN.2050 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Facade | Facade | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Shop Drawings ¦ Facade ¦ Facade Lighting Fixtures | QP.E.FA.GEN.GEN.1450 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | GRC Cladding | GRC Cladding | GRC Cladding | GRC Cladding | Shop Drawings ¦ Facade ¦ GRC Cladding | QP.E.FA.GEN.GEN.1390 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 1 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 1 | QP.E.CV.MBL.GEN.3060 | Submittal | 28 | 2026-08-06 | 2026-09-07
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 2 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 2 | QP.E.CV.MBL.GEN.3560 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 3 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 3 | QP.E.CV.MBL.GEN.3580 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 4 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 4 | QP.E.CV.MBL.GEN.3600 | Submittal | 28 | 2027-01-03 | 2027-02-03
Shop Drawings | External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Shop Drawings ¦ External Works ¦ Waterproofing for External Works | QP.E.EX.GEN.GEN.1040 | Submittal | 28 | 2026-06-25 | 2026-07-27
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Excavation | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Excavation | QP.E.CV.MBL.GEN.3320 | Submittal | 28 | 2027-01-06 | 2027-02-07
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Blinding Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Blinding Including Embedded Items | QP.E.CV.MBL.GEN.3500 | Submittal | 28 | 2027-02-23 | 2027-03-29
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Foundation Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Foundation Including Embedded Items | QP.E.CV.MBL.GEN.3480 | Submittal | 28 | 2027-04-13 | 2027-05-19
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Structural Concrete Works Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Structural Concrete Works Including Embedded Items | QP.E.CV.MBL.GEN.3520 | Submittal | 28 | 2027-06-03 | 2027-07-05
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4000 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Finishing | Finishing | Finishing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Finishing | QP.E.AF.MBL.GEN.4030 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4010 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Doors / Openings | QP.E.AF.MBL.GEN.4020 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Fire Suppression | QP.E.ME.MBL.GEN.1690 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Plumbing | Plumbing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Plumbing | QP.E.ME.MBL.GEN.1700 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.1710 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Electrical | Electrical | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Electrical | QP.E.ME.MBL.GEN.1720 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ ELV (Low Current System) | QP.E.ME.MBL.GEN.1730 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | External Utilities | Irrigation Works | Irrigation Works | Irrigation Works | Irrigation Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ Irrigation Works | QP.E.EX.GEN.GEN.1090 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Drainage Works | External Drainage Works | External Drainage Works | External Drainage Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Drainage Works | QP.E.EX.GEN.GEN.1110 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Lighting Works | External Lighting Works | External Lighting Works | External Lighting Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Lighting Works | QP.E.EX.GEN.GEN.1170 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | External Utilities | Low Current | Low Current | Low Current | Low Current | Shop Drawings ¦ External Works ¦ External Utilities ¦ Low Current | QP.E.EX.GEN.GEN.1100 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Shop Drawings ¦ External Works ¦ Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 | Submittal | 14 | 2027-08-07 | 2027-08-22
Shop Drawings | External Works | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Shop Drawings ¦ External Works ¦ Water and Environment | QP.E.EX.GEN.GEN.1220 | Submittal | 21 | 2026-11-23 | 2026-12-16
Shop Drawings | External Works | External Fixtures | External Fixtures | External Fixtures | External Fixtures | External Fixtures | Shop Drawings ¦ External Works ¦ External Fixtures | QP.E.EX.GEN.GEN.1260 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | External Works | LPG System | LPG System | LPG System | LPG System | LPG System | Shop Drawings ¦ External Works ¦ LPG System | QP.E.EX.GEN.GEN.1300 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Fit-out | Fit-out | Fit-out | Fit-out | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Fit-out | QP.C.PS.GEN.GEN.2590 | Submittal | 110 | 2026-07-30 | 2026-12-06
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Stage Engineering | Stage Engineering | Stage Engineering | Stage Engineering | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Stage Engineering | QP.C.PS.GEN.GEN.2560 | Submittal | 110 | 2026-12-07 | 2027-04-17
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | AV / Broadcast | AV / Broadcast | AV / Broadcast | AV / Broadcast | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ AV / Broadcast | QP.C.PS.GEN.GEN.1200 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ Technology (ICT) | QP.C.PS.GEN.GEN.1810 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Control Systems | Control Systems | Control Systems | Control Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Control Systems | QP.C.PS.GEN.GEN.1880 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Lighting Systems | Lighting Systems | Lighting Systems | Lighting Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Lighting Systems | QP.C.PS.GEN.GEN.1850 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Conveying System Finishes | QP.C.PS.GEN.GEN.2120 | Submittal | 150 | 2027-06-07 | 2027-11-29
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | HVAC System | HVAC System | HVAC System | HVAC System | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ HVAC System | QP.C.PS.GEN.GEN.2100 | Submittal | 90 | 2027-11-01 | 2028-02-13
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | ID Finishes | ID Finishes | ID Finishes | ID Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ ID Finishes | QP.C.PS.GEN.GEN.1930 | Submittal | 90 | 2027-07-18 | 2027-10-31
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Water Features | QP.C.PS.GEN.GEN.1960 | Submittal | 120 | 2027-02-16 | 2027-07-13
Shop Drawings | Provisional Sums | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | Shop Drawings ¦ Provisional Sums ¦ PS5 - Signage and Wayfinding | QP.C.PS.GEN.GEN.2140 | Submittal | 60 | 2028-07-29 | 2028-10-07
Shop Drawings | Provisional Sums | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | Shop Drawings ¦ Provisional Sums ¦ PS6 - Soft Landscaping | QP.C.PS.GEN.GEN.2180 | Submittal | 160 | 2027-08-30 | 2028-03-08
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Concrete Superstructure | QP.C.PS.GEN.GEN.2360 | Submittal | 30 | 2028-06-08 | 2028-07-12
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Foundation | Foundation | Foundation | Foundation | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Foundation | QP.C.PS.GEN.GEN.2260 | Submittal | 30 | 2028-05-01 | 2028-06-07
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Landscape | Landscape | Landscape | Landscape | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Landscape | QP.C.PS.GEN.GEN.2320 | Submittal | 30 | 2028-07-31 | 2028-09-03
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Promenade Bridge MEP | QP.C.PS.GEN.GEN.2340 | Submittal | 30 | 2028-06-26 | 2028-07-30
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Technology (ICT) | QP.C.PS.GEN.GEN.2400 | Submittal | 150 | 2027-04-11 | 2027-10-07
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Traffic & Car Parking | QP.C.PS.GEN.GEN.2500 | Submittal | 150 | 2027-07-12 | 2028-01-03

## Picklists
| #VALUE! |  | Numbering System Document - Metadata Mapping
DOCUMENT NUMBERING DROPDOWN ATTRIBUTES | [18 empty] | QIC GENERAL DROPDOWN ATTRIBUTES
FIELD 01 - PROJECT CODE |  | FIELD 02 - ORIGINATOR |  | FIELD 03 - CONTRACT REFERENCE |  | FIELD 04 - DOCUMENT TYPES |  | FIELD 05 - DISCIPLINE |  | FIELD 06 - AREA/ZONE |  | FIELD 07 - VENUE/BUILDING |  | FIELD 08 - SERIAL NUMBER |  |  |  |  | DOCUMENT DETAILS |  |  | SUITABILITY STATUS |  | NAP GENERAL DROPDOWN ATTRIBUTES
Ab. 01 | 1 - Project Name | Ab. 02 | 2 - Originator Name | Ab. 03 | 3 - Contract Reference | Ab. 04 | 4 - Document Type | Ab. 05 | 5 - Discipline | Ab. 06 | 6 - Area/Zone | Ab. 07 | 7 - Venue/Building | Ab. 08A | 8A - Drawing Type | Ab. 08B | 8B - Level | 8C - Sequence Number | Authoring Software | File/Exchange Format | Scope Area | Code | Status | Scale | Classification ID | Classification | Corporate Discipline | Author
QF01012 | Qiddaya Performing Arts Center | NES | Nesma and Partners | C04518 | Contract Number | AGD | Agenda | ACO | Acoustic | 00 | Overall | Z00000 | Overall | 0 | General (General Notes, Abbreviations, Legends, Single Line Diagrams, General Detail) | 00 | Non-Specific ( For Blade ) | 4 Digit Sequence Number For Drawings/Models | Revit | .rvt | Design Management | S0 (WIP) | Initial status or WIP | NTS | FI_60_25 | Drawing | Architectural | Nesma & Partners
[6 empty] | AVV | Agreed Value of Variation | ADM | Administration | 01 | Zone Sheet 1 | CENT01 | Center Block | 1 | Elevations (Vertical View) | B1 | Basement 1 - Parking A +900.50 | 3 Digit Sequence Number For Documents | Civil3D | .nwc | Architecture / LDC | S1 (Shared) | Suitable for Coordination | AS INDICATED | FI_90_75 | Schedule or table | Electrical | GINGGONG
[6 empty] | ASB | As Built | ARC | Architectural | 02 | Zone Sheet 2 | GARD01 | Guard House | 2 | Plans (Overall, Horizontal View, Floor Plan, Ceiling Plan, Site Plan, Loading Plan) | B2 | Basement 2 - Service +893.50 |  | MicrosoftWord | .nwd | Landscape | S2 (Shared) | Suitable for Information | 1:1 | FI_60_53 | Model | Façade | ALUTEC
[6 empty] | AUR | Audit Report | ADT | Area Development | 03 | Zone Sheet 3 | BLAD01 | Blade 01 | 3 | Sections (Sectional View, Wall Section, Riser) | B3 | Basement 3 - Promenade +887.750 |  | MicrosoftExcel | .ifc | Interior Design | S3 (Shared) | Suitable for Review and Comment | 1:2 | FI_60_15 | Clash Rendition | Fire & Life Safety | AFCO
[6 empty] | BOQ | Bill of Quantities | ASM | Assets Management | 04 | Zone Sheet 4 | BLAD02 | Blade 02 | 4 | Large-scale Views (Enlarged Details) (Plans, Elevations, Stair Sections, etc) | FL | Foundation level |  | Navisworks | .pdf | Signage & Wayfinding | S4 (Shared) | Suitable for Review and Authorisation | 1:5 | FI_40_10 | Calculations | Interior Design | DOKA
[6 empty] | BEP | BIM Execution Plan | AVL | Audio Visual | 05 | Zone Sheet 5 | BLAD03 | Blade 03 | 5 | Details (Any detail view, such as Wall / Floor / Manhole Detail, etc) | L1 | Lobby Level +905.0 |  | inDesign | .jpg | Public Interaction & Activation | S5 (Shared) | Suitable for Review and Acceptance | 1:10 | FI_90_72 | Report | Infrastructure | RAWABI
[6 empty] | BIM | BIM Model | AUV | Audio/Video | 06 | Zone Sheet 6 | BLAD04 | Blade 04 | 6 | Schedules and Diagrams | L2 | Theater Stalls +913.0 |  | Inviso | .xls | Structure | A1 (Published) | Authorised and Accepted-Concept Design | 1:20 | FI_10_90 | Transmittal | Landscape | Subcontractor - Façade Lighting
[6 empty] | BRF | Brief | BRG | Bridges | 07 | Zone Sheet 7 | BLAD05 | Blade 05 | 7 | Combination of different views | L3 | Stalles Mezz & AD Theater +917.5 |  | JPG | .xer | Geotechnical Engineering | A2 (Published) | Authorised and Accepted-Schematic Design 100% | 1:25 | FI_90_47 | Log | Mechanical | Subcontractor - AR / Vertical Transportation
[6 empty] | BUD | Budget | BRC | Broadcast | 08 | Zone Sheet 8 | MBLAD1 | Mini Blade 01 | 8 | User-Defined (For types that do not fall in other categories) | L4 | First Circle & AD Theater +921.0 |  | Recap | .dwf | Civil Engineering | A3 (Published) | Authorised and Accepted-Detailed Design 100% | 1:50 | FI_80_50 | Method statement | Structural | Subcontractor - Unassigned
[6 empty] | CAL | Calculation | BIM | Building Information Modelling | 09 | Zone Sheet 9 | MBLAD4 | Mini Blade 04 | 9 | 3D Representation (Isometric, Perspectives, Photographes) | L5 | Second Circle & Loft |  | Rhino | .dwg | MEP Engineering | A4 (Published) | Authorised and Accepted-Tender | 1:100 | FI_90_64 | Plan |  | Provisional Sum
[6 empty] | CER | Certificate | BMS | Building Management System | 10 | Zone Sheet 10 | SECE001 | SEC Room |  |  | L6 | SKY Garden +935.85 |  | Sketchup | .bcf | Fire & Life Safety | A5 (Published) | Authorised and Accepted-IFC | 1:150
[6 empty] | COR | Change Order | CWC | Chilled Water / Cooling | 11 | Zone Sheet 11 | PARK01 | Parking Building |  |  | L8 | Royal Majlis +948.10M |  | Autocad | .3ds | Pitch Design & Sports Playing Surfaces | A6 (Published) | Authorised and Accepted-Construction (Shop Drawing) | 1:200
[6 empty] | CRA | Change Request Authorization | CIV | Civil | 12 | Zone Sheet 12 |  |  |  |  | M1 | Mez Upper Lobby +909.0 |  | ArcGIS | .skp | Specialist Lighting (Services and Systems) | A7 (Published) | Authorised and Accepted-As Built | 1:250
[6 empty] | CDT | Clash Detection Report | CPM | Contracts & Procurement | 13 | Zone Sheet 13 |  |  |  |  | M2 | Mez Loft MEP +931.10 |  |  | .docx | Acoustics | A8(Published) | Authorised and Accepted-In Use | 1:300
[6 empty] | CLM | Claim | CIN | Controls & Instrumentation | 14 | Zone Sheet 14 |  |  |  |  | RL | Roof Level |  |  | .rvt,.nwd,.ifc | AV / Broadcast |  |  | 1:350
[6 empty] | CIN | Client Instruction | CRE | Creative Designer | 15 | Zone Sheet 15 |  |  |  |  | ZZ | Overall |  |  | .nwc,.nwd,.ifc | Security |  |  | 1:500
[6 empty] | CRS | Comments Resolution Sheet | CDM | Crowd Management | 16 | Zone Sheet 16 | [8 empty] | .dwg,.nwc,.ifc | Vertical Transport
[6 empty] | CON | Contract | CUL | Culvert | 17 | Zone Sheet 17 | [8 empty] | .docx,.pdf | Facade & Roof Envelope
[6 empty] | COS | Cost Estimate | DRN | Drainage | 18 | Zone Sheet 18 | [8 empty] | .xer,.pdf | Crowd Modelling / Pedestrian Flow
[6 empty] | DAB | Dashboard | ELP | Earthing & Lighting Protection | 19 | Zone Sheet 19 | [8 empty] | .xls,.pdf | Sustainability
[6 empty] | DOA | Delegation of Authority | ELE | Electrical | 20 | Zone Sheet 20 | [8 empty] | .msp,.pdf | Accessibility
[6 empty] | DES | Design | ELC | Electrical Containment | 21 | Zone Sheet 21 | [8 empty] | .dwg,.pdf | Architect of Record
[6 empty] | MTX | Distribution Matrix | ENV | Environmental | 22 | Zone Sheet 22 | [8 empty] | .indd | Food & Beverage & Operations
[6 empty] | DSS | Dossier | EQP | Equipment | 23 | Zone Sheet 23 | [8 empty] | .pdf, .indd | Utilities, Roads & Infrastructure
[6 empty] | DRW | Drawing | FAC | Facade | 24 | Zone Sheet 24 | [8 empty] | .rvt,.nwc,.ifc | Traffic & Car Parking
[6 empty] | ENI | Engineer Instruction | FED | Federated | 25 | Zone Sheet 25 | [8 empty] | .gdb | Technology (ICT)
[6 empty] | EXP | Expenses | FIN | Finance | 26 | Zone Sheet 26 | [9 empty] | Sports & Specialist Lighting
[6 empty] | HOC | Handover Certificate | FAE | Fire Alarm & Emergency Lighting | 27 | Zone Sheet 27 | [9 empty] | BMS & Access Control
[6 empty] | IRT | Incident Report | FLS | Fire Life Safety | 28 | Zone Sheet 28 | [9 empty] | Waste Management
[6 empty] | ITP | Inspection & Test Plan | FPR | Fire Protection | [11 empty] | Health & Safety in Design
[6 empty] | INS | Instruction | FFE | Furniture Fixture & Equipment | [11 empty] | Wind
[6 empty] | IAB | Insurance and Bonds | GEN | General
[6 empty] | INV | Invoice | GIS | Geospatial Information System
[6 empty] | LAR | Laydown Area Access Request | GEH | Geotechnical & Hydraulics
[6 empty] | LTR | Letter | GRA | Graphics
[6 empty] | LIC | License | HSE | Health and Safety
[6 empty] | LST | List | EHV | High Voltage
[6 empty] | MAN | Manual | HVC | HVAC
[6 empty] | MPL | Master Plan | ICT | Information & Communication Technology
[6 empty] | MAR | Material Approval Request | INF | Infrastructure
[6 empty] | MIR | Material Inspection Request | INS | Installation
[6 empty] | MST | Method Statement | ITS | Intelligent Transportation System
[6 empty] | MOM | Minutes of Meeting | INT | Interior Design
[6 empty] | MIX | Mix Design | IRR | Irrigation
[6 empty] | MOD | Model | KNL | Kitchen & Laundry
[6 empty] | MRP | Monthly Report | LSE | Landscape
[6 empty] | NOC | No Objection Certificate | ELL | Lighting
[6 empty] | NCR | Non-Conformance Report | LTC | Lighting Control
[6 empty] | NDA | Non-Disclosure Agreement | ELV | Low Voltage
[6 empty] | NTC | Notice | LPG | LPG
[6 empty] | OMM | Operation & Maintenance Manual | MAR | Marine Engineering
[6 empty] | ORC | Organizational Chart | MPL | Master Planning
[6 empty] | OTR | Overtime Request | MEC | Mechanical
[6 empty] | PAP | Payment Application | EMV | Medium Voltage
[6 empty] | PYC | Payment Certificate | MEP | MEPF
[6 empty] | PRM | Permit | NTD | Non-Technical Document
[6 empty] | PAF | Personnel Approval Form | OSE | Operating Supplies and Equipment
[6 empty] | PIV | Photographs, Images & Videos | OTH | Others
[6 empty] | PLN | Plan | PLB | Plumbing
[6 empty] | PLT | Plant | PTW | Potable Water
[6 empty] | PPG | Policy & Procedure | PJC | Project Control
[6 empty] | PQS | Prequalification Submittal | QMS | Quality Management
[6 empty] | PRE | Presentation | RID | Rides
[6 empty] | PRO | Procedure | ERL | Road Lighting
[6 empty] | PEP | Project Execution Plan | RKW | Rockwork
[6 empty] | PRS | Proposal | SEC | Security System
[6 empty] | POR | Purchase Order | SEW | Sewage
[6 empty] | REG | Register | SHW | Show
[6 empty] | REP | Report | SGN | Signage / Wayfinding
[6 empty] | RFC | Request For Change | ESP | Small Power
[6 empty] | RSM | Resume | SSC | Smart City
[6 empty] | SVR | Safety Violation Report | SPL | Specialist Lighting
[6 empty] | SMP | Sample | SWD | Storm Water Drainage
[6 empty] | SCH | Schedule | STR | Structural
[6 empty] | SDW | Shop Drawing | SUR | Surveying / Mapping
[6 empty] | SIN | Site Instruction | SUS | Sustainability
[6 empty] | SOR | Site Observation Report | TEL | Telecommunication
[6 empty] | SPE | Specification | TNC | Testing/Commissioning
[6 empty] | STD | Standard | TFC | Traffic System
[6 empty] | SFA | Statement of Final Account | UTI | Utilities
[6 empty] | STR | Strategy | VNT | Ventilation Ductwork
[6 empty] | TOC | Taking Over Certificate | VTR | Vertical Transportation
[6 empty] | TOR | Task Order | VES | Voice Evacuation
[6 empty] | TEM | Template | WSM | Waste Management
[6 empty] | TDC | Tender Document | WTR | Water
[6 empty] | TRP | Test Report | CTV | CCTV System
[6 empty] | TMS | Time Sheet | ACS | Access Control System
[6 empty] | VOR | Variation Order | EFL | Facade Lighting
[6 empty] | WAR | Warranty / Guarantees | DES | Diesel
[6 empty] | WRP | Weekly Report | SMK | Smoke Ductwork
[6 empty] | WIR | Work Inspection Request | STL | Steel Structure
[6 empty] | RLM | RedLine Mark Drawing | FWR | Formwork
[6 empty] | MDP | Master Information Delivery Plan | ELS | Emergency Lighting system
[6 empty] | TDP | Task Information Delivery Plan | EBW | Electrical Builder Works
[8 empty] | MBW | Mechanical Builder Works
[8 empty] | EBC | Electrical Busway