## TIDP_Sheet
TASK INFORMATION DELIVERY PLAN (TIDP)
CLIENT | Qiddiya | #VALUE!
PROJECT | Qiddiya Performing Arts Center (QPAC)
ORGANISATION | Nesma & Partners
DISCIPLINE | Architectural
APPROVER | BSBG
DATE CREATED
DATE LAST UPDATED
REVISION NUMBER | 00
DOCUMENT REFERENCE | QF01012-NES-C04518-TDP-ARC-00-000000-000001
This document shall be populated and kept up-to-date by the task team | [10 empty] | REFER TO THE FILE NAMING CONVENTION IN THE BIM EXECUTION PLAN | [10 empty] | DATA EXCHANGE #01 | [5 empty] | DATA EXCHANGE #02
[11 empty] | DOC REFERENCE GENERATOR | [10 empty] | STAGE: | CONSTRUCTION |  |  |  |  | STAGE: | HAND OVER
[22 empty] | PROGRAMME REF: | [5 empty] | PROGRAMME REF:
[5 empty] | EXCHANGE FORMATS | [5 empty] | FIELD 01 | FIELD 02 | FIELD 03 | FIELD 04 | FIELD 05 | FIELD 06 | FIELD 07 | FIELD 08 |  |  |  |  | LEVEL OF INFORMATION NEED | [5 empty] | LEVEL OF INFORMATION NEED
DOCUMENT NUMBER | DOCUMENT TITLE | EXTRACTED FROM MODEL | SCOPE AREA | AUTHORING SOFTWARE | EXCHANGE FORMAT | SCALE | DELIVERY MILESTONE | PACKAGE NAME | ACTIVITY ID | CLASSIFICATION CODE | PROJECT | ORIGINATOR | CONTRACT | DOCUMENT TYPE | DISCIPLINE | AREA/ZONE | VENUE/BUILDING | DRAWING TYPE | LEVEL | SEQUENCE NUMBER | CORPORATE DISCIPLINE | 01-AUTHOR | 01-GEOMETRICAL | 01-NON GEOMETRICAL | 01-DURATION (DAYS) | 01-PREDECESSOR | 01-EXCHANGE DATE | 02-AUTHOR | 02-GEOMETRICAL | 02-NON GEOMETRICAL | 02-DURATION (DAYS) | 02-PREDECESSOR | 02-EXCHANGE DATE
QF01012-NES-C04518-MOD-ARC-00-CENT01-0000001 | CENTRAL BUILDING |  | Architecture / LDC | Revit | .rvt,.nwc,.ifc | NTS |  | REVIT MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ARC | 00 | CENT01 | 0 | 00 | 0001 | Architectural | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-ARC-00-BLAD01-0000001 | BLADE 1 |  | Architecture / LDC | Revit | .rvt,.nwc,.ifc | NTS |  | REVIT MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ARC | 00 | BLAD01 | 0 | 00 | 0001 | Architectural | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-ARC-00-BLAD02-0000001 | BLADE 2 |  | Architecture / LDC | Revit | .rvt,.nwc,.ifc | NTS |  | REVIT MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ARC | 00 | BLAD02 | 0 | 00 | 0001 | Architectural | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-ARC-00-BLAD03-0000001 | BLADE 3 |  | Architecture / LDC | Revit | .rvt,.nwc,.ifc | NTS |  | REVIT MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ARC | 00 | BLAD03 | 0 | 00 | 0001 | Architectural | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-ARC-00-BLAD04-0000001 | BLADE 4 |  | Architecture / LDC | Revit | .rvt,.nwc,.ifc | NTS |  | REVIT MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ARC | 00 | BLAD04 | 0 | 00 | 0001 | Architectural | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-ARC-00-BLAD05-0000001 | BLADE 5 |  | Architecture / LDC | Revit | .rvt,.nwc,.ifc | NTS |  | REVIT MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ARC | 00 | BLAD05 | 0 | 00 | 0001 | Architectural | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-ARC-00-PARK01-0000001 | Parking |  | Architecture / LDC | Revit | .rvt,.nwc,.ifc | NTS |  | REVIT MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ARC | 00 | PARK01 | 0 | 00 | 0001 | Architectural | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-ARC-00-Z00000-0000001 | RAMPS & STAIRS |  | Architecture / LDC | Revit | .rvt,.nwc,.ifc | NTS |  | REVIT MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | ARC | 00 | Z00000 | 0 | 00 | 0001 | Architectural | Nesma & Partners | LOD400
QF01012-NES-C04518-MOD-VTR-00-Z00000-0000001 | VERTICAL TRANSPORTATION |  | Architecture / LDC | Revit | .rvt,.nwc,.ifc | NTS |  | REVIT MODEL |  | FI_60_53 | QF01012 | NES | C04518 | MOD | VTR | 00 | Z00000 | 0 | 00 | 0001 | Architectural | Nesma & Partners | LOD400
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31000 | B3 +887.75M - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-07-30 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1000 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B31001 | B3 +887.75M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B3 | 1001 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B31002 | B3 +887.75M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B3 | 1002 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B31003 | B3 +887.75M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B3 | 1003 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-11-CENT01-2B31004 | B3 +887.75M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 11 | CENT01 | 2 | B3 | 1004 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B21005 | B2 +893.50M - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-08-13 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B2 | 1005 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21006 | B2 +893.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1006 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21007 | B2 +893.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1007 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21008 | B2 +893.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1008 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-06-CENT01-2B21009 | B2 +893.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | B2 | 1009 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-06-CENT01-2B21010 | B2 +893.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | B2 | 1010 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B21011 | B2 +893.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B2 | 1011 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B21012 | B2 +893.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 7/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B2 | 1012 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B11013 | B1 +900.50M - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B1 | 1013 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11014 | B1 +900.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1014 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B11015 | B1 +900.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B1 | 1015 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B11016 | B1 +900.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B1 | 1016 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11017 | B1 +900.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1017 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-07-CENT01-2B11018 | B1 +900.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 07 | CENT01 | 2 | B1 | 1018 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B11019 | B1 +900.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B1 | 1019 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-09-CENT01-2B11020 | B1 +900.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 7/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 09 | CENT01 | 2 | B1 | 1020 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-00-PARK01-2B11021 | B1 PARKING - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | GENERAL ARRANGEMENT | QP.E.AF.PAR.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | PARK01 | 2 | B1 | 1021 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ARC-13-PARK01-2B11022 | B1 PARKING - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | GENERAL ARRANGEMENT | QP.E.AF.PAR.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 13 | PARK01 | 2 | B1 | 1022 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ARC-14-PARK01-2B11023 | B1 PARKING - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | GENERAL ARRANGEMENT | QP.E.AF.PAR.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 14 | PARK01 | 2 | B1 | 1023 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ARC-15-PARK01-2B11024 | B1 PARKING - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | GENERAL ARRANGEMENT | QP.E.AF.PAR.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 15 | PARK01 | 2 | B1 | 1024 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L11025 | L1 +905.00M - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 1025 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L11026 | L1 +905.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L1 | 1026 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L11027 | L1 +905.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L1 | 1027 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L11028 | L1 +905.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L1 | 1028 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11029 | L1 +905.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1029 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L11030 | L1 AMPHITHEATRE - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.4040 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 1030 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-02
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L11031 | L1 AMPHITHEATRE - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.4040 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L1 | 1031 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-02
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L11032 | L1 AMPHITHEATRE - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.4040 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L1 | 1032 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-02
QF01012-NES-C04518-SDW-ARC-11-CENT01-2L11033 | L1 AMPHITHEATRE - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.4040 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 11 | CENT01 | 2 | L1 | 1033 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-02
QF01012-NES-C04518-SDW-ARC-12-CENT01-2L11034 | L1 AMPHITHEATRE - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.4040 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 12 | CENT01 | 2 | L1 | 1034 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-02
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M11035 | M1 +909.00M - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M1 | 1035 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M11036 | M1 +909.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M1 | 1036 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M11037 | M1 +909.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M1 | 1037 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M11038 | M1 +909.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M1 | 1038 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M11039 | M1 +909.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M1 | 1039 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M11040 | M1 +909.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M1 | 1040 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M11041 | M1 +909.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M1 | 1041 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L21042 | L2 +913.00M - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-29 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L2 | 1042 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L21043 | L2 +913.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L2 | 1043 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L21044 | L2 +913.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L2 | 1044 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L21045 | L2 +913.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/6) | [5 empty] | 2026-10-29 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L2 | 1045 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L21046 | L2 +913.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/6) | [5 empty] | 2026-10-29 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L2 | 1046 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L21047 | L2 +913.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5/6) | [5 empty] | 2026-10-29 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L2 | 1047 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L21048 | L2 +913.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6/6) | [5 empty] | 2026-10-29 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L2 | 1048 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L31049 | L3 +917.50M - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1490 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L3 | 1049 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-09-16
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L31050 | L3 +917.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1490 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L3 | 1050 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-09-16
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L31051 | L3 +917.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1490 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L3 | 1051 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-09-16
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L31052 | L3 +917.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1490 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L3 | 1052 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-09-16
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L31053 | L3 +917.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1490 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L3 | 1053 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-09-16
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L31054 | L3 +917.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1490 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L3 | 1054 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-09-16
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L31055 | L3 +917.50M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1490 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L3 | 1055 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-09-16
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L41056 | L4 +921.00M - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L4 | 1056 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L41057 | L4 +921.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L4 | 1057 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L41058 | L4 +921.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L4 | 1058 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L41059 | L4 +921.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L4 | 1059 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L41060 | L4 +921.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L4 | 1060 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L41061 | L4 +921.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L4 | 1061 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L41062 | L4 +921.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L4 | 1062 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L51063 | L5 +928.00M - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L5 | 1063 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L51064 | L5 +928.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L5 | 1064 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L51065 | L5 +928.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L5 | 1065 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L51066 | L5 +928.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L5 | 1066 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L51067 | L5 +928.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L5 | 1067 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L51068 | L5 +928.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L5 | 1068 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L51069 | L5 +928.00M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L5 | 1069 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M21070 | M2+931.70M - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M2 | 1070 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M21071 | M2+931.70M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M2 | 1071 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M21072 | M2+931.70M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M2 | 1072 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M21073 | M2+931.70M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M2 | 1073 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M21074 | M2+931.70M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M2 | 1074 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M21075 | M2+931.70M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M2 | 1075 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M21076 | M2+931.70M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M2 | 1076 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L61077 | L6 +935.85M - GENERAL ARRANGEMENT MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L6 | 1077 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L61078 | L6 +935.85M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L6 | 1078 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L61079 | L6 +935.85M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L6 | 1079 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L61080 | L6 +935.85M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L6 | 1080 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L61081 | L6 +935.85M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L6 | 1081 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L61082 | L6 +935.85M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L6 | 1082 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L61083 | L6 +935.85M - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L6 | 1083 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L81084 | L8 +948.28M - GENERAL ARRANGEMENT ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1800 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L8 | 1084 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ARC-01-CENT01-2RL1085 | RL GENERAL ARRANGEMENT ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.1800 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | RL | 1085 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001000 | BL1 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | GENERAL ARRANGEMENT | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1000 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001001 | BL1 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | GENERAL ARRANGEMENT | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1001 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001002 | BL1 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | GENERAL ARRANGEMENT | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1002 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001003 | BL1 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | GENERAL ARRANGEMENT | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1003 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001004 | BL1 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | GENERAL ARRANGEMENT | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1004 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001005 | BL1 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | GENERAL ARRANGEMENT | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1005 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001006 | BL1 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | GENERAL ARRANGEMENT | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1006 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001007 | MINI BL1 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | GENERAL ARRANGEMENT | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1007 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001008 | MINI BL1 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | GENERAL ARRANGEMENT | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1008 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001009 | BL2 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | GENERAL ARRANGEMENT | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1009 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001010 | BL2 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | GENERAL ARRANGEMENT | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1010 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001011 | BL2 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | GENERAL ARRANGEMENT | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1011 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001012 | BL2 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | GENERAL ARRANGEMENT | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1012 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001013 | BL2 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | GENERAL ARRANGEMENT | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1013 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001014 | BL2 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | GENERAL ARRANGEMENT | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1014 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001015 | BL3 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1015 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001016 | BL3 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1016 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001017 | BL3 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | GENERAL ARRANGEMENT | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1017 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001018 | BL3 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | GENERAL ARRANGEMENT | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1018 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001019 | BL3 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | GENERAL ARRANGEMENT | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1019 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001020 | BL3 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | GENERAL ARRANGEMENT | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1020 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001021 | BL4 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1021 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001022 | BL4 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1022 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001023 | BL4 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1023 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001024 | BL4 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | GENERAL ARRANGEMENT | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1024 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001025 | BL4 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | GENERAL ARRANGEMENT | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1025 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001026 | BL4 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | GENERAL ARRANGEMENT | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1026 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001027 | BL4 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | GENERAL ARRANGEMENT | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1027 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-MBLAD2-2001028 | MINI BL4 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | GENERAL ARRANGEMENT | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD2 | 2 | 00 | 1028 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001029 | BL5 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | GENERAL ARRANGEMENT | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1029 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001030 | BL5 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | GENERAL ARRANGEMENT | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1030 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001031 | BL5 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | GENERAL ARRANGEMENT | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1031 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001032 | BL5 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | GENERAL ARRANGEMENT | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1032 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001033 | BL5 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | GENERAL ARRANGEMENT | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1033 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001034 | BL5 - GENERAL ARRANGEMENT ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | GENERAL ARRANGEMENT | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1034 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-GARD01-2001035 | GUARDHOUSE - GENERAL ARRANGEMENT ENLARGED PLANS & ELEVATIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-14 | GENERAL ARRANGEMENT | QP.E.EX.GEN.GEN.1270 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | GARD01 | 2 | 00 | 1035 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ARC-00-SECE01-2001036 | MRMU ROOM - GENERAL ARRANGEMENT ENLARGED PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-14 | GENERAL ARRANGEMENT | QP.E.EX.GEN.GEN.1270 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | SECE01 | 2 | 00 | 1036 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ARC-00-SECE01-2001037 | MRMU ROOM - ELEVATIONS & SECTIONS | [5 empty] | 2027-01-14 | GENERAL ARRANGEMENT | QP.E.EX.GEN.GEN.1270 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | SECE01 | 2 | 00 | 1037 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ARC-00-Z00000-2005000 | TUNNELS & RAMPS - GENERAL ARRANGEMENT ENLARGED PLANS (SHEET1/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.4000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 5000 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-ARC-00-Z00000-2005001 | TUNNELS & RAMPS - GENERAL ARRANGEMENT ENLARGED PLANS (SHEET2/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.4000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 5001 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-ARC-00-Z00000-2005002 | TUNNELS & RAMPS - GENERAL ARRANGEMENT ENLARGED PLANS (SHEET3/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.4000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 5002 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-ARC-00-Z00000-2005003 | TUNNELS & RAMPS - GENERAL ARRANGEMENT ENLARGED PLANS (SHEET4/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.4000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 5003 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-ARC-00-Z00000-2005004 | TUNNELS & RAMPS - GENERAL ARRANGEMENT ENLARGED PLANS (SHEET5/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | GENERAL ARRANGEMENT | QP.E.AF.MBL.GEN.4000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 5004 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31100 | B3 +887.75M - CMU MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-07-30 | CMU PLANS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1100 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B31101 | B3 +887.75M - CMU ENLARGED PLAN (Sheet1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | CMU PLANS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B3 | 1101 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B31102 | B3 +887.75M - CMU ENLARGED PLAN (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | CMU PLANS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B3 | 1102 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B31103 | B3 +887.75M - CMU ENLARGED PLAN (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | CMU PLANS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B3 | 1103 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-11-CENT01-2B31104 | B3 +887.75M - CMU ENLARGED PLAN (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | CMU PLANS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 11 | CENT01 | 2 | B3 | 1104 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B21105 | B2 +893.50M - CMU MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-08-13 | CMU PLANS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B2 | 1105 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21106 | B2 +893.50M - CMU ENLARGED PLAN (Sheet 1/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | CMU PLANS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1106 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21107 | B2 +893.50M - CMU ENLARGED PLAN (Sheet 2/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | CMU PLANS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1107 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B21108 | B2 +893.50M - CMU ENLARGED PLAN (Sheet 3/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | CMU PLANS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B2 | 1108 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21109 | B2 +893.50M - CMU ENLARGED PLAN (Sheet 4/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | CMU PLANS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1109 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B21110 | B2 +893.50M - CMU ENLARGED PLAN (Sheet 5/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | CMU PLANS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B2 | 1110 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-09-CENT01-2B21111 | B2 +893.50M - CMU ENLARGED PLAN (Sheet 6/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | CMU PLANS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 09 | CENT01 | 2 | B2 | 1111 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-11-CENT01-2B21112 | B2 +893.50M - CMU ENLARGED PLAN (Sheet 7/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | CMU PLANS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 11 | CENT01 | 2 | B2 | 1112 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B11113 | B1 +900.50M - CMU MASTER PLAN MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-03 | CMU PLANS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B1 | 1113 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11114 | B1 +900.50M - CMU ENLARGED PLAN (Sheet 1/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | CMU PLANS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1114 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B11115 | B1 +900.50M - CMU ENLARGED PLAN (Sheet 2/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | CMU PLANS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B1 | 1115 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B11116 | B1 +900.50M - CMU ENLARGED PLAN (Sheet 3/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | CMU PLANS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B1 | 1116 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11117 | B1 +900.50M - CMU ENLARGED PLAN (Sheet 4/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | CMU PLANS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1117 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B11119 | B1 +900.50M - CMU ENLARGED PLAN (Sheet 5/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | CMU PLANS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B1 | 1119 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-00-PARK01-2B11121 | B1 PARKING - CMU MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | CMU PLANS | QP.E.AF.PAR.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | PARK01 | 2 | B1 | 1121 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ARC-13-PARK01-2B11122 | B1 PARKING - CMU ENLARGED PLAN (Sheet 1/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | CMU PLANS | QP.E.AF.PAR.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 13 | PARK01 | 2 | B1 | 1122 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ARC-14-PARK01-2B11123 | B1 PARKING - CMU ENLARGED PLAN (Sheet 2/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | CMU PLANS | QP.E.AF.PAR.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 14 | PARK01 | 2 | B1 | 1123 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ARC-15-PARK01-2B11124 | B1 PARKING - CMU ENLARGED PLAN (Sheet 3/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | CMU PLANS | QP.E.AF.PAR.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 15 | PARK01 | 2 | B1 | 1124 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L11125 | L1 +905.00M - CMU MASTER PLAN MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 1125 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L11126 | L1 +905.00M - CMU ENLARGED PLAN (Sheet 1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L1 | 1126 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L11127 | L1 +905.00M - CMU ENLARGED PLAN (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L1 | 1127 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L11128 | L1 +905.00M - CMU ENLARGED PLAN (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1128 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11129 | L1 +905.00M - CMU ENLARGED PLAN (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L1 | 1129 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M11130 | M1 +909.00M - CMU MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | CMU PLANS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M1 | 1130 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M11131 | M1 +909.00M - CMU ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | CMU PLANS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M1 | 1131 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M11132 | M1 +909.00M - CMU ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | CMU PLANS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M1 | 1132 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M11133 | M1 +909.00M - CMU ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | CMU PLANS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M1 | 1133 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M11134 | M1 +909.00M - CMU ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | CMU PLANS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M1 | 1134 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M11135 | M1 +909.00M - CMU ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | CMU PLANS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M1 | 1135 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M11136 | M1 +909.00M - CMU ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | CMU PLANS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M1 | 1136 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L21137 | L2 +913.00M - CMU MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-29 | CMU PLANS | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L2 | 1137 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L21138 | L2 +913.00M - CMU ENLARGED PLAN (Sheet 1/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | CMU PLANS | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L2 | 1138 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L21139 | L2 +913.00M - CMU ENLARGED PLAN (Sheet 2/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | CMU PLANS | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L2 | 1139 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L31144 | L3 +917.50M - CMU MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | CMU PLANS | QP.E.AF.MBL.GEN.1490 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L3 | 1144 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-09-16
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L31145 | L3 +917.50M - CMU ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | CMU PLANS | QP.E.AF.MBL.GEN.1490 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L3 | 1145 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-09-16
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L31146 | L3 +917.50M - CMU ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | CMU PLANS | QP.E.AF.MBL.GEN.1490 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L3 | 1146 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-09-16
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L41151 | L4 +921.00M - CMU MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | CMU PLANS | QP.E.AF.MBL.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L4 | 1151 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L41152 | L4 +921.00M - CMU ENLARGED PLAN (Sheet 1/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | CMU PLANS | QP.E.AF.MBL.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L4 | 1152 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L41153 | L4 +921.00M - CMU ENLARGED PLAN (Sheet 2/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | CMU PLANS | QP.E.AF.MBL.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L4 | 1153 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-12
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L51158 | L5 +928.00M - CMU MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L5 | 1158 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L51159 | L5 +928.00M - CMU ENLARGED PLAN (Sheet 1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L5 | 1159 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L51160 | L5 +928.00M - CMU ENLARGED PLAN (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L5 | 1160 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L51162 | L5 +928.00M - CMU ENLARGED PLAN (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L5 | 1162 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L51163 | L5 +928.00M - CMU ENLARGED PLAN (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1670 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L5 | 1163 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-12
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M21165 | M2+931.70M - CMU MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M2 | 1165 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M21166 | M2+931.70M - CMU ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M2 | 1166 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M21167 | M2+931.70M - CMU ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M2 | 1167 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M21168 | M2+931.70M - CMU ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M2 | 1168 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M21169 | M2+931.70M - CMU ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M2 | 1169 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M21170 | M2+931.70M - CMU ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M2 | 1170 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M21171 | M2+931.70M - CMU ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.MBL.GEN.1760 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M2 | 1171 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-11
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L61172 | L6 +935.85M - CMU MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | CMU PLANS | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L6 | 1172 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L61173 | L6 +935.85M - CMU ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | CMU PLANS | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L6 | 1173 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L61174 | L6 +935.85M - CMU ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | CMU PLANS | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L6 | 1174 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L61175 | L6 +935.85M - CMU ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | CMU PLANS | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L6 | 1175 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L61176 | L6 +935.85M - CMU ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | CMU PLANS | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L6 | 1176 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L61177 | L6 +935.85M - CMU ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | CMU PLANS | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L6 | 1177 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L61178 | L6 +935.85M - CMU ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | CMU PLANS | QP.E.AF.MBL.GEN.1880 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L6 | 1178 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L81179 | L8 +948.28M - CMU ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | CMU PLANS | QP.E.AF.MBL.GEN.1800 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L8 | 1179 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ARC-01-CENT01-2RL1180 | RL CMU ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | CMU PLANS | QP.E.AF.MBL.GEN.1800 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | RL | 1180 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001100 | BL1 - CMU ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | CMU PLANS | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1100 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001101 | BL1 - CMU ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | CMU PLANS | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1101 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001102 | BL1 - CMU ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | CMU PLANS | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1102 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001103 | BL1 - CMU ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | CMU PLANS | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1103 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001104 | BL1 - CMU ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 |  | CMU PLANS | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1104 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001105 | BL1 - CMU ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | CMU PLANS | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1105 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001106 | BL1 - CMU ENLARGED PLAN (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | CMU PLANS | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1106 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001107 | MINI BL1 - CMU ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | CMU PLANS | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1107 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001108 | MINI BL1 - CMU ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | CMU PLANS | QP.E.AF.BL1.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1108 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001109 | BL2 - CMU ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | CMU PLANS | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1109 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001110 | BL2 - CMU ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | CMU PLANS | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1110 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001111 | BL2 - CMU ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | CMU PLANS | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1111 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001112 | BL2 - CMU ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | CMU PLANS | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1112 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001113 | BL2 - CMU ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | CMU PLANS | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1113 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001114 | BL2 - CMU ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | CMU PLANS | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1114 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001115 | BL3 - CMU ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1115 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001116 | BL3 - CMU ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1116 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001117 | BL3 - CMU ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | CMU PLANS | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1117 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001118 | BL3 - CMU ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | CMU PLANS | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1118 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001119 | BL3 - CMU ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | CMU PLANS | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1119 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001120 | BL3 - CMU ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | CMU PLANS | QP.E.AF.BL3.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1120 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001121 | BL4 - CMU ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | CMU PLANS | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1121 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001122 | BL4 - CMU ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | CMU PLANS | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1122 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001123 | BL4 - CMU ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | CMU PLANS | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1123 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001124 | BL4 - CMU ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | CMU PLANS | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1124 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001125 | BL4 - CMU ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | CMU PLANS | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1125 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001126 | BL4 - CMU ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | CMU PLANS | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1126 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001127 | BL4 - CMU ENLARGED PLAN (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | CMU PLANS | QP.E.AF.BL4.GEN.1820 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1127 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-22
QF01012-NES-C04518-SDW-ARC-00-MBLAD2-2001128 | MINI BL4 - CMU ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | CMU PLANS | QP.E.AF.BL2.GEN.1580 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD2 | 2 | 00 | 1128 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-27
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001129 | BL5 - CMU ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | CMU PLANS | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1129 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001130 | BL5 - CMU ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | CMU PLANS | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1130 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001131 | BL5 - CMU ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | CMU PLANS | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1131 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001132 | BL5 - CMU ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | CMU PLANS | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1132 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001133 | BL5 - CMU ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | CMU PLANS | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1133 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001134 | BL5 - CMU ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | CMU PLANS | QP.E.AF.BL5.GEN.1130 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1134 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-GARD01-2001135 | GUARDHOUSE - CMU ENLARGED PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-14 | CMU PLANS | QP.E.EX.GEN.GEN.1270 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | GARD01 | 2 | 00 | 1135 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ARC-00-SECE01-2001136 | MRMU ROOM - CMU ENLARGED PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-14 | CMU PLANS | QP.E.EX.GEN.GEN.1270 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | SECE01 | 2 | 00 | 1136 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31200 | B3 +887.75M - CMU ENLARGED ELEVATIONS (Sheet 1/8) | [5 empty] | 2026-07-30 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1200 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31201 | B3 +887.75M - CMU ENLARGED ELEVATIONS (Sheet 2/8) | [5 empty] | 2026-07-30 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1201 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31202 | B3 +887.75M - CMU ENLARGED ELEVATIONS (Sheet 3/8) | [5 empty] | 2026-07-30 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1202 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31203 | B3 +887.75M - CMU ENLARGED ELEVATIONS (Sheet 4/8) | [5 empty] | 2026-07-30 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1203 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31204 | B3 +887.75M - CMU ENLARGED ELEVATIONS (Sheet 5/8) | [5 empty] | 2026-07-30 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1204 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31205 | B3 +887.75M - CMU ENLARGED ELEVATIONS (Sheet 6/8) | [5 empty] | 2026-07-30 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1205 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31206 | B3 +887.75M - CMU ENLARGED ELEVATIONS (Sheet 7/8) | [5 empty] | 2026-07-30 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1206 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31207 | B3 +887.75M - CMU ENLARGED ELEVATIONS (Sheet 8/8) | [5 empty] | 2026-07-30 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1207 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B21208 | B2 +893.50M - CMU ENLARGED ELEVATIONS - OVERALL KEY PLAN | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B2 | 1208 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21209 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 1/5) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1209 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21210 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 2/5) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1210 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21211 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 3/5) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1211 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21212 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 4/5) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1212 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21213 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 5/5) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1213 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21214 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 1/7) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1214 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21215 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 2/7) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1215 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21216 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 3/7) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1216 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21217 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 4/7) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1217 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21218 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 5/7) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1218 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21219 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 6/7) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1219 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21220 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 7/7) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1220 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B21221 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 1/4) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B2 | 1221 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B21222 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 2/4) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B2 | 1222 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B21223 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 3/4) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B2 | 1223 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B21224 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 4/4) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B2 | 1224 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21225 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 1/11) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1225 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21226 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 2/11) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1226 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21227 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 3/11) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1227 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21228 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 4/11) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1228 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21229 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 5/11) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1229 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21230 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 6/11) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1230 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21231 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 7/11) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1231 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21232 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 8/11) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1232 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21233 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 9/11) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1233 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21234 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 10/11) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1234 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21235 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 11/11) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1235 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B21236 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART8 (Sheet 1/3) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B2 | 1236 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B21237 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART8 (Sheet 2/3) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B2 | 1237 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B21238 | B2 +893.50M - CMU ENLARGED ELEVATIONS - PART8 (Sheet 3/3) | [5 empty] | 2026-08-13 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B2 | 1238 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B11239 | B1 +900.50M - CMU ENLARGED ELEVATIONS - OVERALL KEY PLAN | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B1 | 1239 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11240 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 1/5) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1240 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11241 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 2/5) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1241 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11242 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 3/5) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1242 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11243 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 4/5) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1243 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11244 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 5/5) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1244 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B11245 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 1/3) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B1 | 1245 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B11246 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 2/3) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B1 | 1246 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B11247 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 3/3) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B1 | 1247 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B11248 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 1/6) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B1 | 1248 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B11249 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 2/6) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B1 | 1249 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B11250 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 3/6) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B1 | 1250 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B11251 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 4/6) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B1 | 1251 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B11252 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 5/6) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B1 | 1252 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B11253 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 6/6) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B1 | 1253 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11254 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 1/11) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1254 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11255 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 2/11) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1255 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11256 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 3/11) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1256 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11257 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 4/11) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1257 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11258 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 5/11) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1258 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11259 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 6/11) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1259 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11260 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 7/11) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1260 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11261 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 8/11) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1261 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11262 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 9/11) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1262 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11263 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 10/11) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1263 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11264 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 11/11) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1264 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B11265 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART8 (Sheet 1/3) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B1 | 1265 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B11266 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART8 (Sheet 2/3) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B1 | 1266 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B11267 | B1 +900.50M - CMU ENLARGED ELEVATIONS - PART8 (Sheet 3/3) | [5 empty] | 2026-09-03 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1220 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B1 | 1267 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-06-10
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L11268 | L1 +905.00M - CMU ENLARGED ELEVATIONS - OVERALL KEY PLAN | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 1268 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L11269 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 1/1) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L1 | 1269 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L11270 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 1/2) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L1 | 1270 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L11271 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 2/2) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L1 | 1271 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L11272 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 1/1) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L1 | 1272 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11273 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 1/8) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1273 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11274 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 2/8) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1274 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11275 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 3/8) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1275 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11276 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 4/8) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1276 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11277 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 5/8) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1277 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11278 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 6/8) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1278 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11279 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 7/8) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1279 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11280 | L1 +905.00M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 8/8) | [5 empty] | 2026-09-24 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1310 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1280 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-05
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M11281 | M1+909.00M - CMU ENLARGED ELEVATIONS - OVERALL KEY PLAN | [5 empty] | 2026-10-08 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M1 | 1281 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M11282 | M1+909.00M - CMU ENLARGED ELEVATIONS - PART1 (Sheet 1/1) | [5 empty] | 2026-10-08 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M1 | 1282 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M11283 | M1+909.00M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 1/2) | [5 empty] | 2026-10-08 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M1 | 1283 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M11284 | M1+909.00M - CMU ENLARGED ELEVATIONS - PART2 (Sheet 2/2) | [5 empty] | 2026-10-08 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M1 | 1284 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M11285 | M1+909.00M - CMU ENLARGED ELEVATIONS - PART4 (Sheet 1/1) | [5 empty] | 2026-10-08 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M1 | 1285 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M11286 | M1+909.00M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 1/2) | [5 empty] | 2026-10-08 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M1 | 1286 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M11287 | M1+909.00M - CMU ENLARGED ELEVATIONS - PART5 (Sheet 2/2) | [5 empty] | 2026-10-08 | CMU ENLARGED ELEVATIONS | QP.E.AF.MBL.GEN.1400 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M1 | 1287 | Architectural | Nesma & Partners |  |  |  |  | 2026-07-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31400 | B3 +887.75M - DRYWALL PARTITIONS MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-07-30 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1400 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B31401 | B3 +887.75M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B3 | 1401 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B31402 | B3 +887.75M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B3 | 1402 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B31403 | B3 +887.75M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B3 | 1403 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-11-CENT01-2B31404 | B3 +887.75M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1090 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 11 | CENT01 | 2 | B3 | 1404 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B21405 | B2 +893.50M - DRYWALL PARTITIONS MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-08-13 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B2 | 1405 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21406 | B2 +893.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1406 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21407 | B2 +893.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1407 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B21408 | B2 +893.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B2 | 1408 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21409 | B2 +893.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1409 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B21410 | B2 +893.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B2 | 1410 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-09-CENT01-2B21411 | B2 +893.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 09 | CENT01 | 2 | B2 | 1411 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-11-CENT01-2B21412 | B2 +893.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 7/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 11 | CENT01 | 2 | B2 | 1412 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B11413 | B1 +900.50M - DRYWALL PARTITIONS MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-03 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B1 | 1413 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11414 | B1 +900.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1414 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B11415 | B1 +900.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B1 | 1415 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B11416 | B1 +900.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B1 | 1416 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11417 | B1 +900.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1417 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L11421 | L1 +905.00M - DRYWALL PARTITIONS MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 1421 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L11422 | L1 +905.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L1 | 1422 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L11423 | L1 +905.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L1 | 1423 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L11424 | L1 +905.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L1 | 1424 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11425 | L1 +905.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1425 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M11426 | M1 +909.00M - DRYWALL PARTITIONS MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M1 | 1426 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M11427 | M1 +909.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M1 | 1427 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M11428 | M1 +909.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M1 | 1428 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M11429 | M1 +909.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M1 | 1429 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M11430 | M1 +909.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M1 | 1430 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M11431 | M1 +909.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M1 | 1431 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M11432 | M1 +909.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M1 | 1432 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L21433 | L2 +913.00M - DRYWALL PARTITIONS MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-29 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L2 | 1433 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L21434 | L2 +913.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L2 | 1434 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L21435 | L2 +913.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L2 | 1435 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L21436 | L2 +913.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L2 | 1436 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L21437 | L2 +913.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L2 | 1437 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L21438 | L2 +913.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L2 | 1438 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L21439 | L2 +913.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1000 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L2 | 1439 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-08-23
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L31440 | L3 +917.50M - DRYWALL PARTITIONS MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L3 | 1440 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L31441 | L3 +917.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L3 | 1441 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L31442 | L3 +917.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L3 | 1442 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L31443 | L3 +917.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L3 | 1443 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L31444 | L3 +917.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L3 | 1444 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L31445 | L3 +917.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L3 | 1445 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L31446 | L3 +917.50M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L3 | 1446 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L41447 | L4 +921.00M - DRYWALL PARTITIONS MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L4 | 1447 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L41448 | L4 +921.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L4 | 1448 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L41449 | L4 +921.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L4 | 1449 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L41450 | L4 +921.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L4 | 1450 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L41451 | L4 +921.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L4 | 1451 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L41452 | L4 +921.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L4 | 1452 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L41453 | L4 +921.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L4 | 1453 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L51454 | L5 +928.00M - DRYWALL PARTITIONS MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L5 | 1454 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L51455 | L5 +928.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L5 | 1455 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L51456 | L5 +928.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L5 | 1456 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L51457 | L5 +928.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L5 | 1457 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L51458 | L5 +928.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L5 | 1458 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L51459 | L5 +928.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L5 | 1459 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L51460 | L5 +928.00M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L5 | 1460 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M21461 | M2+931.70M - DRYWALL PARTITIONS MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M2 | 1461 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M21462 | M2+931.70M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M2 | 1462 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M21463 | M2+931.70M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M2 | 1463 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M21464 | M2+931.70M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M2 | 1464 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M21465 | M2+931.70M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M2 | 1465 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M21466 | M2+931.70M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M2 | 1466 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M21467 | M2+931.70M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M2 | 1467 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L61468 | L6 +935.85M - DRYWALL PARTITIONS MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L6 | 1468 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L61469 | L6 +935.85M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L6 | 1469 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L61470 | L6 +935.85M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L6 | 1470 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L61471 | L6 +935.85M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L6 | 1471 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L61472 | L6 +935.85M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L6 | 1472 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L61473 | L6 +935.85M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L6 | 1473 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L61474 | L6 +935.85M - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L6 | 1474 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L81475 | L8 +948.28M - DRYWALL PARTITIONS ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L8 | 1475 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-01-CENT01-2RL1476 | RL DRYWALL PARTITIONS ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | DRYWALL PARTITIONS PLANS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | RL | 1476 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001400 | BL1 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1400 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001401 | BL1 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1401 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001402 | BL1 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1402 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001403 | BL1 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1403 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001404 | BL1 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1404 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001405 | BL1 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1405 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001406 | BL1 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1406 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001407 | MINI BL1 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1407 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001408 | MINI BL1 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1408 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001409 | BL2 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1409 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001410 | BL2 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1410 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001411 | BL2 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1411 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001412 | BL2 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1412 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001413 | BL2 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1413 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001414 | BL2 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1414 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001415 | BL3 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1415 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001416 | BL3 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1416 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001417 | BL3 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1417 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001418 | BL3 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1418 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001419 | BL3 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1419 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001420 | BL3 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1420 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001421 | BL4 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1421 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001422 | BL4 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1422 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001423 | BL4 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1423 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001424 | BL4 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1424 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001425 | BL4 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1425 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001426 | BL4 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1426 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001427 | BL4 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1427 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-MBLAD2-2001428 | MINI BL4 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD2 | 2 | 00 | 1428 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001429 | BL5 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1429 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001430 | BL5 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1430 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001431 | BL5 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1431 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001432 | BL5 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1432 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001433 | BL5 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1433 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001434 | BL5 - DRYWALL PARTITIONS ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | DRYWALL PARTITIONS PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1434 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31500 | B3 +887.75M - REFLECTED CEILING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-07-30 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1500 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B31501 | B3 +887.75M - REFLECTED CEILING ENLARGED PLAN (Sheet1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B3 | 1501 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B31502 | B3 +887.75M - REFLECTED CEILING ENLARGED PLAN (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B3 | 1502 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B31503 | B3 +887.75M - REFLECTED CEILING ENLARGED PLAN (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B3 | 1503 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-11-CENT01-2B31504 | B3 +887.75M - REFLECTED CEILING ENLARGED PLAN (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 11 | CENT01 | 2 | B3 | 1504 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B21505 | B2 +893.50M - REFLECTED CEILING MASTER PLAN | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B2 | 1505 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21506 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 1/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1506 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21507 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 2/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1507 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21508 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 3/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1508 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21509 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 4/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1509 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21510 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 5/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1510 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21511 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 6/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1511 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B21512 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 7/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B2 | 1512 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B21513 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 8/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B2 | 1513 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21514 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 9/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1514 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21515 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 10/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1515 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B21516 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 11/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B2 | 1516 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21517 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 12/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1517 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21518 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 13/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1518 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B21519 | B2 +893.50M - REFLECTED CEILING ENLARGED PLAN (Sheet 14/14) | [5 empty] | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B2 | 1519 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B11513 | B1 +900.50M - REFLECTED CEILING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-03 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B1 | 1513 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11514 | B1 +900.50M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1514 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B11515 | B1 +900.50M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B1 | 1515 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B11516 | B1 +900.50M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1516 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11517 | B1 +900.50M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | B1 | 1517 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B11519 | B1 +900.50M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B1 | 1519 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-PARK01-2B11521 | B1 PARKING - REFLECTED CEILING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | REFLECTED CEILING PLANS | QP.E.AF.PAR.GEN.1020 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | PARK01 | 2 | B1 | 1521 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-13-PARK01-2B11522 | B1 PARKING - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | REFLECTED CEILING PLANS | QP.E.AF.PAR.GEN.1020 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 13 | PARK01 | 2 | B1 | 1522 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-14-PARK01-2B11523 | B1 PARKING - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | REFLECTED CEILING PLANS | QP.E.AF.PAR.GEN.1020 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 14 | PARK01 | 2 | B1 | 1523 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-15-PARK01-2B11524 | B1 PARKING - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | REFLECTED CEILING PLANS | QP.E.AF.PAR.GEN.1020 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 15 | PARK01 | 2 | B1 | 1524 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L11525 | L1 +905.00M - REFLECTED CEILING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 1525 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L11526 | L1 +905.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L1 | 1526 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L11527 | L1 +905.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L1 | 1527 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11528 | L1 +905.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1528 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L11529 | L1 +905.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L1 | 1529 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M11530 | M1 +909.00M - REFLECTED CEILING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M1 | 1530 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M11531 | M1 +909.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M1 | 1531 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M11532 | M1 +909.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M1 | 1532 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M11533 | M1 +909.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M1 | 1533 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M11534 | M1 +909.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M1 | 1534 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M11535 | M1 +909.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M1 | 1535 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M11536 | M1 +909.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M1 | 1536 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L21537 | L2 +913.00M - REFLECTED CEILING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-29 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L2 | 1537 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L21538 | L2 +913.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L2 | 1538 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L21539 | L2 +913.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L2 | 1539 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L21540 | L2 +913.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L2 | 1540 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L21541 | L2 +913.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L2 | 1541 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L21542 | L2 +913.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L2 | 1542 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L21543 | L2 +913.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L2 | 1543 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L31544 | L3 +917.50M - REFLECTED CEILING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L3 | 1544 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L31545 | L3 +917.50M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L3 | 1545 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L31546 | L3 +917.50M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L3 | 1546 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L31547 | L3 +917.50M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L3 | 1547 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L31548 | L3 +917.50M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L3 | 1548 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L31549 | L3 +917.50M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L3 | 1549 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L31550 | L3 +917.50M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L3 | 1550 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L41551 | L4 +921.00M - REFLECTED CEILING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L4 | 1551 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L41552 | L4 +921.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L4 | 1552 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L41553 | L4 +921.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L4 | 1553 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L41554 | L4 +921.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L4 | 1554 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L41555 | L4 +921.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L4 | 1555 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L41556 | L4 +921.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L4 | 1556 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L41557 | L4 +921.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L4 | 1557 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L51558 | L5 +928.00M - REFLECTED CEILING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L5 | 1558 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L51559 | L5 +928.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L5 | 1559 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L51560 | L5 +928.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L5 | 1560 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L51561 | L5 +928.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L5 | 1561 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L51562 | L5 +928.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L5 | 1562 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L51563 | L5 +928.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L5 | 1563 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L51564 | L5 +928.00M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L5 | 1564 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M21565 | M2+931.70M - REFLECTED CEILING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M2 | 1565 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M21566 | M2+931.70M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M2 | 1566 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M21567 | M2+931.70M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M2 | 1567 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M21568 | M2+931.70M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M2 | 1568 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M21569 | M2+931.70M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M2 | 1569 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M21570 | M2+931.70M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M2 | 1570 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M21571 | M2+931.70M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M2 | 1571 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L61572 | L6 +935.85M - REFLECTED CEILING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L6 | 1572 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L61573 | L6 +935.85M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L6 | 1573 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L61574 | L6 +935.85M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L6 | 1574 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L61575 | L6 +935.85M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L6 | 1575 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L61576 | L6 +935.85M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L6 | 1576 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L61577 | L6 +935.85M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L6 | 1577 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L61578 | L6 +935.85M - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L6 | 1578 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L81579 | L8 +948.28M - REFLECTED CEILING ENLARGED PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L8 | 1579 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-01-CENT01-2RL1580 | RL REFLECTED CEILING ENLARGED PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | RL | 1580 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001500 | BL1 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | REFLECTED CEILING PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1500 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001501 | BL1 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | REFLECTED CEILING PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1501 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001502 | BL1 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | REFLECTED CEILING PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1502 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001503 | BL1 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | REFLECTED CEILING PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1503 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001504 | BL1 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | REFLECTED CEILING PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1504 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001505 | BL1 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | REFLECTED CEILING PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1505 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001506 | BL1 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | REFLECTED CEILING PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1506 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001507 | MINI BL1 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | REFLECTED CEILING PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1507 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001508 | MINI BL1 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | REFLECTED CEILING PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1508 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001509 | BL2 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | REFLECTED CEILING PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1509 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001510 | BL2 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | REFLECTED CEILING PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1510 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001511 | BL2 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | REFLECTED CEILING PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1511 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001512 | BL2 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | REFLECTED CEILING PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1512 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001513 | BL2 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | REFLECTED CEILING PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1513 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001514 | BL2 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | REFLECTED CEILING PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1514 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001515 | BL3 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1515 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001516 | BL3 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1516 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001517 | BL3 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | REFLECTED CEILING PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1517 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001518 | BL3 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | REFLECTED CEILING PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1518 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001519 | BL3 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | REFLECTED CEILING PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1519 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001520 | BL3 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | REFLECTED CEILING PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1520 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001521 | BL4 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | REFLECTED CEILING PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1521 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001522 | BL4 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | REFLECTED CEILING PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1522 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001523 | BL4 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | REFLECTED CEILING PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1523 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001524 | BL4 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | REFLECTED CEILING PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1524 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001525 | BL4 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | REFLECTED CEILING PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1525 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001526 | BL4 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | REFLECTED CEILING PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1526 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001527 | BL4 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | REFLECTED CEILING PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1527 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-MBLAD2-2001528 | MINI BL4 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD2 | 2 | 00 | 1528 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001529 | BL5 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1529 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001530 | BL5 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1530 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001531 | BL5 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | REFLECTED CEILING PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1531 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001532 | BL5 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | REFLECTED CEILING PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1532 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001533 | BL5 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | REFLECTED CEILING PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1533 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001534 | BL5 - REFLECTED CEILING ENLARGED PLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | REFLECTED CEILING PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1534 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-GARD01-2001535 | GUARDHOUSE - REFLECTED CEILING ENLARGED PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-14 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | GARD01 | 2 | 00 | 1535 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-SECE01-2001536 | MRMU ROOM - REFLECTED CEILING ENLARGED PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-14 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | SECE01 | 2 | 00 | 1536 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001537 | TUNNELS & RAMPS - REFLECTED CEILING ENLARGED PLANS (SHEET1/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1537 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001538 | TUNNELS & RAMPS - REFLECTED CEILING ENLARGED PLANS (SHEET2/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1538 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001539 | TUNNELS & RAMPS - REFLECTED CEILING ENLARGED PLANS (SHEET3/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1539 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001540 | TUNNELS & RAMPS - REFLECTED CEILING ENLARGED PLANS (SHEET4/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1540 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001541 | TUNNELS & RAMPS - REFLECTED CEILING ENLARGED PLANS (SHEET5/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | REFLECTED CEILING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1541 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31600 | B3 +887.75M - FLOOR & FINISHES MASTER PLAN - BOH AREA - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-07-30 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1600 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B31601 | B3 +887.75M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B3 | 1601 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B31602 | B3 +887.75M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B3 | 1602 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B31603 | B3 +887.75M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B3 | 1603 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-11-CENT01-2B31604 | B3 +887.75M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 11 | CENT01 | 2 | B3 | 1604 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B21605 | B2 +893.50M - FLOOR & FINISHES MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-08-13 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B2 | 1605 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21606 | B2 +893.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1606 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21607 | B2 +893.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2/) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1607 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21608 | B2 +893.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1608 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-06-CENT01-2B21609 | B2 +893.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | B2 | 1609 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-07-CENT01-2B21610 | B2 +893.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 07 | CENT01 | 2 | B2 | 1610 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B21611 | B2 +893.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B2 | 1611 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-11-CENT01-2B21612 | B2 +893.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 7/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 11 | CENT01 | 2 | B2 | 1612 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B11613 | B1 +900.50M - FLOOR FINISHES MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-03 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B1 | 1613 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11614 | B1 +900.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1614 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B11615 | B1 +900.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B1 | 1615 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11616 | B1 +900.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1616 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-06-CENT01-2B11617 | B1 +900.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | B1 | 1617 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-07-CENT01-2B11618 | B1 +900.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 07 | CENT01 | 2 | B1 | 1618 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B11619 | B1 +900.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B1 | 1619 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-09-CENT01-2B11620 | B1 +900.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 7/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 09 | CENT01 | 2 | B1 | 1620 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-PARK01-2B11621 | B1 PARKING - FLOOR FINISHES MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | PARK01 | 2 | B1 | 1621 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-13-PARK01-2B11622 | B1 PARKING - FLOOR FINISHES ENLARGED PLAN - BOH AREA (Sheet 1/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 13 | PARK01 | 2 | B1 | 1622 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-14-PARK01-2B11623 | B1 PARKING - FLOOR FINISHES ENLARGED PLAN - BOH AREA (Sheet 2/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 14 | PARK01 | 2 | B1 | 1623 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-15-PARK01-2B11624 | B1 PARKING - FLOOR FINISHES ENLARGED PLAN - BOH AREA (Sheet 3/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 15 | PARK01 | 2 | B1 | 1624 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L11625 | L1 +905.00M - FLOOR FINISHES MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 1625 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L11626 | L1 +905.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L1 | 1626 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L11627 | L1 +905.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L1 | 1627 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11628 | L1 +905.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1628 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L11629 | L1 +905.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L1 | 1629 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M11630 | M1 +909.00M - FLOOR FINISHES MASTER |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M1 | 1630 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M11631 | M1 +909.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M1 | 1631 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M11632 | M1 +909.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M1 | 1632 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M11633 | M1 +909.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M1 | 1633 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M11634 | M1 +909.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M1 | 1634 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M11635 | M1 +909.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M1 | 1635 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M11636 | M1 +909.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M1 | 1636 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L21637 | L2 +913.00M - FLOOR FINISHES MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-29 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L2 | 1637 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L21638 | L2 +913.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L2 | 1638 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L21639 | L2 +913.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L2 | 1639 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L21640 | L2 +913.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L2 | 1640 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L21641 | L2 +913.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L2 | 1641 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L21642 | L2 +913.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L2 | 1642 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L21643 | L2 +913.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L2 | 1643 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L31644 | L3 +917.50M - FLOOR FINISHES MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L3 | 1644 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L31645 | L3 +917.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L3 | 1645 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L31646 | L3 +917.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L3 | 1646 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L31647 | L3 +917.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L3 | 1647 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L31648 | L3 +917.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L3 | 1648 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L31649 | L3 +917.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L3 | 1649 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L31650 | L3 +917.50M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L3 | 1650 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L41651 | L4 +921.00M - FLOOR FINISHES MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L4 | 1651 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L41652 | L4 +921.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L4 | 1652 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L41653 | L4 +921.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L4 | 1653 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L41654 | L4 +921.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L4 | 1654 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L41655 | L4 +921.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L4 | 1655 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L41656 | L4 +921.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L4 | 1656 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L41657 | L4 +921.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L4 | 1657 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L51658 | L5 +928.00M - FLOOR FINISHES MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L5 | 1658 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L51659 | L5 +928.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L5 | 1659 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L51660 | L5 +928.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L5 | 1660 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L51661 | L5 +928.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L5 | 1661 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L51662 | L5 +928.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L5 | 1662 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L51663 | L5 +928.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L5 | 1663 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L51664 | L5 +928.00M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L5 | 1664 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M21665 | M2+931.70M - FLOOR FINISHES MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M2 | 1665 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M21666 | M2+931.70M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M2 | 1666 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M21667 | M2+931.70M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M2 | 1667 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M21668 | M2+931.70M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M2 | 1668 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M21669 | M2+931.70M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M2 | 1669 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M21670 | M2+931.70M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M2 | 1670 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M21671 | M2+931.70M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M2 | 1671 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L61672 | L6 +935.85M - FLOOR FINISHES MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L6 | 1672 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L61673 | L6 +935.85M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L6 | 1673 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L61674 | L6 +935.85M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L6 | 1674 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L61675 | L6 +935.85M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L6 | 1675 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L61676 | L6 +935.85M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L6 | 1676 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L61677 | L6 +935.85M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L6 | 1677 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L61678 | L6 +935.85M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L6 | 1678 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L81679 | L8 +948.28M - FLOOR FINISHES ENLARGEDPLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L8 | 1679 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-01-CENT01-2RL1680 | RL FLOOR FINISHES ENLARGEDPLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | RL | 1680 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001600 | BL1 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FLOOR FINISHES PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1600 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001601 | BL1 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FLOOR FINISHES PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1601 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001602 | BL1 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FLOOR FINISHES PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1602 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001603 | BL1 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FLOOR FINISHES PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1603 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001604 | BL1 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FLOOR FINISHES PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1604 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001605 | BL1 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FLOOR FINISHES PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1605 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001606 | BL1 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FLOOR FINISHES PLANS | QP.E.AF.BL1.GEN.1140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1606 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-23
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001607 | MINI BL1 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1607 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001608 | MINI BL1 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1608 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001609 | BL2 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FLOOR FINISHES PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1609 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001610 | BL2 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FLOOR FINISHES PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1610 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001611 | BL2 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FLOOR FINISHES PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1611 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001612 | BL2 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FLOOR FINISHES PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1612 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001613 | BL2 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FLOOR FINISHES PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1613 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001614 | BL2 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FLOOR FINISHES PLANS | QP.E.AF.BL2.GEN.1110 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1614 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-07
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001615 | BL3 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1615 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001616 | BL3 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1616 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001617 | BL3 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FLOOR FINISHES PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1617 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001618 | BL3 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | FLOOR FINISHES PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1618 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001619 | BL3 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | FLOOR FINISHES PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1619 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001620 | BL3 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | FLOOR FINISHES PLANS | QP.E.AF.BL3.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1620 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-24
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001621 | BL4 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FLOOR FINISHES PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1621 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001622 | BL4 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FLOOR FINISHES PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1622 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001623 | BL4 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FLOOR FINISHES PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1623 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001624 | BL4 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FLOOR FINISHES PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1624 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001625 | BL4 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FLOOR FINISHES PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1625 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001626 | BL4 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FLOOR FINISHES PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1626 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001627 | BL4 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FLOOR FINISHES PLANS | QP.E.AF.BL4.GEN.1240 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1627 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-MBLAD2-2001628 | MINI BL4 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD2 | 2 | 00 | 1628 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001629 | BL5 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FLOOR FINISHES PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1629 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001630 | BL5 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FLOOR FINISHES PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1630 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001631 | BL5 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FLOOR FINISHES PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1631 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001632 | BL5 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FLOOR FINISHES PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1632 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001633 | BL5 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FLOOR FINISHES PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1633 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001634 | BL5 - FLOOR FINISHES ENLARGEDPLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FLOOR FINISHES PLANS | QP.E.AF.BL5.GEN.2340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1634 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-13
QF01012-NES-C04518-SDW-ARC-00-GARD01-2001635 | GUARDHOUSE - FLOOR FINISHES ENLARGEDPLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | GARD01 | 2 | 00 | 1635 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-SECE01-2001636 | MRMU ROOM - FLOOR FINISHES ENLARGEDPLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | SECE01 | 2 | 00 | 1636 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001637 | TUNNELS & RAMPS - FLOOR FINISHES ENLARGED PLAN - BOH AREA S (SHEET 1/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1637 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001638 | TUNNELS & RAMPS - FLOOR FINISHES ENLARGED PLAN - BOH AREA S (SHEET 2/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1638 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001639 | TUNNELS & RAMPS - FLOOR FINISHES ENLARGED PLAN - BOH AREA S (SHEET 3/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1639 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001640 | TUNNELS & RAMPS - FLOOR FINISHES ENLARGED PLAN - BOH AREA S (SHEET 4/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1640 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001641 | TUNNELS & RAMPS - FLOOR FINISHES ENLARGED PLAN - BOH AREA S (SHEET 5/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | FLOOR FINISHES PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1641 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31700 | B3 +887.75M - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-07-30 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1700 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B31701 | B3 +887.75M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B3 | 1701 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B31702 | B3 +887.75M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B3 | 1702 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B31703 | B3 +887.75M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B3 | 1703 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-11-CENT01-2B31704 | B3 +887.75M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 11 | CENT01 | 2 | B3 | 1704 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-10-10
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B21705 | B2 +893.50M - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-08-13 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B2 | 1705 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21706 | B2 +893.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1706 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21707 | B2 +893.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1707 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21708 | B2 +893.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1708 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-06-CENT01-2B21709 | B2 +893.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | B2 | 1709 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-07-CENT01-2B21710 | B2 +893.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 07 | CENT01 | 2 | B2 | 1710 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B21711 | B2 +893.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B2 | 1711 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-11-CENT01-2B21712 | B2 +893.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 7/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 11 | CENT01 | 2 | B2 | 1712 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B11713 | B1 +900.50M - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-03 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B1 | 1713 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11714 | B1 +900.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1714 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B11715 | B1 +900.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B1 | 1715 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11716 | B1 +900.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1716 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-06-CENT01-2B11717 | B1 +900.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | B1 | 1717 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-07-CENT01-2B11718 | B1 +900.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 07 | CENT01 | 2 | B1 | 1718 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B11719 | B1 +900.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B1 | 1719 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-09-CENT01-2B11720 | B1 +900.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 7/7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 09 | CENT01 | 2 | B1 | 1720 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-PARK01-2B11721 | B1 PARKING - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | PARK01 | 2 | B1 | 1721 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-13-PARK01-2B11722 | B1 PARKING - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 13 | PARK01 | 2 | B1 | 1722 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-14-PARK01-2B11723 | B1 PARKING - WALL LINLING & FINISHINGS ENLARGED PLAN - BOH AREA (Sheet 2/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 14 | PARK01 | 2 | B1 | 1723 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-15-PARK01-2B11724 | B1 PARKING - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 15 | PARK01 | 2 | B1 | 1724 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L11725 | L1 +905.00M - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 1725 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L11726 | L1 +905.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L1 | 1726 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L11727 | L1 +905.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L1 | 1727 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11728 | L1 +905.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1728 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L11729 | L1 +905.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L1 | 1729 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M11730 | M1 +909.00M - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M1 | 1730 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M11731 | M1 +909.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M1 | 1731 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M11732 | M1 +909.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M1 | 1732 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M11733 | M1 +909.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M1 | 1733 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M11734 | M1 +909.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M1 | 1734 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M11735 | M1 +909.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M1 | 1735 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M11736 | M1 +909.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M1 | 1736 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L21737 | L2 +913.00M - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-29 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L2 | 1737 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L21738 | L2 +913.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L2 | 1738 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L21739 | L2 +913.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L2 | 1739 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L21740 | L2 +913.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L2 | 1740 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L21741 | L2 +913.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L2 | 1741 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L21742 | L2 +913.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L2 | 1742 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L21743 | L2 +913.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L2 | 1743 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L31744 | L3 +917.50M - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L3 | 1744 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L31745 | L3 +917.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L3 | 1745 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L31746 | L3 +917.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L3 | 1746 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L31747 | L3 +917.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L3 | 1747 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L31748 | L3 +917.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L3 | 1748 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L31749 | L3 +917.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L3 | 1749 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L31750 | L3 +917.50M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L3 | 1750 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L41751 | L4 +921.00M - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L4 | 1751 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L41752 | L4 +921.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L4 | 1752 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L41753 | L4 +921.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L4 | 1753 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L41754 | L4 +921.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L4 | 1754 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L41755 | L4 +921.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L4 | 1755 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L41756 | L4 +921.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L4 | 1756 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L41757 | L4 +921.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L4 | 1757 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L51758 | L5 +928.00M - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L5 | 1758 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L51759 | L5 +928.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L5 | 1759 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L51760 | L5 +928.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L5 | 1760 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L51761 | L5 +928.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L5 | 1761 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L51762 | L5 +928.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L5 | 1762 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L51763 | L5 +928.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L5 | 1763 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L51764 | L5 +928.00M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L5 | 1764 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M21765 | M2+931.70M - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M2 | 1765 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M21766 | M2+931.70M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M2 | 1766 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M21767 | M2+931.70M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M2 | 1767 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M21768 | M2+931.70M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M2 | 1768 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M21769 | M2+931.70M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M2 | 1769 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M21770 | M2+931.70M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M2 | 1770 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M21771 | M2+931.70M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M2 | 1771 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L61772 | L6 +935.85M - WALL LINLING & FINISHING MASTER PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L6 | 1772 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L61773 | L6 +935.85M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L6 | 1773 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L61774 | L6 +935.85M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L6 | 1774 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L61775 | L6 +935.85M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L6 | 1775 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L61776 | L6 +935.85M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L6 | 1776 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L61777 | L6 +935.85M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L6 | 1777 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L61778 | L6 +935.85M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1910 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L6 | 1778 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L81779 | L8 +948.28M - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L8 | 1779 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-01-CENT01-2RL1780 | RL WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | RL | 1780 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001700 | BL1 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1700 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001701 | BL1 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1701 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001702 | BL1 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1702 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001703 | BL1 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1703 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001704 | BL1 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1704 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001705 | BL1 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1705 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001706 | BL1 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1706 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001707 | MINI BL1 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1707 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001708 | MINI BL1 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL1.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1708 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-16
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001709 | BL2 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1709 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001710 | BL2 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1710 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001711 | BL2 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1711 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001712 | BL2 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1712 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001713 | BL2 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1713 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001714 | BL2 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL2.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1714 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-01
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001715 | BL3 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1715 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001716 | BL3 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1716 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001717 | BL3 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1717 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001718 | BL3 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1718 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001719 | BL3 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1719 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001720 | BL3 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL3.GEN.1370 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1720 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-03
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001721 | BL4 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1721 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001722 | BL4 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1722 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001723 | BL4 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1723 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001724 | BL4 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1724 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001725 | BL4 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1725 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001726 | BL4 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1726 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001727 | BL4 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL4.GEN.1850 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1727 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-MBLAD2-2001728 | MINI BL4 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL4.GEN.1210 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD2 | 2 | 00 | 1728 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-23
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001729 | BL5 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1729 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001730 | BL5 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1730 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001731 | BL5 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1731 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001732 | BL5 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1732 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001733 | BL5 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1733 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001734 | BL5 - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL LINLING & FINISHING PLANS | QP.E.AF.BL5.GEN.1160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1734 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-09
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001735 | TUNNELS & RAMPS - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA S (SHEET1/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.4030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1735 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-24
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001736 | TUNNELS & RAMPS - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA S (SHEET2/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.4030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1736 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-24
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001737 | TUNNELS & RAMPS - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA S (SHEET3/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.4030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1737 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-24
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001738 | TUNNELS & RAMPS - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA S (SHEET4/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.4030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1738 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-24
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001739 | TUNNELS & RAMPS - WALL LINLING & FINISHING ENLARGED PLAN - BOH AREA S (SHEET5/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-03-04 | WALL LINLING & FINISHING PLANS | QP.E.AF.MBL.GEN.4030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1739 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31800 | B3 +887.75M - WATERPROOFING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-07-30 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1800 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B21801 | B2 +893.50M - WATERPROOFING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-08-13 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B2 | 1801 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B11802 | B1 +900.50M - WATERPROOFING MASTER PLAN (SHEET 1/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B1 | 1802 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-PARK01-2B11803 | B1 PARKING - WATERPROOFING MASTER PLAN (SHEET 2/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | PARK01 | 2 | B1 | 1803 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L11804 | L1 +905.00M - WATERPROOFING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 1804 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L11805 | L1 AMPHITHEATRE - WATERPROOFING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 1805 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M11806 | M1 +909.00M - WATERPROOFING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M1 | 1806 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L21807 | L2 +913.00M - WATERPROOFING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-29 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L2 | 1807 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L31808 | L3 +917.50M - WATERPROOFING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L3 | 1808 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L41809 | L4 +921.00M - WATERPROOFING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L4 | 1809 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L51810 | L5 +928.00M - WATERPROOFING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L5 | 1810 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M21811 | M2+931.70M - WATERPROOFING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M2 | 1811 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L61812 | L6 +935.85M - WATERPROOFING MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L6 | 1812 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L81813 | L8 +948.28M - WATERPROOFING ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L8 | 1813 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-01-CENT01-2RL1814 | RL WATERPROOFING ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | RL | 1814 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001815 | BL1 - WATERPROOFING ENLARGED PLAN (Sheet 1/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:150 | 2026-10-08 | WATERPROOFING PLANS | QP.E.AF.BL1.GEN.6100 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1815 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-02
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001816 | BL1 - WATERPROOFING ENLARGED PLAN (Sheet 2/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:150 | 2026-10-08 | WATERPROOFING PLANS | QP.E.AF.BL1.GEN.6100 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1816 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-02
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001817 | MINI BL1 - WATERPROOFING ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:150 | 2027-01-14 | WATERPROOFING PLANS | QP.E.AF.BL1.GEN.6100 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1817 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-02
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001818 | BL2 - WATERPROOFING ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:150 | 2026-09-17 | WATERPROOFING PLANS | QP.E.AF.BL2.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1818 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-02
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001819 | BL3 - WATERPROOFING ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:150 | 2026-09-24 | WATERPROOFING PLANS | QP.E.AF.BL3.GEN.6140 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1819 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-11-10
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001820 | BL4 - WATERPROOFING ENLARGED PLAN (Sheet 1/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:150 | 2026-11-19 | WATERPROOFING PLANS | QP.E.AF.BL4.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1820 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001821 | BL4 - WATERPROOFING ENLARGED PLAN (Sheet 2/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:150 | 2026-11-19 | WATERPROOFING PLANS | QP.E.AF.BL4.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1821 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-ARC-00-MBLAD2-2001822 | MINI BL4 - WATERPROOFING ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:150 | 2026-11-26 | WATERPROOFING PLANS | QP.E.AF.BL4.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD2 | 2 | 00 | 1822 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001823 | BL5 - WATERPROOFING ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:150 | 2026-10-29 | WATERPROOFING PLANS | QP.E.AF.BL5.GEN.6180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1823 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001824 | TUNNELS & RAMPS - WATERPROOFING ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:150 | 2027-03-04 | WATERPROOFING PLANS | QP.E.AF.MBL.GEN.6060 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1824 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B31900 | B3 +887.75M - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-07-30 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1100 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B3 | 1900 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-28
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B31901 | B3 +887.75M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet1/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1100 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B3 | 1901 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-28
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B31902 | B3 +887.75M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1100 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B3 | 1902 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-28
QF01012-NES-C04518-SDW-ARC-07-CENT01-2B31903 | B3 +887.75M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-07-30 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1100 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 07 | CENT01 | 2 | B3 | 1903 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-28
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B21905 | B2 +893.50M - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-08-13 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B2 | 1905 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-16
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B21906 | B2 +893.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 1906 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-16
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B21907 | B2 +893.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 1907 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-16
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B21908 | B2 +893.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B2 | 1908 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-16
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B21909 | B2 +893.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B2 | 1909 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-16
QF01012-NES-C04518-SDW-ARC-07-CENT01-2B21910 | B2 +893.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 07 | CENT01 | 2 | B2 | 1910 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-16
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B21911 | B2 +893.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B2 | 1911 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-16
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B11913 | B1 +900.50M - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-03 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1230 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B1 | 1913 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-16
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B11914 | B1 +900.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1230 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 1914 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-16
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B11915 | B1 +900.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1230 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B1 | 1915 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-16
QF01012-NES-C04518-SDW-ARC-04-CENT01-2B11916 | B1 +900.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1230 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | B1 | 1916 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-16
QF01012-NES-C04518-SDW-ARC-05-CENT01-2B11917 | B1 +900.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1230 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | B1 | 1917 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-16
QF01012-NES-C04518-SDW-ARC-08-CENT01-2B11919 | B1 +900.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1230 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 08 | CENT01 | 2 | B1 | 1919 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-16
QF01012-NES-C04518-SDW-ARC-00-PARK01-2B11921 | B1 PARKING - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.5200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | PARK01 | 2 | B1 | 1921 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-01
QF01012-NES-C04518-SDW-ARC-13-PARK01-2B11922 | B1 PARKING - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.5200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 13 | PARK01 | 2 | B1 | 1922 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-01
QF01012-NES-C04518-SDW-ARC-14-PARK01-2B11923 | B1 PARKING - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.5200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 14 | PARK01 | 2 | B1 | 1923 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-01
QF01012-NES-C04518-SDW-ARC-15-PARK01-2B11924 | B1 PARKING - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3/3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.5200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 15 | PARK01 | 2 | B1 | 1924 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-01
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L11925 | L1 +905.00M - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1320 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 1925 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-24
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L11928 | L1 +905.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1320 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L1 | 1928 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-24
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L11929 | L1 +905.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1320 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L1 | 1929 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M11930 | M1 +909.00M - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1410 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M1 | 1930 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M11931 | M1 +909.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1410 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M1 | 1931 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M11932 | M1 +909.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1410 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M1 | 1932 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M11933 | M1 +909.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1410 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M1 | 1933 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M11934 | M1 +909.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1410 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M1 | 1934 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M11935 | M1 +909.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1410 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M1 | 1935 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M11936 | M1 +909.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1410 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M1 | 1936 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L21937 | L2 +913.00M - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-29 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L2 | 1937 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L21938 | L2 +913.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L2 | 1938 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L21939 | L2 +913.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L2 | 1939 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L21940 | L2 +913.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L2 | 1940 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L21941 | L2 +913.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L2 | 1941 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L21942 | L2 +913.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L2 | 1942 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L21943 | L2 +913.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L2 | 1943 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L31944 | L3 +917.50M - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1500 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L3 | 1944 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L31945 | L3 +917.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1500 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L3 | 1945 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-10
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L31946 | L3 +917.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1500 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L3 | 1946 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-10
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L31947 | L3 +917.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1500 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L3 | 1947 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-10
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L31948 | L3 +917.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1500 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L3 | 1948 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-10
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L31949 | L3 +917.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1500 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L3 | 1949 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-10
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L31950 | L3 +917.50M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1500 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L3 | 1950 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-10
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L41951 | L4 +921.00M - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1590 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L4 | 1951 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L41952 | L4 +921.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1590 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L4 | 1952 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L41953 | L4 +921.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1590 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L4 | 1953 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L41954 | L4 +921.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1590 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L4 | 1954 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L41955 | L4 +921.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1590 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L4 | 1955 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L41956 | L4 +921.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1590 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L4 | 1956 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L41957 | L4 +921.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1590 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L4 | 1957 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L51958 | L5 +928.00M - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L5 | 1958 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-18
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L51959 | L5 +928.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L5 | 1959 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-18
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L51960 | L5 +928.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L5 | 1960 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-18
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L51961 | L5 +928.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L5 | 1961 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-18
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L51962 | L5 +928.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L5 | 1962 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-18
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L51963 | L5 +928.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L5 | 1963 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-18
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L51964 | L5 +928.00M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L5 | 1964 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-18
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M21965 | M2+931.70M - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1770 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M2 | 1965 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-12
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M21966 | M2+931.70M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1770 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M2 | 1966 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-12
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M21967 | M2+931.70M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1770 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M2 | 1967 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-12
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M21968 | M2+931.70M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1770 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M2 | 1968 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-12
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M21969 | M2+931.70M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1770 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M2 | 1969 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-12
QF01012-NES-C04518-SDW-ARC-05-CENT01-2M21970 | M2+931.70M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1770 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | M2 | 1970 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-12
QF01012-NES-C04518-SDW-ARC-06-CENT01-2M21971 | M2+931.70M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1770 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | M2 | 1971 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-12
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L61972 | L6 +935.85M - WALL PROTECTION & STEEL LADDER MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1890 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L6 | 1972 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L61973 | L6 +935.85M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1890 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L6 | 1973 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L61974 | L6 +935.85M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1890 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L6 | 1974 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L61975 | L6 +935.85M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1890 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L6 | 1975 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L61976 | L6 +935.85M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1890 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L6 | 1976 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L61977 | L6 +935.85M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1890 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L6 | 1977 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ARC-06-CENT01-2L61978 | L6 +935.85M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6/6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1890 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 06 | CENT01 | 2 | L6 | 1978 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-10-07
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L81979 | L8 +948.28M - WALL PROTECTION & STEEL LADDER ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1810 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L8 | 1979 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-11-01
QF01012-NES-C04518-SDW-ARC-01-CENT01-2RL1980 | RL WALL PROTECTION & STEEL LADDER ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.1810 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | RL | 1980 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-11-01
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001900 | BL1 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL1.GEN.1660 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1900 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001901 | BL1 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL1.GEN.1660 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1901 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001902 | BL1 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL1.GEN.1660 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1902 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001903 | BL1 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL1.GEN.1660 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1903 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001904 | BL1 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL1.GEN.1660 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1904 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001905 | BL1 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL1.GEN.1660 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1905 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD01-2001906 | BL1 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL1.GEN.1660 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 2 | 00 | 1906 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-12
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001907 | MINI BL1 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL1.GEN.1660 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1907 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-12
QF01012-NES-C04518-SDW-ARC-00-MBLAD1-2001908 | MINI BL1 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL1.GEN.1660 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD1 | 2 | 00 | 1908 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-12
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001909 | BL2 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL2.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1909 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-02
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001910 | BL2 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL2.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1910 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-02
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001911 | BL2 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL2.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1911 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-02
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001912 | BL2 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL2.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1912 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-02
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001913 | BL2 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL2.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1913 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-02
QF01012-NES-C04518-SDW-ARC-00-BLAD02-2001914 | BL2 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL2.GEN.1680 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 2 | 00 | 1914 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-02
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001915 | BL3 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL3.GEN.1350 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1915 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-15
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001916 | BL3 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL3.GEN.1350 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1916 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-15
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001917 | BL3 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL3.GEN.1350 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1917 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-15
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001918 | BL3 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL3.GEN.1350 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1918 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-15
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001919 | BL3 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL3.GEN.1350 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1919 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-15
QF01012-NES-C04518-SDW-ARC-00-BLAD03-2001920 | BL3 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL3.GEN.1350 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 2 | 00 | 1920 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-15
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001921 | BL4 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL4.GEN.1740 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1921 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001922 | BL4 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL4.GEN.1740 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1922 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001923 | BL4 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL4.GEN.1740 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1923 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001924 | BL4 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL4.GEN.1740 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1924 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001925 | BL4 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL4.GEN.1740 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1925 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001926 | BL4 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL4.GEN.1740 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1926 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-ARC-00-BLAD04-2001927 | BL4 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 7) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL4.GEN.1740 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 2 | 00 | 1927 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-ARC-00-MBLAD2-2001928 | MINI BL4 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL4.GEN.1740 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | MBLAD2 | 2 | 00 | 1928 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001929 | BL5 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL5.GEN.1510 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1929 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-23
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001930 | BL5 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL5.GEN.1510 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1930 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-23
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001931 | BL5 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL5.GEN.1510 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1931 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-23
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001932 | BL5 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL5.GEN.1510 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1932 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-23
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001933 | BL5 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL5.GEN.1510 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1933 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-23
QF01012-NES-C04518-SDW-ARC-00-BLAD05-2001934 | BL5 - WALL PROTECTION & STEEL LADDER ENLARGED PLAN (Sheet 6) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.BL5.GEN.1510 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 2 | 00 | 1934 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-23
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001935 | TUNNELS & RAMPS - WALL PROTECTION & STEEL LADDER ENLARGED PLANS (SHEET1/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.4010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1935 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-03-07
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001936 | TUNNELS & RAMPS - WALL PROTECTION & STEEL LADDER ENLARGED PLANS (SHEET2/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.4010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1936 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-03-07
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001937 | TUNNELS & RAMPS - WALL PROTECTION & STEEL LADDER ENLARGED PLANS (SHEET3/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.4010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1937 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-03-07
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001938 | TUNNELS & RAMPS - WALL PROTECTION & STEEL LADDER ENLARGED PLANS (SHEET4/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.4010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1938 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-03-07
QF01012-NES-C04518-SDW-ARC-00-Z00000-2001939 | TUNNELS & RAMPS - WALL PROTECTION & STEEL LADDER ENLARGED PLANS (SHEET5/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-03-04 | WALL PROTECTION & STEEL LADDER PLANS | QP.E.AF.MBL.GEN.4010 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 2 | 00 | 1939 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-03-07
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B22200 | B2 +893.50M - BOH+ FURNITURE MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-08-13 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5280 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B2 | 2200 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-09
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B22201 | B2 +893.50M - BOH+ FURNITURE ENLARGED PLAN (Sheet1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5280 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B2 | 2201 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-09
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B22202 | B2 +893.50M - BOH+ FURNITURE ENLARGED PLAN (Sheet2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5280 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B2 | 2202 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-09
QF01012-NES-C04518-SDW-ARC-00-CENT01-2B12203 | B1 +900.50M - BOH+ FURNITURE MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-03 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5300 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | B1 | 2203 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-16
QF01012-NES-C04518-SDW-ARC-01-CENT01-2B12204 | B1 +900.50M - BOH+ FURNITURE ENLARGED PLAN (Sheet1/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5300 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | B1 | 2204 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-16
QF01012-NES-C04518-SDW-ARC-02-CENT01-2B12205 | B1 +900.50M - BOH+ FURNITURE ENLARGED PLAN (Sheet2/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5300 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | B1 | 2205 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-16
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L12206 | L1 +905.00M - BOH+ FURNITURE MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5320 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L1 | 2206 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L12207 | L1 +905.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5320 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L1 | 2207 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L12208 | L1 +905.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5320 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L1 | 2208 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L12209 | L1 +905.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5320 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L1 | 2209 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L12210 | L1 +905.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5320 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L1 | 2210 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-18
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M12211 | M1 +909.00M - BOH+ FURNITURE MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M1 | 2211 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M12212 | M1 +909.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M1 | 2212 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M12213 | M1 +909.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M1 | 2213 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M12214 | M1 +909.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M1 | 2214 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M12215 | M1 +909.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M1 | 2215 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-12
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L22216 | L2 +913.00M - BOH+ FURNITURE MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-10-29 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5360 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L2 | 2216 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-10
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L22217 | L2 +913.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet1/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5360 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L2 | 2217 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-10
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L22218 | L2 +913.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet2/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5360 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L2 | 2218 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-10
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L32219 | L3 +917.50M - BOH+ FURNITURE MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-12 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5380 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L3 | 2219 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L32220 | L3 +917.50M - BOH+ FURNITURE ENLARGED PLAN (Sheet1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5380 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L3 | 2220 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L32221 | L3 +917.50M - BOH+ FURNITURE ENLARGED PLAN (Sheet2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5380 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L3 | 2221 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L32222 | L3 +917.50M - BOH+ FURNITURE ENLARGED PLAN (Sheet3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5380 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L3 | 2222 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L32223 | L3 +917.50M - BOH+ FURNITURE ENLARGED PLAN (Sheet4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5380 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L3 | 2223 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L42224 | L4 +921.00M - BOH+ FURNITURE MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-11-26 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5420 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L4 | 2224 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-31
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L42225 | L4 +921.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet1/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5420 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L4 | 2225 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-31
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L42226 | L4 +921.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet2/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5420 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L4 | 2226 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-2L52227 | L5 +928.00M - BOH+ FURNITURE MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5420 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | L5 | 2227 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-31
QF01012-NES-C04518-SDW-ARC-01-CENT01-2L52228 | L5 +928.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet1/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5420 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | L5 | 2228 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-31
QF01012-NES-C04518-SDW-ARC-02-CENT01-2L52229 | L5 +928.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet2/) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5420 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | L5 | 2229 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-31
QF01012-NES-C04518-SDW-ARC-03-CENT01-2L52230 | L5 +928.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet3/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5420 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | L5 | 2230 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-31
QF01012-NES-C04518-SDW-ARC-04-CENT01-2L52231 | L5 +928.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet4/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5420 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | L5 | 2231 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-31
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L52232 | L5 +928.00M - BOH+ FURNITURE ENLARGED PLAN (Sheet5/5) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5420 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L5 | 2232 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-2M22233 | M2+931.70M - BOH+ FURNITURE MASTER PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5440 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 2 | M2 | 2233 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-26
QF01012-NES-C04518-SDW-ARC-01-CENT01-2M22234 | M2+931.70M - BOH+ FURNITURE ENLARGED PLAN (Sheet1/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5440 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 01 | CENT01 | 2 | M2 | 2234 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-26
QF01012-NES-C04518-SDW-ARC-02-CENT01-2M22235 | M2+931.70M - BOH+ FURNITURE ENLARGED PLAN (Sheet2/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5440 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 02 | CENT01 | 2 | M2 | 2235 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-26
QF01012-NES-C04518-SDW-ARC-03-CENT01-2M22236 | M2+931.70M - BOH+ FURNITURE ENLARGED PLAN (Sheet3/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5440 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 03 | CENT01 | 2 | M2 | 2236 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-26
QF01012-NES-C04518-SDW-ARC-04-CENT01-2M22237 | M2+931.70M - BOH+ FURNITURE ENLARGED PLAN (Sheet4/4) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5440 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 04 | CENT01 | 2 | M2 | 2237 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-09-26
QF01012-NES-C04518-SDW-ARC-05-CENT01-2L62238 | L6 +935.85M - BOH+ FURNITURE ENLARGED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2026-11-12 | BOH++ FURNITURE PLANS | QP.E.AF.MBL.GEN.5460 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 05 | CENT01 | 2 | L6 | 2238 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-11-01
QF01012-NES-C04518-SDW-ARC-00-Z00000-3ZZ3100 | INTERFACE DETAIL -FACADE & INT, EXT(E-W SECTION A-A) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 3 | ZZ | 3100 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-Z00000-3ZZ3101 | INTERFACE DETAIL -FACADE & INT, EXT(E-W SECTION B-B) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 3 | ZZ | 3101 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3102 | INTERFACE DETAIL -FACADE & INT, EXT(PREMIUM THEATRE) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3102 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-3ZZ3103 | INTERFACE DETAIL -FACADE & INT, EXT(N-S SECTION C-C) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 3 | ZZ | 3103 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-Z00000-3ZZ3104 | INTERFACE DETAIL -FACADE & INT, EXT (N-S SECTION D-D) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 3 | ZZ | 3104 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3105 | INTERFACE DETAIL -FACADE & INT, EXT (PREMIUM THEATRE) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3105 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-3ZZ3106 | INTERFACE DETAIL -FACADE & INT, EXT (SECTION OVERALL) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 3 | ZZ | 3106 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3107 | INTERFACE DETAIL -FACADE & INT, EXT (ADAPTABLE THEATRE)(SHEET1/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3107 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3108 | INTERFACE DETAIL -FACADE & INT, EXT (ADAPTABLE THEATRE)(SHEET2/2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3108 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3109 | INTERFACE DETAIL -FACADE & INT, EXT (PREMIUM THEATRE) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3109 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-PARK01-3B13110 | INTERFACE DETAIL -FACADE & INT, EXT (ENLARGED PARKING) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.PAR.GEN.1050 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | PARK01 | 3 | B1 | 3110 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-12-25
QF01012-NES-C04518-SDW-ARC-00-BLAD01-3ZZ3111 | BLADE 1 INTERFACE DETAIL -FACADE & INT, EXT (SHEET 1 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 3 | ZZ | 3111 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD01-3ZZ3112 | BLADE 1 INTERFACE DETAIL -FACADE & INT, EXT (SHEET 2 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 3 | ZZ | 3112 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD02-3ZZ3113 | BLADE 2 INTERFACE DETAIL -FACADE & INT, EXT (SHEET 1 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 3 | ZZ | 3113 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD02-3ZZ3114 | BLADE 2 INTERFACE DETAIL -FACADE & INT, EXT (SHEET 2 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 3 | ZZ | 3114 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD03-3ZZ3115 | BLADE 3 INTERFACE DETAIL -FACADE & INT, EXT (SHEET 1 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 3 | ZZ | 3115 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD03-3ZZ3116 | BLADE 3 INTERFACE DETAIL -FACADE & INT, EXT (SHEET 2 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 3 | ZZ | 3116 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD04-3ZZ3117 | BLADE 4 INTERFACE DETAIL -FACADE & INT, EXT (SHEET 1 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 3 | ZZ | 3117 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD04-3ZZ3118 | BLADE 4 INTERFACE DETAIL -FACADE & INT, EXT (SHEET 2 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 3 | ZZ | 3118 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD05-3ZZ3119 | BLADE 5 INTERFACE DETAIL -FACADE & INT, EXT (SHEET 1 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 3 | ZZ | 3119 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD05-3ZZ3120 | BLADE 5 INTERFACE DETAIL -FACADE & INT, EXT (SHEET 2 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:100 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 3 | ZZ | 3120 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD01-3ZZ3121 | INTERFACE DETAIL - FACADE & INT, EXT 1 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 3 | ZZ | 3121 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD02-3ZZ3122 | INTERFACE DETAIL - FACADE & INT, EXT 2 (SHEET 1 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 3 | ZZ | 3122 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-BLAD02-3ZZ3123 | INTERFACE DETAIL - FACADE & INT, EXT 2 (SHEET 2 OF 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 3 | ZZ | 3123 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3124 | INTERFACE DETAIL - FACADE & INT, EXT 3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3124 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3125 | INTERFACE DETAIL - FACADE & INT, EXT 4 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3125 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3126 | INTERFACE DETAIL - FACADE & INT, EXT 5 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3126 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3127 | INTERFACE DETAIL - FACADE & INT, EXT 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3127 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3128 | INTERFACE DETAIL - FACADE & INT, EXT 7 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3128 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3129 | INTERFACE DETAIL - FACADE & INT, EXT 8 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3129 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3130 | INTERFACE DETAIL - FACADE & INT, EXT 9 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3130 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD05-3ZZ3131 | INTERFACE DETAIL - FACADE & INT, EXT 10 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 3 | ZZ | 3131 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3132 | INTERFACE DETAIL - FACADE & INT, EXT 11 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3132 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3133 | INTERFACE DETAIL - FACADE & INT, EXT 12 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3133 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3134 | INTERFACE DETAIL - FACADE & INT, EXT 13 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3134 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-3ZZ3135 | INTERFACE DETAIL - FACADE & INT, EXT 14 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.FA.GEN.GEN.1450 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 3 | ZZ | 3135 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3136 | INTERFACE DETAIL - FACADE & INT, EXT 15 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-07 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3136 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-3ZZ3137 | INTERFACE DETAIL - FACADE & INT, EXT 16 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-15 | SECTIONS/WALL SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 3 | ZZ | 3137 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-4ZZ4000 | MAIN STAIRS ESCALATORS AND LIFTS KEY PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:300 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 4 | ZZ | 4000 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4001 | CIRCULATION - CORE A SHEET 01 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4001 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4002 | CIRCULATION - CORE A SHEET 02 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4002 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4003 | CIRCULATION - CORE A-SHEET 03 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4003 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4004 | CIRCULATION - CORE A- SHEET 04 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4004 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4005 | CIRCULATION - CORE B SHEET 01 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4005 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4006 | CIRCULATION - CORE B SHEET 02 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4006 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4007 | CIRCULATION - CORE B-SHEET 03 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4007 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4008 | CIRCULATION - CORE B- SHEET 04 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4008 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4009 | CIRCULATION - ST-B TRANSFER |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4009 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4010 | CIRCULATION - CORE C- SHEET 01 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4010 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4011 | CIRCULATION - CORE C- SHEET 02 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4011 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4012 | CIRCULATION - CORE C- SHEET 03 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4012 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4013 | CIRCULATION - ST-C TRANSFER |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4013 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4014 | CIRCULATION - CORE D (SHEET 01) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4014 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4015 | CIRCULATION - CORE D (SHEET 02) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4015 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4016 | CIRCULATION - CORE D (SHEET 03) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4016 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4017 | CIRCULATION - ST-D TRANSFER |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4017 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-4ZZ4018 | ADDITIONAL STAIRS KEY PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:350 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 4 | ZZ | 4018 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4019 | CENTRAL BLOCK ADDITIONAL STAIR-1 @ B2 SERVICE LEVEL |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4019 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4020 | CENTRAL BLOCK ADDITIONAL STAIR-2 @ B2 SERVICE LEVEL |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4020 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4021 | CENTRAL BLOCK STAIR ADJACENT TO RAMP@ B2 SERVICE LEVEL |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4021 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4022 | PIT ACCESS STAIR PLAN AND SECTIONS @ LI MEZZANINE LEVEL |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4022 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4023 | UNDERSTAGE STAIR-1 PLAN AND SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4023 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4024 | UNDERSTAGE STAIR-2 PLAN AND SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4024 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4025 | ADAPTABLE THEATRE STAIR-G PLAN AND SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4025 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4026 | STAIR-I PLAN AND SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4026 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4027 | STAIR-H PLAN AND SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4027 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4028 | STAIR-H PLAN AND SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4028 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-PARK01-4B14029 | B1 SERVICE PARKING STALLS- STAIR-M &N |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | PARK01 | 4 | B1 | 4029 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4030 | CENTRAL BLOCK ADDITIONAL STAIR TUNNEL @ B1 SERVICE LEVEL |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4030 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4031 | CENTRAL BLOCK STAIR TUNNEL @ B2 SERVICE LEVEL |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4031 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4032 | BLADE 1 STAIRS ST-1B PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4032 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-4ZZ4033 | BLADE 1 STAIRS ST-1B ENLARGED SECTION (1-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-07 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 4 | ZZ | 4033 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-4ZZ4034 | BLADE 1 STAIRS ST-1B ENLARGED SECTION (2-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-07 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 4 | ZZ | 4034 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-4ZZ4035 | BLADE 1 STAIRS ST-1B ENLARGED SECTION (3-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-07 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 4 | ZZ | 4035 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-4ZZ4036 | BLADE 1 STAIRS ST-1A PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-07 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 4 | ZZ | 4036 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-4ZZ4037 | BLADE 1 STAIRS ST-1A ENLARGED SECTION (1-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-07 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 4 | ZZ | 4037 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-4ZZ4038 | BLADE 1 STAIRS ST-1A ENLARGED SECTION (2-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-07 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 4 | ZZ | 4038 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-4ZZ4039 | BLADE 1 STAIRS ST-1A ENLARGED SECTION (3-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-07 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 4 | ZZ | 4039 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-4ZZ4040 | BLADE 1 B3 E&O SECONDARY ENTRY STAIRS PLANS AND SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-07 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 4 | ZZ | 4040 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-4ZZ4041 | BLADE 1 ADDITIONAL STAIR 2 - PLANS & SECTION |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-01-07 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 4 | ZZ | 4041 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD02-4ZZ4042 | BLADE 2 STAIRS ST-2A PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-31 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 4 | ZZ | 4042 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD02-4ZZ4043 | BLADE 2 STAIRS ST-2A ENLARGED SECTION 1-3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-31 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 4 | ZZ | 4043 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD02-4ZZ4044 | BLADE 2 STAIRS ST-2A ENLARGED SECTION 2-3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-31 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 4 | ZZ | 4044 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD02-4ZZ4045 | BLADE 2 STAIRS ST-2A ENLARGED SECTION 3-3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-31 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 4 | ZZ | 4045 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD02-4ZZ4046 | BLADE 2 STAIRS ST-2B PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-31 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 4 | ZZ | 4046 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD02-4ZZ4047 | BLADE 2 STAIRS ST-2B ENLARGED SECTION 1-3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-31 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 4 | ZZ | 4047 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD02-4ZZ4048 | BLADE 2 STAIRS ST-2B ENLARGED SECTION 2-3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-31 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 4 | ZZ | 4048 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD02-4ZZ4049 | BLADE 2 STAIRS ST-2B ENLARGED SECTION 3-3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-31 | STAIR PACKAGE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 4 | ZZ | 4049 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD03-4ZZ4050 | BLADE 3 STAIRS ST-3A PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-17 | STAIR PACKAGE | QP.E.AF.BL3.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 4 | ZZ | 4050 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD03-4ZZ4051 | BLADE 3 STAIRS ST-3A ENLARGED SECTION (1-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-17 | STAIR PACKAGE | QP.E.AF.BL3.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 4 | ZZ | 4051 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD03-4ZZ4052 | BLADE 3 STAIRS ST-3A ENLARGED SECTION (2-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-17 | STAIR PACKAGE | QP.E.AF.BL3.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 4 | ZZ | 4052 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD03-4ZZ4053 | BLADE 3 STAIRS ST-3A ENLARGED SECTION (3-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-17 | STAIR PACKAGE | QP.E.AF.BL3.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 4 | ZZ | 4053 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD03-4ZZ4054 | BLADE 3 STAIRS ST-3B PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-17 | STAIR PACKAGE | QP.E.AF.BL3.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 4 | ZZ | 4054 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD03-4ZZ4055 | BLADE 3 STAIRS ST-3B ENLARGED SECTION (1-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-17 | STAIR PACKAGE | QP.E.AF.BL3.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 4 | ZZ | 4055 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD03-4ZZ4056 | BLADE 3 STAIRS ST-3B ENLARGED SECTION (2-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-17 | STAIR PACKAGE | QP.E.AF.BL3.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 4 | ZZ | 4056 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD03-4ZZ4057 | BLADE 3 STAIRS ST-3B ENLARGED SECTION (3-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-12-17 | STAIR PACKAGE | QP.E.AF.BL3.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 4 | ZZ | 4057 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD04-4ZZ4058 | BLADE 4 STAIRS ST-4A PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | STAIR PACKAGE | QP.E.AF.BL4.GEN.6180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 4 | ZZ | 4058 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD04-4ZZ4059 | BLADE 4 STAIRS ST-4A ENLARGED SECTION (1-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | STAIR PACKAGE | QP.E.AF.BL4.GEN.6180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 4 | ZZ | 4059 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD04-4ZZ4060 | BLADE 4 STAIRS ST-4A ENLARGED SECTION (2-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | STAIR PACKAGE | QP.E.AF.BL4.GEN.6180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 4 | ZZ | 4060 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD04-4ZZ4061 | BLADE 4 STAIRS ST-4A ENLARGED SECTION (3-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | STAIR PACKAGE | QP.E.AF.BL4.GEN.6180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 4 | ZZ | 4061 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD04-4ZZ4062 | BLADE 4 STAIRS ST-4B PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | STAIR PACKAGE | QP.E.AF.BL4.GEN.6180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 4 | ZZ | 4062 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD04-4ZZ4063 | BLADE 4 STAIRS ST-4B ENLARGED SECTION (1-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | STAIR PACKAGE | QP.E.AF.BL4.GEN.6180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 4 | ZZ | 4063 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD04-4ZZ4064 | BLADE 4 STAIRS ST-4B ENLARGED SECTION (2-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | STAIR PACKAGE | QP.E.AF.BL4.GEN.6180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 4 | ZZ | 4064 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD04-4ZZ4065 | BLADE 4 STAIRS ST-4B ENLARGED SECTION (3-3) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | STAIR PACKAGE | QP.E.AF.BL4.GEN.6180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 4 | ZZ | 4065 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD05-4ZZ4066 | BLADE 5 STAIRS ST-5A PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-10-29 | STAIR PACKAGE | QP.E.AF.BL5.GEN.6200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 4 | ZZ | 4066 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD05-4ZZ4067 | BLADE 5 STAIRS ST-5A ENLARGED SECTION (1-2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-10-29 | STAIR PACKAGE | QP.E.AF.BL5.GEN.6200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 4 | ZZ | 4067 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD05-4ZZ4068 | BLADE 5 STAIRS ST-5A ENLARGED SECTION (2-2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-10-29 | STAIR PACKAGE | QP.E.AF.BL5.GEN.6200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 4 | ZZ | 4068 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD05-4ZZ4069 | BLADE 5 STAIRS ST-5B PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-10-29 | STAIR PACKAGE | QP.E.AF.BL5.GEN.6200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 4 | ZZ | 4069 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD05-4ZZ4070 | BLADE 5 STAIRS ST-5B ENLARGED SECTION (1-2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-10-29 | STAIR PACKAGE | QP.E.AF.BL5.GEN.6200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 4 | ZZ | 4070 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD05-4ZZ4071 | BLADE 5 STAIRS ST-5B ENLARGED SECTION (2-2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-10-29 | STAIR PACKAGE | QP.E.AF.BL5.GEN.6200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 4 | ZZ | 4071 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD05-4ZZ4072 | BLADE 5 STAIRS ST-5B ENLARGED 3D VIEW |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-10-29 | STAIR PACKAGE | QP.E.AF.BL5.GEN.6200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 4 | ZZ | 4072 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4073 | STAIR F@ B3 PROMENADE- PLANS & SECTIONS (sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4073 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4075 | STAIR-E PLANS AND SECTIONS- B3 PROMENADE(sheet 1) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4075 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4076 | STAIR-E PLANS AND SECTIONS- B3 PROMENADE(sheet 2) |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4076 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-4ZZ4077 | STAIR-J PLANS AND SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-02-12 | STAIR PACKAGE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 4 | ZZ | 4077 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5000 | ROAD MARKING - TYPICAL CAR PARK DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5000 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5001 | SANITARY & ELECTRICAL STANDARD MOUNTING HEIGHT |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5001 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5002 | FLOOR DETAILS - SHEET 1 OF 3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5002 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5003 | FLOOR DETAILS - SHEET 2 OF 3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5003 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5004 | FLOOR DETAILS - SHEET 3 OF 3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5004 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5005 | EXPANSION JOINTS FLOOR TO FLOOR DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5005 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5006 | SCREED CONTROL JOINTS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5006 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5007 | WALL DETAILS - SHEET 1 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5007 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5008 | WALL DETAILS - SHEET 2 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5008 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5009 | WALL DETAILS - SHEET 3 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5009 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5010 | WALL DETAILS - SHEET 4 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5010 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5011 | WALL DETAILS - SHEET 5 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5011 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5012 | WALL DETAILS - SHEET 6 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5012 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5013 | EXPANSION JOINTS WALL TO WALL DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5013 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5014 | EXPANSION JOINTS WALL TO CORNER WALL DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5014 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5015 | EXPANSION JOINTS FLOOR TO WALL DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5015 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5016 | WALL PROTECTION DETAILS - SHEET 1 OF 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5016 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5017 | WALL PROTECTION DETAILS - SHEET 12OF 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5017 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5018 | CEILING DETAILS - SHEET 1 OF 4 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5018 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5019 | CEILING DETAILS - SHEET 2 OF 4 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5019 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5020 | CEILING DETAILS - SHEET 3 OF 4 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5020 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5021 | CEILING DETAILS - SHEET 4 OF 4 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5021 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5022 | BLADE BOX CEILING DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5022 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5023 | CEILING TERMINATION AT FACADE - SHEET 1 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5023 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5024 | CEILING TERMINATION AT FACADE - SHEET 2 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5024 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5025 | CEILING TERMINATION AT FACADE - SHEET 3 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5025 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5026 | CEILING TERMINATION AT FACADE - SHEET 4 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5026 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5027 | CEILING TERMINATION AT FACADE - SHEET 5 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5027 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5028 | CEILING TERMINATION AT FACADE - SHEET 6 OF 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5028 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5029 | FHC & BREECHING INLET DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:2 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5029 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5030 | FHC DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:10 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5030 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5031 | FIRE PENETRATION DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:5 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5031 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5032 | FIRE PROOFING DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:5 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5032 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5033 | WATER TANK ACCESS LADDER DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5033 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5034 | ACCESS LADDER DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5034 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5035 | SHAFTS & PARTITION DETAIL SHEET 1 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5035 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5036 | SHAFTS & PARTITION DETAIL SHEET 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5036 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5037 | SHAFTS & PARTITION DETAIL SHEET 3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5037 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5038 | SHAFTS & PARTITION DETAIL SHEET 4 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5038 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5039 | SHAFTS & PARTITION DETAIL SHEET 5 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5039 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5040 | SHAFTS & PARTITION DETAIL SHEET 6 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5040 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5041 | SHAFTS & PARTITION DETAIL SHEET 7 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5041 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5042 | SHAFTS & PARTITION DETAIL SHEET 8 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5042 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5043 | SHAFTS & PARTITION DETAIL SHEET 9 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5043 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5044 | CAR PARK AREA_ALUMINIUM CLADDING |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5044 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5045 | GRC CLADDING TO PLANTER DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5045 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5046 | STAIR AND BALUSTRADE DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | ARCH-DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5046 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5200 | JOINERY DETAILS - SHEET 01 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | JOINERY DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5200 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5201 | JOINERY DETAILS - SHEET 02 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | JOINERY DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5201 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5202 | JOINERY DETAILS - SHEET 03 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | JOINERY DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5202 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5203 | JOINERY DETAILS - SHEET 04 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | JOINERY DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5203 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5204 | TYPICAL JOINERY DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | JOINERY DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5204 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5205 | TYPICAL JOINERY DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | JOINERY DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5205 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5206 | TYPICAL VANITY JOINERY DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | JOINERY DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5206 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5207 | JOINERY DETAILS - SHEET 05 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | JOINERY DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5207 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-Z00000-5ZZ5208 | JOINERY DETAILS - SHEET 06 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-03-31 | JOINERY DETAILS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | Z00000 | 5 | ZZ | 5208 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD01-6ZZ6500 | BOH ROOM FINISHES SCHEDULE - BLADE 1 |  | Architecture / LDC | Revit | .dwg,.pdf | NTS | 2027-01-07 | ROOM FINISHES SCHEDULE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD01 | 6 | ZZ | 6500 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD02-6ZZ6501 | BOH ROOM FINISHES SCHEDULE - BLADE 2 |  | Architecture / LDC | Revit | .dwg,.pdf | NTS | 2026-12-31 | ROOM FINISHES SCHEDULE | QP.E.AF.BL1.GEN.6120 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD02 | 6 | ZZ | 6501 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD03-6ZZ6502 | BOH ROOM FINISHES SCHEDULE - BLADE 3 |  | Architecture / LDC | Revit | .dwg,.pdf | NTS | 2026-12-17 | ROOM FINISHES SCHEDULE | QP.E.AF.BL3.GEN.6160 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD03 | 6 | ZZ | 6502 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD04-6ZZ6503 | BOH ROOM FINISHES SCHEDULE - BLADE 4 |  | Architecture / LDC | Revit | .dwg,.pdf | NTS | 2026-11-19 | ROOM FINISHES SCHEDULE | QP.E.AF.BL4.GEN.6180 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD04 | 6 | ZZ | 6503 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-BLAD05-6ZZ6504 | BOH ROOM FINISHES SCHEDULE - BLADE 5 |  | Architecture / LDC | Revit | .dwg,.pdf | NTS | 2026-10-29 | ROOM FINISHES SCHEDULE | QP.E.AF.BL5.GEN.6200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | BLAD05 | 6 | ZZ | 6504 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-6ZZ6505 | BOH ROOM FINISHES SCHEDULE - CENTRAL BLOCK - SHEET 1 OF 2 |  | Architecture / LDC | Revit | .dwg,.pdf | NTS | 2027-04-15 | ROOM FINISHES SCHEDULE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 6 | ZZ | 6505 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-6ZZ6506 | BOH ROOM FINISHES SCHEDULE - CENTRAL BLOCK - SHEET 2 OF 2 |  | Architecture / LDC | Revit | .dwg,.pdf | NTS | 2027-04-15 | ROOM FINISHES SCHEDULE | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 6 | ZZ | 6506 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27000 | B2 BOH - LOCKER ROOM DETAILED PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7000 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27001 | B2 BOH - LOCKER ROOM DETAILED RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7001 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27002 | B2 BOH - LOCKER ROOM DETAILED SECTION 1&2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7002 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27003 | B2 BOH - LOCKER ROOM DETAILED SECTION 3&4 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7003 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27004 | B2 BOH - W.C (M) & M. PRAYER DETAILED PLANS & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7004 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27005 | B2 BOH - W.C (M) & M. PRAYER DETAILED SECTION A&B |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7005 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27006 | B2 BOH - W.C (M) & M. PRAYER DETAILED SECTION C&D |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7006 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27011 | B2 BOH - SERVERY & BREAK ROOM |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7011 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27012 | B2 BOH - RECEPTION FOYER SECURITY & BOH ROOMS DETAILED PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7012 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27013 | B2 BOH - RECEPTION FOYER SECURITY & BOH ROOMS DETAILED RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7013 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27014 | B2 BOH - RECEPTION FOYER, SECURITY & BOH ROOMS DETAILED SECTION A&B |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7014 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27015 | B2 BOH - RECEPTION FOYER, SECURITY & BOH ROOMS DETAILED SECTION C&D |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7015 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27016 | B2 BOH - RECEPTION FOYER, SECURITY & BOH ROOMS DETAILED SECTION E&F |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7016 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27021 | B2 BOH - OFFICES DETAILED PLANS & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-08-06 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1200 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7021 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17035 | L1 LOBBY BOH - BOH ROOMS PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7035 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17036 | L1 LOBBY BOH - BOH ROOMS SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7036 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17037 | L1 LOBBY BOH - STORAGE DETAILED PLANS & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7037 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L37051 | L3 MEZZANINE BOH - TOURING OFFICES-DETAILED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-12 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L3 | 7051 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L37052 | L3 MEZZANINE BOH - TOURING OFFICES - RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-12 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L3 | 7052 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L37053 | L3 MEZZANINE BOH - TOURING OFFICES - SECTIONS SHEET 01 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-12 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L3 | 7053 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L37054 | L3 MEZZANINE BOH - TOURING OFFICES - SECTIONS SHEET 02 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-12 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L3 | 7054 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17059 | B1 BOH - LOST&FOUND - SEC.EQUIP PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7059 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17062 | B1 BOH - FIRST AID PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7062 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17063 | B1 BOH- AV STORE/ WORKBENCH/OFFICES DETAILED PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7063 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17064 | B1 BOH- STAFF BRIEFING - UNIFORM ISSUE- PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7064 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17065 | B1 BOH- STAFF BRIEFING - UNIFORM ISSUE - RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7065 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17066 | B1 BOH - STAFF BRIEFING & UNIFORM ISSUE - SECTION A&B |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7066 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17067 | B1 BOH - STAFF BRIEFING & UNIFORM ISSUE - SECTION C&D |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7067 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57072 | L5 BOH - SEC. MANAGERS OFFICE- PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7072 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57073 | L5 BOH- L5 BOH- SEC. MANAGERS OFFICE- SECTION 1& 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7073 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57074 | L5 BOH- L5 BOH- SEC. MANAGERS OFFICE- SECTION 3&4 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7074 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57075 | L5 BOH - ADMINISTRATION OPERATION PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7075 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57076 | L5 BOH- ADMINISTRATION OPERATION SECTION A&B |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7076 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57077 | L5 BOH- ADMINISTRATION OPERATION SECTION C&D |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7077 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57083 | L5 BOH - TRASH HOLDING DETAILED PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7083 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57085 | L5 BOH - JAN. PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7085 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57086 | L5 BOH - PREPARATION AREA PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7086 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57087 | L5 BOH- PREPARATION AREA RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7087 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57088 | L5 BOH - PREPARATION AREA DETAILED SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7088 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17089 | B1 BOH - LOST&FOUND - SEC.EQUIP SECTIONS A&B |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7089 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17090 | B1 BOH - MAIN SEC. CONTROL- PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7090 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17091 | B1 BOH - LOST&FOUND - SEC.EQUIP SECTIONS C&D |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7091 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17092 | B1 BOH - MAIN SEC. CONTROL SECTIONS A&B |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7092 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17093 | B1 BOH - MAIN SEC. CONTROL SECTIONS C&D |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7093 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17096 | B1 BOH - CREW READY - PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7096 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17097 | B1 BOH - CENTRAL PRODUCTION FACILITY- PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7097 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17098 | B1 BOH - CENTRAL PRODUCTION FACILITY- SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7098 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17099 | B1 BOH - SHOP PAINTS WORKSHOP - DETAILED PLAN &RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7099 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17100 | L1 BOH - WARDROBE - DETAILED PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7100 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17101 | L1 MEZZ BOH - ORCH INSTRUM 1 - DETAILED PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7101 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17102 | L1 MEZZ BOH - ORCH INSTRUM 2 DETAILED PLANS & SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7102 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17103 | L1 MEZZ BOH - ORCH INSTRUM 3 - PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7103 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L27104 | L2 STAGE BOH - STAGE TOOLS - PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-10-29 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L2 | 7104 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L27105 | L2 STAGE BOH - STORAGE AUDIO MIX |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-10-29 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L2 | 7105 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L27106 | L2 AT-BOH - STORAGE RIGGING |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-10-29 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L2 | 7106 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L27107 | L2 AT- BOH - VISITING PRODUCTION - PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-10-29 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1030 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L2 | 7107 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-03-22
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57109 | L5 BOH - STAGE MANAGER OFFICE - PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7109 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17110 | B1 BOH- DRIVER ROOM PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7110 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17111 | B1 BOH- DRIVER ROOM SECTIONS A&B |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7111 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17112 | B1 BOH- DRIVER ROOM SECTIONS C&D |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7112 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L37113 | L3 MEZZANINE BOH - RECEPTION |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-12 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L3 | 7113 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57114 | L5 BOH - TECHNICAL ROOM STORAGE |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7114 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17116 | L01 BOH - GUARDHOUSE PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7116 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B17117 | B1 BOH - VALET MALE & FEMALE TOILET SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-03 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1250 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B1 | 7117 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-12-29
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L47118 | L4 - AT- VISITING TECH PLAN & RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-26 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L4 | 7118 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L47119 | L4 - AT- VISITING TECH ELEVATION |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-26 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L4 | 7119 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17120 | L1 MEZZ BOH - MUSICIAN DRESSING ROOM DETAILED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7120 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17121 | L1 MEZZ BOH - MUSICIAN DRESSING ROOM DETAILED RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7121 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17122 | L1 MEZZ BOH - MUSICIAN DRESSING ROOM DETAILED SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7122 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17123 | L1 MEZZ BOH - MUSICIAN DRESSING ROOM DETAILED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7123 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17124 | L1 MEZZ BOH - MUSICIAN DRESSING ROOM DETAILED RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7124 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17125 | L1 MEZZ BOH - MUSICIAN DRESSING ROOM DETAILED SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1430 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7125 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-02-24
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L37128 | L3 MEZZ BOH - STAR DRESSING ROOM DETAILED PLAN AND RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-12 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L3 | 7128 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L37129 | L3 MEZZ BOH - STAR DRESSING ROOM DETAILED SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-12 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1520 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L3 | 7129 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-04-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L47130 | L4 BOH - PERFORMER-TECHNICAL CIRCULATION DETAILED PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-26 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L4 | 7130 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L47131 | L4 BOH - PERFORMER-TECHNICAL CIRCULATION DETAILED RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-26 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L4 | 7131 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L47132 | L4 BOH - PERFORMER-TECHNICAL CIRCULATION DETAILED SECTIONS 1 of 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-26 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L4 | 7132 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L47133 | L4 BOH - PERFORMER-TECHNICAL CIRCULATION DETAILED SECTIONS 2 of 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-26 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L4 | 7133 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L47134 | L4 BOH - TOILET |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-26 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L4 | 7134 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L47136 | L4 BOH - STORE MUSICAL INSTR. DETAILED PLANS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-26 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L4 | 7136 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L47137 | L4 BOH - STORE MUSICAL INSTR. DETAILED SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-26 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L4 | 7137 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L47138 | L4 BOH - STORAGE - LIGHTING DETAILED PLANS & SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-26 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L4 | 7138 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L47139 | L4 BOH - STORAGE - SOUND DETAILED PLANS & SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-11-26 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1610 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L4 | 7139 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-05-08
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17143 | AMPHITHEATRE DRESSING ROOMS - DETAIL PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7143 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17144 | AMPHITHEATRE DRESSING ROOMS - DETAIL RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7144 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17145 | AMPHITHEATRE DRESSING ROOMS - DETAIL SETIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7145 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17146 | PT L1 DRESSING ROOM & FOYER - DETAIL PLAN PART 1 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7146 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17147 | PT L1 DRESSING ROOM & FOYER - DETAIL PLAN PART 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7147 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17148 | PT L1 DRESSING ROOM & FOYER - DETAIL RCP PART 1 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7148 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17149 | PT L1 DRESSING ROOM & FOYER - DETAIL RCP PART 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7149 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17150 | PT L1 DRESSING ROOM & FOYER - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7150 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17151 | PT L1 DRESSING ROOM & FOYER - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7151 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17152 | PT L1 DRESSING ROOM & FOYER - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7152 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17153 | PT L1 DRESSING ROOM & FOYER - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7153 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17154 | PT L1 HAIR&MAKE-UP, PROSTHETICS - DETAIL PLAN, RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7154 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L17155 | PT L1 HAIR&MAKE-UP, PROSTHETICS - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1340 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L1 | 7155 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-01-31
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7156 | PT TYPICAL STAR DRESSING ROOM & FOYER - DETAIL PLAN PART 1 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7156 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7157 | PT TYPICAL STAR DRESSING ROOM & FOYER - DETAIL PLAN PART 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7157 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7158 | PT TYPICAL STAR DRESSING ROOM & FOYER - DETAIL RCP PART 1 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7158 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7159 | PT TYPICAL STAR DRESSING ROOM & FOYER - DETAIL RCP PART 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7159 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7160 | PT TYPICAL STAR DRESSING ROOM & FOYER - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7160 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7161 | PREMIUM THEATRE PEOPLE DRESSING ROOM - DETAIL PLAN PART 1 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7161 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7162 | PREMIUM THEATRE PEOPLE DRESSING ROOM - DETAIL PLAN PART 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7162 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7163 | PREMIUM THEATRE PEOPLE DRESSING ROOM - DETAIL RCP PART 1 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7163 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7164 | PREMIUM THEATRE PEOPLE DRESSING ROOM - DETAIL RCP PART 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7164 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7165 | PREMIUM THEATRE PEOPLE DRESSING ROOM - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7165 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7166 | PREMIUM THEATRE PEOPLE DRESSING ROOM - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7166 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7M27167 | LOFT - DRESSING ROOMS - DETAIL PLAN PART 1 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | M2 | 7167 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-7M27168 | LOFT - DRESSING ROOMS - DETAIL PLAN PART 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | M2 | 7168 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-7M27169 | LOFT - DRESSING ROOMS - DETAIL RCP PART 1 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | M2 | 7169 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-7M27170 | LOFT - DRESSING ROOMS - DETAIL RCP PART 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | M2 | 7170 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-7M27171 | LOFT - DRESSING ROOMS - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | M2 | 7171 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-7M27172 | LOFT - DRESSING ROOMS - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | M2 | 7172 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-7M27173 | LOFT - CREW READY - DETAIL PLAN, DETAIL RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | M2 | 7173 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-7M27174 | LOFT - CREW READY - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | M2 | 7174 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-7M27175 | LOFT - MUSICIAN DRESS - DETAIL PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | M2 | 7175 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-7M27176 | LOFT - MUSICIAN DRESS - DETAIL RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | M2 | 7176 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-7M27177 | LOFT - MUSICIAN DRESS - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-09-24 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1790 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | M2 | 7177 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-15
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7178 | TYPICAL BOH CORRIDOR RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2027-04-15 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7178 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L87179 | L8 - SECURITY - DETAIL PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-12-10 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L8 | 7179 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L87180 | L8 - SECURITY - DETAIL RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-12-10 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L8 | 7180 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L87181 | L8 - SECURITY - DETAIL SECTION 1 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-12-10 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L8 | 7181 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L87182 | L8 - SECURITY - DETAIL SECTION 2 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-12-10 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L8 | 7182 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L87183 | L8 - SECURITY - DETAIL SECTION 3 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-12-10 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L8 | 7183 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L87184 | L8 - SECURITY - DETAIL SECTION 4 |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-12-10 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L8 | 7184 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L87186 | L8 - SECURITY TOILET - DETAIL PLAN, RCP |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-12-10 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L8 | 7186 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L87187 | L8 - SECURITY TOILET - DETAIL SECTIONS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:20 | 2026-12-10 | ENLARGED BOH PLANS & SECTIONS | QP.E.AF.MBL.GEN.1830 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L8 | 7187 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-08-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27501 | ETS ROOM DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-08-06 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7501 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27502 | GENERATOR ROOM DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-08-06 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7502 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27503 | GENERATOR ROOM DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-08-06 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7503 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27504 | LV PANEL ROOM DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-08-06 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7504 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27505 | TRANSFORMER ROOM DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-08-06 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.1170 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7505 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2026-05-13
QF01012-NES-C04518-SDW-ARC-00-CENT01-7B27506 | DIESEL TANK - POE - MTR ROOM DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-08-06 | ENLARGED MEP ROOMS | QP.E.ME.MBL.GEN.7420 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | B2 | 7506 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-02-26
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57507 | MEP ABOVE ADAPTABLE THEATRE DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-09-24 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7507 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57508 | MEP ABOVE ADAPTABLE THEATRE DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-09-24 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7508 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57509 | MEP ABOVE PREMIUM THEATRE DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-09-24 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7509 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7L57510 | MEP ABOVE PREMIUM THEATRE DETAILS |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2026-09-24 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.1700 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | L5 | 7510 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2027-06-14
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7511 | PROJECTOR ROOM DETAILS A |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-15 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7511 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7512 | PROJECTOR ROOM DETAILS B |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-15 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7512 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7513 | PROJECTOR ROOM DETAILS C |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-15 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7513 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-ARC-00-CENT01-7ZZ7514 | PROJECTOR ROOM KEY PLAN |  | Architecture / LDC | Revit | .dwg,.pdf | 1:50 | 2027-04-15 | ENLARGED MEP ROOMS | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | ARC | 00 | CENT01 | 7 | ZZ | 7514 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-LOG-00-Z00000-0000029 | TMP LAYOUT LAYDOWN AREA | [5 empty] | 2027-04-15 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | LOG | 00 | Z00000 | 0 | 00 | 0029 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-LOG-00-Z00000-000030 | TMP LAYOUT LAYDOWN AREA - ALUTEC FACTORY | [5 empty] | 2027-04-15 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | LOG | 00 | Z00000 | 0 | 00 | 030 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-LOG-00-Z00000-0000031 | Logistics Plan for Jinggong Laydown Area | [5 empty] | 2027-04-15 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | LOG | 00 | Z00000 | 0 | 00 | 0031 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-LOG-00-Z00000-0000030 | B1 LAY DOWN PLAN | [5 empty] | 2027-04-15 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | LOG | 00 | Z00000 | 0 | 00 | 0030 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-LOG-00-Z00000-0000032 | TC FENCE |  | 2027-03-24 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | 2027-04-15 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | LOG | 00 | Z00000 | 0 | 00 | 0032 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-LOG-00-Z00000-0000033 | SIGNAGE |  | 46470 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | 2027-04-15 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | LOG | 00 | Z00000 | 0 | 00 | 0033 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-LOG-00-Z00000-0000034 | PMO BUILDING A GENERAL ARRANGMENT PLAN |  | 46470 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | 2027-04-15 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | LOG | 00 | Z00000 | 0 | 00 | 0034 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-LOG-00-Z00000-0000035 | PMV- Workshop |  | 46470 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | 2027-04-15 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | LOG | 00 | Z00000 | 0 | 00 | 0035 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-LOG-00-Z00000-0000036 | PROPOSAL LOCATION GATE 1 |  | 46470 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | 2027-04-15 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | LOG | 00 | Z00000 | 0 | 00 | 0036 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17
QF01012-NES-C04518-SDW-LOG-00-Z00000-0000037 | JING JONG SITE AREA |  | 46470 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | 2027-04-15 | Lay Down Area | QP.E.AF.MBL.GEN.5540 | FI_60_53 | QF01012 | NES | C04518 | SDW | LOG | 00 | Z00000 | 0 | 00 | 0037 | Architectural | Nesma & Partners | LOD400 |  |  |  | 2028-01-17

## Baseline (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | Package | Activity Code | Activity | Original Duration | Start | Finish
Shop Drawings | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Shop Drawings ¦ Mobilization | QP.M.GN.GEN.GEN.1400 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Shop Drawings ¦ Mobilization ¦ Tower Crane Foundation - Concrete Works | QP.M.GN.GEN.GEN.1470 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Blades Below Loft | QP.M.GN.GEN.GEN.1540 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Loft | QP.M.GN.GEN.GEN.1560 | Submittal | 12 | 2026-08-29 | 2026-09-10
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Above Loft | QP.M.GN.GEN.GEN.1580 | Submittal | 12 | 2026-10-01 | 2026-10-14
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works | QP.E.CV.MBL.GEN.3460 | Submittal | 28 | 2025-10-11 | 2025-11-11
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works Outside Core Area | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works Outside Core Area | QP.E.CV.MBL.GEN.3540 | Submittal | 14 | 2025-11-12 | 2025-11-27
Shop Drawings | Civil | Blades | Blade 1 | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 1 | QP.E.CV.BL1.GEN.1060 | Submittal | 28 | 2026-02-21 | 2026-03-28
Shop Drawings | Civil | Blades | Blade 2 | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 2 | QP.E.CV.BL2.GEN.1060 | Submittal | 28 | 2026-01-19 | 2026-02-19
Shop Drawings | Civil | Blades | Blade 3 | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 3 | QP.E.CV.BL3.GEN.1060 | Submittal | 28 | 2025-12-17 | 2026-01-18
Shop Drawings | Civil | Blades | Blade 4 | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 4 | QP.E.CV.BL4.GEN.1060 | Submittal | 28 | 2025-12-03 | 2026-01-04
Shop Drawings | Civil | Blades | Blade 5 | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 5 | QP.E.CV.BL5.GEN.1060 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Civil | Parking | Parking | Parking | Parking | Parking | Shop Drawings ¦ Civil ¦ Parking | QP.E.CV.PAR.GEN.1000 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - Foundation Works Core Area | QP.E.CV.MBL.GEN.3000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 03 +887.750M | QP.E.CV.MBL.GEN.3030 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - SOG | QP.E.CV.MBL.GEN.3640 | Submittal | 14 | 2026-03-16 | 2026-04-02
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 02 - Foundation Works Outside Core Area | QP.E.CV.MBL.GEN.3020 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 02 +893.5M | QP.E.CV.MBL.GEN.3070 | Submittal | 21 | 2026-02-18 | 2026-03-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 01 +900.5M | QP.E.CV.MBL.GEN.3100 | Submittal | 28 | 2026-03-16 | 2026-04-19
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01- LOBBY LEVEL +905M | QP.E.CV.MBL.GEN.3120 | Submittal | 25 | 2026-04-20 | 2026-05-18
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01 - MEZZANINE +909M | QP.E.CV.MBL.GEN.3140 | Submittal | 15 | 2026-05-19 | 2026-06-08
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3180 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3380 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3220 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3400 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3240 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3420 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3260 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3440 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | QP.E.CV.MBL.GEN.3280 | Submittal | 25 | 2026-10-08 | 2026-11-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | QP.E.CV.MBL.GEN.3300 | Submittal | 28 | 2027-03-13 | 2027-04-13
Shop Drawings | Concrete | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Premium Theatre Concrete Works | QP.E.CV.MBL.GEN.3150 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Amphitheatre Concrete Works | QP.E.CV.MBL.GEN.3200 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Premium Theater | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Premium Theater | QP.E.CV.MBL.GEN.3660 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Loft and Adaptable Theatre | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Loft and Adaptable Theatre | QP.E.CV.MBL.GEN.3700 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Fly Tower | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Fly Tower | QP.E.CV.MBL.GEN.3710 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Lobby & Plaza | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Lobby & Plaza | QP.E.CV.MBL.GEN.3680 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Royal Majlis | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Royal Majlis | QP.E.CV.MBL.GEN.3740 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Foundation | QP.E.CV.BL1.GEN.1000 | Submittal | 25 | 2026-02-25 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL1.GEN.1040 | Submittal | 25 | 2026-03-29 | 2026-04-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL1.GEN.1080 | Submittal | 18 | 2026-05-12 | 2026-06-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL1.GEN.1020 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL1.GEN.1120 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL1.GEN.1100 | Submittal | 28 | 2026-10-27 | 2026-11-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Foundation | QP.E.CV.BL2.GEN.1000 | Submittal | 21 | 2026-03-02 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL2.GEN.1040 | Submittal | 21 | 2026-03-10 | 2026-04-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL2.GEN.1080 | Submittal | 18 | 2026-04-21 | 2026-05-11
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL2.GEN.1020 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL2.GEN.1140 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL2.GEN.1120 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Foundation | QP.E.CV.BL3.GEN.1000 | Submittal | 21 | 2026-02-07 | 2026-03-03
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Steel Composite Slab Including Embedded items Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Steel Composite Slab Including Embedded items Below Loft | QP.E.CV.BL3.GEN.1030 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL3.GEN.1080 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL3.GEN.1020 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Foundation | QP.E.CV.BL4.GEN.1000 | Submittal | 28 | 2026-01-05 | 2026-02-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL4.GEN.1030 | Submittal | 28 | 2026-02-24 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL4.GEN.1080 | Submittal | 15 | 2026-03-31 | 2026-04-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL4.GEN.1020 | Submittal | 28 | 2026-04-18 | 2026-05-19
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL4.GEN.1100 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL4.GEN.1120 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Foundation | QP.E.CV.BL5.GEN.1000 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL5.GEN.1030 | Submittal | 28 | 2026-03-23 | 2026-04-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL5.GEN.1080 | Submittal | 18 | 2026-03-31 | 2026-04-20
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL5.GEN.1020 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL5.GEN.1100 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL5.GEN.1120 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Foundation Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Foundation Including Embedded items | QP.E.CV.PAR.GEN.1020 | Submittal | 28 | 2027-04-28 | 2027-06-03
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Structural Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Structural Concrete Works Including Embedded items | QP.E.CV.PAR.GEN.1040 | Submittal | 28 | 2027-06-19 | 2027-07-20
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Below Loft | QP.E.ST.GEN.GEN.1090 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1100 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1110 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1050 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1060 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1070 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 3,4,5 | QP.E.ST.GEN.GEN.1000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | QP.E.ST.GEN.GEN.1010 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Truss below Auditorium, Side and Back Stage | QP.E.ST.GEN.GEN.2120 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1220 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1230 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1200 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1210 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1190 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Embedded part - Main Building Above Level 5 | QP.E.ST.GEN.GEN.1040 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Premium Theater - Frame Balconies and Back Stage Dressing | QP.E.ST.GEN.GEN.2140 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Loft and adaptable Theatre | QP.E.ST.GEN.GEN.1340 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1390 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1400 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1310 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1320 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1330 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1470 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ Truss above Auditorium Incl. Metal Deck | QP.E.ST.GEN.GEN.2100 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Temporay Tower ROYAL MAJLIS and Blades above loft | QP.E.ST.GEN.GEN.1490 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2160 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1520 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Truss above Flytower | QP.E.ST.GEN.GEN.2180 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1540 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ Blade 2 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2200 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ Adaptable Theatre Incl. Metal Deck | QP.E.ST.GEN.GEN.1560 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.2220 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Loft Truss and Infilled Beam North Side Incl. Metal Deck | QP.E.ST.GEN.GEN.1610 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1600 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Lobby and Plaza Incl. Metal Deck | QP.E.ST.GEN.GEN.1660 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Frame for Mezzanine | QP.E.ST.GEN.GEN.1670 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Link Bridge and Helix Stair | QP.E.ST.GEN.GEN.1570 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1680 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | Shop Drawings ¦ Structural Steel ¦ Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck ¦ ROYAL MAJLIS | QP.E.ST.GEN.GEN.1640 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1090 | Submittal | 21 | 2026-03-26 | 2026-04-19
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1120 | Submittal | 21 | 2026-09-15 | 2026-10-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Wall Cladding | QP.E.AF.MBL.GEN.4440 | Submittal | 21 | 2026-10-11 | 2026-11-03
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1100 | Submittal | 21 | 2026-11-04 | 2026-11-28
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ FFE | QP.E.AF.MBL.GEN.5260 | Submittal | 21 | 2026-11-29 | 2026-12-22
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1170 | Submittal | 21 | 2026-04-20 | 2026-05-13
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1200 | Submittal | 20 | 2026-11-04 | 2026-11-26
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5700 | Submittal | 21 | 2026-11-28 | 2026-12-21
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1180 | Submittal | 21 | 2026-12-23 | 2027-01-16
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ FFE | QP.E.AF.MBL.GEN.5280 | Submittal | 21 | 2027-01-17 | 2027-02-09
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1220 | Submittal | 21 | 2026-05-14 | 2026-06-10
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1250 | Submittal | 28 | 2026-11-28 | 2026-12-29
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5720 | Submittal | 21 | 2026-12-30 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1230 | Submittal | 21 | 2027-01-24 | 2027-02-16
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ FFE | QP.E.AF.MBL.GEN.5300 | Submittal | 21 | 2027-02-17 | 2027-03-16
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1310 | Submittal | 21 | 2026-06-11 | 2026-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1340 | Submittal | 28 | 2026-12-30 | 2027-01-31
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5800 | Submittal | 21 | 2027-02-01 | 2027-02-25
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1320 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ FFE | QP.E.AF.MBL.GEN.5320 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1400 | Submittal | 21 | 2026-07-06 | 2026-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1430 | Submittal | 20 | 2027-02-01 | 2027-02-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5740 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1410 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ FFE | QP.E.AF.MBL.GEN.5340 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1000 | Submittal | 21 | 2026-07-30 | 2026-08-23
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1030 | Submittal | 20 | 2027-02-25 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5760 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1010 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ FFE | QP.E.AF.MBL.GEN.5360 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1490 | Submittal | 21 | 2026-08-24 | 2026-09-16
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1520 | Submittal | 20 | 2027-03-23 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5820 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1500 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ FFE | QP.E.AF.MBL.GEN.5380 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1580 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1610 | Submittal | 20 | 2027-04-15 | 2027-05-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5840 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1590 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ FFE | QP.E.AF.MBL.GEN.5400 | Submittal | 21 | 2027-07-06 | 2027-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1670 | Submittal | 21 | 2026-12-20 | 2027-01-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1700 | Submittal | 20 | 2027-05-23 | 2027-06-14
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5860 | Submittal | 28 | 2027-06-15 | 2027-07-17
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1680 | Submittal | 28 | 2027-07-18 | 2027-08-18
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ FFE | QP.E.AF.MBL.GEN.5420 | Submittal | 28 | 2027-07-31 | 2027-08-31
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1760 | Submittal | 21 | 2027-01-19 | 2027-02-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1790 | Submittal | 21 | 2027-05-23 | 2027-06-15
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5880 | Submittal | 21 | 2027-07-18 | 2027-08-10
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1770 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ FFE | QP.E.AF.MBL.GEN.5440 | Submittal | 21 | 2027-09-01 | 2027-09-26
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1880 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1910 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5900 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1890 | Submittal | 21 | 2027-09-13 | 2027-10-07
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ FFE | QP.E.AF.MBL.GEN.5460 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1800 | Submittal | 21 | 2027-04-22 | 2027-05-20
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1830 | Submittal | 21 | 2027-07-25 | 2027-08-17
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5920 | Submittal | 21 | 2027-08-25 | 2027-09-18
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1810 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ FFE | QP.E.AF.MBL.GEN.5480 | Submittal | 21 | 2027-10-11 | 2027-11-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1110 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1140 | Submittal | 21 | 2027-05-31 | 2027-06-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1120 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1370 | Submittal | 21 | 2027-03-01 | 2027-03-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1360 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Wall Cladding | QP.E.AF.BL1.GEN.5940 | Submittal | 21 | 2027-07-19 | 2027-08-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1340 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1650 | Submittal | 21 | 2027-06-14 | 2027-07-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1680 | Submittal | 14 | 2027-09-01 | 2027-09-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1660 | Submittal | 21 | 2027-11-18 | 2027-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1080 | Submittal | 21 | 2027-05-26 | 2027-06-19
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1110 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Wall Cladding | QP.E.AF.BL2.GEN.5960 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1090 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1580 | Submittal | 21 | 2027-07-04 | 2027-07-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1610 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1590 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1670 | Submittal | 21 | 2027-07-28 | 2027-08-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1700 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1680 | Submittal | 14 | 2028-01-18 | 2028-02-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1000 | Submittal | 24 | 2026-11-15 | 2026-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1030 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL3.GEN.5980 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1010 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1340 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1370 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1350 | Submittal | 21 | 2027-12-22 | 2028-01-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1210 | Submittal | 24 | 2026-12-27 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1240 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL4.GEN.6000 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1220 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1820 | Submittal | 21 | 2027-04-24 | 2027-05-22
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1850 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1830 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1730 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1760 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1740 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.2280 | Submittal | 24 | 2027-02-07 | 2027-03-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.2340 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.2300 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1130 | Submittal | 21 | 2027-03-22 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1160 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1140 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1500 | Submittal | 28 | 2027-06-29 | 2027-07-31
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1530 | Submittal | 21 | 2027-10-10 | 2027-11-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Wall Cladding | QP.E.AF.BL5.GEN.6020 | Submittal | 21 | 2027-12-16 | 2028-01-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1510 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1000 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1020 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Doors / Openings | QP.E.AF.PAR.GEN.1010 | Submittal | 28 | 2027-12-22 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Specialities | QP.E.AF.MBL.GEN.5160 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1030 | Submittal | 28 | 2027-10-16 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1050 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Doors / Openings | QP.E.AF.PAR.GEN.1040 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Specialities | QP.E.AF.MBL.GEN.5200 | Submittal | 21 | 2028-01-09 | 2028-02-01
Shop Drawings | Architecture and Fitouts | Amphitheatre | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4040 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Architecture and Fitouts | Amphitheatre | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.4070 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Amphitheatre | Wall Cladding | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Wall Cladding | QP.E.AF.MBL.GEN.6040 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | Architecture and Fitouts | Amphitheatre | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4050 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | Shop Drawings ¦ External Building Works (Guard House, SEC Room) | QP.E.EX.GEN.GEN.1270 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Main Building | QP.E.AF.MBL.GEN.6060 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 5 | Water Proofing - Roof - Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 5 | QP.E.AF.BL5.GEN.6180 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 4 | Water Proofing - Roof - Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 4 | QP.E.AF.BL4.GEN.6160 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 3 | Water Proofing - Roof - Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 3 | QP.E.AF.BL3.GEN.6140 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 1 | Water Proofing - Roof - Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 1 | QP.E.AF.BL1.GEN.6100 | Submittal | 21 | 2027-12-09 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 2 | Water Proofing - Roof - Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 2 | QP.E.AF.BL2.GEN.6120 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Wet Areas | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Wet Areas ¦ Main Building | QP.E.AF.MBL.GEN.4400 | Submittal | 21 | 2027-08-08 | 2027-08-31
Shop Drawings | Specialist Systems | Doors/ Openings | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Main Building | QP.E.AF.MBL.GEN.1140 | Submittal | 20 | 2027-06-29 | 2027-07-21
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.1130 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 2 | QP.E.AF.BL2.GEN.1100 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.1020 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.1230 | Submittal | 21 | 2027-08-16 | 2027-09-08
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.2320 | Submittal | 21 | 2027-09-09 | 2027-10-04
Shop Drawings | Specialist Systems | Doors/ Openings | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Amphitheatre | QP.E.AF.MBL.GEN.4060 | Submittal | 28 | 2027-11-13 | 2027-12-14
Shop Drawings | Specialist Systems | Conveying System | Waste Management | Waste Management | Waste Management | Waste Management | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Waste Management | QP.E.CY.GEN.GEN.1280 | Submittal | 14 | 2027-12-02 | 2027-12-18
Shop Drawings | Specialist Systems | Conveying System | Escalators | Escalators | Escalators | Escalators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Escalators | QP.E.CY.GEN.GEN.1040 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | Specialist Systems | Conveying System | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | QP.E.CY.GEN.GEN.1020 | Submittal | 28 | 2026-10-22 | 2026-11-23
Shop Drawings | Specialist Systems | Conveying System | Truck Elevators | Truck Elevators | Truck Elevators | Truck Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Truck Elevators | QP.E.CY.GEN.GEN.1000 | Submittal | 28 | 2026-09-19 | 2026-10-21
Shop Drawings | Specialist Systems | Conveying System | Inclined Elevators | Inclined Elevators | Inclined Elevators | Inclined Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Inclined Elevators | QP.E.CY.GEN.GEN.1050 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Main Building | QP.E.CY.GEN.GEN.1090 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 1 | QP.E.CY.GEN.GEN.1130 | Submittal | 28 | 2027-10-17 | 2027-11-17
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 2 | QP.E.CY.GEN.GEN.1170 | Submittal | 28 | 2027-09-13 | 2027-10-16
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 3 | Balde 3 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 3 | QP.E.CY.GEN.GEN.1210 | Submittal | 28 | 2027-06-07 | 2027-07-08
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 4 | QP.E.CY.GEN.GEN.1110 | Submittal | 28 | 2027-07-10 | 2027-08-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 5 | Balde 5 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 5 | QP.E.CY.GEN.GEN.1150 | Submittal | 28 | 2027-08-11 | 2027-09-12
Shop Drawings | Specialist Systems | Joinery Works | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Main Building | QP.E.AF.MBL.GEN.5540 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.6120 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.6160 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.6180 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.6200 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Shop Drawings ¦ Specialist Systems ¦ Kitchen and Laundary | QP.E.AF.MBL.GEN.5500 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Specialist Systems | Water Features | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Specialist Systems ¦ Water Features | QP.E.AF.MBL.GEN.6100 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Mechanical | QP.E.ME.MBL.GEN.6780 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical | QP.E.ME.MBL.GEN.6800 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6840 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical | QP.E.ME.MBL.GEN.6850 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6860 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical | QP.E.ME.MBL.GEN.6870 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Mechanical | QP.E.ME.MBL.GEN.6900 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical | QP.E.ME.MBL.GEN.6910 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Mechanical | QP.E.ME.MBL.GEN.6940 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical | QP.E.ME.MBL.GEN.6950 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Mechanical | QP.E.ME.MBL.GEN.6980 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Electrical | QP.E.ME.MBL.GEN.6990 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Mechanical | QP.E.ME.MBL.GEN.7020 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical | QP.E.ME.MBL.GEN.7030 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7060 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical | QP.E.ME.MBL.GEN.7070 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7100 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical | QP.E.ME.MBL.GEN.7110 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Mechanical | QP.E.ME.MBL.GEN.7140 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical | QP.E.ME.MBL.GEN.7150 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Mechanical | QP.E.ME.MBL.GEN.7180 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Electrical | QP.E.ME.MBL.GEN.7190 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Mechanical | QP.E.ME.MBL.GEN.7220 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical | QP.E.ME.MBL.GEN.7230 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1320 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1330 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1340 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1350 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ ICT Containment | QP.E.ME.MBL.GEN.1360 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1420 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1430 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1440 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1450 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1460 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1740 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1750 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1760 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1770 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1780 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1590 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1600 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1610 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1620 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.1630 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2040 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2050 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2060 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2070 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ ICT Containment | QP.E.ME.MBL.GEN.2080 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2240 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2250 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2260 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2270 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ ICT Containment | QP.E.ME.MBL.GEN.2280 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2440 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2450 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2460 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2470 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.2480 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2640 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2650 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2660 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2670 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2680 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2850 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2860 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2870 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2880 | Submittal | 28 | 2026-12-08 | 2027-01-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2890 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3070 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3080 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3090 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3100 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ ICT Containment | QP.E.ME.MBL.GEN.3110 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3290 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3300 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3310 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3320 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ ICT Containment | QP.E.ME.MBL.GEN.3330 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3500 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3510 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3520 | Submittal | 28 | 2026-12-23 | 2027-01-24
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3530 | Submittal | 28 | 2027-02-11 | 2027-03-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ ICT Containment | QP.E.ME.MBL.GEN.3540 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.MBL.GEN.5000 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.MBL.GEN.5040 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.MBL.GEN.5060 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.MBL.GEN.5080 | Submittal | 28 | 2027-03-07 | 2027-04-10
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.MBL.GEN.7280 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.MBL.GEN.7300 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.MBL.GEN.7320 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.MBL.GEN.7260 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.MBL.GEN.7340 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | LPG System | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ LPG System | QP.E.ME.MBL.GEN.5100 | Submittal | 21 | 2027-09-22 | 2027-10-17
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.MBL.GEN.7360 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Fire Suppression | QP.E.ME.CBR.GEN.1000 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Plumbing | Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Plumbing | QP.E.ME.CBR.GEN.1011 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ LPG System | QP.E.ME.CBR.GEN.1055 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.CBR.GEN.1022 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Electrical | QP.E.ME.CBR.GEN.1033 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ ELV (Low Current System) | QP.E.ME.CBR.GEN.1044 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.MBL.GEN.7380 | Submittal | 28 | 2027-12-09 | 2028-01-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Diesel | Diesel | Diesel | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Diesel | QP.E.ME.MBL.GEN.7420 | Submittal | 21 | 2028-02-01 | 2028-02-26
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Water Features | Water Features | Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Water Features | QP.E.ME.MBL.GEN.7440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M | QP.E.ME.MBL.GEN.6520 | Submittal | 28 | 2026-06-14 | 2026-07-15
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Grey Water Treatment/ Sewage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Grey Water Treatment/ Sewage | QP.E.ME.MBL.GEN.1050 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Stromwater/ Drainage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Stromwater/ Drainage | QP.E.ME.MBL.GEN.1060 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1040 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M | QP.E.ME.MBL.GEN.6540 | Submittal | 28 | 2026-07-16 | 2026-08-17
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ AHU Room | QP.E.ME.MBL.GEN.1160 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Transformer/ Switchgear/ Panel Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Transformer/ Switchgear/ Panel Room | QP.E.ME.MBL.GEN.1240 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Generator Room/ Diesel Tank | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Generator Room/ Diesel Tank | QP.E.ME.MBL.GEN.1250 | Submittal | 14 | 2026-10-05 | 2026-10-20
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | ETS/ CWP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ ETS/ CWP Room | QP.E.ME.MBL.GEN.1170 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1030 | Submittal | 14 | 2026-09-24 | 2026-10-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1290 | Submittal | 28 | 2026-09-01 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M | QP.E.ME.MBL.GEN.6560 | Submittal | 14 | 2026-08-18 | 2026-09-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1020 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Domestic Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Domestic Water | QP.E.ME.MBL.GEN.1010 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Fire Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Fire Water | QP.E.ME.MBL.GEN.1000 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1280 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 LOBBY LEVEL +905.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 LOBBY LEVEL +905.00M | QP.E.ME.MBL.GEN.6640 | Submittal | 21 | 2026-09-03 | 2026-09-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 UPEER LOBBY LEVEL MEZZANINE +909M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M | QP.E.ME.MBL.GEN.6660 | Submittal | 21 | 2026-09-29 | 2026-10-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L2 THEATRE STALLS +913M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L2 THEATRE STALLS +913M | QP.E.ME.MBL.GEN.6680 | Submittal | 21 | 2026-10-24 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | QP.E.ME.MBL.GEN.6700 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | QP.E.ME.MBL.GEN.6720 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 SECOND CIRCLE AND LOFT +928.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 SECOND CIRCLE AND LOFT +928.00M | QP.E.ME.MBL.GEN.6740 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M | QP.E.ME.MBL.GEN.5540 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - AHU Room | QP.E.ME.MBL.GEN.1180 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Makeup Air Unit and Ecology | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Makeup Air Unit and Ecology | QP.E.ME.MBL.GEN.1190 | Submittal | 14 | 2027-01-06 | 2027-01-21
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Sky Garden Irrigation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Sky Garden Irrigation | QP.E.ME.MBL.GEN.1070 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L6 SKY GARDEN +935.85M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L6 SKY GARDEN +935.85M | QP.E.ME.MBL.GEN.6760 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M | QP.E.ME.MBL.GEN.6580 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | Plant Room - Fan Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M ¦ Plant Room - Fan Room | QP.E.ME.MBL.GEN.6600 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Kitchen and Laundry | Kitchen and Laundry | Kitchen and Laundry | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Kitchen and Laundry | QP.E.ME.MBL.GEN.7400 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | MEP | Panels | Panels | Panels | Panels | Panels | Shop Drawings ¦ MEP ¦ Panels | QP.E.ME.MBL.GEN.6510 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Mechanical | QP.E.ME.BL1.GEN.3720 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical | QP.E.ME.BL1.GEN.3740 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL1.GEN.3760 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL1.GEN.3780 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Mechanical | QP.E.ME.BL1.GEN.3800 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical | QP.E.ME.BL1.GEN.3820 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1020 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1030 | Submittal | 21 | 2027-02-25 | 2027-03-23
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1040 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1050 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ ICT Containment | QP.E.ME.BL1.GEN.1060 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL1.GEN.2940 | Submittal | 21 | 2027-04-11 | 2027-05-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.2950 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.2960 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.2970 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL1.GEN.2980 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1510 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1520 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1530 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1540 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ ICT Containment | QP.E.ME.BL1.GEN.1550 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.BL1.GEN.3280 | Submittal | 21 | 2027-08-30 | 2027-09-22
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL1.GEN.3320 | Submittal | 21 | 2027-10-07 | 2027-10-31
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL1.GEN.3340 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL1.GEN.3360 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL1.GEN.3580 | Submittal | 21 | 2027-11-15 | 2027-12-08
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL1.GEN.3600 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL1.GEN.3620 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL1.GEN.3680 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL1.GEN.3640 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL1.GEN.3660 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3480 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL1.GEN.1000 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL1.GEN.3700 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3400 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical | QP.E.ME.BL2.GEN.3420 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL2.GEN.3440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL2.GEN.3460 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3480 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical | QP.E.ME.BL2.GEN.3500 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1020 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1030 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1040 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1050 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.1060 | Submittal | 21 | 2027-04-18 | 2027-05-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1910 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1920 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1930 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1940 | Submittal | 21 | 2027-04-29 | 2027-05-27
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL2.GEN.1950 | Submittal | 21 | 2027-05-12 | 2027-06-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.2110 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.2120 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.2130 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.2140 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.2150 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL2.GEN.3160 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL2.GEN.3200 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL2.GEN.3220 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL2.GEN.3240 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL2.GEN.3260 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL2.GEN.3280 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL2.GEN.3300 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL2.GEN.3380 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL2.GEN.3320 | Submittal | 28 | 2027-11-22 | 2027-12-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL2.GEN.3340 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3500 | Submittal | 14 | 2028-02-17 | 2028-03-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL2.GEN.1000 | Submittal | 16 | 2028-02-17 | 2028-03-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL2.GEN.3360 | Submittal | 14 | 2028-04-09 | 2028-04-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Mechanical | QP.E.ME.BL3.GEN.3640 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical | QP.E.ME.BL3.GEN.3660 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical | QP.E.ME.BL3.GEN.3700 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Mechanical | QP.E.ME.BL3.GEN.3680 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1020 | Submittal | 21 | 2026-06-17 | 2026-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.1030 | Submittal | 21 | 2026-07-12 | 2026-08-04
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1040 | Submittal | 21 | 2026-08-05 | 2026-08-29
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1050 | Submittal | 21 | 2026-08-30 | 2026-09-22
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ ICT Containment | QP.E.ME.BL3.GEN.1060 | Submittal | 21 | 2026-10-07 | 2026-10-31
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1790 | Submittal | 21 | 2026-12-31 | 2027-01-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.3280 | Submittal | 21 | 2027-01-25 | 2027-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1810 | Submittal | 21 | 2027-02-18 | 2027-03-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1820 | Submittal | 21 | 2027-03-18 | 2027-04-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ ICT Containment | QP.E.ME.BL3.GEN.1830 | Submittal | 21 | 2027-04-12 | 2027-05-05
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL3.GEN.3400 | Submittal | 21 | 2027-06-23 | 2027-07-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL3.GEN.3440 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL3.GEN.3460 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL3.GEN.3480 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL3.GEN.3500 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL3.GEN.3540 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL3.GEN.3560 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL3.GEN.3620 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL3.GEN.3600 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL3.GEN.3580 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3520 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL3.GEN.1000 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL3.GEN.3520 | Submittal | 14 | 2028-04-04 | 2028-04-19
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Mechanical | QP.E.ME.BL4.GEN.6010 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical | QP.E.ME.BL4.GEN.6030 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Mechanical | QP.E.ME.BL4.GEN.6050 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Electrical | QP.E.ME.BL4.GEN.6070 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Mechanical | QP.E.ME.BL4.GEN.6090 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical | QP.E.ME.BL4.GEN.6110 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Fire Suppression | QP.E.ME.BL4.GEN.2110 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2120 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2130 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2140 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ ICT Containment | QP.E.ME.BL4.GEN.2150 | Submittal | 21 | 2026-11-01 | 2026-11-24
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2910 | Submittal | 21 | 2026-12-05 | 2026-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.5550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2930 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2940 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ ICT Containment | QP.E.ME.BL4.GEN.2950 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2810 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2820 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2830 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2840 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ ICT Containment | QP.E.ME.BL4.GEN.2850 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL4.GEN.5770 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL4.GEN.5810 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL4.GEN.5830 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL4.GEN.5850 | Submittal | 21 | 2027-09-29 | 2027-10-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL4.GEN.5870 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL4.GEN.5930 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL4.GEN.5950 | Submittal | 21 | 2027-12-05 | 2027-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL4.GEN.5890 | Submittal | 21 | 2028-01-12 | 2028-02-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL4.GEN.5970 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL4.GEN.5990 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3540 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL4.GEN.3110 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL4.GEN.5910 | Submittal | 14 | 2028-04-02 | 2028-04-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Mechanical | QP.E.ME.BL5.GEN.3040 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical | QP.E.ME.BL5.GEN.3060 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL5.GEN.3080 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL5.GEN.3100 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Mechanical | QP.E.ME.BL5.GEN.3120 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical | QP.E.ME.BL5.GEN.3140 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1020 | Submittal | 21 | 2026-10-29 | 2026-11-22
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1030 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1040 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1050 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ ICT Containment | QP.E.ME.BL5.GEN.1060 | Submittal | 21 | 2026-11-25 | 2026-12-19
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1560 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1570 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1580 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL5.GEN.1590 | Submittal | 21 | 2027-04-10 | 2027-05-03
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1750 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1760 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1770 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1780 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ ICT Containment | QP.E.ME.BL5.GEN.1790 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL5.GEN.2800 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL5.GEN.2840 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL5.GEN.2860 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL5.GEN.2880 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL5.GEN.3020 | Submittal | 14 | 2027-10-24 | 2027-11-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL5.GEN.2900 | Submittal | 14 | 2027-12-01 | 2027-12-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL5.GEN.2920 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL5.GEN.3000 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL5.GEN.2940 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL5.GEN.2960 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3560 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL5.GEN.1000 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL5.GEN.2980 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Mechanical | QP.E.ME.PAR.GEN.1459 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Electrical | QP.E.ME.PAR.GEN.1479 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Mechanical | QP.E.ME.PAR.GEN.1499 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Electrical | QP.E.ME.PAR.GEN.1519 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Fire Suppression | QP.E.ME.PAR.GEN.1000 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1011 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1022 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1033 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ ICT Containment | QP.E.ME.PAR.GEN.1044 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Fire Suppression | QP.E.ME.PAR.GEN.1055 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1066 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1077 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1088 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ ICT Containment | QP.E.ME.PAR.GEN.1099 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.PAR.GEN.1219 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.PAR.GEN.1259 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.PAR.GEN.1279 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.PAR.GEN.1299 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.PAR.GEN.1419 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.PAR.GEN.1319 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.PAR.GEN.1339 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.PAR.GEN.1439 | Submittal | 14 | 2028-02-07 | 2028-02-23
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.PAR.GEN.1359 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.PAR.GEN.1379 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.PAR.GEN.1399 | Submittal | 14 | 2028-03-09 | 2028-03-25
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3600 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3610 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3620 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.4430 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4440 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.4450 | Submittal | 14 | 2027-12-18 | 2028-01-02
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3960 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3970 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3980 | Submittal | 14 | 2028-01-01 | 2028-01-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Fire Suppression | QP.E.ME.MBL.GEN.3930 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3940 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Electrical | QP.E.ME.MBL.GEN.3950 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Fire Suppression | QP.E.ME.MBL.GEN.3810 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3820 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Electrical | QP.E.ME.MBL.GEN.3830 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4400 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4410 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4420 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4340 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4350 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4360 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4520 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4530 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4540 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4640 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4650 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4660 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3870 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3880 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3890 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3840 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3850 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3860 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.4550 | Submittal | 21 | 2028-02-08 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4560 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.4570 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 3, 4 & 5 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 3, 4 & 5 | QP.E.FA.GEN.GEN.1460 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 1 & 2 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 1 & 2 | QP.E.FA.GEN.GEN.2180 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Loft and Lobby | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Loft and Lobby | QP.E.FA.GEN.GEN.2140 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | QP.E.FA.GEN.GEN.2160 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Blades | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Blades | QP.E.FA.GEN.GEN.1820 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Lobby and Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Lobby and Loft | QP.E.FA.GEN.GEN.1770 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Above Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Above Loft | QP.E.FA.GEN.GEN.1780 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Blades | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Blades | QP.E.FA.GEN.GEN.1890 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Main Building | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Main Building | QP.E.FA.GEN.GEN.2230 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Facade | Facade | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 1 | QP.E.FA.GEN.GEN.1920 | Submittal | 28 | 2026-09-29 | 2026-10-31
Shop Drawings | Facade | Facade | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 2 | QP.E.FA.GEN.GEN.1930 | Submittal | 28 | 2026-08-26 | 2026-09-28
Shop Drawings | Facade | Facade | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 3 | QP.E.FA.GEN.GEN.1940 | Submittal | 28 | 2026-05-17 | 2026-06-21
Shop Drawings | Facade | Facade | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 4 | QP.E.FA.GEN.GEN.1950 | Submittal | 28 | 2026-06-22 | 2026-07-23
Shop Drawings | Facade | Facade | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 5 | QP.E.FA.GEN.GEN.1960 | Submittal | 28 | 2026-07-25 | 2026-08-25
Shop Drawings | Facade | Facade | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Facade ¦ Amphitheatre | QP.E.FA.GEN.GEN.2240 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Lobby | Lobby | Lobby | Lobby | Shop Drawings ¦ Facade ¦ Lobby | QP.E.FA.GEN.GEN.2090 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | Loft | Loft | Loft | Loft | Shop Drawings ¦ Facade ¦ Loft | QP.E.FA.GEN.GEN.2100 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Above Loft | Above Loft | Above Loft | Above Loft | Shop Drawings ¦ Facade ¦ Above Loft | QP.E.FA.GEN.GEN.1910 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | Link Bridges | Link Bridges | Link Bridges | Link Bridges | Shop Drawings ¦ Facade ¦ Link Bridges | QP.E.FA.GEN.GEN.2050 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Facade | Facade | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Shop Drawings ¦ Facade ¦ Facade Lighting Fixtures | QP.E.FA.GEN.GEN.1450 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | GRC Cladding | GRC Cladding | GRC Cladding | GRC Cladding | Shop Drawings ¦ Facade ¦ GRC Cladding | QP.E.FA.GEN.GEN.1390 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 1 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 1 | QP.E.CV.MBL.GEN.3060 | Submittal | 28 | 2026-08-06 | 2026-09-07
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 2 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 2 | QP.E.CV.MBL.GEN.3560 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 3 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 3 | QP.E.CV.MBL.GEN.3580 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 4 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 4 | QP.E.CV.MBL.GEN.3600 | Submittal | 28 | 2027-01-03 | 2027-02-03
Shop Drawings | External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Shop Drawings ¦ External Works ¦ Waterproofing for External Works | QP.E.EX.GEN.GEN.1040 | Submittal | 28 | 2026-06-25 | 2026-07-27
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Excavation | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Excavation | QP.E.CV.MBL.GEN.3320 | Submittal | 28 | 2027-01-06 | 2027-02-07
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Blinding Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Blinding Including Embedded Items | QP.E.CV.MBL.GEN.3500 | Submittal | 28 | 2027-02-23 | 2027-03-29
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Foundation Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Foundation Including Embedded Items | QP.E.CV.MBL.GEN.3480 | Submittal | 28 | 2027-04-13 | 2027-05-19
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Structural Concrete Works Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Structural Concrete Works Including Embedded Items | QP.E.CV.MBL.GEN.3520 | Submittal | 28 | 2027-06-03 | 2027-07-05
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4000 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Finishing | Finishing | Finishing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Finishing | QP.E.AF.MBL.GEN.4030 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4010 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Doors / Openings | QP.E.AF.MBL.GEN.4020 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Fire Suppression | QP.E.ME.MBL.GEN.1690 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Plumbing | Plumbing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Plumbing | QP.E.ME.MBL.GEN.1700 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.1710 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Electrical | Electrical | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Electrical | QP.E.ME.MBL.GEN.1720 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ ELV (Low Current System) | QP.E.ME.MBL.GEN.1730 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | External Utilities | Irrigation Works | Irrigation Works | Irrigation Works | Irrigation Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ Irrigation Works | QP.E.EX.GEN.GEN.1090 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Drainage Works | External Drainage Works | External Drainage Works | External Drainage Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Drainage Works | QP.E.EX.GEN.GEN.1110 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Lighting Works | External Lighting Works | External Lighting Works | External Lighting Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Lighting Works | QP.E.EX.GEN.GEN.1170 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | External Utilities | Low Current | Low Current | Low Current | Low Current | Shop Drawings ¦ External Works ¦ External Utilities ¦ Low Current | QP.E.EX.GEN.GEN.1100 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Shop Drawings ¦ External Works ¦ Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 | Submittal | 14 | 2027-08-07 | 2027-08-22
Shop Drawings | External Works | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Shop Drawings ¦ External Works ¦ Water and Environment | QP.E.EX.GEN.GEN.1220 | Submittal | 21 | 2026-11-23 | 2026-12-16
Shop Drawings | External Works | External Fixtures | External Fixtures | External Fixtures | External Fixtures | External Fixtures | Shop Drawings ¦ External Works ¦ External Fixtures | QP.E.EX.GEN.GEN.1260 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | External Works | LPG System | LPG System | LPG System | LPG System | LPG System | Shop Drawings ¦ External Works ¦ LPG System | QP.E.EX.GEN.GEN.1300 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Fit-out | Fit-out | Fit-out | Fit-out | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Fit-out | QP.C.PS.GEN.GEN.2590 | Submittal | 110 | 2026-07-30 | 2026-12-06
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Stage Engineering | Stage Engineering | Stage Engineering | Stage Engineering | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Stage Engineering | QP.C.PS.GEN.GEN.2560 | Submittal | 110 | 2026-12-07 | 2027-04-17
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | AV / Broadcast | AV / Broadcast | AV / Broadcast | AV / Broadcast | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ AV / Broadcast | QP.C.PS.GEN.GEN.1200 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ Technology (ICT) | QP.C.PS.GEN.GEN.1810 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Control Systems | Control Systems | Control Systems | Control Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Control Systems | QP.C.PS.GEN.GEN.1880 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Lighting Systems | Lighting Systems | Lighting Systems | Lighting Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Lighting Systems | QP.C.PS.GEN.GEN.1850 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Conveying System Finishes | QP.C.PS.GEN.GEN.2120 | Submittal | 150 | 2027-06-07 | 2027-11-29
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | HVAC System | HVAC System | HVAC System | HVAC System | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ HVAC System | QP.C.PS.GEN.GEN.2100 | Submittal | 90 | 2027-11-01 | 2028-02-13
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | ID Finishes | ID Finishes | ID Finishes | ID Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ ID Finishes | QP.C.PS.GEN.GEN.1930 | Submittal | 90 | 2027-07-18 | 2027-10-31
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Water Features | QP.C.PS.GEN.GEN.1960 | Submittal | 120 | 2027-02-16 | 2027-07-13
Shop Drawings | Provisional Sums | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | Shop Drawings ¦ Provisional Sums ¦ PS5 - Signage and Wayfinding | QP.C.PS.GEN.GEN.2140 | Submittal | 60 | 2028-07-29 | 2028-10-07
Shop Drawings | Provisional Sums | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | Shop Drawings ¦ Provisional Sums ¦ PS6 - Soft Landscaping | QP.C.PS.GEN.GEN.2180 | Submittal | 160 | 2027-08-30 | 2028-03-08
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Concrete Superstructure | QP.C.PS.GEN.GEN.2360 | Submittal | 30 | 2028-06-08 | 2028-07-12
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Foundation | Foundation | Foundation | Foundation | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Foundation | QP.C.PS.GEN.GEN.2260 | Submittal | 30 | 2028-05-01 | 2028-06-07
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Landscape | Landscape | Landscape | Landscape | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Landscape | QP.C.PS.GEN.GEN.2320 | Submittal | 30 | 2028-07-31 | 2028-09-03
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Promenade Bridge MEP | QP.C.PS.GEN.GEN.2340 | Submittal | 30 | 2028-06-26 | 2028-07-30
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Technology (ICT) | QP.C.PS.GEN.GEN.2400 | Submittal | 150 | 2027-04-11 | 2027-10-07
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Traffic & Car Parking | QP.C.PS.GEN.GEN.2500 | Submittal | 150 | 2027-07-12 | 2028-01-03

## Picklists (hidden)
| #VALUE! |  | Numbering System Document - Metadata Mapping
DOCUMENT NUMBERING DROPDOWN ATTRIBUTES | [18 empty] | QIC GENERAL DROPDOWN ATTRIBUTES
FIELD 01 - PROJECT CODE |  | FIELD 02 - ORIGINATOR |  | FIELD 03 - CONTRACT REFERENCE |  | FIELD 04 - DOCUMENT TYPES |  | FIELD 05 - DISCIPLINE |  | FIELD 06 - AREA/ZONE |  | FIELD 07 - VENUE/BUILDING |  | FIELD 08 - SERIAL NUMBER |  |  |  |  | DOCUMENT DETAILS |  |  | SUITABILITY STATUS |  | NAP GENERAL DROPDOWN ATTRIBUTES
Ab. 01 | 1 - Project Name | Ab. 02 | 2 - Originator Name | Ab. 03 | 3 - Contract Reference | Ab. 04 | 4 - Document Type | Ab. 05 | 5 - Discipline | Ab. 06 | 6 - Area/Zone | Ab. 07 | 7 - Venue/Building | Ab. 08A | 8A - Drawing Type | Ab. 08B | 8B - Level | 8C - Sequence Number | Authoring Software | File/Exchange Format | Scope Area | Code | Status | Scale | Classification ID | Classification | Corporate Discipline | Author
QF01012 | Qiddaya Performing Arts Center | NES | Nesma and Partners | C04518 | Contract Number | AGD | Agenda | ACO | Acoustic | 00 | Overall | Z00000 | Overall | 0 | General (General Notes, Abbreviations, Legends, Single Line Diagrams, General Detail) | 00 | Non-Specific ( For Blade ) | 4 Digit Sequence Number For Drawings/Models | Revit | .rvt | Design Management | S0 (WIP) | Initial status or WIP | NTS | FI_60_25 | Drawing | Architectural | Nesma & Partners
[6 empty] | AVV | Agreed Value of Variation | ADM | Administration | 01 | Zone Sheet 1 | CENT01 | Center Block | 1 | Elevations (Vertical View) | B1 | Basement 1 - Parking A +900.50 | 3 Digit Sequence Number For Documents | Civil3D | .nwc | Architecture / LDC | S1 (Shared) | Suitable for Coordination | AS INDICATED | FI_90_75 | Schedule or table | Electrical | JINGGONG
[6 empty] | ASB | As Built | ARC | Architectural | 02 | Zone Sheet 2 | GARD01 | Guard House | 2 | Plans (Overall, Horizontal View, Floor Plan, Ceiling Plan, Site Plan, Loading Plan) | B2 | Basement 2 - Service +893.50 |  | MicrosoftWord | .nwd | Landscape | S2 (Shared) | Suitable for Information | 1:1 | FI_60_53 | Model | Façade | ALUTEC
[6 empty] | AUR | Audit Report | ADT | Area Development | 03 | Zone Sheet 3 | BLAD01 | Blade 01 | 3 | Sections (Sectional View, Wall Section, Riser) | B3 | Basement 3 - Promenade +887.750 |  | MicrosoftExcel | .ifc | Interior Design | S3 (Shared) | Suitable for Review and Comment | 1:2 | FI_60_15 | Clash Rendition | Fire & Life Safety | AFCO
[6 empty] | BOQ | Bill of Quantities | ASM | Assets Management | 04 | Zone Sheet 4 | BLAD02 | Blade 02 | 4 | Large-scale Views (Enlarged Details) (Plans, Elevations, Stair Sections, etc) | FL | Foundation level |  | Navisworks | .pdf | Signage & Wayfinding | S4 (Shared) | Suitable for Review and Authorisation | 1:5 | FI_40_10 | Calculations | Interior Design | DOKA
[6 empty] | BEP | BIM Execution Plan | AVL | Audio Visual | 05 | Zone Sheet 5 | BLAD03 | Blade 03 | 5 | Details (Any detail view, such as Wall / Floor / Manhole Detail, etc) | L1 | Lobby Level +905.0 |  | inDesign | .jpg | Public Interaction & Activation | S5 (Shared) | Suitable for Review and Acceptance | 1:10 | FI_90_72 | Report | Infrastructure | RAWABI
[6 empty] | BIM | BIM Model | AUV | Audio/Video | 06 | Zone Sheet 6 | BLAD04 | Blade 04 | 6 | Schedules and Diagrams | L2 | Theater Stalls +913.0 |  | Inviso | .xls | Structure | A1 (Published) | Authorised and Accepted-Concept Design | 1:20 | FI_10_90 | Transmittal | Landscape | FALLPROTEC
[6 empty] | BRF | Brief | BRG | Bridges | 07 | Zone Sheet 7 | BLAD05 | Blade 05 | 7 | Combination of different views | L3 | Stalles Mezz & AD Theater +917.5 |  | JPG | .xer | Geotechnical Engineering | A2 (Published) | Authorised and Accepted-Schematic Design 100% | 1:25 | FI_90_47 | Log | Mechanical | TKE
[6 empty] | BUD | Budget | BRC | Broadcast | 08 | Zone Sheet 8 | MBLAD1 | Mini Blade 01 | 8 | User-Defined (For types that do not fall in other categories) | L4 | First Circle & AD Theater +921.0 |  | Recap | .dwf | Civil Engineering | A3 (Published) | Authorised and Accepted-Detailed Design 100% | 1:50 | FI_80_50 | Method statement | Structural | Subcontractor - Unassigned
[6 empty] | CAL | Calculation | BIM | Building Information Modelling | 09 | Zone Sheet 9 | MBLAD4 | Mini Blade 04 | 9 | 3D Representation (Isometric, Perspectives, Photographes) | L5 | Second Circle & Loft |  | Rhino | .dwg | MEP Engineering | A4 (Published) | Authorised and Accepted-Tender | 1:100 | FI_90_64 | Plan |  | Provisional Sum
[6 empty] | CER | Certificate | BMS | Building Management System | 10 | Zone Sheet 10 | SECE01 | SEC Room |  |  | L6 | SKY Garden +935.85 |  | Sketchup | .bcf | Fire & Life Safety | A5 (Published) | Authorised and Accepted-IFC | 1:150
[6 empty] | COR | Change Order | CWC | Chilled Water / Cooling | 11 | Zone Sheet 11 | PARK01 | Parking Building |  |  | L8 | Royal Majlis +948.10M |  | Autocad | .3ds | Pitch Design & Sports Playing Surfaces | A6 (Published) | Authorised and Accepted-Construction (Shop Drawing) | 1:200
[6 empty] | CRA | Change Request Authorization | CIV | Civil | 12 | Zone Sheet 12 |  |  |  |  | M1 | Mez Upper Lobby +909.0 |  | ArcGIS | .skp | Specialist Lighting (Services and Systems) | A7 (Published) | Authorised and Accepted-As Built | 1:250
[6 empty] | CDT | Clash Detection Report | CPM | Contracts & Procurement | 13 | Zone Sheet 13 |  |  |  |  | M2 | Mez Loft MEP +931.10 |  |  | .docx | Acoustics | A8(Published) | Authorised and Accepted-In Use | 1:300
[6 empty] | CLM | Claim | CIN | Controls & Instrumentation | 14 | Zone Sheet 14 |  |  |  |  | RL | Roof Level |  |  | .rvt,.nwd,.ifc | AV / Broadcast |  |  | 1:350
[6 empty] | CIN | Client Instruction | CRE | Creative Designer | 15 | Zone Sheet 15 |  |  |  |  | ZZ | Overall |  |  | .nwc,.nwd,.ifc | Security |  |  | 1:500
[6 empty] | CRS | Comments Resolution Sheet | CDM | Crowd Management | 16 | Zone Sheet 16 | [8 empty] | .dwg,.nwc,.ifc | Vertical Transport
[6 empty] | CON | Contract | CUL | Culvert | 17 | Zone Sheet 17 | [8 empty] | .docx,.pdf | Facade & Roof Envelope
[6 empty] | COS | Cost Estimate | DRN | Drainage | 18 | Zone Sheet 18 | [8 empty] | .xer,.pdf | Crowd Modelling / Pedestrian Flow
[6 empty] | DAB | Dashboard | ELP | Earthing & Lighting Protection | 19 | Zone Sheet 19 | [8 empty] | .xls,.pdf | Sustainability
[6 empty] | DOA | Delegation of Authority | ELE | Electrical | 20 | Zone Sheet 20 | [8 empty] | .msp,.pdf | Accessibility
[6 empty] | DES | Design | ELC | Electrical Containment | 21 | Zone Sheet 21 | [8 empty] | .dwg,.pdf | Architect of Record
[6 empty] | MTX | Distribution Matrix | ENV | Environmental | 22 | Zone Sheet 22 | [8 empty] | .indd | Food & Beverage & Operations
[6 empty] | DSS | Dossier | EQP | Equipment | 23 | Zone Sheet 23 | [8 empty] | .pdf, .indd | Utilities, Roads & Infrastructure
[6 empty] | DRW | Drawing | FAC | Facade | 24 | Zone Sheet 24 | [8 empty] | .rvt,.nwc,.ifc | Traffic & Car Parking
[6 empty] | ENI | Engineer Instruction | FED | Federated | 25 | Zone Sheet 25 | [8 empty] | .gdb | Technology (ICT)
[6 empty] | EXP | Expenses | FIN | Finance | 26 | Zone Sheet 26 | [9 empty] | Sports & Specialist Lighting
[6 empty] | HOC | Handover Certificate | FAE | Fire Alarm & Emergency Lighting | 27 | Zone Sheet 27 | [9 empty] | BMS & Access Control
[6 empty] | IRT | Incident Report | FLS | Fire Life Safety | 28 | Zone Sheet 28 | [9 empty] | Waste Management
[6 empty] | ITP | Inspection & Test Plan | FPR | Fire Protection | [11 empty] | Health & Safety in Design
[6 empty] | INS | Instruction | FFE | Furniture Fixture & Equipment | [11 empty] | Wind
[6 empty] | IAB | Insurance and Bonds | GEN | General
[6 empty] | INV | Invoice | GIS | Geospatial Information System
[6 empty] | LAR | Laydown Area Access Request | GEH | Geotechnical & Hydraulics
[6 empty] | LTR | Letter | GRA | Graphics
[6 empty] | LIC | License | HSE | Health and Safety
[6 empty] | LST | List | EHV | High Voltage
[6 empty] | MAN | Manual | HVC | HVAC
[6 empty] | MPL | Master Plan | ICT | Information & Communication Technology
[6 empty] | MAR | Material Approval Request | INF | Infrastructure
[6 empty] | MIR | Material Inspection Request | INS | Installation
[6 empty] | MST | Method Statement | ITS | Intelligent Transportation System
[6 empty] | MOM | Minutes of Meeting | INT | Interior Design
[6 empty] | MIX | Mix Design | IRR | Irrigation
[6 empty] | MOD | Model | KNL | Kitchen & Laundry
[6 empty] | MRP | Monthly Report | LSE | Landscape
[6 empty] | NOC | No Objection Certificate | ELL | Lighting
[6 empty] | NCR | Non-Conformance Report | LTC | Lighting Control
[6 empty] | NDA | Non-Disclosure Agreement | ELV | Low Voltage
[6 empty] | NTC | Notice | LPG | LPG
[6 empty] | OMM | Operation & Maintenance Manual | MAR | Marine Engineering
[6 empty] | ORC | Organizational Chart | MPL | Master Planning
[6 empty] | OTR | Overtime Request | MEC | Mechanical
[6 empty] | PAP | Payment Application | EMV | Medium Voltage
[6 empty] | PYC | Payment Certificate | MEP | MEPF
[6 empty] | PRM | Permit | NTD | Non-Technical Document
[6 empty] | PAF | Personnel Approval Form | OSE | Operating Supplies and Equipment
[6 empty] | PIV | Photographs, Images & Videos | OTH | Others
[6 empty] | PLN | Plan | PLB | Plumbing
[6 empty] | PLT | Plant | PTW | Potable Water
[6 empty] | PPG | Policy & Procedure | PJC | Project Control
[6 empty] | PQS | Prequalification Submittal | QMS | Quality Management
[6 empty] | PRE | Presentation | RID | Rides
[6 empty] | PRO | Procedure | ERL | Road Lighting
[6 empty] | PEP | Project Execution Plan | RKW | Rockwork
[6 empty] | PRS | Proposal | SEC | Security System
[6 empty] | POR | Purchase Order | SEW | Sewage
[6 empty] | REG | Register | SHW | Show
[6 empty] | REP | Report | SGN | Signage / Wayfinding
[6 empty] | RFC | Request For Change | ESP | Small Power
[6 empty] | RSM | Resume | SSC | Smart City
[6 empty] | SVR | Safety Violation Report | SPL | Specialist Lighting
[6 empty] | SMP | Sample | SWD | Storm Water Drainage
[6 empty] | SCH | Schedule | STR | Structural
[6 empty] | SDW | Shop Drawing | SUR | Surveying / Mapping
[6 empty] | SIN | Site Instruction | SUS | Sustainability
[6 empty] | SOR | Site Observation Report | TEL | Telecommunication
[6 empty] | SPE | Specification | TNC | Testing/Commissioning
[6 empty] | STD | Standard | TFC | Traffic System
[6 empty] | SFA | Statement of Final Account | UTI | Utilities
[6 empty] | STR | Strategy | VNT | Ventilation Ductwork
[6 empty] | TOC | Taking Over Certificate | VTR | Vertical Transportation
[6 empty] | TOR | Task Order | VES | Voice Evacuation
[6 empty] | TEM | Template | WSM | Waste Management
[6 empty] | TDC | Tender Document | WTR | Water
[6 empty] | TRP | Test Report | CTV | CCTV System
[6 empty] | TMS | Time Sheet | ACS | Access Control System
[6 empty] | VOR | Variation Order | EFL | Facade Lighting
[6 empty] | WAR | Warranty / Guarantees | DES | Diesel
[6 empty] | WRP | Weekly Report | SMK | Smoke Ductwork
[6 empty] | WIR | Work Inspection Request | STL | Steel Structure
[6 empty] | RLM | RedLine Mark Drawing | FWR | Formwork
[6 empty] | MDP | Master Information Delivery Plan | ELS | Emergency Lighting system
[6 empty] | TDP | Task Information Delivery Plan | EBW | Electrical Builder Works
[8 empty] | MBW | Mechanical Builder Works
[8 empty] | EBC | Electrical Busway
[8 empty] | WFT | Water Features
[8 empty] | LOG | Logistics