## TIDP_Sheet
TASK INFORMATION DELIVERY PLAN (TIDP)
CLIENT | Qiddiya | #VALUE!
PROJECT | Qiddiya Performing Arts Center (QPAC)
ORGANISATION | Nesma & Partners
DISCIPLINE | Fire & Life Safety
APPROVER | BSBG
DATE CREATED
DATE LAST UPDATED
REVISION NUMBER | 00
DOCUMENT REFERENCE | QF01012-NES-C04518-TDP-FLS-00-000000-000001
This document shall be populated and kept up-to-date by the task team | [10 empty] | REFER TO THE FILE NAMING CONVENTION IN THE BIM EXECUTION PLAN | [10 empty] | DATA EXCHANGE #01 | [5 empty] | DATA EXCHANGE #02
[11 empty] | DOC REFERENCE GENERATOR | [10 empty] | STAGE: | CONSTRUCTION |  |  |  |  | STAGE: | HAND OVER
[22 empty] | PROGRAMME REF: | [5 empty] | PROGRAMME REF:
[5 empty] | EXCHANGE FORMATS | [5 empty] | FIELD 01 | FIELD 02 | FIELD 03 | FIELD 04 | FIELD 05 | FIELD 06 | FIELD 07 | FIELD 08 |  |  |  |  | LEVEL OF INFORMATION NEED | [5 empty] | LEVEL OF INFORMATION NEED
DOCUMENT NUMBER | DOCUMENT TITLE | EXTRACTED FROM MODEL | SCOPE AREA | AUTHORING SOFTWARE | EXCHANGE FORMAT | SCALE | DELIVERY MILESTONE | PACKAGE NAME | ACTIVITY ID | CLASSIFICATION CODE | PROJECT | ORIGINATOR | CONTRACT | DOCUMENT TYPE | DISCIPLINE | AREA/ZONE | VENUE/BUILDING | DRAWING TYPE | LEVEL | SEQUENCE NUMBER | CORPORATE DISCIPLINE | 01-AUTHOR | 01-GEOMETRICAL | 01-NON GEOMETRICAL | 01-DURATION (DAYS) | 01-PREDECESSOR | 01-EXCHANGE DATE | 02-AUTHOR | 02-GEOMETRICAL | 02-NON GEOMETRICAL | 02-DURATION (DAYS) | 02-PREDECESSOR | 02-EXCHANGE DATE
QF01012-NES-C04518-MOD-FLS-00-Z00000-0000001 | PASSIVE SYSTEM MODEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .rvt | NTS |  | 2D MODEL PASSIVE SYSTEM |  | FI_60_53 | QF01012 | NES | C04518 | MOD | FLS | 00 | Z00000 | 0 | 00 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-REP-FLS-00-Z00000-000001 | FIRE & LIFE SAFETY REPORT | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | MicrosoftWord | .docx,.pdf | NTS | 2027-02-12 | PASSIVE SYSTEM | QP.E.ME.CBR.GEN.1044 | FI_90_72 | QF01012 | NES | C04518 | REP | FLS | 00 | Z00000 | 0 | 00 | 001 | Fire & Life Safety | Nesma & Partners |  |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2002010 | FIRE AND LIFE SAFETY BLADE 1 GA PLAN (01 OF 07) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 2010 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2002011 | FIRE AND LIFE SAFETY BLADE 1 GA PLAN (02 OF 07) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 2011 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2002012 | FIRE AND LIFE SAFETY BLADE 1 GA PLAN (03 OF 07) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 2012 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2002013 | FIRE AND LIFE SAFETY BLADE 1 GA PLAN (04 OF 07) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 2013 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2002014 | FIRE AND LIFE SAFETY BLADE 1 GA PLAN (05 OF 07) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 2014 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2002015 | FIRE AND LIFE SAFETY BLADE 1 GA PLAN (06 OF 07) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 2015 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2002016 | FIRE AND LIFE SAFETY BLADE 1 GA PLAN (07 OF 07) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 2016 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005000 | EVACUATION LAYOUT BLADE 1 GA PLAN - +870.6M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5000 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005001 | EVACUATION LAYOUT BLADE 1 GA PLAN - +882M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005002 | EVACUATION LAYOUT BLADE 1 GA PLAN - +884.75M - NATURE PATH LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005003 | EVACUATION LAYOUT BLADE 1 GA PLAN - +887.75M - PROMENADE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005004 | EVACUATION LAYOUT BLADE 1 GA PLAN - +893.5M - B2 SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005005 | EVACUATION LAYOUT BLADE 1 GA PLAN - +899.25M - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005006 | EVACUATION LAYOUT BLADE 1 GA PLAN - +905M - L1 LOBBY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005007 | EVACUATION LAYOUT BLADE 1 GA PLAN - +910.75M - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005008 | EVACUATION LAYOUT BLADE 1 GA PLAN - +917.5M - L3 STALLS MEZZANINE | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5008 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005009 | EVACUATION LAYOUT BLADE 1 GA PLAN - +922.25M - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5009 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005010 | EVACUATION LAYOUT BLADE 1 GA PLAN - +928M - L5 LOFT | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5010 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005011 | EVACUATION LAYOUT BLADE 1 GA PLAN - +935.85M - L6 SKY GARDEN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5011 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005012 | EVACUATION LAYOUT BLADE 1 GA PLAN - +941.6M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5012 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005013 | EVACUATION LAYOUT BLADE 1 GA PLAN - +947.3M - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5013 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005014 | EVACUATION LAYOUT BLADE 1 GA PLAN - +953 M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5014 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005015 | EVACUATION LAYOUT BLADE 1 GA PLAN - +958.75 M - GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5015 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005016 | EVACUATION LAYOUT BLADE 1 GA PLAN - MECH LEVEL +966.515M | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5016 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005017 | EVACUATION LAYOUT BLADE 1 GA PLAN - +970.65M - GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5017 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005018 | EVACUATION LAYOUT BLADE 1 GA PLAN - MECH LEVEL +974.755M | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5018 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005019 | EVACUATION LAYOUT BLADE 1 GA PLAN - +989.00M - MEP LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5019 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD01-2005020 | EVACUATION LAYOUT BLADE 1 GA PLAN - +993.11M- GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD01 | 2 | 00 | 5020 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2002020 | FIRE AND LIFE SAFETY BLADE 2 GA PLAN (01 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 2020 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2002021 | FIRE AND LIFE SAFETY BLADE 2 GA PLAN (02 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 2021 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2002022 | FIRE AND LIFE SAFETY BLADE 2 GA PLAN (03 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 2022 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2002023 | FIRE AND LIFE SAFETY BLADE 2 GA PLAN (04 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 2023 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2002024 | FIRE AND LIFE SAFETY BLADE 2 GA PLAN (05 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 2024 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005030 | EVACUATION LAYOUT BLADE 2 GA PLAN - +876.25M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5030 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005031 | EVACUATION LAYOUT BLADE 2 GA PLAN - +882M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5031 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005032 | EVACUATION LAYOUT BLADE 2 GA PLAN - +887.75M - PROMENADE | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5032 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005033 | EVACUATION LAYOUT BLADE 2 GA PLAN - +893.5M - B2 SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5033 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005034 | EVACUATION LAYOUT BLADE 2 GA PLAN - +899.25M - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5034 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005035 | EVACUATION LAYOUT BLADE 2 GA PLAN - +905M - L1 LOBBY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5035 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005036 | EVACUATION LAYOUT BLADE 2 GA PLAN - +910.75M - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5036 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005037 | EVACUATION LAYOUT BLADE 2 GA PLAN - +916.5M - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5037 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005038 | EVACUATION LAYOUT BLADE 2 GA PLAN - +928M - L5 LOFT | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5038 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005039 | EVACUATION LAYOUT BLADE 2 GA PLAN - +935.85M - L6 SKY GARDEN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5039 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005040 | EVACUATION LAYOUT BLADE 2 GA PLAN - +941.6M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5040 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005041 | EVACUATION LAYOUT BLADE 2 GA PLAN - +945.40M -SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5041 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005042 | EVACUATION LAYOUT BLADE 2 GA PLAN - +948.10M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5042 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005043 | EVACUATION LAYOUT BLADE 2 GA PLAN - +951.625 - GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5043 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD02-2005044 | EVACUATION LAYOUT BLADE 2 GA PLAN - +957.25M - GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | PASSIVE SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD02 | 2 | 00 | 5044 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2002030 | FIRE AND LIFE SAFETY BLADE 3 GA PLAN (01 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 2030 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2002031 | FIRE AND LIFE SAFETY BLADE 3 GA PLAN (02 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 2031 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2002032 | FIRE AND LIFE SAFETY BLADE 3 GA PLAN (03 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 2032 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2002033 | FIRE AND LIFE SAFETY BLADE 3 GA PLAN (04 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 2033 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2002034 | FIRE AND LIFE SAFETY BLADE 3 GA PLAN (05 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 2034 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005050 | EVACUATION LAYOUT BLADE 3 GA PLAN - +847.5M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5050 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005051 | EVACUATION LAYOUT BLADE 3 GA PLAN - +853.25M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5051 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005052 | EVACUATION LAYOUT BLADE 3 GA PLAN - +859.00M - NATURE PATH DISCHARGE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5052 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005053 | EVACUATION LAYOUT BLADE 3 GA PLAN - +867.62M RENTABLE VIP LOUNGE 5 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5053 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005054 | EVACUATION LAYOUT BLADE 3 GA PLAN - +876.25M RENTABLE VIP LOUNGE 4 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5054 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005055 | EVACUATION LAYOUT BLADE 3 GA PLAN - +887.75M - B3 RENTABLE VIP LOUNGE 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5055 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005056 | EVACUATION LAYOUT BLADE 3 GA PLAN - +891.58M - B2 JOURNEY | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5056 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005057 | EVACUATION LAYOUT BLADE 3 GA PLAN - +900.33M - B1 JOURNEY | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5057 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005058 | EVACUATION LAYOUT BLADE 3 GA PLAN - +905M - L1 RECEPTION LOUNGE | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5058 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005059 | EVACUATION LAYOUT BLADE 3 GA PLAN - +910.75M - RENTABLE VIP LOUNGE 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5059 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005060 | EVACUATION LAYOUT BLADE 3 GA PLAN - +916.5M - RENTABLE VIP LOUNGE 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5060 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005061 | EVACUATION LAYOUT BLADE 3 GA PLAN - +921M - L4 ROYAL OBERVATION | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5061 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005062 | EVACUATION LAYOUT BLADE 3 GA PLAN - +928M - L5 LOFT | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5062 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD03-2005063 | EVACUATION LAYOUT BLADE 3 GA PLAN - +931.1M SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | PASSIVE SYSTEM | QP.E.ME.BL3.GEN.3400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD03 | 2 | 00 | 5063 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2002040 | FIRE AND LIFE SAFETY BLADE 4 GA PLAN (01 OF 06) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 2040 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2002041 | FIRE AND LIFE SAFETY BLADE 4 GA PLAN (02 OF 06) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 2041 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2002042 | FIRE AND LIFE SAFETY BLADE 4 GA PLAN (03 OF 06) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 2042 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2002043 | FIRE AND LIFE SAFETY BLADE 4 GA PLAN (04 OF 06) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 2043 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2002044 | FIRE AND LIFE SAFETY BLADE 4 GA PLAN (05 OF 06) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 2044 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2002045 | FIRE AND LIFE SAFETY BLADE 4 GA PLAN (06 OF 06) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 2045 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005070 | EVACUATION LAYOUT BLADE 4 GA PLAN - +863.85M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5070 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005071 | EVACUATION LAYOUT BLADE 4 GA PLAN - +870.5M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5071 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005072 | EVACUATION LAYOUT BLADE 4 GA PLAN - +876.25M - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5072 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005073 | EVACUATION LAYOUT BLADE 4 GA PLAN - +887.75M PROMENADE | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5073 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005074 | EVACUATION LAYOUT BLADE 4 GA PLAN - +899.25M - B1 JOURNEY | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5074 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005075 | EVACUATION LAYOUT BLADE 4 GA PLAN - +910.75M - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5075 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005076 | EVACUATION LAYOUT BLADE 4 GA PLAN - +916.5M - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5076 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005077 | EVACUATION LAYOUT BLADE 4 GA PLAN - +922.25M - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5077 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005078 | EVACUATION LAYOUT BLADE 4 GA PLAN - +928M - L5 LOFT | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5078 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005079 | EVACUATION LAYOUT BLADE 4 GA PLAN - +935.85M - L6 SKY GARDEN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5079 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005080 | EVACUATION LAYOUT BLADE 4 GA PLAN - +941.6M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5080 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005081 | EVACUATION LAYOUT BLADE 4 GA PLAN - +947.35 L8 MACHINE ROOM LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5081 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005082 | EVACUATION LAYOUT BLADE 4 GA PLAN - +952.45M - GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5082 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005083 | EVACUATION LAYOUT BLADE 4 GA PLAN - +959.0M - GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5083 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005084 | EVACUATION LAYOUT BLADE 4 GA PLAN - +968.30M - GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5084 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD04-2005085 | EVACUATION LAYOUT BLADE 4 GA PLAN - +975.82.30M - GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD04 | 2 | 00 | 5085 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2002050 | FIRE AND LIFE SAFETY BLADE 5 GA PLAN (01 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 2050 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2002051 | FIRE AND LIFE SAFETY BLADE 5 GA PLAN (02 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 2051 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2002052 | FIRE AND LIFE SAFETY BLADE 5 GA PLAN (03 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 2052 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2002053 | FIRE AND LIFE SAFETY BLADE 5 GA PLAN (04 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 2053 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2002054 | FIRE AND LIFE SAFETY BLADE 5 GA PLAN (05 OF 05) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 2054 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005090 | EVACUATION LAYOUT BLADE 5 GA PLAN - +894.5M - B2 SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5090 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005091 | EVACUATION LAYOUT BLADE 5 GA PLAN - +899.5M - B1 PARKING | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5091 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005092 | EVACUATION LAYOUT BLADE 5 GA PLAN - +905M - L1 LOBBY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5092 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005093 | EVACUATION LAYOUT BLADE 5 GA PLAN - +910.75M - BOX OFFICE SUPPORT | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5093 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005094 | EVACUATION LAYOUT BLADE 5 GA PLAN - +917.5M - L3 STALLS MEZZANINE | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5094 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005095 | EVACUATION LAYOUT BLADE 5 GA PLAN - +922.25M. - JOURNEY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5095 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005096 | EVACUATION LAYOUT BLADE 5 GA PLAN - +928M - L5 LOFT | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5096 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005097 | EVACUATION LAYOUT BLADE 5 GA PLAN - +935.85M - L6 SKY GARDEN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5097 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005098 | EVACUATION LAYOUT BLADE 5 GA PLAN - +941.6M - SERVICE LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5098 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005099 | EVACUATION LAYOUT BLADE 5 GA PLAN - +948.10 - L8 ROYAL MAJLIS | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5099 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005100 | EVACUATION LAYOUT BLADE 5 GA PLAN - +953.75 - MACHINE ROOM LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5100 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005101 | EVACUATION LAYOUT BLADE 5 GA PLAN - +957.35 - GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5101 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005102 | EVACUATION LAYOUT BLADE 5 GA PLAN - +962.64 - GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5102 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-BLAD05-2005103 | EVACUATION LAYOUT BLADE 5 GA PLAN - +969.30M - GANTRY LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | PASSIVE SYSTEM | QP.E.ME.BL5.GEN.2800 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | BLAD05 | 2 | 00 | 5103 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2000070 | FIRE AND LIFE SAFETY GANTRY GA PLAN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | 00 | 0070 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2000071 | FIRE AND LIFE SAFETY GANTRY GA PLAN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | 00 | 0071 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2000072 | FIRE AND LIFE SAFETY GANTRY GA PLAN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | 00 | 0072 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2004130 | EVACUATION LAYOUT GANTRY PLANS - +924.500 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | 00 | 4130 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2004131 | EVACUATION LAYOUT GANTRY PLANS - +928.000 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | 00 | 4131 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2004132 | EVACUATION LAYOUT GANTRY PLANS - +931.500 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | 00 | 4132 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2004133 | EVACUATION LAYOUT GANTRY PLANS - +934.200 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | 00 | 4133 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2004134 | EVACUATION LAYOUT GANTRY PLANS - OVERSTAGE GRID LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | 00 | 4134 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2004135 | EVACUATION LAYOUT GANTRY PLANS - MEP @ +942.200 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | 00 | 4135 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B10090 | FIRE AND LIFE SAFETY DRAWING PLAN - B1 PARKING A +900.5M - EXIT STRATEGY | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-02-12 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B1 | 0090 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B11020 | FIRE AND LIFE SAFETY B1 PARKING PLAN-A - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B1 | 1020 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B11030 | FIRE AND LIFE SAFETY B1 SERVICE PLAN -B- OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B1 | 1030 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B13030 | FIREFIGHTER ACCESS ROUTE DRAWING - PLAN - B1 PARKING B +900.5M | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B1 | 3030 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B14020 | EVACUATION LAYOUT B1 PARKING - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B1 | 4020 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B14021 | EVACUATION LAYOUT B1 PARKING - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B1 | 4021 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B14022 | EVACUATION LAYOUT B1 PARKING - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B1 | 4022 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B14023 | EVACUATION LAYOUT B1 SERVICE - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B1 | 4023 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B14024 | EVACUATION LAYOUT B1 SERVICE - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B1 | 4024 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B14025 | EVACUATION LAYOUT B1 SERVICE - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B1 | 4025 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B14026 | EVACUATION LAYOUT B1 SERVICE - PART 4 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B1 | 4026 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B21010 | FIRE AND LIFE SAFETY B2 SERVICE PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B2 | 1010 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B24010 | EVACUATION LAYOUT B2 SERVICE - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B2 | 4010 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B24011 | EVACUATION LAYOUT B2 SERVICE - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B2 | 4011 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B24012 | EVACUATION LAYOUT B2 SERVICE - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B2 | 4012 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B24013 | EVACUATION LAYOUT B2 SERVICE - PART 4 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B2 | 4013 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B24014 | EVACUATION LAYOUT B2 SERVICE - PART 5 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B2 | 4014 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B24015 | EVACUATION LAYOUT B2 SERVICE - PART 6 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B2 | 4015 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B30080 | FIRE AND LIFE SAFETY DRAWING PROMENADE PLAN +887.750M - EXIT STRATEGY | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-02-12 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B3 | 0080 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B31000 | FIRE AND LIFE SAFETY PROMENADE PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-07-23 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B3 | 1000 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B33000 | FIREFIGHTER ACCESS ROUTE DRAWING - PROMENADE PLAN FIRE VEHICLE ACCESS ROAD | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-01-21 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B3 | 3000 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B33020 | FIREFIGHTER ACCESS ROUTE DRAWING - PROMENADE PLAN +887.750M | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B3 | 3020 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B34000 | EVACUATION LAYOUT PROMENADE - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B3 | 4000 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2B34001 | EVACUATION LAYOUT PROMENADE - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | B3 | 4001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L10100 | FIRE AND LIFE SAFETY DRAWING PLAN - LOBBY LEVEL +905M - EXIT STRATEGY | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-02-12 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L1 | 0100 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L11040 | FIRE AND LIFE SAFETY LOBBY PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L1 | 1040 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L13010 | FIREFIGHTER ACCESS ROUTE DRAWING - LOBBY PLAN FIRE VEHICLE ACCESS ROAD | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-01-21 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L1 | 3010 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L13040 | FIREFIGHTER ACCESS ROUTE DRAWING - PLAN - LOBBY LEVEL +905M | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L1 | 3040 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L14030 | EVACUATION LAYOUT LOBBY - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L1 | 4030 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L14031 | EVACUATION LAYOUT LOBBY - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L1 | 4031 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L14032 | EVACUATION LAYOUT LOBBY - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L1 | 4032 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L14033 | EVACUATION LAYOUT LOBBY - PART 4 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L1 | 4033 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L14034 | EVACUATION LAYOUT LOBBY - PART 5 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L1 | 4034 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L14035 | EVACUATION LAYOUT LOBBY - PART 6 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L1 | 4035 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L21060 | FIRE AND LIFE SAFETY THEATRE STALLS PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L2 | 1060 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L24050 | EVACUATION LAYOUT THEATRE STALLS - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L2 | 4050 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L24051 | EVACUATION LAYOUT THEATRE STALLS - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L2 | 4051 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L24052 | EVACUATION LAYOUT THEATRE STALLS - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L2 | 4052 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L24053 | EVACUATION LAYOUT THEATRE STALLS - PART 4 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L2 | 4053 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L24054 | EVACUATION LAYOUT THEATRE STALLS - PART 5 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L2 | 4054 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L24055 | EVACUATION LAYOUT THEATRE STALLS - PART 6 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L2 | 4055 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L24056 | EVACUATION LAYOUT THEATRE STALLS - PART 7 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L2 | 4056 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L24057 | EVACUATION LAYOUT THEATRE STALLS - PART 8 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L2 | 4057 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L31070 | FIRE AND LIFE SAFETY STALL MEZZANINE & ADAPTIVE THEATRE PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L3 | 1070 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L33050 | FIREFIGHTER ACCESS ROUTE DRAWING - L3 STALL MEZZANINE & ADAPTIVE THEATER +917.5M | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L3 | 3050 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L34060 | EVACUATION LAYOUT STALL MEZZANINE & ADAPTIVE THEATRE - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L3 | 4060 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L34061 | EVACUATION LAYOUT STALL MEZZANINE & ADAPTIVE THEATRE - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L3 | 4061 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L34062 | EVACUATION LAYOUT STALL MEZZANINE & ADAPTIVE THEATRE - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L3 | 4062 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L34063 | EVACUATION LAYOUT STALL MEZZANINE & ADAPTIVE THEATRE - PART 4 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L3 | 4063 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L34064 | EVACUATION LAYOUT STALL MEZZANINE & ADAPTIVE THEATRE - PART 5 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L3 | 4064 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L34065 | EVACUATION LAYOUT STALL MEZZANINE & ADAPTIVE THEATRE - PART 6 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L3 | 4065 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L41080 | FIRE AND LIFE SAFETY FIRST CIRCLE & ADAPTIVE THEATRE PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L4 | 1080 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L43060 | FIREFIGHTER ACCESS ROUTE DRAWING - L4 FIRST CIRCLE & ADAPTIVE THEATER +921M GA | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L4 | 3060 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L44070 | EVACUATION LAYOUT FIRST CIRCLE & ADAPTIVE THEATRE - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L4 | 4070 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L44071 | EVACUATION LAYOUT FIRST CIRCLE & ADAPTIVE THEATRE - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L4 | 4071 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L44072 | EVACUATION LAYOUT FIRST CIRCLE & ADAPTIVE THEATRE - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L4 | 4072 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L44073 | EVACUATION LAYOUT FIRST CIRCLE & ADAPTIVE THEATRE - PART 4 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L4 | 4073 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L51090 | FIRE AND LIFE SAFETY SECOND CIRCLE & LOFT PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L5 | 1090 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L53070 | FIREFIGHTER ACCESS ROUTE DRAWING - SECOND CIRCLE & LOFT +928M | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-08 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L5 | 3070 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L54080 | EVACUATION LAYOUT SECOND CIRCLE & LOFT - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L5 | 4080 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L54081 | EVACUATION LAYOUT SECOND CIRCLE & LOFT - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L5 | 4081 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L54082 | EVACUATION LAYOUT SECOND CIRCLE & LOFT - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L5 | 4082 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L54083 | EVACUATION LAYOUT SECOND CIRCLE & LOFT - PART 4 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L5 | 4083 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L54084 | EVACUATION LAYOUT SECOND CIRCLE & LOFT - PART 5 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L5 | 4084 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L54085 | EVACUATION LAYOUT SECOND CIRCLE & LOFT - PART 6 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L5 | 4085 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L54086 | EVACUATION LAYOUT SECOND CIRCLE & LOFT - PART 7 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L5 | 4086 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L61110 | FIRE AND LIFE SAFETY SKY GARDEN PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L6 | 1110 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L63080 | FIREFIGHTER ACCESS ROUTE DRAWING - PLAN - SKY GARDEN +935.85M | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L6 | 3080 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L64100 | EVACUATION LAYOUT SKY GARDEN - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L6 | 4100 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L64101 | EVACUATION LAYOUT SKY GARDEN - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L6 | 4101 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L64102 | EVACUATION LAYOUT SKY GARDEN - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L6 | 4102 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L64103 | EVACUATION LAYOUT SKY GARDEN - PART 4 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L6 | 4103 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L64104 | EVACUATION LAYOUT SKY GARDEN - PART 5 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L6 | 4104 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L64105 | EVACUATION LAYOUT SKY GARDEN - PART 6 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L6 | 4105 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L81120 | FIRE AND LIFE SAFETY ROYAL MAJLIS PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-12-03 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L8 | 1120 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L83090 | FIREFIGHTER ACCESS ROUTE DRAWING -PLAN -ROYAL MAJLIS +948.10 M | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L8 | 3090 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L84110 | EVACUATION LAYOUT ROYAL MAJLIS - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L8 | 4110 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L84111 | EVACUATION LAYOUT ROYAL MAJLIS - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L8 | 4111 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2L84112 | EVACUATION LAYOUT ROYAL MAJLIS - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | L8 | 4112 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2M11050 | FIRE AND LIFE SAFETY UPPER LOBBY PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-01 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | M1 | 1050 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2M14040 | EVACUATION LAYOUT MEZ UPPER LOBBY MEZZANINE - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | M1 | 4040 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2M14041 | EVACUATION LAYOUT MEZ UPPER LOBBY MEZZANINE - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | M1 | 4041 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2M14042 | EVACUATION LAYOUT MEZ UPPER LOBBY MEZZANINE - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | M1 | 4042 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2M21100 | FIRE AND LIFE SAFETY LOFT MEP MEZZANINE PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | M2 | 1100 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2M24090 | EVACUATION LAYOUT LOFT MEP MEZZANINE - PART 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | M2 | 4090 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2M24091 | EVACUATION LAYOUT LOFT MEP MEZZANINE - PART 2 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | M2 | 4091 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2M24092 | EVACUATION LAYOUT LOFT MEP MEZZANINE - PART 3 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | M2 | 4092 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2M24093 | EVACUATION LAYOUT LOFT MEP MEZZANINE - PART 4 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | M2 | 4093 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2M24094 | EVACUATION LAYOUT LOFT MEP MEZZANINE - PART 5 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | M2 | 4094 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2M24095 | EVACUATION LAYOUT LOFT MEP MEZZANINE - PART 6 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | M2 | 4095 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-2RL1130 | FIRE AND LIFE SAFETY ROOF PLAN - OVERALL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-12-24 | PASSIVE SYSTEM | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 2 | RL | 1130 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-16-GARD01-2004120 | EVACUATION LAYOUT GUARDHOUSE | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-11 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 16 | GARD01 | 2 | 00 | 4120 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-MBLAD1-2002017 | FIRE AND LIFE SAFETY- MINI BLADE 1 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.BL1.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | MBLAD1 | 2 | 00 | 2017 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-MBLAD4-2002046 | FIRE AND LIFE SAFETY - MINI BLADE 4 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | PASSIVE SYSTEM | QP.E.ME.BL4.GEN.5770 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | MBLAD4 | 2 | 00 | 2046 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-Z00000-0ZZ0002 | General Details | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | AS INDICATED | 2027-02-12 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | Z00000 | 0 | ZZ | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-4L30001 | FIRE AND LIFE SAFETY ADAPTABLE THEATRE CONFIGURATIONS PART 01 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 4 | L3 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-4L30002 | FIRE AND LIFE SAFETY ADAPTABLE THEATRE CONFIGURATIONS PART 02 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 4 | L3 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-4L30003 | FIRE AND LIFE SAFETY ADAPTABLE THEATRE CONFIGURATIONS PART 03 | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 4 | L3 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-4L20011 | FIRE AND LIFE SAFETY PREMIUM THEATRE CONFIGURATIONS L02 LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 4 | L2 | 0011 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-4L30012 | FIRE AND LIFE SAFETY PREMIUM THEATRE CONFIGURATIONS L03 LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 4 | L3 | 0012 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-4L40013 | FIRE AND LIFE SAFETY PREMIUM THEATRE CONFIGURATIONS L04 LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 4 | L4 | 0013 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-CENT01-4L50014 | FIRE AND LIFE SAFETY PREMIUM THEATRE CONFIGURATIONS L05 LEVEL | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-21 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | CENT01 | 4 | L5 | 0014 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-Z00000-2B30030 | FIRE VEICHLE ACCESS ROAD PROMENADE PLAN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-01-21 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | Z00000 | 2 | B3 | 0030 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-Z00000-2L10040 | FIRE VEHICLE ACCESS ROAD LOBBY PLAN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-01-21 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | Z00000 | 2 | L1 | 0040 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-Z00000-2ZZ0010 | FIRE AND LIFESAFETY-RAMPED ACCESS ROAD SITE PLAN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-01-21 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | Z00000 | 2 | ZZ | 0010 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-Z00000-2ZZ0020 | FIRE VEHICLE ACCESS ROAD SITE PLAN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-01-21 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | Z00000 | 2 | ZZ | 0020 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-Z00000-6ZZ0010 | FIRE AND LIFE SAFETY BLADE OCCUPANT LOAD TABLES (SHEET 1) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | Z00000 | 6 | ZZ | 0010 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-Z00000-6ZZ0011 | FIRE AND LIFE SAFETY BLADE OCCUPANT LOAD TABLES (SHEET 2) | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | Z00000 | 6 | ZZ | 0011 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-00-Z00000-6ZZ0020 | FIRE AND LIFE SAFETY EXIT STAIRS DISCHARGE MATRIX | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 00 | Z00000 | 6 | ZZ | 0020 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-16-GARD01-2000050 | FIRE AND LIFE SAFETY GUARDHOUSE GA PLAN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-11 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 16 | GARD01 | 2 | 00 | 0050 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-17-SECE01-2000060 | FIRE AND LIFE SAFETY-WRMU ROOM PLAN | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-11 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 17 | SECE01 | 2 | 00 | 0060 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FLS-17-SECE01-2000061 | EVACUATION LAYOU T-WRMU ROOM | QF01012-BSB-MOD-3DM-ARC-00-Z00-00001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-11 | PASSIVE SYSTEM | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FLS | 17 | SECE01 | 2 | 00 | 0061 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2B30001 | FIRE ALARM & VOICE EVACUATION SYSTEM - B3 PROMENADE +887.750M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-07-23 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | B3 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2B30002 | FIRE ALARM & VOICE EVACUATION SYSTEM - B3 PROMENADE +887.750M - SHEET 01-(01/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | B3 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2B30003 | FIRE ALARM & VOICE EVACUATION SYSTEM - B3 PROMENADE +887.750M - SHEET 02-(02/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | B3 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2B30004 | FIRE ALARM & VOICE EVACUATION SYSTEM - B3 PROMENADE +887.750M - SHEET 05-(03/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | B3 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-11-CENT01-2B30005 | FIRE ALARM & VOICE EVACUATION SYSTEM - B3 PROMENADE +887.750M - SHEET 11-(04/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 11 | CENT01 | 2 | B3 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2B20001 | FIRE ALARM & VOICE EVACUATION SYSTEM - B2 SERVICE +893.5M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | B2 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2B20002 | FIRE ALARM & VOICE EVACUATION SYSTEM - B2 SERVICE +893.5M - SHEET 01-(01/08) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | B2 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2B20003 | FIRE ALARM & VOICE EVACUATION SYSTEM - B2 SERVICE +893.5M - SHEET 02-(02/08) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | B2 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-04-CENT01-2B20004 | FIRE ALARM & VOICE EVACUATION SYSTEM - B2 SERVICE +893.5M - SHEET 04-(03/08) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 04 | CENT01 | 2 | B2 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2B20005 | FIRE ALARM & VOICE EVACUATION SYSTEM - B2 SERVICE +893.5M - SHEET 05-(04/08) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | B2 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-06-CENT01-2B20006 | FIRE ALARM & VOICE EVACUATION SYSTEM - B2 SERVICE +893.5M - SHEET 06-(05/08) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 06 | CENT01 | 2 | B2 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-07-CENT01-2B20007 | FIRE ALARM & VOICE EVACUATION SYSTEM - B2 SERVICE +893.5M - SHEET 07-(06/08) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 07 | CENT01 | 2 | B2 | 0007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-08-CENT01-2B20008 | FIRE ALARM & VOICE EVACUATION SYSTEM - B2 SERVICE +893.5M - SHEET 08-(07/08) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 08 | CENT01 | 2 | B2 | 0008 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-09-CENT01-2B20009 | FIRE ALARM & VOICE EVACUATION SYSTEM - B2 SERVICE +893.5M - SHEET 09-(08/08) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 09 | CENT01 | 2 | B2 | 0009 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-PARK01-2B10001 | FIRE ALARM & VOICE EVACUATION SYSTEM - B1 PARKING +900.5M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | FIRE ALARM SYSTEM | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | PARK01 | 2 | B1 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-PARK01-2B10002 | FIRE ALARM & VOICE EVACUATION SYSTEM - B1 PARKING +900.5M - SHEET 01-(01/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | FIRE ALARM SYSTEM | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | PARK01 | 2 | B1 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-PARK01-2B10003 | FIRE ALARM & VOICE EVACUATION SYSTEM - B1 PARKING +900.5M - SHEET 02-(02/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | FIRE ALARM SYSTEM | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | PARK01 | 2 | B1 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-03-PARK01-2B10004 | FIRE ALARM & VOICE EVACUATION SYSTEM - B1 PARKING +900.5M - SHEET 03-(03/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | FIRE ALARM SYSTEM | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 03 | PARK01 | 2 | B1 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-08-PARK01-2B10005 | FIRE ALARM & VOICE EVACUATION SYSTEM - B1 PARKING SERVICE TUNNEL - SHEET 08 -(04/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | FIRE ALARM SYSTEM | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 08 | PARK01 | 2 | B1 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2B10001 | FIRE ALARM & VOICE EVACUATION SYSTEM PLAN - B1 SERVICE+900.5M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | B1 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2B10002 | FIRE ALARM & VOICE EVACUATION SYSTEM PLAN - B1 SERVICE+900.5M - SHEET 01 (01/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | B1 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2B10003 | FIRE ALARM & VOICE EVACUATION SYSTEM PLAN - B1 SERVICE+900.5M - SHEET 02 (02/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | B1 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-04-CENT01-2B10004 | FIRE ALARM & VOICE EVACUATION SYSTEM PLAN - B1 SERVICE+900.5M - SHEET 04 (03/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 04 | CENT01 | 2 | B1 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2B10005 | FIRE ALARM & VOICE EVACUATION SYSTEM PLAN - B1 SERVICE+900.5M - SHEET 05 (04/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | B1 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-07-CENT01-2B10006 | FIRE ALARM & VOICE EVACUATION SYSTEM PLAN - B1 SERVICE+900.5M - SHEET 07 (05/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 07 | CENT01 | 2 | B1 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-08-CENT01-2B10007 | FIRE ALARM & VOICE EVACUATION SYSTEM PLAN - B1 SERVICE+900.5M - SHEET 08 (06/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 08 | CENT01 | 2 | B1 | 0007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-09-CENT01-2B10008 | FIRE ALARM & VOICE EVACUATION SYSTEM PLAN - B1 SERVICE+900.5M - SHEET 09 (07/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 09 | CENT01 | 2 | B1 | 0008 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2L10001 | FIRE ALARM & VOICE EVACUATION SYSTEM - L1- LOBBY LEVEL +905M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | L1 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2L10002 | FIRE ALARM & VOICE EVACUATION SYSTEM - L1- LOBBY LEVEL +905M - SHEET 01 (01/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | L1 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2L10003 | FIRE ALARM & VOICE EVACUATION SYSTEM - L1- LOBBY LEVEL +905M - SHEET 02 (02/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | L1 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-04-CENT01-2L10004 | FIRE ALARM & VOICE EVACUATION SYSTEM - L1- LOBBY LEVEL +905M - SHEET 04 (03/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 04 | CENT01 | 2 | L1 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2L10005 | FIRE ALARM & VOICE EVACUATION SYSTEM - L1- LOBBY LEVEL +905M - SHEET 05 (04/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | L1 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2M10001 | FIRE ALARM & VOICE EVACUATION SYSTEM - L1- UPPER LOBBY MEZZANINE +909M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-01 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | M1 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2M10002 | FIRE ALARM & VOICE EVACUATION SYSTEM - L1- UPPER LOBBY MEZZANINE +909M - SHEET 01 (01/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | M1 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2M10003 | FIRE ALARM & VOICE EVACUATION SYSTEM - L1- UPPER LOBBY MEZZANINE +909M - SHEET 02 (02/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | M1 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-04-CENT01-2M10004 | FIRE ALARM & VOICE EVACUATION SYSTEM - L1- UPPER LOBBY MEZZANINE +909M - SHEET 04 (03/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 04 | CENT01 | 2 | M1 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2M10005 | FIRE ALARM & VOICE EVACUATION SYSTEM - L1- UPPER LOBBY MEZZANINE +909M - SHEET 05 (04/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | M1 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2L20001 | FIRE ALARM & VOICE EVACUATION SYSTEM - L2- THEATRE STALLS +913M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | L2 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2L20002 | FIRE ALARM & VOICE EVACUATION SYSTEM - L2- THEATRE STALLS +913M - SHEET 01 (01/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | L2 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2L20003 | FIRE ALARM & VOICE EVACUATION SYSTEM - L2- THEATRE STALLS +913M - SHEET 02 (02/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | L2 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-03-CENT01-2L20004 | FIRE ALARM & VOICE EVACUATION SYSTEM - L2- THEATRE STALLS +913M - SHEET 03 (03/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 03 | CENT01 | 2 | L2 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-04-CENT01-2L20005 | FIRE ALARM & VOICE EVACUATION SYSTEM - L2- THEATRE STALLS +913M - SHEET 04 (04/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 04 | CENT01 | 2 | L2 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2L20006 | FIRE ALARM & VOICE EVACUATION SYSTEM - L2- THEATRE STALLS +913M - SHEET 05 (05/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | L2 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-06-CENT01-2L20007 | FIRE ALARM & VOICE EVACUATION SYSTEM - L2- THEATRE STALLS +913M - SHEET 06 (06/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 06 | CENT01 | 2 | L2 | 0007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2L30001 | FIRE ALARM & VOICE EVACUATION SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | L3 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2L30002 | FIRE ALARM & VOICE EVACUATION SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01 (01/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | L3 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2L30003 | FIRE ALARM & VOICE EVACUATION SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02 (02/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | L3 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-03-CENT01-2L30004 | FIRE ALARM & VOICE EVACUATION SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03 (03/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 03 | CENT01 | 2 | L3 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-04-CENT01-2L30005 | FIRE ALARM & VOICE EVACUATION SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04 (04/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 04 | CENT01 | 2 | L3 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2L30006 | FIRE ALARM & VOICE EVACUATION SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05 (05/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | L3 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-06-CENT01-2L30007 | FIRE ALARM & VOICE EVACUATION SYSTEM - L3- STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06 (06/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 06 | CENT01 | 2 | L3 | 0007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2L40001 | FIRE ALARM & VOICE EVACUATION SYSTEM - L4- FIRST CIRCLE & ADAPTIVE THEATRE +921M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | L4 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2L40002 | FIRE ALARM & VOICE EVACUATION SYSTEM - L4- FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01 (01/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | L4 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2L40003 | FIRE ALARM & VOICE EVACUATION SYSTEM - L4- FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02 (02/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | L4 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-03-CENT01-2L40004 | FIRE ALARM & VOICE EVACUATION SYSTEM - L4- FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03 (03/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 03 | CENT01 | 2 | L4 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-04-CENT01-2L40005 | FIRE ALARM & VOICE EVACUATION SYSTEM - L4- FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04 (04/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 04 | CENT01 | 2 | L4 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2L40006 | FIRE ALARM & VOICE EVACUATION SYSTEM - L4- FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05 (05/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | L4 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-06-CENT01-2L40007 | FIRE ALARM & VOICE EVACUATION SYSTEM - L4- FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06 (06/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 06 | CENT01 | 2 | L4 | 0007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2L50001 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5- SECOND CIRCLE & LOFT - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | L5 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2L50002 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5- SECOND CIRCLE & LOFT - SHEET 01 (01/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | L5 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2L50003 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5- SECOND CIRCLE & LOFT - SHEET 02 (02/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | L5 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-03-CENT01-2L50004 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5- SECOND CIRCLE & LOFT - SHEET 03 (03/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 03 | CENT01 | 2 | L5 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-04-CENT01-2L50005 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5- SECOND CIRCLE & LOFT - SHEET 04 (04/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 04 | CENT01 | 2 | L5 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2L50006 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5- SECOND CIRCLE & LOFT - SHEET 05 (05/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | L5 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-06-CENT01-2L50007 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5- SECOND CIRCLE & LOFT - SHEET 06 (06/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 06 | CENT01 | 2 | L5 | 0007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2M20001 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | M2 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2M20002 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 01 (01/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | M2 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2M20003 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 02 (02/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | M2 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-03-CENT01-2M20004 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 03 (03/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 03 | CENT01 | 2 | M2 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-04-CENT01-2M20005 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 04 (04/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 04 | CENT01 | 2 | M2 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2M20006 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 05 (05/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | M2 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-06-CENT01-2M20007 | FIRE ALARM & VOICE EVACUATION SYSTEM - L5-MEZZ-LOFT MEP MEZZANINE +931.1M - SHEET 06 (06/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 06 | CENT01 | 2 | M2 | 0007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2L60001 | FIRE ALARM & VOICE EVACUATION SYSTEM - L6- SKY GARDEN +935.85M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | L6 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2L60002 | FIRE ALARM & VOICE EVACUATION SYSTEM - L6- SKY GARDEN +935.85M - SHEET 01 (01/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | L6 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2L60003 | FIRE ALARM & VOICE EVACUATION SYSTEM - L6- SKY GARDEN +935.85M - SHEET 02 (02/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | L6 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-03-CENT01-2L60004 | FIRE ALARM & VOICE EVACUATION SYSTEM - L6- SKY GARDEN +935.85M - SHEET 03 (03/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 03 | CENT01 | 2 | L6 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-04-CENT01-2L60005 | FIRE ALARM & VOICE EVACUATION SYSTEM - L6- SKY GARDEN +935.85M - SHEET 04 (04/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 04 | CENT01 | 2 | L6 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2L60006 | FIRE ALARM & VOICE EVACUATION SYSTEM - L6- SKY GARDEN +935.85M - SHEET 05 (05/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | L6 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-06-CENT01-2L60007 | FIRE ALARM & VOICE EVACUATION SYSTEM - L6- SKY GARDEN +935.85M - SHEET 06 (06/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 06 | CENT01 | 2 | L6 | 0007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2L80001 | FIRE ALARM & VOICE EVACUATION SYSTEM - L8 ROYAL MAJLIS +948.28M - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-12-03 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | L8 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-CENT01-2L80002 | FIRE ALARM & VOICE EVACUATION SYSTEM - L8 ROYAL MAJLIS +948.28M - SHEET 01 (01/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | CENT01 | 2 | L8 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-02-CENT01-2L80003 | FIRE ALARM & VOICE EVACUATION SYSTEM - L8 ROYAL MAJLIS +948.28M - SHEET 02 (02/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 02 | CENT01 | 2 | L8 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2L80004 | FIRE ALARM & VOICE EVACUATION SYSTEM - L8 ROYAL MAJLIS +948.28M - SHEET 03 (03/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | L8 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-06-CENT01-2L80005 | FIRE ALARM & VOICE EVACUATION SYSTEM - L8 ROYAL MAJLIS +948.28M - SHEET 04 (04/04) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 06 | CENT01 | 2 | L8 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-2RL0001 | FIRE ALARM & VOICE EVACUATION SYSTEM - ROOF FLOOR - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-12-24 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 2 | RL | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2000001 | FIRE ALARM & VOICE EVACUATION SYSTEM - GANTRY LEVELS - SHEET 01 (01/03) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | 00 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2000002 | FIRE ALARM & VOICE EVACUATION SYSTEM - GANTRY LEVELS - SHEET 02 (01/03) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | 00 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-CENT01-2000003 | FIRE ALARM & VOICE EVACUATION SYSTEM - GANTRY LEVELS - SHEET 03 (01/03) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | CENT01 | 2 | 00 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-SECE01-2000001 | FIRE ALARM & VOICE EVACUATION SYSTEM - SEC MRMU ROOM AND TUNNEL - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | SECE01 | 2 | 00 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-07-SECE01-2000002 | FIRE ALARM & VOICE EVACUATION SYSTEM - SEC MRMU ROOM AND TUNNEL - SHEET 07 (01/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 07 | SECE01 | 2 | 00 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-19-GARD01-2000003 | FIRE ALARM & VOICE EVACUATION SYSTEM - SEC MRMU ROOM AND TUNNEL - SHEET 19 (02/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 19 | GARD01 | 2 | 00 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-20-SECE01-2000004 | FIRE ALARM & VOICE EVACUATION SYSTEM - SEC MRMU ROOM AND TUNNEL - SHEET 20 (03/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 20 | SECE01 | 2 | 00 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-21-SECE01-2000005 | FIRE ALARM & VOICE EVACUATION SYSTEM - SEC MRMU ROOM AND TUNNEL - SHEET 21 (04/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 21 | SECE01 | 2 | 00 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-22-SECE01-2000006 | FIRE ALARM & VOICE EVACUATION SYSTEM - SEC MRMU ROOM AND TUNNEL - SHEET 22 (05/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 22 | SECE01 | 2 | 00 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-2000001 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-01 - OVERALL PLAN - PART 01 | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:150 | 2027-01-07 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 2 | 00 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-2000002 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-01 - OVERALL PLAN - PART 02 | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:150 | 2027-01-07 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 2 | 00 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-2000003 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-01 - SHEET 1 (876.25M , 882M M, 887.75M) (01/10) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 2 | 00 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-2000004 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-01 - SHEET 2 (884.75M, 887.75M, 893.5M) (02/10) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 2 | 00 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-2000005 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-01 - SHEET 3 (899.25M, 905M, 910.75M) (03/10) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 2 | 00 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-2000006 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-01 - SHEET 4 (917.5M, 922.25M, TYPICAL FIRE ALARM PLACEMENT) (04/10) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 2 | 00 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-2000007 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-01 - SHEET 5 (928M, 935.85M,941.6M ) (05/10) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-05 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 2 | 00 | 0007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-2000008 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-01 - SHEET 6 (947.35M, 953M, 958.75M) (06/10) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 2 | 00 | 0008 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-2000009 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-01 - SHEET 7 (962.30M , 966.515M, 970.65M ) (07/10) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 2 | 00 | 0009 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-2000010 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-01 - SHEET 8 (974.75M , 989.00M, 993.11M,BL1 - EXTERNAL ROOF ) (08/10) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 2 | 00 | 0010 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-MBLAD1-2000011 | FIRE ALARM & VOICE EVACUATION SYSTEM - MINI BLADE-01 - SHEET 9 (935.85M , 948.10M , 956.36M ) (09/10) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | MBLAD1 | 2 | 00 | 0011 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-MBLAD1-2000012 | FIRE ALARM & VOICE EVACUATION SYSTEM - MINI BLADE-01 - SHEET 10 (962.30M , MINI BL1- ROOF LEVEL) (10/10) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | MBLAD1 | 2 | 00 | 0012 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD02-2000001 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-02 - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-12-31 | FIRE ALARM SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD02 | 2 | 00 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD02-2000002 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-02 - SHEET 1(+876.25M, +882.0, +887.75M) (01/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD02 | 2 | 00 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD02-2000003 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-02 - SHEET 2(+893.5M, +899.25M, +905M) (02/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD02 | 2 | 00 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD02-2000004 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-02 - SHEET 3 (910.75M, 916.5M, 922.25M) (03/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD02 | 2 | 00 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD02-2000005 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-02 - SHEET 4 (+928M,+935.85M, +941.60) (04/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE ALARM SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD02 | 2 | 00 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD02-2000006 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-02 - SHEET 5 (944.85M,948.1M, +951.40M,957.25M ) (05/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FIRE ALARM SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD02 | 2 | 00 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD03-2000001 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-03 - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-21 | FIRE ALARM SYSTEM | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD03 | 2 | 00 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD03-2000002 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-03 - SHEET 1(+847.5M, +853.25M,+859M) (01/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-21 | FIRE ALARM SYSTEM | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD03 | 2 | 00 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD03-2000003 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-03 - SHEET 2 (+867.62M, +876.25M,+876.25MHL) (02/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-21 | FIRE ALARM SYSTEM | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD03 | 2 | 00 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD03-2000004 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-03 - SHEET 3 (+887.75M, +894.58M,+900.33M) (03/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-21 | FIRE ALARM SYSTEM | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD03 | 2 | 00 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD03-2000005 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-03 - SHEET 4 (+905M, +910.75M, +916.5M) (04/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-21 | FIRE ALARM SYSTEM | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD03 | 2 | 00 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD03-2000006 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-03 - SHEET 5 (+921M, +928M, +931.1) (05/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-21 | FIRE ALARM SYSTEM | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD03 | 2 | 00 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD04-2000001 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-04 - OVERALL PLAN - PART 01 | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD04 | 2 | 00 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD04-2000002 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-04 - OVERALL PLAN - PART 02 | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD04 | 2 | 00 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD04-2000003 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-04 - SHEET 1(+863.85M, +870.5, +876.25M) (01/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FIRE ALARM SYSTEM | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD04 | 2 | 00 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD04-2000004 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-04 - SHEET 2 (+882.00M, +887.75M, +893.5M) (02/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FIRE ALARM SYSTEM | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD04 | 2 | 00 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD04-2000005 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-04 - SHEET 3 (+899.25M, +905M, +910.75M) (03/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FIRE ALARM SYSTEM | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD04 | 2 | 00 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD04-2000006 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-04 - SHEET 4 (+916.5M, +922.25M, +928M - LOFT) (04/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD04 | 2 | 00 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD04-2000007 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-04 - SHEET 5 (+935.85M, +941.60M, 947.35M) (05/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD04 | 2 | 00 | 0007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD04-2000008 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-04 - SHEET 6 (+952.45,+959,+968.30,975.82) (06/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD04 | 2 | 00 | 0008 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-MBLAD4-2000009 | FIRE ALARM & VOICE EVACUATION SYSTEM - MINI BLADE-04 - SHEET 7 (+935.85M, +948.10M) (07/07) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | MBLAD4 | 2 | 00 | 0009 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD05-2000001 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-05 - OVERALL PLAN | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-29 | FIRE ALARM SYSTEM | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD05 | 2 | 00 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD05-2000002 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-05 - SHEET 1 (+894.5M, +899.5M, +905M) (01/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FIRE ALARM SYSTEM | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD05 | 2 | 00 | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD05-2000003 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-05 - SHEET 2 (+910.75M, +917.5M, +922.25M) (02/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FIRE ALARM SYSTEM | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD05 | 2 | 00 | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD05-2000004 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-05 - SHEET 3 (+928M,+935.85, +941.6) (03/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FIRE ALARM SYSTEM | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD05 | 2 | 00 | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD05-2000005 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-05 - SHEET 4 (+948.28M,+953.85,+957.50) (04/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FIRE ALARM SYSTEM | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD05 | 2 | 00 | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD05-2000006 | FIRE ALARM & VOICE EVACUATION SYSTEM - BLADE-05 - SHEET 5 (+962.64M,+969.3M,ROOF) (05/05) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FIRE ALARM SYSTEM | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD05 | 2 | 00 | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0100 | FIRE ALARM & VOICE EVACUATION SYSTEM SCHEMATIC DIAGRAM - OVERALL -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0100 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-0ZZ0101 | FIRE ALARM & VOICE EVACUATION SYSTEM SCHEMATIC DIAGRAM - CENTRAL BUILDING -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 0 | ZZ | 0101 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-PARK01-0ZZ0102 | FIRE ALARM & VOICE EVACUATION SYSTEM SCHEMATIC DIAGRAM - PARKING -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | PARK01 | 0 | ZZ | 0102 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-0ZZ0103 | FIRE ALARM & VOICE EVACUATION SYSTEM SCHEMATIC DIAGRAM - BLADE-01 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 0 | ZZ | 0103 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD02-0ZZ0104 | FIRE ALARM & VOICE EVACUATION SYSTEM SCHEMATIC DIAGRAM - BLADE-02 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD02 | 0 | ZZ | 0104 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD03-0ZZ0105 | FIRE ALARM & VOICE EVACUATION SYSTEM SCHEMATIC DIAGRAM - BLADE-03 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD03 | 0 | ZZ | 0105 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD04-0ZZ0106 | FIRE ALARM & VOICE EVACUATION SYSTEM SCHEMATIC DIAGRAM - BLADE-04 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD04 | 0 | ZZ | 0106 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD05-0ZZ0107 | FIRE ALARM & VOICE EVACUATION SYSTEM SCHEMATIC DIAGRAM - BLADE-05 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD05 | 0 | ZZ | 0107 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-2ZZ0001 | FIRE ALARM – B3 +887.5M - OVERALL LAYOUT INFRA | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 2 | ZZ | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-01-Z00000-2ZZ0002 | FIRE ALARM - INFRA B3 +887.5M - SHEET 01 - (01/11) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 01 | Z00000 | 2 | ZZ | 0002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-03-Z00000-2ZZ0003 | FIRE ALARM - INFRA B3 +887.5M - SHEET 03 - (02/11) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 03 | Z00000 | 2 | ZZ | 0003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-04-Z00000-2ZZ0004 | FIRE ALARM - INFRA B3 +887.5M - SHEET 04 - (03/11) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 04 | Z00000 | 2 | ZZ | 0004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-05-Z00000-2ZZ0005 | FIRE ALARM - INFRA B3 +887.5M - SHEET 05 - (04/11) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 05 | Z00000 | 2 | ZZ | 0005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-06-Z00000-2ZZ0006 | FIRE ALARM - INFRA B3 +887.5M - SHEET 06 - (05/11) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 06 | Z00000 | 2 | ZZ | 0006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-07-Z00000-2ZZ0007 | FIRE ALARM - INFRA B3 +887.5M - SHEET 07 - (06/11) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 07 | Z00000 | 2 | ZZ | 0007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-08-Z00000-2ZZ0008 | FIRE ALARM - INFRA B3 +887.5M - SHEET 08 - (07/11) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 08 | Z00000 | 2 | ZZ | 0008 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-09-Z00000-2ZZ0009 | FIRE ALARM - INFRA B3 +887.5M - SHEET 09 - (08/11) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 09 | Z00000 | 2 | ZZ | 0009 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-11-Z00000-2ZZ0010 | FIRE ALARM - INFRA B3 +887.5M - SHEET 11 - (09/11) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 11 | Z00000 | 2 | ZZ | 0010 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-25-Z00000-2ZZ0011 | FIRE ALARM - INFRA B3 +887.5M - SHEET 25 - (10/11) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 25 | Z00000 | 2 | ZZ | 0011 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-26-Z00000-2ZZ0012 | FIRE ALARM - INFRA B3 +887.5M - SHEET 26 - (11/11) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-24 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 26 | Z00000 | 2 | ZZ | 0012 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0200 | FIRE ALARM ZONING PLAN -(01/03) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0200 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0201 | FIRE ALARM ZONING PLAN -(02/03) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0201 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0202 | FIRE ALARM ZONING PLAN -(03/03) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0202 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-CENT01-0ZZ0300 | FIRE ALARM CAUSE & EFFECT MATRIX - CENTRAL BUILDING -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.MBL.GEN.5080 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | CENT01 | 0 | ZZ | 0300 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-PARK01-0ZZ0301 | FIRE ALARM CAUSE & EFFECT MATRIX - PARKING -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.PAR.GEN.1299 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | PARK01 | 0 | ZZ | 0301 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD01-0ZZ0302 | FIRE ALARM CAUSE & EFFECT MATRIX - BLADE-01 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.BL1.GEN.3360 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD01 | 0 | ZZ | 0302 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD02-0ZZ0303 | FIRE ALARM CAUSE & EFFECT MATRIX - BLADE-02 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.BL2.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD02 | 0 | ZZ | 0303 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD03-0ZZ0304 | FIRE ALARM CAUSE & EFFECT MATRIX - BLADE-03 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.BL3.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD03 | 0 | ZZ | 0304 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD04-0ZZ0305 | FIRE ALARM CAUSE & EFFECT MATRIX - BLADE-04 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.BL4.GEN.5850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD04 | 0 | ZZ | 0305 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-BLAD05-0ZZ0306 | FIRE ALARM CAUSE & EFFECT MATRIX - BLADE-05 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.ME.BL5.GEN.2880 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | BLAD05 | 0 | ZZ | 0306 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0400 | FIRE ALARM SYSTEM STANDARD INSTALLATION DETAILS - (01/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0400 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0401 | FIRE ALARM SYSTEM STANDARD INSTALLATION DETAILS - (02/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0401 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0402 | FIRE ALARM SYSTEM STANDARD INSTALLATION DETAILS - (03/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0402 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0403 | FIRE ALARM SYSTEM STANDARD INSTALLATION DETAILS - (04/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0403 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0404 | FIRE ALARM SYSTEM STANDARD INSTALLATION DETAILS - (05/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0404 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0405 | FIRE ALARM SYSTEM STANDARD INSTALLATION DETAILS - (06/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0405 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0406 | FIRE ALARM & VOICE EVACUATION SYSTEM WIRING DIAGRAM-(01/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0406 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0407 | FIRE ALARM & VOICE EVACUATION SYSTEM WIRING DIAGRAM-(02/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0407 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0408 | FIRE ALARM & VOICE EVACUATION SYSTEM WIRING DIAGRAM-(03/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0408 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0409 | FIRE ALARM & VOICE EVACUATION SYSTEM WIRING DIAGRAM-(04/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0409 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0410 | FIRE ALARM & VOICE EVACUATION SYSTEM WIRING DIAGRAM-(05/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0410 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0411 | FIRE ALARM & VOICE EVACUATION SYSTEM WIRING DIAGRAM-(06/06) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0411 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0500 | FIRE ALARM & VOICE EVACUATION SYSTEM SECTION DETAIL -BLADE-01 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-01-07 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0500 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0501 | FIRE ALARM & VOICE EVACUATION SYSTEM SECTION DETAIL -BLADE-02 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-12-31 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0501 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0502 | FIRE ALARM & VOICE EVACUATION SYSTEM SECTION DETAIL -BLADE-03 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-09-21 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0502 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0503 | FIRE ALARM & VOICE EVACUATION SYSTEM SECTION DETAIL -BLADE-04 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0503 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FAE-00-Z00000-0ZZ0504 | FIRE ALARM & VOICE EVACUATION SYSTEM SECTION DETAIL -BLADE-05 -(01/01) | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2026-10-29 | FIRE ALARM SYSTEM | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | FAE | 00 | Z00000 | 0 | ZZ | 0504 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-CAL-FAE-00-Z00000-000001 | FIRE ALARM SYSTEM CALCULATION | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | MicrosoftWord | .docx,.pdf | NTS | 2026-11-19 | FIRE ALARM SYSTEM | QP.E.ME.CBR.GEN.1044 | FI_40_10 | QF01012 | NES | C04518 | CAL | FAE | 00 | Z00000 | 0 | 00 | 001 | Fire & Life Safety | Nesma & Partners |  |  |  |  | #REF!
QF01012-NES-C04518-MOD-FAE-00-Z00000-0000001 | FIRE ALARM SYSTEM BIM MODEL | QF01012-BSB-MOD-3DM-FAE-00-Z00-10000 | Fire & Life Safety | Revit | .rvt,.nwc,.ifc | NTS |  | 3D MODEL FIRE ALARM SYSTEM |  | FI_60_53 | QF01012 | NES | C04518 | MOD | FAE | 00 | Z00000 | 0 | 00 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-CAL-FPR-00-Z00000-000001 | Fire Fighting Pipes Supporting Calculation Report | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-02-12 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1320 | FI_60_25 | QF01012 | NES | C04518 | CAL | FPR | 00 | Z00000 | 0 | 00 | 001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2B31100 | FIRE PROTECTION - B3 +887.5M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-07-23 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1320 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | B3 | 1100 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2B31101 | FIRE PROTECTION - B3 +887.5M - SHEET 01 - (01/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1320 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | B3 | 1101 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2B31102 | FIRE PROTECTION - B3 +887.5M - SHEET 02 - (02/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1320 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | B3 | 1102 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2B31103 | FIRE PROTECTION - B3 +887.5M - SHEET 04 - (03/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1320 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | B3 | 1103 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-05-CENT01-2B31104 | FIRE PROTECTION - B3 +887.5M - SHEET 05 - (04/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1320 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 05 | CENT01 | 2 | B3 | 1104 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-06-CENT01-2B31105 | FIRE PROTECTION - B3 +887.5M - SHEET 06 - (05/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1320 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 06 | CENT01 | 2 | B3 | 1105 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-10-CENT01-2B31106 | FIRE PROTECTION - B3 +887.5M - SHEET 10 - (06/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1320 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 10 | CENT01 | 2 | B3 | 1106 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-11-CENT01-2B31107 | FIRE PROTECTION - B3 +887.5M - SHEET 11 - (07/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1320 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 11 | CENT01 | 2 | B3 | 1107 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3B31108 | FIRE PROTECTION - B3 +887.5M - SECTION SHEET - (08/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1320 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | B3 | 1108 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B34000 | FIRE PROTECTION - KITCHENHOOD - B3 +887.5M (01/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6520 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B3 | 4000 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B34001 | FIRE PROTECTION - KITCHENHOOD - B3 +887.5M (02/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6520 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B3 | 4001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-4B35002 | FIRE PROTECTION - NOVEC SYSTEM - +887.5M - BLADE 2 (01/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL2.GEN.3380 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 4 | B3 | 5002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-4B35003 | FIRE PROTECTION - NOVEC SYSTEM - +887.5M - BLADE 2 (02/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL2.GEN.3380 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 4 | B3 | 5003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-4B35006 | FIRE PROTECTION - NOVEC SYSTEM - +887.5M - BLADE 3 (01/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL3.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 4 | B3 | 5006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-4B35007 | FIRE PROTECTION - NOVEC SYSTEM - +887.5M - BLADE 3 (02/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL3.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 4 | B3 | 5007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B35047 | FIRE PROTECTION - NOVEC SYSTEM -B3 +887.5M - CENTRAL BUILDING (29/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B3 | 5047 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B35048 | FIRE PROTECTION - NOVEC SYSTEM -B3 +887.5M - CENTRAL BUILDING (30/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B3 | 5048 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B35049 | FIRE PROTECTION - NOVEC SYSTEM -B3 +887.5M - CENTRAL BUILDING (31/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.5000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B3 | 5049 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2B21200 | FIRE PROTECTION - B2 SERVICE +893.5M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1420 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | B2 | 1200 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2B21201 | FIRE PROTECTION - B2 SERVICE +893.5M - SHEET 01 - (01/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1420 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | B2 | 1201 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2B21202 | FIRE PROTECTION - B2 SERVICE +893.5M - SHEET 02 - (02/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1420 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | B2 | 1202 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2B21203 | FIRE PROTECTION - B2 SERVICE +893.5M - SHEET 04 - (03/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1420 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | B2 | 1203 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-05-CENT01-2B21204 | FIRE PROTECTION - B2 SERVICE +893.5M - SHEET 05 - (04/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1420 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 05 | CENT01 | 2 | B2 | 1204 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-08-CENT01-2B21205 | FIRE PROTECTION - B2 SERVICE +893.5M - SHEET 08 - (05/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1420 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 08 | CENT01 | 2 | B2 | 1205 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-09-CENT01-2B21206 | FIRE PROTECTION - B2 SERVICE +893.5M - SHEET 09 - (06/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1420 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 09 | CENT01 | 2 | B2 | 1206 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-11-CENT01-2B21207 | FIRE PROTECTION - B2 SERVICE +893.5M - SHEET 11 - (07/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1420 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 11 | CENT01 | 2 | B2 | 1207 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3B21208 | FIRE PROTECTION - B2 SERVICE - +893.5M - SECTION SHEET - (08/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1420 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | B2 | 1208 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B21209 | FIRE PROTECTION - B2 SERVICE RAMP +893.5M - ENLARGED 1 - (01/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 1209 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B21210 | FIRE PROTECTION - B2 SERVICE RAMP +893.5M - ENLARGED 2 - (02/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 1210 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B21211 | FIRE PROTECTION - B2 SERVICE RAMP +893.5M - ENLARGED 3 - (03/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 1211 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B21212 | FIRE PROTECTION - B2 SERVICE RAMP +893.5M - ENLARGED 4 - (04/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 1212 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B21213 | FIRE PROTECTION - FOAM SYSTEM +893.5M - B2 SERVICE - 1 | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 1213 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B21214 | FIRE PROTECTION - FOAM SYSTEM +893.5M - B2 SERVICE - 1 | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 1214 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B21215 | FIRE PROTECTION - FOAM SYSTEM +893.5M - B2 SERVICE - 2 | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 1215 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B21216 | FIRE PROTECTION - FOAM SYSTEM +893.5M - B2 SERVICE - 2 | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 1216 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B25038 | FIRE PROTECTION - NOVEC SYSTEM -B2 +893.5M - CENTRAL BUILDING (20/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 5038 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B25039 | FIRE PROTECTION - NOVEC SYSTEM -B2 +893.5M - CENTRAL BUILDING (21/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 5039 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B25040 | FIRE PROTECTION - NOVEC SYSTEM -B2 +893.5M - CENTRAL BUILDING (22/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 5040 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B25041 | FIRE PROTECTION - NOVEC SYSTEM -B2 +893.5M - CENTRAL BUILDING (23/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 5041 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B25042 | FIRE PROTECTION - NOVEC SYSTEM -B2 +893.5M - CENTRAL BUILDING (24/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 5042 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B25043 | FIRE PROTECTION - NOVEC SYSTEM -B2 +893.5M - CENTRAL BUILDING (25/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 5043 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B25044 | FIRE PROTECTION - NOVEC SYSTEM -B2 +893.5M - CENTRAL BUILDING (26/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 5044 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B25045 | FIRE PROTECTION - NOVEC SYSTEM -B2 +893.5M - CENTRAL BUILDING (27/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 5045 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B25046 | FIRE PROTECTION - NOVEC SYSTEM -B2 +893.5M - CENTRAL BUILDING (28/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B2 | 5046 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2B11300 | FIRE PROTECTION - B1 SERVICE +900.5M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | B1 | 1300 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2B11301 | FIRE PROTECTION - B1 SERVICE +900.5M - SHEET 01 - (01/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | B1 | 1301 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2B11302 | FIRE PROTECTION - B1 SERVICE +900.5M - SHEET 02 - (02/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | B1 | 1302 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2B11303 | FIRE PROTECTION - B1 SERVICE +900.5M - SHEET 04 - (03/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | B1 | 1303 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-05-CENT01-2B11304 | FIRE PROTECTION - B1 SERVICE +900.5M - SHEET 05 - (04/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 05 | CENT01 | 2 | B1 | 1304 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-07-CENT01-2B11305 | FIRE PROTECTION - B1 SERVICE +900.5M - SHEET 07 - (05/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 07 | CENT01 | 2 | B1 | 1305 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-08-CENT01-2B11306 | FIRE PROTECTION - B1 SERVICE +900.5M - SHEET 08 - (06/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 08 | CENT01 | 2 | B1 | 1306 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-09-CENT01-2B11307 | FIRE PROTECTION - B1 SERVICE +900.5M - SHEET 09 - (07/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 09 | CENT01 | 2 | B1 | 1307 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3B11308 | FIRE PROTECTION - B1 SERVICE +900.5M - SECTION SHEET - (08/08) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | B1 | 1308 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B11309 | FIRE PROTECTION - B1 SERVICE +900.5M - FIRE PUMP ROOM - ENLARGED 2 | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 1309 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B11310 | FIRE PROTECTION - B1 SERVICE +900.5M - FIRE PUMP ROOM - ENLARGED 1 | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 1310 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-PARK01-2B11311 | FIRE PROTECTION - B1 PARKING +900.5M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-15 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | PARK01 | 2 | B1 | 1311 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-PARK01-2B11312 | FIRE PROTECTION - B1 PARKING +900.5M - SHEET 13 - (01/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | PARK01 | 2 | B1 | 1312 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-PARK01-2B11313 | FIRE PROTECTION - B1 PARKING +900.5M - SHEET 14 - (02/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | PARK01 | 2 | B1 | 1313 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-03-PARK01-2B11314 | FIRE PROTECTION - B1 PARKING +900.5M - SHEET 15 - (03/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 03 | PARK01 | 2 | B1 | 1314 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-PARK01-3B11315 | FIRE PROTECTION - B1 PARKING +900.5M - SECTION SHEET - (04/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | PARK01 | 3 | B1 | 1315 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15000 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING - (01/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5000 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-4B15017 | FIRE PROTECTION - NOVEC SYSTEM B1 - +900.5M - BLADE 5 (01/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL5.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 4 | B1 | 5017 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15020 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (02/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5020 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15021 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (03/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5021 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15022 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (04/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5022 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15023 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (05/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5023 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15024 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (06/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5024 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15025 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (07/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5025 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15026 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (08/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5026 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15027 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (09/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5027 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15028 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (10/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5028 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15029 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (11/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5029 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15030 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (12/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5030 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15031 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (13/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5031 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15032 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (14/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5032 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15033 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (15/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5033 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15034 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (16/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5034 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15035 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (17/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5035 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15036 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (18/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5036 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4B15037 | FIRE PROTECTION - NOVEC SYSTEM -B1 +900.5M - CENTRAL BUILDING (19/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | B1 | 5037 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2L11400 | FIRE PROTECTION - L1 LOBBY +905M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1590 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | L1 | 1400 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2L11401 | FIRE PROTECTION - L1 LOBBY +905M - SHEET 01-(1/5) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1590 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | L1 | 1401 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2L11402 | FIRE PROTECTION - L1 LOBBY +905M - SHEET 02-(2/5) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1590 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | L1 | 1402 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2L11403 | FIRE PROTECTION - L1 LOBBY +905M - SHEET 04-(3/5) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1590 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | L1 | 1403 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-05-CENT01-2L11404 | FIRE PROTECTION - L1 LOBBY +905M - SHEET 05-(4/5) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1590 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 05 | CENT01 | 2 | L1 | 1404 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3L11405 | FIRE PROTECTION - L1 LOBBY +905M - SECTION SHEET-(5/5) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.1590 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | L1 | 1405 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-4L15004 | FIRE PROTECTION - NOVEC SYSTEM - +905M - BLADE 2 (03/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL2.GEN.3380 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 4 | L1 | 5004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-4L15005 | FIRE PROTECTION - NOVEC SYSTEM - +905M - BLADE 2 (04/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL2.GEN.3380 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 4 | L1 | 5005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-4L15012 | FIRE PROTECTION - NOVEC SYSTEM - +905M - BLADE 3 (07/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL3.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 4 | L1 | 5012 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-4L15019 | FIRE PROTECTION - NOVEC SYSTEM L1 - +905M - BLADE 5 (03/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL5.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 4 | L1 | 5019 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L15050 | FIRE PROTECTION - NOVEC SYSTEM -L1 +905M - CENTRAL BUILDING (32/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L1 | 5050 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L15051 | FIRE PROTECTION - NOVEC SYSTEM -L1 +905M - CENTRAL BUILDING (33/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L1 | 5051 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L15052 | FIRE PROTECTION - NOVEC SYSTEM -L1 +905M - CENTRAL BUILDING (34/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L1 | 5052 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L15053 | FIRE PROTECTION - NOVEC SYSTEM -L1 +905M - CENTRAL BUILDING (35/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L1 | 5053 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L15054 | FIRE PROTECTION - NOVEC SYSTEM -L1 +905M - CENTRAL BUILDING (36/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L1 | 5054 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2M11500 | FIRE PROTECTION - M1 UPPER LOBBY +909M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-01 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2040 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | M1 | 1500 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2M11501 | FIRE PROTECTION - M1 UPPER LOBBY +909M - SHEET 01-(1/5) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2040 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | M1 | 1501 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2M11502 | FIRE PROTECTION - M1 UPPER LOBBY +909M - SHEET 02-(2/5) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2040 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | M1 | 1502 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2M11503 | FIRE PROTECTION - M1 UPPER LOBBY +909M - SHEET 04-(3/5) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2040 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | M1 | 1503 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-05-CENT01-2M11504 | FIRE PROTECTION - M1 UPPER LOBBY +909M - SHEET 05-(4/5) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2040 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 05 | CENT01 | 2 | M1 | 1504 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3M11505 | FIRE PROTECTION - M1 UPPER LOBBY +909M - SECTION SHEET-(5/5) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2040 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | M1 | 1505 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4M15055 | FIRE PROTECTION - NOVEC SYSTEM -M1 +909M - CENTRAL BUILDING (37/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | M1 | 5055 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4M15056 | FIRE PROTECTION - NOVEC SYSTEM -M1 +909M - CENTRAL BUILDING (38/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | M1 | 5056 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4M15057 | FIRE PROTECTION - NOVEC SYSTEM -M1 +909M - CENTRAL BUILDING (39/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | M1 | 5057 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4M15058 | FIRE PROTECTION - NOVEC SYSTEM -M1 +909M - CENTRAL BUILDING (40/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | M1 | 5058 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2L21600 | FIRE PROTECTION - L2 THEATRE STALLS +913M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-10-22 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | L2 | 1600 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2L21601 | FIRE PROTECTION - L2 THEATRE STALLS +913M - SHEET 01-(1/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | L2 | 1601 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2L21602 | FIRE PROTECTION - L2 THEATRE STALLS +913M - SHEET 02-(2/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | L2 | 1602 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-03-CENT01-2L21603 | FIRE PROTECTION - L2 THEATRE STALLS +913M - SHEET 03-(3/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 03 | CENT01 | 2 | L2 | 1603 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2L21604 | FIRE PROTECTION - L2 THEATRE STALLS +913M - SHEET 04-(4/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | L2 | 1604 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-05-CENT01-2L21605 | FIRE PROTECTION - L2 THEATRE STALLS +913M - SHEET 05-(5/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 05 | CENT01 | 2 | L2 | 1605 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-06-CENT01-2L21606 | FIRE PROTECTION - L2 THEATRE STALLS +913M - SHEET 06-(6/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 06 | CENT01 | 2 | L2 | 1606 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3L21607 | FIRE PROTECTION - L2 THEATRE STALLS +913M - SECTION SHEET - (07/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2240 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | L2 | 1607 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L25059 | FIRE PROTECTION - NOVEC SYSTEM -L2 +913M - CENTRAL BUILDING (41/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L2 | 5059 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L25060 | FIRE PROTECTION - NOVEC SYSTEM -L2 +913M - CENTRAL BUILDING (42/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L2 | 5060 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L25061 | FIRE PROTECTION - NOVEC SYSTEM -L2 +913M - CENTRAL BUILDING (43/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L2 | 5061 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L25062 | FIRE PROTECTION - NOVEC SYSTEM -L2 +913M - CENTRAL BUILDING (44/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L2 | 5062 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2L31700 | FIRE PROTECTION - L3 STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2440 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | L3 | 1700 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2L31701 | FIRE PROTECTION - L3 STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 01-(1/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2440 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | L3 | 1701 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2L31702 | FIRE PROTECTION - L3 STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 02-(2/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2440 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | L3 | 1702 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-03-CENT01-2L31703 | FIRE PROTECTION - L3 STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 03-(3/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2440 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 03 | CENT01 | 2 | L3 | 1703 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2L31704 | FIRE PROTECTION - L3 STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 04-(4/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2440 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | L3 | 1704 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-05-CENT01-2L31705 | FIRE PROTECTION - L3 STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 05-(5/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2440 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 05 | CENT01 | 2 | L3 | 1705 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-06-CENT01-2L31706 | FIRE PROTECTION - L3 STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SHEET 06-(6/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2440 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 06 | CENT01 | 2 | L3 | 1706 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3L31707 | FIRE PROTECTION - L3 STALL MEZZANINE & ADAPTIVE THEATRE +917.5M - SECTION SHEET - (7/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2440 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | L3 | 1707 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2L41800 | FIRE PROTECTION - L4 FIRST CIRCLE & ADAPTIVE THEATRE +921M -OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2640 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | L4 | 1800 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2L41801 | FIRE PROTECTION - L4 FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 01-(1/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2640 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | L4 | 1801 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2L41802 | FIRE PROTECTION - L4 FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 02-(2/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2640 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | L4 | 1802 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-03-CENT01-2L41803 | FIRE PROTECTION - L4 FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 03-(3/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2640 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 03 | CENT01 | 2 | L4 | 1803 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2L41804 | FIRE PROTECTION - L4 FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 04-(4/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2640 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | L4 | 1804 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-05-CENT01-2L41805 | FIRE PROTECTION - L4 FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 05-(5/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2640 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 05 | CENT01 | 2 | L4 | 1805 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-06-CENT01-2L41806 | FIRE PROTECTION - L4 FIRST CIRCLE & ADAPTIVE THEATRE +921M - SHEET 06-(6/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2640 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 06 | CENT01 | 2 | L4 | 1806 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3L41807 | FIRE PROTECTION - L4 FIRST CIRCLE & ADAPTIVE THEATRE +921M - SECTION SHEET - (07/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2640 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | L4 | 1807 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L45063 | FIRE PROTECTION - NOVEC SYSTEM -L4 +921M - CENTRAL BUILDING (45/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L4 | 5063 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L45064 | FIRE PROTECTION - NOVEC SYSTEM -L4 +921M - CENTRAL BUILDING (46/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L4 | 5064 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2L51900 | FIRE PROTECTION - L5 SECOND CIRCLE & LOFT +928M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | L5 | 1900 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2L51901 | FIRE PROTECTION - L5 SECOND CIRCLE & LOFT +928M - SHEET 01-(01/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | L5 | 1901 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2L51902 | FIRE PROTECTION - L5 SECOND CIRCLE & LOFT +928M - SHEET 02-(02/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | L5 | 1902 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-03-CENT01-2L51903 | FIRE PROTECTION - L5 SECOND CIRCLE & LOFT +928M - SHEET 03-(03/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 03 | CENT01 | 2 | L5 | 1903 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2L51904 | FIRE PROTECTION - L5 SECOND CIRCLE & LOFT +928M - SHEET 04-(04/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | L5 | 1904 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-05-CENT01-2L51905 | FIRE PROTECTION - L5 SECOND CIRCLE & LOFT +928M - SHEET 05-(05/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 05 | CENT01 | 2 | L5 | 1905 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-06-CENT01-2L51906 | FIRE PROTECTION - L5 SECOND CIRCLE & LOFT +928M - SHEET 06-(06/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 06 | CENT01 | 2 | L5 | 1906 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3L51907 | FIRE PROTECTION - L5 SECOND CIRCLE & LOFT +928M - SECTION SHEET - (07/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.2850 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | L5 | 1907 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L51908 | FIRE PROTECTION - L5 MAIN THEATRE CATWALK +928M - ENLARGED 1 - (01/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 1908 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L51909 | FIRE PROTECTION - L5 MAIN THEATRE CATWALK +928M - ENLARGED 2 - (01/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 1909 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L51910 | FIRE PROTECTION - L5 ADAPTIVE THEATRE CATWALK +928M - ENLARGED 1 - (01/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 1910 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L51911 | FIRE PROTECTION - L5 ADAPTIVE THEATRE CATWALK +928M - ENLARGED 2 - (02/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 1911 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2M22000 | FIRE PROTECTION - M2 LOFT MEP MEZZANINE +931.1M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | M2 | 2000 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2M22001 | FIRE PROTECTION - M2 LOFT MEP MEZZANINE +931.1M - SHEET 01-(1/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | M2 | 2001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2M22002 | FIRE PROTECTION - M2 LOFT MEP MEZZANINE +931.1M - SHEET 02-(2/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | M2 | 2002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-03-CENT01-2M22003 | FIRE PROTECTION - M2 LOFT MEP MEZZANINE +931.1M - SHEET 03-(3/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 03 | CENT01 | 2 | M2 | 2003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2M22004 | FIRE PROTECTION - M2 LOFT MEP MEZZANINE +931.1M - SHEET 04-(4/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | M2 | 2004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-05-CENT01-2M22005 | FIRE PROTECTION - M2 LOFT MEP MEZZANINE +931.1M - SHEET 05-(5/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 05 | CENT01 | 2 | M2 | 2005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-06-CENT01-2M22006 | FIRE PROTECTION - M2 LOFT MEP MEZZANINE +931.1M - SHEET 06-(6/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 06 | CENT01 | 2 | M2 | 2006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3M22007 | FIRE PROTECTION - M2 LOFT MEP MEZZANINE +931.1M - SECTION SHEET - (7/7) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | M2 | 2007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L54002 | FIRE PROTECTION - KITCHENHOOD - L5 +928M (01/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 4002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L54003 | FIRE PROTECTION - KITCHENHOOD - L5 +928M (02/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 4003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-4L55008 | FIRE PROTECTION - NOVEC SYSTEM - +928M - BLADE 3 (03/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL3.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 4 | L5 | 5008 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-4L55009 | FIRE PROTECTION - NOVEC SYSTEM - +928M - BLADE 3 (04/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL3.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 4 | L5 | 5009 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-4L55010 | FIRE PROTECTION - NOVEC SYSTEM - +928M - BLADE 3 (05/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL3.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 4 | L5 | 5010 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-4L55011 | FIRE PROTECTION - NOVEC SYSTEM - +928M - BLADE 3 (06/07) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL3.GEN.3620 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 4 | L5 | 5011 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L55065 | FIRE PROTECTION - NOVEC SYSTEM -L5 +928M - CENTRAL BUILDING (47/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 5065 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L55066 | FIRE PROTECTION - NOVEC SYSTEM -L5 +928M - CENTRAL BUILDING (48/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 5066 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L55067 | FIRE PROTECTION - NOVEC SYSTEM -L5 +928M - CENTRAL BUILDING (49/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 5067 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L55068 | FIRE PROTECTION - NOVEC SYSTEM -L5 +928M - CENTRAL BUILDING (50/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 5068 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L55069 | FIRE PROTECTION - NOVEC SYSTEM -L5 +928M - CENTRAL BUILDING (51/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 5069 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L55070 | FIRE PROTECTION - NOVEC SYSTEM -L5 +928M - CENTRAL BUILDING (52/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 5070 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L55071 | FIRE PROTECTION - NOVEC SYSTEM -L5 +928M - CENTRAL BUILDING (53/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 5071 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L55072 | FIRE PROTECTION - NOVEC SYSTEM -L5 +928M - CENTRAL BUILDING (54/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 5072 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L55073 | FIRE PROTECTION - NOVEC SYSTEM -L5 +928M - CENTRAL BUILDING (55/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 5073 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L55074 | FIRE PROTECTION - NOVEC SYSTEM -L5 +928M - CENTRAL BUILDING (56/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 5074 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L55075 | FIRE PROTECTION - NOVEC SYSTEM -L5 +928M - CENTRAL BUILDING (57/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L5 | 5075 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4M25076 | FIRE PROTECTION - NOVEC SYSTEM -M2 +931.1M - CENTRAL BUILDING (58/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | M2 | 5076 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4M25077 | FIRE PROTECTION - NOVEC SYSTEM -M2 +931.1M - CENTRAL BUILDING (59/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | M2 | 5077 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4M25078 | FIRE PROTECTION - NOVEC SYSTEM -M2 +931.1M - CENTRAL BUILDING (60/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | M2 | 5078 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4M25079 | FIRE PROTECTION - NOVEC SYSTEM -M2 +931.1M - CENTRAL BUILDING (61/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | M2 | 5079 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4M25080 | FIRE PROTECTION - NOVEC SYSTEM -M2 +931.1M - CENTRAL BUILDING (62/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | M2 | 5080 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4M25081 | FIRE PROTECTION - NOVEC SYSTEM -M2 +931.1M - CENTRAL BUILDING (63/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | M2 | 5081 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4M25082 | FIRE PROTECTION - NOVEC SYSTEM -M2 +931.1M - CENTRAL BUILDING (64/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | M2 | 5082 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2L62100 | FIRE PROTECTION - L6 SKY GARDEN +935.85M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3290 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | L6 | 2100 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2L62101 | FIRE PROTECTION - L6 SKY GARDEN +935.85M - SHEET 01-(1/6) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3290 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | L6 | 2101 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2L62102 | FIRE PROTECTION - L6 SKY GARDEN +935.85M - SHEET 02-(2/6) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3290 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | L6 | 2102 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-03-CENT01-2L62103 | FIRE PROTECTION - L6 SKY GARDEN +935.85M - SHEET 03-(3/6) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3290 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 03 | CENT01 | 2 | L6 | 2103 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2L62104 | FIRE PROTECTION - L6 SKY GARDEN +935.85M - SHEET 04-(4/6) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3290 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | L6 | 2104 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-06-CENT01-2L62105 | FIRE PROTECTION - L6 SKY GARDEN +935.85M - SHEET 06-(5/6) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3290 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 06 | CENT01 | 2 | L6 | 2105 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3L62106 | FIRE PROTECTION - L6 SKY GARDEN +935.85M - SECTION SHEET - (06/06) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3290 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | L6 | 2106 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-4L65018 | FIRE PROTECTION - NOVEC SYSTEM L6 - +935.85M - BLADE 5 (02/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL5.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 4 | L6 | 5018 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L65083 | FIRE PROTECTION - NOVEC SYSTEM -L6 +935.85M - CENTRAL BUILDING (65/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L6 | 5083 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-2L82200 | FIRE PROTECTION - L8 SIGNATURE RESTAURANT +948.10M - OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 2 | L8 | 2200 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-CENT01-2L82201 | FIRE PROTECTION - L8 SIGNATURE RESTAURANT +948.10M - SHEET 01-(1/6) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | CENT01 | 2 | L8 | 2201 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-CENT01-2L82202 | FIRE PROTECTION - L8 SIGNATURE RESTAURANT +948.10M - SHEET 02-(2/6) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | CENT01 | 2 | L8 | 2202 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-03-CENT01-2L82203 | FIRE PROTECTION - L8 SIGNATURE RESTAURANT +948.10M - SHEET 03-(3/6) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 03 | CENT01 | 2 | L8 | 2203 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2L82204 | FIRE PROTECTION - L8 SIGNATURE RESTAURANT +948.10M - SHEET 04-(4/6) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | L8 | 2204 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3L82206 | FIRE PROTECTION - L8 SIGNATURE RESTAURANT +948.10M - SECTION SHEET - (6/6) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | L8 | 2206 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L84004 | FIRE PROTECTION - KITCHENHOOD - L8 +948.10M (01/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L8 | 4004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L84005 | FIRE PROTECTION - KITCHENHOOD - L8 +948.10M (02/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7400 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L8 | 4005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L85084 | FIRE PROTECTION - NOVEC SYSTEM -L8 +948.10M - CENTRAL BUILDING (66/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L8 | 5084 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-4L85085 | FIRE PROTECTION - NOVEC SYSTEM -L8 +948.10M - CENTRAL BUILDING (67/67) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.7260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 4 | L8 | 5085 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-CENT01-2RL2205 | FIRE PROTECTION - L8 SIGNATURE RESTAURANT ROOF-(5/6) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.MBL.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | CENT01 | 2 | RL | 2205 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003100 | FIRE PROTECTION - BL1 (870.6M, 882M, 884.75M) - ENLARGED LAYOUT - (1/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3100 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003101 | FIRE PROTECTION - BL1 (887.75M, 893.5M, 899.25M) - ENLARGED LAYOUT - (2/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3101 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003102 | FIRE PROTECTION - BL1 (905M, 910.75M, 917.5M) - ENLARGED LAYOUT - (3/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FIRE PROTECTION | QP.E.ME.BL1.GEN.2940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3102 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003103 | FIRE PROTECTION - BL1 (922.25M, 928M, 935.85 M) - ENLARGED LAYOUT - (4/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FIRE PROTECTION | QP.E.ME.BL1.GEN.2940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3103 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003104 | FIRE PROTECTION - BL1 (941.6M, 947.35M, 953M) - ENLARGED LAYOUT - (5/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3104 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003105 | FIRE PROTECTION - BL1 (958.75M, 962.30M, 966.515M) - ENLARGED LAYOUT - (6/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3105 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003109 | FIRE PROTECTION - BL1 (970.65M, 974.755M, 989.00M) - ENLARGED LAYOUT - (7/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3109 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-MBLAD1-2003124 | FIRE PROTECTION - MINI BLADE - ENLARGED - LAYOUT - (8/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | MBLAD1 | 2 | 00 | 3124 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-MBLAD1-2003125 | FIRE PROTECTION - MINI BLADE - ENLARGED - LAYOUT - (9/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | MBLAD1 | 2 | 00 | 3125 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003110 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL1 (870.6M, 882M, 884.75M) - ENLARGED LAYOUT - (10/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3110 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003111 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL1 (887.75M, 893.5M, 899.25M) - ENLARGED LAYOUT - (11/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3111 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003112 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL1 (905M, 910.75M, 917.5M) - ENLARGED LAYOUT - (12/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | FIRE PROTECTION | QP.E.ME.BL1.GEN.2940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3112 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003113 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL1 (922.25M, 928M, 935.85 M) - ENLARGED LAYOUT - (13/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE PROTECTION | QP.E.ME.BL1.GEN.2940 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3113 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003114 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL1 (941.6M, 947.35M, 953M) - ENLARGED LAYOUT - (14/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3114 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003115 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL1 (958.75M, 962.30M, 966.515M) - ENLARGED LAYOUT - (15/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3115 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003116 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL1 (970.65M, 974.755M, 989.00M) - ENLARGED LAYOUT - (16/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3116 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003117 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL1 MINI BLADE - ENLARGED - LAYOUT - (17/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3117 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003118 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL1 MINI BLADE - ENLARGED - LAYOUT - (18/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3118 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003119 | FIRE PROTECTION - BL1 SECTION SHEET 01 - (19/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3119 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003120 | FIRE PROTECTION - BL1 SECTION SHEET 02 - (20/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3120 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003121 | FIRE PROTECTION - BL1 SECTION SHEET 03 - (21/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3121 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003122 | FIRE PROTECTION - BL1 SECTION SHEET 04 - (22/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3122 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003123 | FIRE PROTECTION - BL1 SECTION SHEET 05 - (23/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3123 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003124 | FIRE PROTECTION - BL1 SECTION SHEET 06 - (24/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3124 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-2003125 | FIRE PROTECTION - BL1 SECTION SHEET 07 - (25/25) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL1.GEN.1510 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 2 | 00 | 3125 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-4005013 | FIRE PROTECTION - NOVEC SYSTEM - BLADE 4 (01/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.5890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 4 | 00 | 5013 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-4005014 | FIRE PROTECTION - NOVEC SYSTEM - BLADE 4 (02/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.5890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 4 | 00 | 5014 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-4005015 | FIRE PROTECTION - NOVEC SYSTEM - BLADE 4 (03/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.5890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 4 | 00 | 5015 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-4005016 | FIRE PROTECTION - NOVEC SYSTEM - BLADE 4 (04/04) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.5890 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 4 | 00 | 5016 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003200 | FIRE PROTECTION - BL2 (876.25M, 882M, 887.75M) - ENLARGED LAYOUT - (1/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.BL2.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3200 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003201 | FIRE PROTECTION - BL2 (893.5M, 899.25M, 905M) - ENLARGED LAYOUT - (2/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.BL2.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3201 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-3003202 | FIRE PROTECTION - BL2 (910.75M, 916.5M, 922.25M) - ENLARGED LAYOUT - (3/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.BL2.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 3 | 00 | 3202 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003203 | FIRE PROTECTION - BL2 (928M, 935.85M, 941.6M) - ENLARGED LAYOUT - (4/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FIRE PROTECTION | QP.E.ME.BL2.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3203 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003204 | FIRE PROTECTION - BL2 (945.40M, 948.1M, 951.625) - ENLARGED LAYOUT - (5/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FIRE PROTECTION | QP.E.ME.BL2.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3204 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003205 | FIRE PROTECTION - BL2 (957.25, 847.5M) - ENLARGEDLAYOUT - (6/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FIRE PROTECTION | QP.E.ME.BL2.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3205 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003206 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL2 (876.25M, 882M, 887.75M) - ENLARGED LAYOUT - (7/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.BL2.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3206 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003207 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL2 (893.5M, 899.25M, 905M) - ENLARGED LAYOUT - (8/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.BL2.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3207 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003208 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL2 (910.75M, 916.5M, 922.25M) - ENLARGED LAYOUT - (9/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | FIRE PROTECTION | QP.E.ME.BL2.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3208 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003209 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL2 (928M, 935.85M, 941.6M) - ENLARGED LAYOUT - (10/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FIRE PROTECTION | QP.E.ME.BL2.GEN.1910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3209 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003210 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL2 (945.40M, 948.1M, 951.625) - ENLARGED LAYOUT - (11/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FIRE PROTECTION | QP.E.ME.BL2.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3210 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003211 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL2 (957.25, 847.5M) - ENLARGEDLAYOUT - (12/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FIRE PROTECTION | QP.E.ME.BL2.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3211 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003212 | FIRE PROTECTION - BL2 SECTION SHEET 01 - (13/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL2.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3212 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003213 | FIRE PROTECTION - BL2 SECTION SHEET 02 - (14/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL2.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3213 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003214 | FIRE PROTECTION - BL2 SECTION SHEET 03 - (15/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL2.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3214 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003215 | FIRE PROTECTION - BL2 SECTION SHEET 04 - (16/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL2.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3215 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-2003216 | FIRE PROTECTION - BL2 SECTION SHEET 05 - (17/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL2.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 2 | 00 | 3216 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD02-3003205 | FIRE PROTECTION - BL2 SECTION SHEET 06 - (18/18) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL2.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD02 | 3 | 00 | 3205 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-3003300 | FIRE PROTECTION - BL3 (847.5M, 853.25M, 859.00M) - ENLARGED LAYOUT - (1/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 3 | 00 | 3300 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-2003301 | FIRE PROTECTION - BL3 (867.62M, 876.25M, 887.75M) - ENLARGED LAYOUT - (2/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 2 | 00 | 3301 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-2003302 | FIRE PROTECTION - BL3 (894.58M, 900.33M, 905M) - ENLARGED LAYOUT - (3/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 2 | 00 | 3302 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-2003303 | FIRE PROTECTION - BL3 (910.75M, 916.5M, 921M) - ENLARGED LAYOUT - (4/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 2 | 00 | 3303 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-2003217 | FIRE PROTECTION - BL3 (928M, 931.1M, ) - ENLARGED LAYOUT - (5/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 2 | 00 | 3217 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-2003218 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL3 (847.5M, 853.25M, 859.00M) - ENLARGED LAYOUT - (6/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 2 | 00 | 3218 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-2003219 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL3 (867.62M, 876.25M, 887.75M) - ENLARGED LAYOUT - (7/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 2 | 00 | 3219 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-2003220 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL3 (894.58M, 900.33M, 905M) - ENLARGED LAYOUT - (8/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 2 | 00 | 3220 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-2003221 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL3 (910.75M, 916.5M, 921M) - ENLARGED LAYOUT - (9/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 2 | 00 | 3221 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-2003222 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL3 (928M, 931.1M, ) - ENLARGED LAYOUT - (10/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-31 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 2 | 00 | 3222 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-3003223 | FIRE PROTECTION - BL3 SECTION SHEET 01 - (11/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 3 | 00 | 3223 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-3003224 | FIRE PROTECTION - BL3 SECTION SHEET 02 - (12/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 3 | 00 | 3224 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-3003225 | FIRE PROTECTION - BL3 SECTION SHEET 03 - (13/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 3 | 00 | 3225 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-3003226 | FIRE PROTECTION - BL3 SECTION SHEET 04 - (14/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 3 | 00 | 3226 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD03-3003304 | FIRE PROTECTION - BL3 SECTION SHEET 05 - (15/15) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL3.GEN.1790 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD03 | 3 | 00 | 3304 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003400 | FIRE PROTECTION - BL4 (863.85M, 870.5M, 876.25M) - ENLARGED LAYOUT - (1/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3400 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003401 | FIRE PROTECTION - BL4 (876.25M , 887.75M , 887.75M) - ENLARGED LAYOUT - (2/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3401 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003402 | FIRE PROTECTION - BL4 (899.25M, 905M , 910.75M) - ENLARGED LAYOUT - (3/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3402 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003403 | FIRE PROTECTION - BL4 (916.5M, 922.25M, 928M) - ENLARGED LAYOUT - (4/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3403 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003404 | FIRE PROTECTION - BL4 (935.85M , 935.85M , 941.6M) - ENLARGED LAYOUT - (5/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3404 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003405 | FIRE PROTECTION - BL4 (947.35, 952.45M , 959.0M) - ENLARGED LAYOUT - (6/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3405 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003406 | FIRE PROTECTION - BL4 (968.30M , 975.82M) - ENLARGED LAYOUT - (7/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3406 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-MBLAD4-2003407 | FIRE PROTECTION - BL4 MINI BLADE - ENLARGED - LAYOUT - (8/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-19 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | MBLAD4 | 2 | 00 | 3407 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-MBLAD4-2003408 | FIRE PROTECTION - BL4 MINI BLADE - ENLARGED - LAYOUT - (9/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-19 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | MBLAD4 | 2 | 00 | 3408 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003227 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL4 (863.85M, 870.5M, 876.25M) - ENLARGED LAYOUT - (10/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3227 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003228 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL4 (876.25M , 887.75M , 887.75M) - ENLARGED LAYOUT - (11/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3228 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003229 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL4 (899.25M, 905M , 910.75M) - ENLARGED LAYOUT - (12/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2110 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3229 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003230 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL4 (916.5M, 922.25M, 928M) - ENLARGED LAYOUT - (13/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2910 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3230 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003231 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL4 (935.85M , 935.85M , 941.6M) - ENLARGED LAYOUT - (14/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3231 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003232 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL4 (947.35, 952.45M , 959.0M ) - ENLARGED LAYOUT - (15/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3232 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003409 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL4 (968.30M , 975.82M , ) - ENLARGED LAYOUT - (16/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3409 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003233 | FIRE EXTINGUISHER DISTRIBUTION PLAN - MINI BLADE - ENLARGED - LAYOUT - (17/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3233 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-2003234 | FIRE EXTINGUISHER DISTRIBUTION PLAN - MINI BLADE - ENLARGED - LAYOUT - (18/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 2 | 00 | 3234 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-3003235 | FIRE PROTECTION - BL4 SECTION SHEET 01 - (19/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 3 | 00 | 3235 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-3003236 | FIRE PROTECTION - BL4 SECTION SHEET 02 - (20/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 3 | 00 | 3236 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-3003237 | FIRE PROTECTION - BL4 SECTION SHEET 03 - (21/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 3 | 00 | 3237 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-3003238 | FIRE PROTECTION - BL4 SECTION SHEET 04 - (22/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 3 | 00 | 3238 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-3003239 | FIRE PROTECTION - BL4 SECTION SHEET 05 - (23/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 3 | 00 | 3239 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD04-3003410 | FIRE PROTECTION - BL4 SECTION SHEET 06 - (24/24) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL4.GEN.2810 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD04 | 3 | 00 | 3410 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-2003500 | FIRE PROTECTION - BL5 (894.5M , 899.5M , 905M) - ENLARGED LAYOUT - (1/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 2 | 00 | 3500 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-2003501 | FIRE PROTECTION - BL5 (910.75M , 917.5M , 922.25M) - ENLARGED LAYOUT - (2/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1550 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 2 | 00 | 3501 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-2003502 | FIRE PROTECTION - BL5 (928M , 931.7M , 935.85) - ENLARGED LAYOUT - (3/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1550 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 2 | 00 | 3502 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-2003503 | FIRE PROTECTION - BL5 (941.6M , 948.10 , 953.85M) - ENLARGED LAYOUT - (4/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1750 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 2 | 00 | 3503 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-2003504 | FIRE PROTECTION - BL5 (957.50 , 962.64 , 969.3) - ENLARGED LAYOUT - (5/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1750 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 2 | 00 | 3504 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-2003240 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL5 (894.5M , 899.5M , 905M) - ENLARGED LAYOUT - (6/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 2 | 00 | 3240 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-2003241 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL5 (910.75M , 917.5M , 922.25M) - ENLARGED LAYOUT - (7/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1550 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 2 | 00 | 3241 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-2003242 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL5 (928M , 931.7M , 935.85) - ENLARGED LAYOUT - (8/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1550 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 2 | 00 | 3242 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-2003243 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL5 (941.6M , 948.10 , 953.85M) - ENLARGED LAYOUT - (9/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1750 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 2 | 00 | 3243 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-2003505 | FIRE EXTINGUISHER DISTRIBUTION PLAN - BL5 (957.50 , 962.64 , 969.3 ) - ENLARGED LAYOUT - (10/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1750 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 2 | 00 | 3505 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-3003244 | FIRE PROTECTION - BL5 SECTION SHEET 01 - (11/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1750 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 3 | 00 | 3244 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-3003245 | FIRE PROTECTION - BL5 SECTION SHEET 02 - (12/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1750 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 3 | 00 | 3245 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-3003246 | FIRE PROTECTION - BL5 SECTION SHEET 03 - (13/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1750 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 3 | 00 | 3246 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD05-3003506 | FIRE PROTECTION - BL5 SECTION SHEET 04 - (14/14) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.BL5.GEN.1750 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD05 | 3 | 00 | 3506 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-4005000 | FIRE PROTECTION - NOVEC SYSTEM - BLADE 1 (01/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL1.GEN.3680 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 4 | 00 | 5000 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-BLAD01-4005001 | FIRE PROTECTION - NOVEC SYSTEM - BLADE 1 (02/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-12-03 | FIRE PROTECTION | QP.E.ME.BL1.GEN.3680 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | BLAD01 | 4 | 00 | 5001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-0ZZ6001 | FIRE PROTECTION - SCHEMATIC - 1 - (01/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 0 | ZZ | 6001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-0ZZ6002 | FIRE PROTECTION - SCHEMATIC - 2 - (02/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 0 | ZZ | 6002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-0ZZ6003 | FIRE PROTECTION - SCHEMATIC - 3 - (03/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 0 | ZZ | 6003 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-5ZZ6005 | FIRE PROTECTION - STANDARD DETAILS - 1 - (01/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 5 | ZZ | 6005 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-5ZZ6006 | FIRE PROTECTION - STANDARD DETAILS - 2 - (02/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 5 | ZZ | 6006 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-5ZZ6007 | FIRE PROTECTION - STANDARD DETAILS - 3 - (03/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 5 | ZZ | 6007 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-2ZZ6008 | FIRE PROTECTION - ZONING - 1 - (01/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-02-12 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 2 | ZZ | 6008 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-2ZZ6009 | FIRE PROTECTION - ZONING - 2 - (02/02) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2027-02-12 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 2 | ZZ | 6009 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-CAL-FPR-00-Z00000-000002 | FIRE PROTECTION - HYDRAULIC CALCULATION | QF01012-BSB-TEC-CAL-FPR-00-Z00-00002_(0A) | Fire & Life Safety | MicrosoftWord | .docx,.pdf | NTS | 2027-02-12 | FIRE PROTECTION | QP.E.ME.CBR.GEN.1000 | FI_40_10 | QF01012 | NES | C04518 | CAL | FPR | 00 | Z00000 | 0 | 00 | 002 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-000000-2ZZ6004 | FIRE PROTECTION - SITE PLAN OVERALL LAYOUT | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | 000000 | 2 | ZZ | 6004 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-2ZZ7100 | FIRE PROTECTION - B3 +887.5M - OVERALL LAYOUT INFRA | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 2 | ZZ | 7100 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-Z00000-2ZZ7101 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 01 - (01/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | Z00000 | 2 | ZZ | 7101 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-Z00000-2ZZ7102 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 02 - (02/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | Z00000 | 2 | ZZ | 7102 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-03-Z00000-2ZZ7103 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 03 - (03/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 03 | Z00000 | 2 | ZZ | 7103 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-Z00000-2ZZ7104 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 04 - (04/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | Z00000 | 2 | ZZ | 7104 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-05-Z00000-2ZZ7105 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 05 - (05/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 05 | Z00000 | 2 | ZZ | 7105 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-06-Z00000-2ZZ7106 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 06 - (06/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 06 | Z00000 | 2 | ZZ | 7106 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-07-Z00000-2ZZ7107 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 07 - (07/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 07 | Z00000 | 2 | ZZ | 7107 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-08-Z00000-2ZZ7108 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 08- (08/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 08 | Z00000 | 2 | ZZ | 7108 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-10-Z00000-2ZZ7109 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 10 - (09/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 10 | Z00000 | 2 | ZZ | 7109 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-11-Z00000-2ZZ7110 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 11 - (10/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 11 | Z00000 | 2 | ZZ | 7110 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-25-Z00000-2ZZ7111 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 25 - (11/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 25 | Z00000 | 2 | ZZ | 7111 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-26-Z00000-2ZZ7112 | FIRE PROTECTION - INFRA B3 +887.5M - SHEET 26 - (12/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 26 | Z00000 | 2 | ZZ | 7112 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-3ZZ7113 | FIRE PROTECTION - INFRA B3 +887.5M - SECTION SHEET - (13/13) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 3 | ZZ | 7113 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-2ZZ7200 | FIRE PROTECTION - INFRA B1 +900.5M - OVERALL LAYOUT INFRA | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 2 | ZZ | 7200 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-01-Z00000-2ZZ7201 | FIRE PROTECTION - INFRA B1 +900.5M - SHEET 01 - (01/05) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 01 | Z00000 | 2 | ZZ | 7201 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-02-Z00000-2ZZ7202 | FIRE PROTECTION - INFRA B1 +900.5M - SHEET 02 - (02/05) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 02 | Z00000 | 2 | ZZ | 7202 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-03-Z00000-2ZZ7203 | FIRE PROTECTION - INFRA B1 +900.5M - SHEET 03 - (03/05) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 03 | Z00000 | 2 | ZZ | 7203 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-04-Z00000-2ZZ7204 | FIRE PROTECTION - INFRA B1 +900.5M - SHEET 04 - (04/05) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 04 | Z00000 | 2 | ZZ | 7204 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-Z00000-3ZZ7205 | FIRE PROTECTION - INFRA B1 +900.5M - SECTION SHEET - (05/05) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1260 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | Z00000 | 3 | ZZ | 7205 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-MOD-FPR-00-Z00000-0000001 | FIRE PROTECTION BIM MODEL | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .rvt,.nwc,.ifc | NTS | 2026-09-24 | 3D MODEL FIRE PROTECTION |  | FI_60_53 | QF01012 | NES | C04518 | MOD | FPR | 00 | Z00000 | 0 | 00 | 0001 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-SECE01-4001406 | FIRE PROTECTION - SEC MRMU ROOM - OVERALL PLAN | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:300 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | SECE01 | 4 | 00 | 1406 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-07-SECE01-4001407 | FIRE PROTECTION - SEC MRMU ROOM - ENLARGED PLAN (01/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 07 | SECE01 | 4 | 00 | 1407 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-20-SECE01-4001408 | FIRE PROTECTION - SEC MRMU ROOM - ENLARGED PLAN (02/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 20 | SECE01 | 4 | 00 | 1408 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-21-SECE01-4001409 | FIRE PROTECTION - SEC MRMU ROOM - ENLARGED PLAN (03/03) | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 21 | SECE01 | 4 | 00 | 1409 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-22-GARD01-4001410 | FIRE PROTECTION - GAURD ROOM - OVERALL PLAN | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | FIRE PROTECTION | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 22 | GARD01 | 4 | 00 | 1410 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3B11311 | FIRE PROTECTION - B1 SERVICE +900.5M - FIRE PUMP ROOM - SECTION DETAIL 1 | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | B1 | 1311 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-3B11312 | FIRE PROTECTION - B1 SERVICE +900.5M - FIRE PUMP ROOM - SECTION DETAIL 2 | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 3 | B1 | 1312 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!
QF01012-NES-C04518-SDW-FPR-00-CENT01-9B11313 | FIRE PROTECTION - B1 SERVICE +900.5M - FIRE PUMP ROOM - ISOMETRIC | QF01012-BSB-MOD-3DM-FPR-00-Z00-10001 | Fire & Life Safety | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | FIRE PROTECTION | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | FPR | 00 | CENT01 | 9 | B1 | 1313 | Fire & Life Safety | Nesma & Partners | LOD400 |  |  |  | #REF!

## Baseline (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | Package | Activity Code | Activity | Original Duration | Start | Finish
Shop Drawings | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Shop Drawings ¦ Mobilization | QP.M.GN.GEN.GEN.1400 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Shop Drawings ¦ Mobilization ¦ Tower Crane Foundation - Concrete Works | QP.M.GN.GEN.GEN.1470 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Blades Below Loft | QP.M.GN.GEN.GEN.1540 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Loft | QP.M.GN.GEN.GEN.1560 | Submittal | 12 | 2026-08-29 | 2026-09-10
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Above Loft | QP.M.GN.GEN.GEN.1580 | Submittal | 12 | 2026-10-01 | 2026-10-14
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works | QP.E.CV.MBL.GEN.3460 | Submittal | 28 | 2025-10-11 | 2025-11-11
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works Outside Core Area | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works Outside Core Area | QP.E.CV.MBL.GEN.3540 | Submittal | 14 | 2025-11-12 | 2025-11-27
Shop Drawings | Civil | Blades | Blade 1 | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 1 | QP.E.CV.BL1.GEN.1060 | Submittal | 28 | 2026-02-21 | 2026-03-28
Shop Drawings | Civil | Blades | Blade 2 | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 2 | QP.E.CV.BL2.GEN.1060 | Submittal | 28 | 2026-01-19 | 2026-02-19
Shop Drawings | Civil | Blades | Blade 3 | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 3 | QP.E.CV.BL3.GEN.1060 | Submittal | 28 | 2025-12-17 | 2026-01-18
Shop Drawings | Civil | Blades | Blade 4 | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 4 | QP.E.CV.BL4.GEN.1060 | Submittal | 28 | 2025-12-03 | 2026-01-04
Shop Drawings | Civil | Blades | Blade 5 | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 5 | QP.E.CV.BL5.GEN.1060 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Civil | Parking | Parking | Parking | Parking | Parking | Shop Drawings ¦ Civil ¦ Parking | QP.E.CV.PAR.GEN.1000 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - Foundation Works Core Area | QP.E.CV.MBL.GEN.3000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 03 +887.750M | QP.E.CV.MBL.GEN.3030 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - SOG | QP.E.CV.MBL.GEN.3640 | Submittal | 14 | 2026-03-16 | 2026-04-02
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 02 - Foundation Works Outside Core Area | QP.E.CV.MBL.GEN.3020 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 02 +893.5M | QP.E.CV.MBL.GEN.3070 | Submittal | 21 | 2026-02-18 | 2026-03-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 01 +900.5M | QP.E.CV.MBL.GEN.3100 | Submittal | 28 | 2026-03-16 | 2026-04-19
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01- LOBBY LEVEL +905M | QP.E.CV.MBL.GEN.3120 | Submittal | 25 | 2026-04-20 | 2026-05-18
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01 - MEZZANINE +909M | QP.E.CV.MBL.GEN.3140 | Submittal | 15 | 2026-05-19 | 2026-06-08
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3180 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3380 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3220 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3400 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3240 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3420 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3260 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3440 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | QP.E.CV.MBL.GEN.3280 | Submittal | 25 | 2026-10-08 | 2026-11-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | QP.E.CV.MBL.GEN.3300 | Submittal | 28 | 2027-03-13 | 2027-04-13
Shop Drawings | Concrete | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Premium Theatre Concrete Works | QP.E.CV.MBL.GEN.3150 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Amphitheatre Concrete Works | QP.E.CV.MBL.GEN.3200 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Premium Theater | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Premium Theater | QP.E.CV.MBL.GEN.3660 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Loft and Adaptable Theatre | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Loft and Adaptable Theatre | QP.E.CV.MBL.GEN.3700 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Fly Tower | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Fly Tower | QP.E.CV.MBL.GEN.3710 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Lobby & Plaza | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Lobby & Plaza | QP.E.CV.MBL.GEN.3680 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Royal Majlis | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Royal Majlis | QP.E.CV.MBL.GEN.3740 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Foundation | QP.E.CV.BL1.GEN.1000 | Submittal | 25 | 2026-02-25 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL1.GEN.1040 | Submittal | 25 | 2026-03-29 | 2026-04-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL1.GEN.1080 | Submittal | 18 | 2026-05-12 | 2026-06-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL1.GEN.1020 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL1.GEN.1120 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL1.GEN.1100 | Submittal | 28 | 2026-10-27 | 2026-11-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Foundation | QP.E.CV.BL2.GEN.1000 | Submittal | 21 | 2026-03-02 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL2.GEN.1040 | Submittal | 21 | 2026-03-10 | 2026-04-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL2.GEN.1080 | Submittal | 18 | 2026-04-21 | 2026-05-11
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL2.GEN.1020 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL2.GEN.1140 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL2.GEN.1120 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Foundation | QP.E.CV.BL3.GEN.1000 | Submittal | 21 | 2026-02-07 | 2026-03-03
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Steel Composite Slab Including Embedded items Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Steel Composite Slab Including Embedded items Below Loft | QP.E.CV.BL3.GEN.1030 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL3.GEN.1080 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL3.GEN.1020 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Foundation | QP.E.CV.BL4.GEN.1000 | Submittal | 28 | 2026-01-05 | 2026-02-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL4.GEN.1030 | Submittal | 28 | 2026-02-24 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL4.GEN.1080 | Submittal | 15 | 2026-03-31 | 2026-04-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL4.GEN.1020 | Submittal | 28 | 2026-04-18 | 2026-05-19
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL4.GEN.1100 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL4.GEN.1120 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Foundation | QP.E.CV.BL5.GEN.1000 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL5.GEN.1030 | Submittal | 28 | 2026-03-23 | 2026-04-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL5.GEN.1080 | Submittal | 18 | 2026-03-31 | 2026-04-20
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL5.GEN.1020 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL5.GEN.1100 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL5.GEN.1120 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Foundation Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Foundation Including Embedded items | QP.E.CV.PAR.GEN.1020 | Submittal | 28 | 2027-04-28 | 2027-06-03
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Structural Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Structural Concrete Works Including Embedded items | QP.E.CV.PAR.GEN.1040 | Submittal | 28 | 2027-06-19 | 2027-07-20
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Below Loft | QP.E.ST.GEN.GEN.1090 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1100 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1110 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1050 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1060 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1070 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 3,4,5 | QP.E.ST.GEN.GEN.1000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | QP.E.ST.GEN.GEN.1010 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Truss below Auditorium, Side and Back Stage | QP.E.ST.GEN.GEN.2120 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1220 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1230 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1200 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1210 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1190 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Embedded part - Main Building Above Level 5 | QP.E.ST.GEN.GEN.1040 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Premium Theater - Frame Balconies and Back Stage Dressing | QP.E.ST.GEN.GEN.2140 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Loft and adaptable Theatre | QP.E.ST.GEN.GEN.1340 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1390 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1400 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1310 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1320 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1330 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1470 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ Truss above Auditorium Incl. Metal Deck | QP.E.ST.GEN.GEN.2100 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Temporay Tower ROYAL MAJLIS and Blades above loft | QP.E.ST.GEN.GEN.1490 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2160 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1520 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Truss above Flytower | QP.E.ST.GEN.GEN.2180 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1540 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ Blade 2 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2200 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ Adaptable Theatre Incl. Metal Deck | QP.E.ST.GEN.GEN.1560 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.2220 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Loft Truss and Infilled Beam North Side Incl. Metal Deck | QP.E.ST.GEN.GEN.1610 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1600 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Lobby and Plaza Incl. Metal Deck | QP.E.ST.GEN.GEN.1660 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Frame for Mezzanine | QP.E.ST.GEN.GEN.1670 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Link Bridge and Helix Stair | QP.E.ST.GEN.GEN.1570 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1680 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | Shop Drawings ¦ Structural Steel ¦ Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck ¦ ROYAL MAJLIS | QP.E.ST.GEN.GEN.1640 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1090 | Submittal | 21 | 2026-03-26 | 2026-04-19
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1120 | Submittal | 21 | 2026-09-15 | 2026-10-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Wall Cladding | QP.E.AF.MBL.GEN.4440 | Submittal | 21 | 2026-10-11 | 2026-11-03
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1100 | Submittal | 21 | 2026-11-04 | 2026-11-28
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ FFE | QP.E.AF.MBL.GEN.5260 | Submittal | 21 | 2026-11-29 | 2026-12-22
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1170 | Submittal | 21 | 2026-04-20 | 2026-05-13
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1200 | Submittal | 20 | 2026-11-04 | 2026-11-26
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5700 | Submittal | 21 | 2026-11-28 | 2026-12-21
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1180 | Submittal | 21 | 2026-12-23 | 2027-01-16
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ FFE | QP.E.AF.MBL.GEN.5280 | Submittal | 21 | 2027-01-17 | 2027-02-09
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1220 | Submittal | 21 | 2026-05-14 | 2026-06-10
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1250 | Submittal | 28 | 2026-11-28 | 2026-12-29
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5720 | Submittal | 21 | 2026-12-30 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1230 | Submittal | 21 | 2027-01-24 | 2027-02-16
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ FFE | QP.E.AF.MBL.GEN.5300 | Submittal | 21 | 2027-02-17 | 2027-03-16
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1310 | Submittal | 21 | 2026-06-11 | 2026-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1340 | Submittal | 28 | 2026-12-30 | 2027-01-31
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5800 | Submittal | 21 | 2027-02-01 | 2027-02-25
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1320 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ FFE | QP.E.AF.MBL.GEN.5320 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1400 | Submittal | 21 | 2026-07-06 | 2026-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1430 | Submittal | 20 | 2027-02-01 | 2027-02-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5740 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1410 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ FFE | QP.E.AF.MBL.GEN.5340 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1000 | Submittal | 21 | 2026-07-30 | 2026-08-23
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1030 | Submittal | 20 | 2027-02-25 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5760 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1010 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ FFE | QP.E.AF.MBL.GEN.5360 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1490 | Submittal | 21 | 2026-08-24 | 2026-09-16
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1520 | Submittal | 20 | 2027-03-23 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5820 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1500 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ FFE | QP.E.AF.MBL.GEN.5380 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1580 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1610 | Submittal | 20 | 2027-04-15 | 2027-05-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5840 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1590 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ FFE | QP.E.AF.MBL.GEN.5400 | Submittal | 21 | 2027-07-06 | 2027-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1670 | Submittal | 21 | 2026-12-20 | 2027-01-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1700 | Submittal | 20 | 2027-05-23 | 2027-06-14
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5860 | Submittal | 28 | 2027-06-15 | 2027-07-17
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1680 | Submittal | 28 | 2027-07-18 | 2027-08-18
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ FFE | QP.E.AF.MBL.GEN.5420 | Submittal | 28 | 2027-07-31 | 2027-08-31
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1760 | Submittal | 21 | 2027-01-19 | 2027-02-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1790 | Submittal | 21 | 2027-05-23 | 2027-06-15
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5880 | Submittal | 21 | 2027-07-18 | 2027-08-10
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1770 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ FFE | QP.E.AF.MBL.GEN.5440 | Submittal | 21 | 2027-09-01 | 2027-09-26
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1880 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1910 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5900 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1890 | Submittal | 21 | 2027-09-13 | 2027-10-07
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ FFE | QP.E.AF.MBL.GEN.5460 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1800 | Submittal | 21 | 2027-04-22 | 2027-05-20
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1830 | Submittal | 21 | 2027-07-25 | 2027-08-17
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5920 | Submittal | 21 | 2027-08-25 | 2027-09-18
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1810 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ FFE | QP.E.AF.MBL.GEN.5480 | Submittal | 21 | 2027-10-11 | 2027-11-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1110 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1140 | Submittal | 21 | 2027-05-31 | 2027-06-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1120 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1370 | Submittal | 21 | 2027-03-01 | 2027-03-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1360 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Wall Cladding | QP.E.AF.BL1.GEN.5940 | Submittal | 21 | 2027-07-19 | 2027-08-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1340 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1650 | Submittal | 21 | 2027-06-14 | 2027-07-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1680 | Submittal | 14 | 2027-09-01 | 2027-09-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1660 | Submittal | 21 | 2027-11-18 | 2027-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1080 | Submittal | 21 | 2027-05-26 | 2027-06-19
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1110 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Wall Cladding | QP.E.AF.BL2.GEN.5960 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1090 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1580 | Submittal | 21 | 2027-07-04 | 2027-07-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1610 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1590 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1670 | Submittal | 21 | 2027-07-28 | 2027-08-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1700 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1680 | Submittal | 14 | 2028-01-18 | 2028-02-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1000 | Submittal | 24 | 2026-11-15 | 2026-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1030 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL3.GEN.5980 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1010 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1340 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1370 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1350 | Submittal | 21 | 2027-12-22 | 2028-01-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1210 | Submittal | 24 | 2026-12-27 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1240 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL4.GEN.6000 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1220 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1820 | Submittal | 21 | 2027-04-24 | 2027-05-22
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1850 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1830 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1730 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1760 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1740 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.2280 | Submittal | 24 | 2027-02-07 | 2027-03-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.2340 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.2300 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1130 | Submittal | 21 | 2027-03-22 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1160 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1140 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1500 | Submittal | 28 | 2027-06-29 | 2027-07-31
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1530 | Submittal | 21 | 2027-10-10 | 2027-11-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Wall Cladding | QP.E.AF.BL5.GEN.6020 | Submittal | 21 | 2027-12-16 | 2028-01-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1510 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1000 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1020 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Doors / Openings | QP.E.AF.PAR.GEN.1010 | Submittal | 28 | 2027-12-22 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Specialities | QP.E.AF.MBL.GEN.5160 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1030 | Submittal | 28 | 2027-10-16 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1050 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Doors / Openings | QP.E.AF.PAR.GEN.1040 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Specialities | QP.E.AF.MBL.GEN.5200 | Submittal | 21 | 2028-01-09 | 2028-02-01
Shop Drawings | Architecture and Fitouts | Amphitheatre | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4040 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Architecture and Fitouts | Amphitheatre | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.4070 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Amphitheatre | Wall Cladding | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Wall Cladding | QP.E.AF.MBL.GEN.6040 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | Architecture and Fitouts | Amphitheatre | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4050 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | Shop Drawings ¦ External Building Works (Guard House, SEC Room) | QP.E.EX.GEN.GEN.1270 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Main Building | QP.E.AF.MBL.GEN.6060 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 5 | Water Proofing - Roof - Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 5 | QP.E.AF.BL5.GEN.6180 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 4 | Water Proofing - Roof - Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 4 | QP.E.AF.BL4.GEN.6160 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 3 | Water Proofing - Roof - Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 3 | QP.E.AF.BL3.GEN.6140 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 1 | Water Proofing - Roof - Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 1 | QP.E.AF.BL1.GEN.6100 | Submittal | 21 | 2027-12-09 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 2 | Water Proofing - Roof - Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 2 | QP.E.AF.BL2.GEN.6120 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Wet Areas | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Wet Areas ¦ Main Building | QP.E.AF.MBL.GEN.4400 | Submittal | 21 | 2027-08-08 | 2027-08-31
Shop Drawings | Specialist Systems | Doors/ Openings | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Main Building | QP.E.AF.MBL.GEN.1140 | Submittal | 20 | 2027-06-29 | 2027-07-21
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.1130 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 2 | QP.E.AF.BL2.GEN.1100 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.1020 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.1230 | Submittal | 21 | 2027-08-16 | 2027-09-08
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.2320 | Submittal | 21 | 2027-09-09 | 2027-10-04
Shop Drawings | Specialist Systems | Doors/ Openings | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Amphitheatre | QP.E.AF.MBL.GEN.4060 | Submittal | 28 | 2027-11-13 | 2027-12-14
Shop Drawings | Specialist Systems | Conveying System | Waste Management | Waste Management | Waste Management | Waste Management | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Waste Management | QP.E.CY.GEN.GEN.1280 | Submittal | 14 | 2027-12-02 | 2027-12-18
Shop Drawings | Specialist Systems | Conveying System | Escalators | Escalators | Escalators | Escalators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Escalators | QP.E.CY.GEN.GEN.1040 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | Specialist Systems | Conveying System | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | QP.E.CY.GEN.GEN.1020 | Submittal | 28 | 2026-10-22 | 2026-11-23
Shop Drawings | Specialist Systems | Conveying System | Truck Elevators | Truck Elevators | Truck Elevators | Truck Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Truck Elevators | QP.E.CY.GEN.GEN.1000 | Submittal | 28 | 2026-09-19 | 2026-10-21
Shop Drawings | Specialist Systems | Conveying System | Inclined Elevators | Inclined Elevators | Inclined Elevators | Inclined Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Inclined Elevators | QP.E.CY.GEN.GEN.1050 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Main Building | QP.E.CY.GEN.GEN.1090 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 1 | QP.E.CY.GEN.GEN.1130 | Submittal | 28 | 2027-10-17 | 2027-11-17
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 2 | QP.E.CY.GEN.GEN.1170 | Submittal | 28 | 2027-09-13 | 2027-10-16
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 3 | Balde 3 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 3 | QP.E.CY.GEN.GEN.1210 | Submittal | 28 | 2027-06-07 | 2027-07-08
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 4 | QP.E.CY.GEN.GEN.1110 | Submittal | 28 | 2027-07-10 | 2027-08-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 5 | Balde 5 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 5 | QP.E.CY.GEN.GEN.1150 | Submittal | 28 | 2027-08-11 | 2027-09-12
Shop Drawings | Specialist Systems | Joinery Works | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Main Building | QP.E.AF.MBL.GEN.5540 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.6120 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.6160 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.6180 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.6200 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Shop Drawings ¦ Specialist Systems ¦ Kitchen and Laundary | QP.E.AF.MBL.GEN.5500 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Specialist Systems | Water Features | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Specialist Systems ¦ Water Features | QP.E.AF.MBL.GEN.6100 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Mechanical | QP.E.ME.MBL.GEN.6780 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical | QP.E.ME.MBL.GEN.6800 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6840 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical | QP.E.ME.MBL.GEN.6850 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6860 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical | QP.E.ME.MBL.GEN.6870 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Mechanical | QP.E.ME.MBL.GEN.6900 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical | QP.E.ME.MBL.GEN.6910 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Mechanical | QP.E.ME.MBL.GEN.6940 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical | QP.E.ME.MBL.GEN.6950 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Mechanical | QP.E.ME.MBL.GEN.6980 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Electrical | QP.E.ME.MBL.GEN.6990 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Mechanical | QP.E.ME.MBL.GEN.7020 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical | QP.E.ME.MBL.GEN.7030 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7060 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical | QP.E.ME.MBL.GEN.7070 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7100 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical | QP.E.ME.MBL.GEN.7110 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Mechanical | QP.E.ME.MBL.GEN.7140 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical | QP.E.ME.MBL.GEN.7150 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Mechanical | QP.E.ME.MBL.GEN.7180 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Electrical | QP.E.ME.MBL.GEN.7190 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Mechanical | QP.E.ME.MBL.GEN.7220 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical | QP.E.ME.MBL.GEN.7230 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1320 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1330 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1340 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1350 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ ICT Containment | QP.E.ME.MBL.GEN.1360 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1420 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1430 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1440 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1450 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1460 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1740 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1750 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1760 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1770 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1780 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1590 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1600 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1610 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1620 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.1630 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2040 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2050 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2060 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2070 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ ICT Containment | QP.E.ME.MBL.GEN.2080 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2240 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2250 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2260 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2270 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ ICT Containment | QP.E.ME.MBL.GEN.2280 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2440 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2450 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2460 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2470 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.2480 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2640 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2650 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2660 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2670 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2680 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2850 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2860 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2870 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2880 | Submittal | 28 | 2026-12-08 | 2027-01-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2890 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3070 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3080 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3090 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3100 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ ICT Containment | QP.E.ME.MBL.GEN.3110 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3290 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3300 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3310 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3320 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ ICT Containment | QP.E.ME.MBL.GEN.3330 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3500 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3510 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3520 | Submittal | 28 | 2026-12-23 | 2027-01-24
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3530 | Submittal | 28 | 2027-02-11 | 2027-03-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ ICT Containment | QP.E.ME.MBL.GEN.3540 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.MBL.GEN.5000 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.MBL.GEN.5040 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.MBL.GEN.5060 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.MBL.GEN.5080 | Submittal | 28 | 2027-03-07 | 2027-04-10
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.MBL.GEN.7280 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.MBL.GEN.7300 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.MBL.GEN.7320 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.MBL.GEN.7260 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.MBL.GEN.7340 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | LPG System | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ LPG System | QP.E.ME.MBL.GEN.5100 | Submittal | 21 | 2027-09-22 | 2027-10-17
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.MBL.GEN.7360 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Fire Suppression | QP.E.ME.CBR.GEN.1000 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Plumbing | Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Plumbing | QP.E.ME.CBR.GEN.1011 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ LPG System | QP.E.ME.CBR.GEN.1055 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.CBR.GEN.1022 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Electrical | QP.E.ME.CBR.GEN.1033 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ ELV (Low Current System) | QP.E.ME.CBR.GEN.1044 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.MBL.GEN.7380 | Submittal | 28 | 2027-12-09 | 2028-01-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Diesel | Diesel | Diesel | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Diesel | QP.E.ME.MBL.GEN.7420 | Submittal | 21 | 2028-02-01 | 2028-02-26
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Water Features | Water Features | Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Water Features | QP.E.ME.MBL.GEN.7440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M | QP.E.ME.MBL.GEN.6520 | Submittal | 28 | 2026-06-14 | 2026-07-15
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Grey Water Treatment/ Sewage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Grey Water Treatment/ Sewage | QP.E.ME.MBL.GEN.1050 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Stromwater/ Drainage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Stromwater/ Drainage | QP.E.ME.MBL.GEN.1060 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1040 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M | QP.E.ME.MBL.GEN.6540 | Submittal | 28 | 2026-07-16 | 2026-08-17
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ AHU Room | QP.E.ME.MBL.GEN.1160 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Transformer/ Switchgear/ Panel Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Transformer/ Switchgear/ Panel Room | QP.E.ME.MBL.GEN.1240 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Generator Room/ Diesel Tank | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Generator Room/ Diesel Tank | QP.E.ME.MBL.GEN.1250 | Submittal | 14 | 2026-10-05 | 2026-10-20
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | ETS/ CWP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ ETS/ CWP Room | QP.E.ME.MBL.GEN.1170 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1030 | Submittal | 14 | 2026-09-24 | 2026-10-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1290 | Submittal | 28 | 2026-09-01 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M | QP.E.ME.MBL.GEN.6560 | Submittal | 14 | 2026-08-18 | 2026-09-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1020 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Domestic Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Domestic Water | QP.E.ME.MBL.GEN.1010 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Fire Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Fire Water | QP.E.ME.MBL.GEN.1000 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1280 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 LOBBY LEVEL +905.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 LOBBY LEVEL +905.00M | QP.E.ME.MBL.GEN.6640 | Submittal | 21 | 2026-09-03 | 2026-09-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 UPEER LOBBY LEVEL MEZZANINE +909M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M | QP.E.ME.MBL.GEN.6660 | Submittal | 21 | 2026-09-29 | 2026-10-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L2 THEATRE STALLS +913M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L2 THEATRE STALLS +913M | QP.E.ME.MBL.GEN.6680 | Submittal | 21 | 2026-10-24 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | QP.E.ME.MBL.GEN.6700 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | QP.E.ME.MBL.GEN.6720 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 SECOND CIRCLE AND LOFT +928.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 SECOND CIRCLE AND LOFT +928.00M | QP.E.ME.MBL.GEN.6740 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M | QP.E.ME.MBL.GEN.5540 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - AHU Room | QP.E.ME.MBL.GEN.1180 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Makeup Air Unit and Ecology | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Makeup Air Unit and Ecology | QP.E.ME.MBL.GEN.1190 | Submittal | 14 | 2027-01-06 | 2027-01-21
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Sky Garden Irrigation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Sky Garden Irrigation | QP.E.ME.MBL.GEN.1070 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L6 SKY GARDEN +935.85M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L6 SKY GARDEN +935.85M | QP.E.ME.MBL.GEN.6760 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M | QP.E.ME.MBL.GEN.6580 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | Plant Room - Fan Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M ¦ Plant Room - Fan Room | QP.E.ME.MBL.GEN.6600 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Kitchen and Laundry | Kitchen and Laundry | Kitchen and Laundry | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Kitchen and Laundry | QP.E.ME.MBL.GEN.7400 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | MEP | Panels | Panels | Panels | Panels | Panels | Shop Drawings ¦ MEP ¦ Panels | QP.E.ME.MBL.GEN.6510 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Mechanical | QP.E.ME.BL1.GEN.3720 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical | QP.E.ME.BL1.GEN.3740 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL1.GEN.3760 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL1.GEN.3780 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Mechanical | QP.E.ME.BL1.GEN.3800 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical | QP.E.ME.BL1.GEN.3820 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1020 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1030 | Submittal | 21 | 2027-02-25 | 2027-03-23
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1040 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1050 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ ICT Containment | QP.E.ME.BL1.GEN.1060 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL1.GEN.2940 | Submittal | 21 | 2027-04-11 | 2027-05-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.2950 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.2960 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.2970 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL1.GEN.2980 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1510 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1520 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1530 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1540 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ ICT Containment | QP.E.ME.BL1.GEN.1550 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.BL1.GEN.3280 | Submittal | 21 | 2027-08-30 | 2027-09-22
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL1.GEN.3320 | Submittal | 21 | 2027-10-07 | 2027-10-31
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL1.GEN.3340 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL1.GEN.3360 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL1.GEN.3580 | Submittal | 21 | 2027-11-15 | 2027-12-08
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL1.GEN.3600 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL1.GEN.3620 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL1.GEN.3680 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL1.GEN.3640 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL1.GEN.3660 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3480 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL1.GEN.1000 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL1.GEN.3700 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3400 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical | QP.E.ME.BL2.GEN.3420 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL2.GEN.3440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL2.GEN.3460 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3480 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical | QP.E.ME.BL2.GEN.3500 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1020 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1030 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1040 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1050 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.1060 | Submittal | 21 | 2027-04-18 | 2027-05-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1910 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1920 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1930 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1940 | Submittal | 21 | 2027-04-29 | 2027-05-27
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL2.GEN.1950 | Submittal | 21 | 2027-05-12 | 2027-06-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.2110 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.2120 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.2130 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.2140 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.2150 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL2.GEN.3160 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL2.GEN.3200 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL2.GEN.3220 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL2.GEN.3240 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL2.GEN.3260 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL2.GEN.3280 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL2.GEN.3300 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL2.GEN.3380 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL2.GEN.3320 | Submittal | 28 | 2027-11-22 | 2027-12-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL2.GEN.3340 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3500 | Submittal | 14 | 2028-02-17 | 2028-03-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL2.GEN.1000 | Submittal | 16 | 2028-02-17 | 2028-03-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL2.GEN.3360 | Submittal | 14 | 2028-04-09 | 2028-04-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Mechanical | QP.E.ME.BL3.GEN.3640 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical | QP.E.ME.BL3.GEN.3660 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical | QP.E.ME.BL3.GEN.3700 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Mechanical | QP.E.ME.BL3.GEN.3680 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1020 | Submittal | 21 | 2026-06-17 | 2026-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.1030 | Submittal | 21 | 2026-07-12 | 2026-08-04
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1040 | Submittal | 21 | 2026-08-05 | 2026-08-29
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1050 | Submittal | 21 | 2026-08-30 | 2026-09-22
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ ICT Containment | QP.E.ME.BL3.GEN.1060 | Submittal | 21 | 2026-10-07 | 2026-10-31
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1790 | Submittal | 21 | 2026-12-31 | 2027-01-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.3280 | Submittal | 21 | 2027-01-25 | 2027-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1810 | Submittal | 21 | 2027-02-18 | 2027-03-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1820 | Submittal | 21 | 2027-03-18 | 2027-04-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ ICT Containment | QP.E.ME.BL3.GEN.1830 | Submittal | 21 | 2027-04-12 | 2027-05-05
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL3.GEN.3400 | Submittal | 21 | 2027-06-23 | 2027-07-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL3.GEN.3440 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL3.GEN.3460 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL3.GEN.3480 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL3.GEN.3500 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL3.GEN.3540 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL3.GEN.3560 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL3.GEN.3620 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL3.GEN.3600 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL3.GEN.3580 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3520 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL3.GEN.1000 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL3.GEN.3520 | Submittal | 14 | 2028-04-04 | 2028-04-19
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Mechanical | QP.E.ME.BL4.GEN.6010 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical | QP.E.ME.BL4.GEN.6030 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Mechanical | QP.E.ME.BL4.GEN.6050 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Electrical | QP.E.ME.BL4.GEN.6070 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Mechanical | QP.E.ME.BL4.GEN.6090 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical | QP.E.ME.BL4.GEN.6110 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Fire Suppression | QP.E.ME.BL4.GEN.2110 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2120 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2130 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2140 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ ICT Containment | QP.E.ME.BL4.GEN.2150 | Submittal | 21 | 2026-11-01 | 2026-11-24
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2910 | Submittal | 21 | 2026-12-05 | 2026-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.5550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2930 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2940 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ ICT Containment | QP.E.ME.BL4.GEN.2950 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2810 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2820 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2830 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2840 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ ICT Containment | QP.E.ME.BL4.GEN.2850 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL4.GEN.5770 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL4.GEN.5810 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL4.GEN.5830 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL4.GEN.5850 | Submittal | 21 | 2027-09-29 | 2027-10-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL4.GEN.5870 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL4.GEN.5930 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL4.GEN.5950 | Submittal | 21 | 2027-12-05 | 2027-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL4.GEN.5890 | Submittal | 21 | 2028-01-12 | 2028-02-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL4.GEN.5970 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL4.GEN.5990 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3540 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL4.GEN.3110 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL4.GEN.5910 | Submittal | 14 | 2028-04-02 | 2028-04-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Mechanical | QP.E.ME.BL5.GEN.3040 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical | QP.E.ME.BL5.GEN.3060 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL5.GEN.3080 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL5.GEN.3100 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Mechanical | QP.E.ME.BL5.GEN.3120 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical | QP.E.ME.BL5.GEN.3140 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1020 | Submittal | 21 | 2026-10-29 | 2026-11-22
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1030 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1040 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1050 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ ICT Containment | QP.E.ME.BL5.GEN.1060 | Submittal | 21 | 2026-11-25 | 2026-12-19
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1560 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1570 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1580 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL5.GEN.1590 | Submittal | 21 | 2027-04-10 | 2027-05-03
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1750 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1760 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1770 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1780 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ ICT Containment | QP.E.ME.BL5.GEN.1790 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL5.GEN.2800 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL5.GEN.2840 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL5.GEN.2860 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL5.GEN.2880 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL5.GEN.3020 | Submittal | 14 | 2027-10-24 | 2027-11-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL5.GEN.2900 | Submittal | 14 | 2027-12-01 | 2027-12-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL5.GEN.2920 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL5.GEN.3000 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL5.GEN.2940 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL5.GEN.2960 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3560 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL5.GEN.1000 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL5.GEN.2980 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Mechanical | QP.E.ME.PAR.GEN.1459 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Electrical | QP.E.ME.PAR.GEN.1479 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Mechanical | QP.E.ME.PAR.GEN.1499 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Electrical | QP.E.ME.PAR.GEN.1519 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Fire Suppression | QP.E.ME.PAR.GEN.1000 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1011 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1022 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1033 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ ICT Containment | QP.E.ME.PAR.GEN.1044 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Fire Suppression | QP.E.ME.PAR.GEN.1055 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1066 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1077 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1088 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ ICT Containment | QP.E.ME.PAR.GEN.1099 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.PAR.GEN.1219 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.PAR.GEN.1259 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.PAR.GEN.1279 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.PAR.GEN.1299 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.PAR.GEN.1419 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.PAR.GEN.1319 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.PAR.GEN.1339 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.PAR.GEN.1439 | Submittal | 14 | 2028-02-07 | 2028-02-23
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.PAR.GEN.1359 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.PAR.GEN.1379 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.PAR.GEN.1399 | Submittal | 14 | 2028-03-09 | 2028-03-25
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3600 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3610 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3620 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.4430 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4440 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.4450 | Submittal | 14 | 2027-12-18 | 2028-01-02
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3960 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3970 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3980 | Submittal | 14 | 2028-01-01 | 2028-01-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Fire Suppression | QP.E.ME.MBL.GEN.3930 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3940 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Electrical | QP.E.ME.MBL.GEN.3950 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Fire Suppression | QP.E.ME.MBL.GEN.3810 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3820 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Electrical | QP.E.ME.MBL.GEN.3830 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4400 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4410 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4420 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4340 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4350 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4360 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4520 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4530 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4540 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4640 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4650 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4660 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3870 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3880 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3890 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3840 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3850 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3860 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.4550 | Submittal | 21 | 2028-02-08 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4560 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.4570 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 3, 4 & 5 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 3, 4 & 5 | QP.E.FA.GEN.GEN.1460 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 1 & 2 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 1 & 2 | QP.E.FA.GEN.GEN.2180 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Loft and Lobby | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Loft and Lobby | QP.E.FA.GEN.GEN.2140 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | QP.E.FA.GEN.GEN.2160 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Blades | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Blades | QP.E.FA.GEN.GEN.1820 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Lobby and Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Lobby and Loft | QP.E.FA.GEN.GEN.1770 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Above Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Above Loft | QP.E.FA.GEN.GEN.1780 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Blades | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Blades | QP.E.FA.GEN.GEN.1890 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Main Building | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Main Building | QP.E.FA.GEN.GEN.2230 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Facade | Facade | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 1 | QP.E.FA.GEN.GEN.1920 | Submittal | 28 | 2026-09-29 | 2026-10-31
Shop Drawings | Facade | Facade | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 2 | QP.E.FA.GEN.GEN.1930 | Submittal | 28 | 2026-08-26 | 2026-09-28
Shop Drawings | Facade | Facade | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 3 | QP.E.FA.GEN.GEN.1940 | Submittal | 28 | 2026-05-17 | 2026-06-21
Shop Drawings | Facade | Facade | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 4 | QP.E.FA.GEN.GEN.1950 | Submittal | 28 | 2026-06-22 | 2026-07-23
Shop Drawings | Facade | Facade | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 5 | QP.E.FA.GEN.GEN.1960 | Submittal | 28 | 2026-07-25 | 2026-08-25
Shop Drawings | Facade | Facade | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Facade ¦ Amphitheatre | QP.E.FA.GEN.GEN.2240 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Lobby | Lobby | Lobby | Lobby | Shop Drawings ¦ Facade ¦ Lobby | QP.E.FA.GEN.GEN.2090 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | Loft | Loft | Loft | Loft | Shop Drawings ¦ Facade ¦ Loft | QP.E.FA.GEN.GEN.2100 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Above Loft | Above Loft | Above Loft | Above Loft | Shop Drawings ¦ Facade ¦ Above Loft | QP.E.FA.GEN.GEN.1910 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | Link Bridges | Link Bridges | Link Bridges | Link Bridges | Shop Drawings ¦ Facade ¦ Link Bridges | QP.E.FA.GEN.GEN.2050 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Facade | Facade | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Shop Drawings ¦ Facade ¦ Facade Lighting Fixtures | QP.E.FA.GEN.GEN.1450 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | GRC Cladding | GRC Cladding | GRC Cladding | GRC Cladding | Shop Drawings ¦ Facade ¦ GRC Cladding | QP.E.FA.GEN.GEN.1390 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 1 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 1 | QP.E.CV.MBL.GEN.3060 | Submittal | 28 | 2026-08-06 | 2026-09-07
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 2 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 2 | QP.E.CV.MBL.GEN.3560 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 3 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 3 | QP.E.CV.MBL.GEN.3580 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 4 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 4 | QP.E.CV.MBL.GEN.3600 | Submittal | 28 | 2027-01-03 | 2027-02-03
Shop Drawings | External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Shop Drawings ¦ External Works ¦ Waterproofing for External Works | QP.E.EX.GEN.GEN.1040 | Submittal | 28 | 2026-06-25 | 2026-07-27
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Excavation | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Excavation | QP.E.CV.MBL.GEN.3320 | Submittal | 28 | 2027-01-06 | 2027-02-07
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Blinding Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Blinding Including Embedded Items | QP.E.CV.MBL.GEN.3500 | Submittal | 28 | 2027-02-23 | 2027-03-29
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Foundation Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Foundation Including Embedded Items | QP.E.CV.MBL.GEN.3480 | Submittal | 28 | 2027-04-13 | 2027-05-19
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Structural Concrete Works Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Structural Concrete Works Including Embedded Items | QP.E.CV.MBL.GEN.3520 | Submittal | 28 | 2027-06-03 | 2027-07-05
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4000 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Finishing | Finishing | Finishing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Finishing | QP.E.AF.MBL.GEN.4030 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4010 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Doors / Openings | QP.E.AF.MBL.GEN.4020 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Fire Suppression | QP.E.ME.MBL.GEN.1690 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Plumbing | Plumbing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Plumbing | QP.E.ME.MBL.GEN.1700 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.1710 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Electrical | Electrical | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Electrical | QP.E.ME.MBL.GEN.1720 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ ELV (Low Current System) | QP.E.ME.MBL.GEN.1730 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | External Utilities | Irrigation Works | Irrigation Works | Irrigation Works | Irrigation Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ Irrigation Works | QP.E.EX.GEN.GEN.1090 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Drainage Works | External Drainage Works | External Drainage Works | External Drainage Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Drainage Works | QP.E.EX.GEN.GEN.1110 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Lighting Works | External Lighting Works | External Lighting Works | External Lighting Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Lighting Works | QP.E.EX.GEN.GEN.1170 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | External Utilities | Low Current | Low Current | Low Current | Low Current | Shop Drawings ¦ External Works ¦ External Utilities ¦ Low Current | QP.E.EX.GEN.GEN.1100 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Shop Drawings ¦ External Works ¦ Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 | Submittal | 14 | 2027-08-07 | 2027-08-22
Shop Drawings | External Works | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Shop Drawings ¦ External Works ¦ Water and Environment | QP.E.EX.GEN.GEN.1220 | Submittal | 21 | 2026-11-23 | 2026-12-16
Shop Drawings | External Works | External Fixtures | External Fixtures | External Fixtures | External Fixtures | External Fixtures | Shop Drawings ¦ External Works ¦ External Fixtures | QP.E.EX.GEN.GEN.1260 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | External Works | LPG System | LPG System | LPG System | LPG System | LPG System | Shop Drawings ¦ External Works ¦ LPG System | QP.E.EX.GEN.GEN.1300 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Fit-out | Fit-out | Fit-out | Fit-out | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Fit-out | QP.C.PS.GEN.GEN.2590 | Submittal | 110 | 2026-07-30 | 2026-12-06
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Stage Engineering | Stage Engineering | Stage Engineering | Stage Engineering | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Stage Engineering | QP.C.PS.GEN.GEN.2560 | Submittal | 110 | 2026-12-07 | 2027-04-17
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | AV / Broadcast | AV / Broadcast | AV / Broadcast | AV / Broadcast | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ AV / Broadcast | QP.C.PS.GEN.GEN.1200 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ Technology (ICT) | QP.C.PS.GEN.GEN.1810 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Control Systems | Control Systems | Control Systems | Control Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Control Systems | QP.C.PS.GEN.GEN.1880 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Lighting Systems | Lighting Systems | Lighting Systems | Lighting Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Lighting Systems | QP.C.PS.GEN.GEN.1850 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Conveying System Finishes | QP.C.PS.GEN.GEN.2120 | Submittal | 150 | 2027-06-07 | 2027-11-29
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | HVAC System | HVAC System | HVAC System | HVAC System | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ HVAC System | QP.C.PS.GEN.GEN.2100 | Submittal | 90 | 2027-11-01 | 2028-02-13
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | ID Finishes | ID Finishes | ID Finishes | ID Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ ID Finishes | QP.C.PS.GEN.GEN.1930 | Submittal | 90 | 2027-07-18 | 2027-10-31
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Water Features | QP.C.PS.GEN.GEN.1960 | Submittal | 120 | 2027-02-16 | 2027-07-13
Shop Drawings | Provisional Sums | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | Shop Drawings ¦ Provisional Sums ¦ PS5 - Signage and Wayfinding | QP.C.PS.GEN.GEN.2140 | Submittal | 60 | 2028-07-29 | 2028-10-07
Shop Drawings | Provisional Sums | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | Shop Drawings ¦ Provisional Sums ¦ PS6 - Soft Landscaping | QP.C.PS.GEN.GEN.2180 | Submittal | 160 | 2027-08-30 | 2028-03-08
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Concrete Superstructure | QP.C.PS.GEN.GEN.2360 | Submittal | 30 | 2028-06-08 | 2028-07-12
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Foundation | Foundation | Foundation | Foundation | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Foundation | QP.C.PS.GEN.GEN.2260 | Submittal | 30 | 2028-05-01 | 2028-06-07
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Landscape | Landscape | Landscape | Landscape | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Landscape | QP.C.PS.GEN.GEN.2320 | Submittal | 30 | 2028-07-31 | 2028-09-03
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Promenade Bridge MEP | QP.C.PS.GEN.GEN.2340 | Submittal | 30 | 2028-06-26 | 2028-07-30
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Technology (ICT) | QP.C.PS.GEN.GEN.2400 | Submittal | 150 | 2027-04-11 | 2027-10-07
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Traffic & Car Parking | QP.C.PS.GEN.GEN.2500 | Submittal | 150 | 2027-07-12 | 2028-01-03

## Picklists (hidden)
| #VALUE! |  | Numbering System Document - Metadata Mapping
DOCUMENT NUMBERING DROPDOWN ATTRIBUTES | [18 empty] | QIC GENERAL DROPDOWN ATTRIBUTES
FIELD 01 - PROJECT CODE |  | FIELD 02 - ORIGINATOR |  | FIELD 03 - CONTRACT REFERENCE |  | FIELD 04 - DOCUMENT TYPES |  | FIELD 05 - DISCIPLINE |  | FIELD 06 - AREA/ZONE |  | FIELD 07 - VENUE/BUILDING |  | FIELD 08 - SERIAL NUMBER |  |  |  |  | DOCUMENT DETAILS |  |  | SUITABILITY STATUS |  | NAP GENERAL DROPDOWN ATTRIBUTES
Ab. 01 | 1 - Project Name | Ab. 02 | 2 - Originator Name | Ab. 03 | 3 - Contract Reference | Ab. 04 | 4 - Document Type | Ab. 05 | 5 - Discipline | Ab. 06 | 6 - Area/Zone | Ab. 07 | 7 - Venue/Building | Ab. 08A | 8A - Drawing Type | Ab. 08B | 8B - Level | 8C - Sequence Number | Authoring Software | File/Exchange Format | Scope Area | Code | Status | Scale | Classification ID | Classification | Corporate Discipline | Author
QF01012 | Qiddaya Performing Arts Center | NES | Nesma and Partners | C04518 | Contract Number | AGD | Agenda | ACO | Acoustic | 00 | Overall | Z00000 | Overall | 0 | General (General Notes, Abbreviations, Legends, Single Line Diagrams, General Detail) | 00 | Non-Specific ( For Blade ) | 4 Digit Sequence Number For Drawings/Models | Revit | .rvt | Design Management | S0 (WIP) | Initial status or WIP | NTS | FI_60_25 | Drawing | Architectural | Nesma & Partners
[6 empty] | AVV | Agreed Value of Variation | ADM | Administration | 01 | Zone Sheet 1 | CENT01 | Center Block | 1 | Elevations (Vertical View) | B1 | Basement 1 - Parking A +900.50 | 3 Digit Sequence Number For Documents | Civil3D | .nwc | Architecture / LDC | S1 (Shared) | Suitable for Coordination | AS INDICATED | FI_90_75 | Schedule or table | Electrical | JINGGONG
[6 empty] | ASB | As Built | ARC | Architectural | 02 | Zone Sheet 2 | GARD01 | Guard House | 2 | Plans (Overall, Horizontal View, Floor Plan, Ceiling Plan, Site Plan, Loading Plan) | B2 | Basement 2 - Service +893.50 |  | MicrosoftWord | .nwd | Landscape | S2 (Shared) | Suitable for Information | 1:1 | FI_60_53 | Model | Façade | ALUTEC
[6 empty] | AUR | Audit Report | ADT | Area Development | 03 | Zone Sheet 3 | BLAD01 | Blade 01 | 3 | Sections (Sectional View, Wall Section, Riser) | B3 | Basement 3 - Promenade +887.750 |  | MicrosoftExcel | .ifc | Interior Design | S3 (Shared) | Suitable for Review and Comment | 1:2 | FI_60_15 | Clash Rendition | Fire & Life Safety | AFCO
[6 empty] | BOQ | Bill of Quantities | ASM | Assets Management | 04 | Zone Sheet 4 | BLAD02 | Blade 02 | 4 | Large-scale Views (Enlarged Details) (Plans, Elevations, Stair Sections, etc) | FL | Foundation level |  | Navisworks | .pdf | Signage & Wayfinding | S4 (Shared) | Suitable for Review and Authorisation | 1:5 | FI_40_10 | Calculations | Interior Design | DOKA
[6 empty] | BEP | BIM Execution Plan | AVL | Audio Visual | 05 | Zone Sheet 5 | BLAD03 | Blade 03 | 5 | Details (Any detail view, such as Wall / Floor / Manhole Detail, etc) | L1 | Lobby Level +905.0 |  | inDesign | .jpg | Public Interaction & Activation | S5 (Shared) | Suitable for Review and Acceptance | 1:10 | FI_90_72 | Report | Infrastructure | RAWABI
[6 empty] | BIM | BIM Model | AUV | Audio/Video | 06 | Zone Sheet 6 | BLAD04 | Blade 04 | 6 | Schedules and Diagrams | L2 | Theater Stalls +913.0 |  | Inviso | .xls | Structure | A1 (Published) | Authorised and Accepted-Concept Design | 1:20 | FI_10_90 | Transmittal | Landscape | FALLPROTEC
[6 empty] | BRF | Brief | BRG | Bridges | 07 | Zone Sheet 7 | BLAD05 | Blade 05 | 7 | Combination of different views | L3 | Stalles Mezz & AD Theater +917.5 |  | JPG | .xer | Geotechnical Engineering | A2 (Published) | Authorised and Accepted-Schematic Design 100% | 1:25 | FI_90_47 | Log | Mechanical | TKE
[6 empty] | BUD | Budget | BRC | Broadcast | 08 | Zone Sheet 8 | MBLAD1 | Mini Blade 01 | 8 | User-Defined (For types that do not fall in other categories) | L4 | First Circle & AD Theater +921.0 |  | Recap | .dwf | Civil Engineering | A3 (Published) | Authorised and Accepted-Detailed Design 100% | 1:50 | FI_80_50 | Method statement | Structural | Subcontractor - Unassigned
[6 empty] | CAL | Calculation | BIM | Building Information Modelling | 09 | Zone Sheet 9 | MBLAD4 | Mini Blade 04 | 9 | 3D Representation (Isometric, Perspectives, Photographes) | L5 | Second Circle & Loft |  | Rhino | .dwg | MEP Engineering | A4 (Published) | Authorised and Accepted-Tender | 1:100 | FI_90_64 | Plan |  | Provisional Sum
[6 empty] | CER | Certificate | BMS | Building Management System | 10 | Zone Sheet 10 | SECE01 | SEC Room |  |  | L6 | SKY Garden +935.85 |  | Sketchup | .bcf | Fire & Life Safety | A5 (Published) | Authorised and Accepted-IFC | 1:150 |  |  |  | NAP PMO
[6 empty] | COR | Change Order | CWC | Chilled Water / Cooling | 11 | Zone Sheet 11 | PARK01 | Parking Building |  |  | L8 | Royal Majlis +948.10M |  | Autocad | .3ds | Pitch Design & Sports Playing Surfaces | A6 (Published) | Authorised and Accepted-Construction (Shop Drawing) | 1:200 |  |  |  | Sana Al-Jazerah
[6 empty] | CRA | Change Request Authorization | CIV | Civil | 12 | Zone Sheet 12 |  |  |  |  | M1 | Mez Upper Lobby +909.0 |  | ArcGIS | .skp | Specialist Lighting (Services and Systems) | A7 (Published) | Authorised and Accepted-As Built | 1:250
[6 empty] | CDT | Clash Detection Report | CPM | Contracts & Procurement | 13 | Zone Sheet 13 |  |  |  |  | M2 | Mez Loft MEP +931.10 |  |  | .docx | Acoustics | A8(Published) | Authorised and Accepted-In Use | 1:300
[6 empty] | CLM | Claim | CIN | Controls & Instrumentation | 14 | Zone Sheet 14 |  |  |  |  | RL | Roof Level |  |  | .rvt,.nwd,.ifc | AV / Broadcast |  |  | 1:350
[6 empty] | CIN | Client Instruction | CRE | Creative Designer | 15 | Zone Sheet 15 |  |  |  |  | ZZ | Overall |  |  | .nwc,.nwd,.ifc | Security |  |  | 1:500
[6 empty] | CRS | Comments Resolution Sheet | CDM | Crowd Management | 16 | Zone Sheet 16 | [8 empty] | .dwg,.nwc,.ifc | Vertical Transport
[6 empty] | CON | Contract | CUL | Culvert | 17 | Zone Sheet 17 | [8 empty] | .docx,.pdf | Facade & Roof Envelope
[6 empty] | COS | Cost Estimate | DRN | Drainage | 18 | Zone Sheet 18 | [8 empty] | .xer,.pdf | Crowd Modelling / Pedestrian Flow
[6 empty] | DAB | Dashboard | ELP | Earthing & Lighting Protection | 19 | Zone Sheet 19 | [8 empty] | .xls,.pdf | Sustainability
[6 empty] | DOA | Delegation of Authority | ELE | Electrical | 20 | Zone Sheet 20 | [8 empty] | .msp,.pdf | Accessibility
[6 empty] | DES | Design | ELC | Electrical Containment | 21 | Zone Sheet 21 | [8 empty] | .dwg,.pdf | Architect of Record
[6 empty] | MTX | Distribution Matrix | ENV | Environmental | 22 | Zone Sheet 22 | [8 empty] | .indd | Food & Beverage & Operations
[6 empty] | DSS | Dossier | EQP | Equipment | 23 | Zone Sheet 23 | [8 empty] | .pdf, .indd | Utilities, Roads & Infrastructure
[6 empty] | DRW | Drawing | FAC | Facade | 24 | Zone Sheet 24 | [8 empty] | .rvt,.nwc,.ifc | Traffic & Car Parking
[6 empty] | ENI | Engineer Instruction | FED | Federated | 25 | Zone Sheet 25 | [8 empty] | .gdb | Technology (ICT)
[6 empty] | EXP | Expenses | FIN | Finance | 26 | Zone Sheet 26 | [9 empty] | Sports & Specialist Lighting
[6 empty] | HOC | Handover Certificate | FAE | Fire Alarm & Emergency Lighting | 27 | Zone Sheet 27 | [9 empty] | BMS & Access Control
[6 empty] | IRT | Incident Report | FLS | Fire Life Safety | 28 | Zone Sheet 28 | [9 empty] | Waste Management
[6 empty] | ITP | Inspection & Test Plan | FPR | Fire Protection | [11 empty] | Health & Safety in Design
[6 empty] | INS | Instruction | FFE | Furniture Fixture & Equipment | [11 empty] | Wind
[6 empty] | IAB | Insurance and Bonds | GEN | General
[6 empty] | INV | Invoice | GIS | Geospatial Information System
[6 empty] | LAR | Laydown Area Access Request | GEH | Geotechnical & Hydraulics
[6 empty] | LTR | Letter | GRA | Graphics
[6 empty] | LIC | License | HSE | Health and Safety
[6 empty] | LST | List | EHV | High Voltage
[6 empty] | MAN | Manual | HVC | HVAC
[6 empty] | MPL | Master Plan | ICT | Information & Communication Technology
[6 empty] | MAR | Material Approval Request | INF | Infrastructure
[6 empty] | MIR | Material Inspection Request | INS | Installation
[6 empty] | MST | Method Statement | ITS | Intelligent Transportation System
[6 empty] | MOM | Minutes of Meeting | INT | Interior Design
[6 empty] | MIX | Mix Design | IRR | Irrigation
[6 empty] | MOD | Model | KNL | Kitchen & Laundry
[6 empty] | MRP | Monthly Report | LSE | Landscape
[6 empty] | NOC | No Objection Certificate | ELL | Lighting
[6 empty] | NCR | Non-Conformance Report | LTC | Lighting Control
[6 empty] | NDA | Non-Disclosure Agreement | ELV | Low Voltage
[6 empty] | NTC | Notice | LPG | LPG
[6 empty] | OMM | Operation & Maintenance Manual | MAR | Marine Engineering
[6 empty] | ORC | Organizational Chart | MPL | Master Planning
[6 empty] | OTR | Overtime Request | MEC | Mechanical
[6 empty] | PAP | Payment Application | EMV | Medium Voltage
[6 empty] | PYC | Payment Certificate | MEP | MEPF
[6 empty] | PRM | Permit | NTD | Non-Technical Document
[6 empty] | PAF | Personnel Approval Form | OSE | Operating Supplies and Equipment
[6 empty] | PIV | Photographs, Images & Videos | OTH | Others
[6 empty] | PLN | Plan | PLB | Plumbing
[6 empty] | PLT | Plant | PTW | Potable Water
[6 empty] | PPG | Policy & Procedure | PJC | Project Control
[6 empty] | PQS | Prequalification Submittal | QMS | Quality Management
[6 empty] | PRE | Presentation | RID | Rides
[6 empty] | PRO | Procedure | ERL | Road Lighting
[6 empty] | PEP | Project Execution Plan | RKW | Rockwork
[6 empty] | PRS | Proposal | SEC | Security System
[6 empty] | POR | Purchase Order | SEW | Sewage
[6 empty] | REG | Register | SHW | Show
[6 empty] | REP | Report | SGN | Signage / Wayfinding
[6 empty] | RFC | Request For Change | ESP | Small Power
[6 empty] | RSM | Resume | SSC | Smart City
[6 empty] | SVR | Safety Violation Report | SPL | Specialist Lighting
[6 empty] | SMP | Sample | SWD | Storm Water Drainage
[6 empty] | SCH | Schedule | STR | Structural
[6 empty] | SDW | Shop Drawing | SUR | Surveying / Mapping
[6 empty] | SIN | Site Instruction | SUS | Sustainability
[6 empty] | SOR | Site Observation Report | TEL | Telecommunication
[6 empty] | SPE | Specification | TNC | Testing/Commissioning
[6 empty] | STD | Standard | TFC | Traffic System
[6 empty] | SFA | Statement of Final Account | UTI | Utilities
[6 empty] | STR | Strategy | VNT | Ventilation Ductwork
[6 empty] | TOC | Taking Over Certificate | VTR | Vertical Transportation
[6 empty] | TOR | Task Order | VES | Voice Evacuation
[6 empty] | TEM | Template | WSM | Waste Management
[6 empty] | TDC | Tender Document | WTR | Water
[6 empty] | TRP | Test Report | CTV | CCTV System
[6 empty] | TMS | Time Sheet | ACS | Access Control System
[6 empty] | VOR | Variation Order | EFL | Facade Lighting
[6 empty] | WAR | Warranty / Guarantees | DES | Diesel
[6 empty] | WRP | Weekly Report | SMK | Smoke Ductwork
[6 empty] | WIR | Work Inspection Request | STL | Steel Structure
[6 empty] | RLM | RedLine Mark Drawing | FWR | Formwork
[6 empty] | MDP | Master Information Delivery Plan | ELS | Emergency Lighting system
[6 empty] | TDP | Task Information Delivery Plan | EBW | Electrical Builder Works
[8 empty] | MBW | Mechanical Builder Works
[8 empty] | EBC | Electrical Busway
[8 empty] | WFT | Water Features
[8 empty] | LOG | Logistics