## TIDP_Sheet
TASK INFORMATION DELIVERY PLAN (TIDP)
CLIENT | Qiddiya | #VALUE!
PROJECT | Qiddiya Performing Arts Center (QPAC)
ORGANISATION | Nesma & Partners
DISCIPLINE | Structural
APPROVER | BSBG
DATE CREATED
DATE LAST UPDATED
REVISION NUMBER | 00
DOCUMENT REFERENCE | QF01012-NES-C04518-TDP-STR-00-000000-000001
This document shall be populated and kept up-to-date by the task team | [10 empty] | REFER TO THE FILE NAMING CONVENTION IN THE BIM EXECUTION PLAN | [10 empty] | DATA EXCHANGE #01 | [5 empty] | DATA EXCHANGE #02
[11 empty] | DOC REFERENCE GENERATOR | [10 empty] | STAGE: | CONSTRUCTION |  |  |  |  | STAGE: | HAND OVER
[22 empty] | PROGRAMME REF: | [5 empty] | PROGRAMME REF:
[5 empty] | EXCHANGE FORMATS | [5 empty] | FIELD 01 | FIELD 02 | FIELD 03 | FIELD 04 | FIELD 05 | FIELD 06 | FIELD 07 | FIELD 08 |  |  |  |  | LEVEL OF INFORMATION NEED | [5 empty] | LEVEL OF INFORMATION NEED
DOCUMENT NUMBER | DOCUMENT TITLE | EXTRACTED FROM MODEL | SCOPE AREA | AUTHORING SOFTWARE | EXCHANGE FORMAT | SCALE | DELIVERY MILESTONE | PACKAGE NAME | ACTIVITY ID | CLASSIFICATION CODE | PROJECT | ORIGINATOR | CONTRACT | DOCUMENT TYPE | DISCIPLINE | AREA/ZONE | VENUE/BUILDING | DRAWING TYPE | LEVEL | SEQUENCE NUMBER | CORPORATE DISCIPLINE | 01-AUTHOR | 01-GEOMETRICAL | 01-NON GEOMETRICAL | 01-DURATION (DAYS) | 01-PREDECESSOR | 01-EXCHANGE DATE | 02-AUTHOR | 02-GEOMETRICAL | 02-NON GEOMETRICAL | 02-DURATION (DAYS) | 02-PREDECESSOR | 02-EXCHANGE DATE
QF01012-NES-C04518-MOD-STR-00-CENT01-0000001 | Central Building Structural Model |  | Structure | Revit | .rvt,.nwc,.ifc | NTS |  |  |  | FI_60_53 | QF01012 | NES | C04518 | MOD | STR | 00 | CENT01 | 0 | 00 | 0001 | Structural | Nesma & Partners
QF01012-NES-C04518-MOD-STR-00-BLAD01-0000001 | Blade 1 Structural Model |  | Structure | Revit | .rvt,.nwc,.ifc | NTS |  |  |  | FI_60_53 | QF01012 | NES | C04518 | MOD | STR | 00 | BLAD01 | 0 | 00 | 0001 | Structural | Nesma & Partners
QF01012-NES-C04518-MOD-STR-00-BLAD02-0000001 | Blade 2 Structural Model |  | Structure | Revit | .rvt,.nwc,.ifc | NTS |  |  |  | FI_60_53 | QF01012 | NES | C04518 | MOD | STR | 00 | BLAD02 | 0 | 00 | 0001 | Structural | Nesma & Partners
QF01012-NES-C04518-MOD-STR-00-BLAD03-0000001 | Blade 3 Structural Model |  | Structure | Revit | .rvt,.nwc,.ifc | NTS |  |  |  | FI_60_53 | QF01012 | NES | C04518 | MOD | STR | 00 | BLAD03 | 0 | 00 | 0001 | Structural | Nesma & Partners
QF01012-NES-C04518-MOD-STR-00-BLAD04-0000001 | Blade 4 Structural Model |  | Structure | Revit | .rvt,.nwc,.ifc | NTS |  |  |  | FI_60_53 | QF01012 | NES | C04518 | MOD | STR | 00 | BLAD04 | 0 | 00 | 0001 | Structural | Nesma & Partners
QF01012-NES-C04518-MOD-STR-00-BLAD05-0000001 | Blade 5 Structural Model |  | Structure | Revit | .rvt,.nwc,.ifc | NTS |  |  |  | FI_60_53 | QF01012 | NES | C04518 | MOD | STR | 00 | BLAD05 | 0 | 00 | 0001 | Structural | Nesma & Partners
QF01012-NES-C04518-MOD-STR-00-PARK01-0000001 | Parking Structural Model |  | Structure | Revit | .rvt,.nwc,.ifc | NTS |  |  |  | FI_60_53 | QF01012 | NES | C04518 | MOD | STR | 00 | PARK01 | 0 | 00 | 0001 | Structural | Nesma & Partners
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0101 | Parking Foundation Plan Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation GA | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0101 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0102 | Parking Foundation Plan Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation GA | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0102 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0103 | Parking Foundation Plan Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation GA | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0103 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-2FL0104 | Parking Foundation Plan Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation GA | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | FL | 0104 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0105 | Parking Foundation Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation GA | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0105 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0106 | Parking Foundation Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation GA | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0106 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0107 | Parking Foundation Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation GA | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0107 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-3FL0108 | Parking Foundation Sections and Details Sheet 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 3 | FL | 0108 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0201 | Parking Foundation Column & axes Part 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Column & axes @ FL Level | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0201 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0202 | Parking Foundation Column & axes Part 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Column & axes @ FL Level | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0202 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0203 | Parking Foundation Column & axes Part 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Column & axes @ FL Level | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0203 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2FL0204 | Parking Foundation Column & axes Part 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Column & axes @ FL Level | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | FL | 0204 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0301 | Parking-FDN- BOTTOM REINFORCEMENT B1 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0301 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0302 | Parking-FDN- BOTTOM REINFORCEMENT B2 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0302 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0303 | Parking-FDN- TOP REINFORCEMENT T1 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0303 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0304 | Parking-FDN- TOP REINFORCEMENT T2 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0304 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0305 | Parking-FDN-BOTTOM RFT ADDITIONAIL B3 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0305 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0306 | Parking-FDN-BOTTOM RFT ADDITIONAIL B4 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0306 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0307 | Parking-FDN-TOP RFT ADDITIONAIL T3 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0307 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0308 | Parking-FDN-TOP RFT ADDITIONAIL T4 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0308 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0309 | Parking-FDN-shear link RFT Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0309 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-2FL0310 | Parking-FDN-Side bar RFT Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | FL | 0310 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0311 | Parking-FDN- BOTTOM REINFORCEMENT B1 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0311 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0312 | Parking-FDN- BOTTOM REINFORCEMENT B2 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0312 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0313 | Parking-FDN- TOP REINFORCEMENT T1 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0313 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0314 | Parking-FDN- TOP REINFORCEMENT T2 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0314 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0315 | Parking-FDN-BOTTOM RFT ADDITIONAIL B3 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0315 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0316 | Parking-FDN-BOTTOM RFT ADDITIONAIL B4 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0316 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0317 | Parking-FDN-TOP RFT ADDITIONAIL T3 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0317 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0318 | Parking-FDN-TOP RFT ADDITIONAIL T4 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0318 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0319 | Parking-FDN-shear link RFT Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0319 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-2FL0320 | Parking-FDN-Side bar RFT Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | FL | 0320 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0321 | Parking-FDN- BOTTOM REINFORCEMENT B1 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0321 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0322 | Parking-FDN- BOTTOM REINFORCEMENT B2 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0322 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0323 | Parking-FDN- TOP REINFORCEMENT T1 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0323 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0324 | Parking-FDN- TOP REINFORCEMENT T2 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0324 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0325 | Parking-FDN-BOTTOM RFT ADDITIONAIL B3 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0325 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0326 | Parking-FDN-BOTTOM RFT ADDITIONAIL B4 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0326 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0327 | Parking-FDN-TOP RFT ADDITIONAIL T3 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0327 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0328 | Parking-FDN-TOP RFT ADDITIONAIL T4 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0328 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0329 | Parking-FDN-shear link RFT Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0329 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-2FL0330 | Parking-FDN-Side bar RFT Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | FL | 0330 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-2FL0331 | Parking-FDN- BOTTOM REINFORCEMENT B1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | FL | 0331 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-2FL0332 | Parking-FDN- BOTTOM REINFORCEMENT B2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | FL | 0332 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-2FL0333 | Parking-FDN- TOP REINFORCEMENT T1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | FL | 0333 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-2FL0334 | Parking-FDN- TOP REINFORCEMENT T2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | FL | 0334 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-2FL0335 | Parking-FDN-BOTTOM RFT ADDITIONAIL B3 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | FL | 0335 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-2FL0336 | Parking-FDN-BOTTOM RFT ADDITIONAIL B4 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | FL | 0336 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-2FL0337 | Parking-FDN-TOP RFT ADDITIONAIL T3 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | FL | 0337 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-2FL0338 | Parking-FDN-TOP RFT ADDITIONAIL T4 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | FL | 0338 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-2FL0339 | Parking-FDN-shear link RFT Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | FL | 0339 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-3FL0340 | Parking-FDN-Side bar RFT Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 3 | FL | 0340 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0341 | Parking Foundation Sections and Reinforcement Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0341 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0342 | Parking Foundation Sections and Reinforcement Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0342 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0343 | Parking Foundation Sections and Reinforcement Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0343 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0344 | Parking Foundation Sections and Reinforcement Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0344 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0345 | Parking Foundation Sections and Reinforcement Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0345 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0346 | Parking Foundation Sections and Reinforcement Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0346 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-3FL0347 | Parking Foundation Sections and Reinforcement Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 3 | FL | 0347 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-08-PARK01-3FL0348 | Parking Foundation Sections and Reinforcement Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 3 | FL | 0348 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0349 | Parking Foundation BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0349 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0350 | Parking Foundation BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0350 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0351 | Parking Foundation BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0351 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0352 | Parking Foundation BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0352 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0353 | Parking Foundation BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0353 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0354 | Parking Foundation BBS Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0354 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0355 | Parking Foundation BBS Sheet 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0355 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0356 | Parking Foundation BBS Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0356 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0357 | Parking Foundation BBS Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0357 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0358 | Parking Foundation BBS Sheet 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0358 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0359 | Parking Foundation BBS Sheet 11 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0359 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0360 | Parking Foundation BBS Sheet 12 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0360 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0361 | Parking Foundation BBS Sheet 13 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0361 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0362 | Parking Foundation BBS Sheet 14 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Foundation RFT | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0362 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0401 | Parking Tie Beams Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0401 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0402 | Parking Tie Beams Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0402 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0403 | Parking Tie Beams Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0403 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0404 | Parking Tie Beams Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0404 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0405 | Parking Tie Beams Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0405 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0406 | Parking Tie Beams Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0406 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0407 | Parking Tie Beams Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0407 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0408 | Parking Tie Beams Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0408 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0409 | Parking Tie Beams Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0409 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0410 | Parking Tie Beams Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0410 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-13-PARK01-3FL0411 | Parking Tie Beams Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | FL | 0411 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0412 | Parking Tie Beams Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0412 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0413 | Parking Tie Beams Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0413 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0414 | Parking Tie Beams Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0414 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0415 | Parking Tie Beams Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0415 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0416 | Parking Tie Beams Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0416 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0417 | Parking Tie Beams Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0417 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0418 | Parking Tie Beams Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0418 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0419 | Parking Tie Beams Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0419 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0420 | Parking Tie Beams Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0420 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0421 | Parking Tie Beams Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0421 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-14-PARK01-3FL0422 | Parking Tie Beams Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | FL | 0422 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0423 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0423 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0424 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0424 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0425 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0425 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0426 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0426 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0427 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0427 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0428 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0428 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0429 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0429 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0430 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0430 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0431 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0431 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0432 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0432 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0433 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0433 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-15-PARK01-3FL0434 | Parking Tie Beams Sections and Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | FL | 0434 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0435 | Parking Tie Beams BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0435 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-01-PARK01-6FL0436 | Parking Tie Beams BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 01 | PARK01 | 6 | FL | 0436 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-02-PARK01-6FL0437 | Parking Tie Beams BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 02 | PARK01 | 6 | FL | 0437 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-03-PARK01-6FL0438 | Parking Tie Beams BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 03 | PARK01 | 6 | FL | 0438 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-04-PARK01-6FL0439 | Parking Tie Beams BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 04 | PARK01 | 6 | FL | 0439 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-05-PARK01-6FL0440 | Parking Tie Beams BBS Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 05 | PARK01 | 6 | FL | 0440 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-06-PARK01-6FL0441 | Parking Tie Beams BBS Sheet 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 06 | PARK01 | 6 | FL | 0441 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-07-PARK01-6FL0442 | Parking Tie Beams BBS Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Tie Beams @ foundation level | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 07 | PARK01 | 6 | FL | 0442 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0501 | Parking-FDN-Column Starter bars Detail 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0501 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0502 | Parking-FDN-Column Starter bars Detail 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0502 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0503 | Parking-FDN-Column Starter bars Detail 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0503 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0504 | Parking-FDN-Column Starter bars Detail 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0504 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0505 | Parking-FDN-Column Starter bars Detail 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0505 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0506 | Parking-FDN-Column Starter bars Detail 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0506 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0507 | Parking-FDN-Column Starter Bars BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Column Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0507 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0508 | Parking-FDN-Column Starter Bars BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Column Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0508 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0509 | Parking-FDN-Column Starter Bars BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Column Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0509 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0601 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0601 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0602 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0602 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0603 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0603 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0604 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 04 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0604 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0605 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 05 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0605 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0606 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 06 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0606 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0607 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 07 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0607 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0608 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 08 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0608 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0609 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 09 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0609 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0610 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 10 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0610 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0611 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 11 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0611 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0612 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 12 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0612 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-4FL0613 | Parking-FDN-Retaining Walls Starter Bars Enlarged Plan RFT Detail 13 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 4 | FL | 0613 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0614 | Parking-FDN-Retaining Walls Starter Bars sections Details sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0614 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0615 | Parking-FDN-Retaining Walls Starter Bars sections Details sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0615 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0616 | Parking-FDN-Retaining Walls Starter Bars sections Details sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0616 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0617 | Parking-FDN-Retaining Walls Starter Bars sections Details sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0617 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0618 | Parking-FDN-Retaining Walls Starter Bars BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0618 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0619 | Parking-FDN-Retaining Walls Starter Bars BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0619 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0620 | Parking-FDN-Retaining Walls Starter Bars BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0620 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0621 | Parking-FDN-Retaining Walls Starter Bars BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0621 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0622 | Parking-FDN-Retaining Walls Starter Bars BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0622 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0623 | Parking-FDN-Retaining Walls Starter Bars BBS Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW Starter Bars | QP.E.CV.PAR.GEN.1020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0623 | Structural | Nesma & Partners |  |  |  |  | 2027-06-03
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0701 | Parking-B1-Column RFT Elevation Detail1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0701 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0702 | Parking-B1-Column RFT Elevation Detail2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0702 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0703 | Parking-B1-Column RFT Elevation Detail3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0703 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0704 | Parking-B1-Column RFT Elevation Detail4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0704 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0705 | Parking-B1-Column RFT Elevation Detail5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0705 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0706 | Parking-B1-Column RFT Elevation Detail6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0706 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0707 | Parking-B1-Column RFT Elevation Detail7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0707 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0708 | Parking-B1-Column RFT Elevation Detail8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0708 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0709 | Parking-B1-Column RFT Elevation Detail9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0709 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0710 | Parking-B1-Column RFT Elevation Detail10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0710 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0711 | Parking-B1-Column RFT Elevation Detail11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0711 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0712 | Parking-B1-Column RFT Elevation Detail12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0712 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0713 | Parking-B1-Column RFT Elevation Detail13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0713 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0714 | Parking-B1-Column RFT Elevation Detail14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0714 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0715 | Parking-B1-Column RFT Elevation Detail15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0715 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0716 | Parking-B1-Column RFT Elevation Detail16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0716 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0717 | Parking-B1-Column RFT Elevation Detail17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0717 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0718 | Parking-B1-Column RFT Elevation Detail18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0718 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0719 | Parking-B1-Column RFT Elevation Detail19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0719 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0720 | Parking-B1-Column RFT Elevation Detail20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0720 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0721 | Parking-B1-Column RFT Elevation Detail21 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0721 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0722 | Parking-B1-Column RFT Elevation Detail22 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0722 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0723 | Parking-B1-Column RFT Elevation BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0723 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0724 | Parking-B1-Column RFT Elevation BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0724 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0725 | Parking-B1-Column RFT Elevation BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0725 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0726 | Parking-B1-Column RFT Elevation BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0726 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0727 | Parking-B1-Column RFT Elevation BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0727 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0728 | Parking-B1-Column RFT Elevation BBS Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Column RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0728 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0801 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0801 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0802 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0802 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0803 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0803 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0804 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0804 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0805 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0805 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0806 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0806 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0807 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0807 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0808 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0808 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0809 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0809 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0810 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0810 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0811 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0811 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0812 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0812 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0813 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0813 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0814 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0814 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0815 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0815 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0816 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0816 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0817 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0817 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0818 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0818 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0819 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0819 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0820 | Parking-FDN-Retaining Walls Elevation GA From FL To L1 - Detail 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0820 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0821 | Parking-FDN-Retaining Walls GA sections Details Detail 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0821 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0822 | Parking-FDN-Retaining Walls GA sections Details Detail 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0822 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0823 | Parking-FDN-Retaining Walls GA sections Details Detail 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0823 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0824 | Parking-FDN-Retaining Walls GA sections Details Detail 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0824 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0825 | Parking-FDN-Retaining Walls GA sections Details Detail 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW GA Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0825 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0901 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0901 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0902 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0902 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0903 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0903 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0904 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0904 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0905 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0905 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0906 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0906 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0907 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0907 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0908 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0908 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0909 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0909 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0910 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0910 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0911 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0911 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0912 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0912 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0913 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0913 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0914 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0914 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0915 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0915 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0916 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0916 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0917 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0917 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0918 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0918 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0919 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0919 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0920 | Parking-FDN-Retaining Walls RFT From FL To L1 - Detail 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0920 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0921 | Parking-FDN-Retaining Walls RFT sections Details Detail 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0921 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0922 | Parking-FDN-Retaining Walls RFT sections Details Detail 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0922 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0923 | Parking-FDN-Retaining Walls RFT sections Details Detail 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0923 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0924 | Parking-FDN-Retaining Walls RFT sections Details Detail 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0924 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3FL0925 | Parking-FDN-Retaining Walls RFT sections Details Detail 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | FL | 0925 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0926 | Parking-FDN-Retaining Walls RFT BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0926 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0927 | Parking-FDN-Retaining Walls RFT BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0927 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0928 | Parking-FDN-Retaining Walls RFT BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0928 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0929 | Parking-FDN-Retaining Walls RFT BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0929 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0930 | Parking-FDN-Retaining Walls RFT BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0930 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6FL0931 | Parking-FDN-Retaining Walls RFT BBS Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking Walls & RW RFT Elevation | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | FL | 0931 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2B11001 | Parking-B1- SOG GA Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | B1 | 1001 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2B11002 | Parking-B1- SOG GA Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | B1 | 1002 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2B11003 | Parking-B1- SOG GA Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | B1 | 1003 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2B11004 | Parking-B1- SOG GA Sheet 08 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | B1 | 1004 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3B11005 | Parking SOG Details -1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking SOG GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | B1 | 1005 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2B11101 | Parking-B1- BOTTOM REINFORCEMENT B1 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | B1 | 1101 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2B11102 | Parking-B1- BOTTOM REINFORCEMENT B2 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | B1 | 1102 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2B11103 | Parking-B1- TOP REINFORCEMENT T1 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | B1 | 1103 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2B11104 | Parking-B1- TOP REINFORCEMENT T2 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | B1 | 1104 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-3B11105 | Parking Section Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | B1 | 1105 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2B11106 | Parking-B1- BOTTOM REINFORCEMENT B1 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | B1 | 1106 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2B11107 | Parking-B1- BOTTOM REINFORCEMENT B2 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | B1 | 1107 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2B11108 | Parking-B1- TOP REINFORCEMENT T1 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | B1 | 1108 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2B11109 | Parking-B1- TOP REINFORCEMENT T2 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | B1 | 1109 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-3B11110 | Parking Section Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | B1 | 1110 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2B11111 | Parking-B1- BOTTOM REINFORCEMENT B1 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | B1 | 1111 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2B11112 | Parking-B1- BOTTOM REINFORCEMENT B2 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | B1 | 1112 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2B11113 | Parking-B1- TOP REINFORCEMENT T1 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | B1 | 1113 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2B11114 | Parking-B1- TOP REINFORCEMENT T2 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | B1 | 1114 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-3B11115 | Parking Section Details Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | B1 | 1115 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2B11116 | Parking-B1- BOTTOM REINFORCEMENT B1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | B1 | 1116 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2B11117 | Parking-B1- BOTTOM REINFORCEMENT B2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | B1 | 1117 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2B11118 | Parking-B1- TOP REINFORCEMENT T1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | B1 | 1118 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2B11119 | Parking-B1- TOP REINFORCEMENT T2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | B1 | 1119 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-3B11120 | Section Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 3 | B1 | 1120 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-6B11121 | Parking-B1-SOG BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 6 | B1 | 1121 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-6B11122 | Parking-B1-SOG BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 6 | B1 | 1122 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-6B11123 | Parking-B1-SOG BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 6 | B1 | 1123 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-6B11124 | Parking-B1-SOG BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 6 | B1 | 1124 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-6B11125 | Parking-B1-SOG BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 6 | B1 | 1125 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-6B11126 | Parking-B1-SOG BBS Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-15 | Parking SOG RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 6 | B1 | 1126 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2L11201 | Parking-L1 - GA Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking First Floor GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | L1 | 1201 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2L11202 | Parking-L1- GA Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking First Floor GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | L1 | 1202 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2L11203 | Parking-L1- GA Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking First Floor GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | L1 | 1203 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2L11204 | Parking-L1- GA Sheet 08 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking First Floor GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | L1 | 1204 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11205 | Parking-L1-Section Details |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking First Floor GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1205 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11206 | Parking-L1-Section Details |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking First Floor GA | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1206 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2L11301 | Parking-L1- BOTTOM REINFORCEMENT B1 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | L1 | 1301 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2L11302 | Parking-L1- BOTTOM REINFORCEMENT B2 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | L1 | 1302 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2L11303 | Parking-L1- TOP REINFORCEMENT T1 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | L1 | 1303 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2L11304 | Parking-L1- TOP REINFORCEMENT T2 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | L1 | 1304 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2L11305 | Parking-L1-BOTTOM RFT ADDITIONAIL B3 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | L1 | 1305 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2L11306 | Parking-L1-BOTTOM RFT ADDITIONAIL B4 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | L1 | 1306 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2L11307 | Parking-L1-TOP RFT ADDITIONAIL T3 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | L1 | 1307 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2L11308 | Parking-L1-TOP RFT ADDITIONAIL T4 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | L1 | 1308 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-2L11309 | Parking-L1-shear link RFT Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 2 | L1 | 1309 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-13-PARK01-3L11310 | Parking-L1-SECTION DETAIL Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 13 | PARK01 | 3 | L1 | 1310 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2L11311 | Parking-L1- BOTTOM REINFORCEMENT B1 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | L1 | 1311 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2L11312 | Parking-L1- BOTTOM REINFORCEMENT B2 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | L1 | 1312 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2L11313 | Parking-L1- TOP REINFORCEMENT T1 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | L1 | 1313 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2L11314 | Parking-L1- TOP REINFORCEMENT T2 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | L1 | 1314 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2L11315 | Parking-L1-BOTTOM RFT ADDITIONAIL B3 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | L1 | 1315 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2L11316 | Parking-L1-BOTTOM RFT ADDITIONAIL B4 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | L1 | 1316 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2L11317 | Parking-L1-TOP RFT ADDITIONAIL T3 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | L1 | 1317 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2L11318 | Parking-L1-TOP RFT ADDITIONAIL T4 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | L1 | 1318 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-2L11319 | Parking-L1-shear link RFT Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 2 | L1 | 1319 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-14-PARK01-3L11320 | Parking-L1-SECTION DETAIL Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 14 | PARK01 | 3 | L1 | 1320 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2L11321 | Parking-L1- BOTTOM REINFORCEMENT B1 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | L1 | 1321 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2L11322 | Parking-L1- BOTTOM REINFORCEMENT B2 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | L1 | 1322 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2L11323 | Parking-L1- TOP REINFORCEMENT T1 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | L1 | 1323 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2L11324 | Parking-L1- TOP REINFORCEMENT T2 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | L1 | 1324 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2L11325 | Parking-L1-BOTTOM RFT ADDITIONAIL B3 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | L1 | 1325 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2L11326 | Parking-L1-BOTTOM RFT ADDITIONAIL B4 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | L1 | 1326 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2L11327 | Parking-L1-TOP RFT ADDITIONAIL T3 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | L1 | 1327 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2L11328 | Parking-L1-TOP RFT ADDITIONAIL T4 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | L1 | 1328 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-2L11329 | Parking-L1-shear link RFT Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 2 | L1 | 1329 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-15-PARK01-3L11330 | Parking-L1-SECTION DETAIL Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 15 | PARK01 | 3 | L1 | 1330 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2L11331 | Parking-L1- BOTTOM REINFORCEMENT B1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | L1 | 1331 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2L11332 | Parking-L1- BOTTOM REINFORCEMENT B2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | L1 | 1332 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2L11333 | Parking-L1- TOP REINFORCEMENT T1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | L1 | 1333 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2L11334 | Parking-L1- TOP REINFORCEMENT T2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | L1 | 1334 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2L11335 | Parking-L1-BOTTOM RFT ADDITIONAIL B3 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | L1 | 1335 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2L11336 | Parking-L1-BOTTOM RFT ADDITIONAIL B4 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | L1 | 1336 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2L11337 | Parking-L1-TOP RFT ADDITIONAIL T3 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | L1 | 1337 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-2L11338 | Parking-L1-TOP RFT ADDITIONAIL T4 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 2 | L1 | 1338 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-3L11339 | Parking-L1-shear link RFT Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 3 | L1 | 1339 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-08-PARK01-3L11340 | Parking-L1-SECTION DETAIL Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | PARK01 | 3 | L1 | 1340 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11341 | Parking-L1 - Slab RFT BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1341 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11342 | Parking-L1 - Slab RFT BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1342 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11343 | Parking-L1 - Slab RFT BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1343 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11344 | Parking-L1 - Slab RFT BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1344 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11345 | Parking-L1 - Slab RFT BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1345 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11346 | Parking-L1 - Slab RFT BBS Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1346 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11347 | Parking-L1 - Slab RFT BBS Sheet 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1347 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11348 | Parking-L1 - Slab RFT BBS Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1348 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11349 | Parking-L1 - Slab RFT BBS Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1349 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11350 | Parking-L1 - Slab RFT BBS Sheet 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1350 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11351 | Parking-L1 - Slab RFT BBS Sheet 11 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1351 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11352 | Parking-L1 - Slab RFT BBS Sheet 12 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1- RFT | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1352 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11401 | Parking L1-Beams Reinforcement Detail 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1401 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11402 | Parking-L1-Beams Reinforcement Detail 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1402 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11403 | Parking-L1-Beams Reinforcement Detail 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1403 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11404 | Parking-L1-Beams Reinforcement Detail 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1404 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11405 | Parking-L1-Beams Reinforcement Detail 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1405 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11406 | Parking-L1-Beams Reinforcement Detail 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1406 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11407 | Parking-L1-Beams Reinforcement Detail 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1407 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11408 | Parking-L1-Beams Reinforcement Detail 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1408 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11409 | Parking-L1-Beams Reinforcement Detail 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1409 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11410 | Parking-L1-Beams Reinforcement Detail 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1410 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11411 | Parking-L1-Beams Reinforcement Detail 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1411 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11412 | Parking-L1-Beams Reinforcement Detail 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1412 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11413 | Parking-L1-Beams Reinforcement Detail 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1413 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11414 | Parking-L1-Beams Reinforcement Detail 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1414 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11415 | Parking-L1-Beams Reinforcement Detail 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1415 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11416 | Parking-L1-Beams Reinforcement Detail 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1416 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11417 | Parking-L1-Beams Reinforcement Detail 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1417 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11418 | Parking-L1-Beams Reinforcement Detail 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1418 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11419 | Parking-L1-Beams Reinforcement Detail 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1419 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-3L11420 | Parking-L1-Beams Reinforcement Detail 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 3 | L1 | 1420 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11421 | Parking-L1-Beams Reinforcement BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1421 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11422 | Parking-L1-Beams Reinforcement BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1422 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11423 | Parking-L1-Beams Reinforcement BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1423 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11424 | Parking-L1-Beams Reinforcement BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1424 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-PARK01-6L11425 | Parking-L1-Beams Reinforcement BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-29 | Parking Level L1-Beams RFT Detail | QP.E.CV.PAR.GEN.1040 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | PARK01 | 6 | L1 | 1425 | Structural | Nesma & Partners |  |  |  |  | 2027-07-20
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL0100 | Central Block Foundation Over All plan |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 0100 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0101 | Central Block Columns and Walls Plan Sheet 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0101 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0102 | Central Block Columns and Walls Plan Sheet 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0102 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0103 | Central Block Columns and Walls Plan Sheet 5 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0103 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0104 | Central Block Columns and Walls Plan Sheet 6 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0104 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0105 | Central Block Columns and Walls Plan Sheet 8 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0105 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0106 | Central Block Columns and Walls Plan Sheet 9 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0106 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0107 | Central Block Foundation Plan Sheet 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0107 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0108 | Central Block Foundation Plan Sheet 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0108 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0109 | Central Block Foundation Plan Sheet 5 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0109 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0110 | Central Block Foundation Plan Sheet 6 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0110 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0111 | Central Block Foundation Plan Sheet 8 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0111 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0112 | Central Block Foundation Plan Sheet 9 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0112 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0113 | Central Block Foundation Sections and Details Concrete Dim. Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0113 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0114 | Central Block Foundation Sections and Details Concrete Dim. Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0114 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0115 | Central Block Foundation Sections and Details Concrete Dim. Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0115 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0116 | Central Block Foundation Sections and Details Concrete Dim. Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0116 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0117 | Central Block Foundation Sections and Details Concrete Dim. Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0117 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0118 | Central Block Foundation Sections and Details Concrete Dim. Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0118 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0119 | Central Block Foundation Sections and Details Concrete Dim. Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0119 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0120 | Central Block Foundation Sections and Details Concrete Dim. Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0120 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL0113 | AMPHITHEATRE COLUMN AND WALL PLAN SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 0113 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL0114 | AMPHITHEATRE FOUNDATION PLAN SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 0114 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL0121 | Central Block Tower Crane 1-2 GA |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 0121 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL0122 | Central Block Tower Crane Typical RFT |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 0122 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0123 | Central Block Tower Crane Typical BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0123 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0124 | Central Block Foundation RAFT AM-RAFT-01 Details 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0124 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0125 | Central Block Foundation RAFT AM-RAFT-01 Details 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0125 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0126 | Central Block Foundation Sections and Details Concrete Dim. Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0126 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0127 | Central Block Foundation Sections and Details Concrete Dim. Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0127 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0201 | Central Block Foundation Bottom Reinforcement Plan In X Direction Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0201 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0202 | Central Block Foundation Bottom Reinforcement Plan In Y Direction Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0202 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0203 | Central Block Foundation Top Reinforcement Plan In X Direction Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0203 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0204 | Central Block Foundation Top Reinforcement Plan In Y Direction Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0204 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0205 | Central Block Foundation ADD. Bottom Reinforcement Plan In X Direction Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0205 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0206 | Central Block Foundation ADD. Bottom Reinforcement Plan In Y Direction Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0206 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0207 | Central Block Foundation ADD. Top Reinforcement Plan In X Direction Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0207 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0208 | Central Block Foundation ADD. TopReinforcement Plan In Y Direction Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0208 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0209 | Central Block Foundation Side Bars and AAO Reinforcement Plan Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0209 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0210 | Central Block Foundation Shear Reinforcement Plan Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0210 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0211 | Central Block Foundation Bottom Reinforcement Plan In X Direction Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0211 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0212 | Central Block Foundation Bottom Reinforcement Plan In Y Direction Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0212 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0213 | Central Block Foundation Top Reinforcement Plan In X Direction Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0213 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0214 | Central Block Foundation Top Reinforcement Plan In Y Direction Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0214 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0215 | Central Block Foundation ADD. Bottom Reinforcement Plan In X Direction Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0215 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0216 | Central Block Foundation ADD. Bottom Reinforcement Plan In Y Direction Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0216 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0217 | Central Block Foundation ADD. Top Reinforcement Plan In X Direction Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0217 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0218 | Central Block Foundation ADD. TopReinforcement Plan In Y Direction Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0218 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0219 | Central Block Foundation Side Bars and AAO Reinforcement Plan Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0219 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0220 | Central Block Foundation Shear Reinforcement Plan Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0220 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0221 | Central Block Foundation Bottom Reinforcement Plan In X Direction Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0221 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0222 | Central Block Foundation Bottom Reinforcement Plan In Y Direction Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0222 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0223 | Central Block Foundation Top Reinforcement Plan In X Direction Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0223 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0224 | Central Block Foundation Top Reinforcement Plan In Y Direction Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0224 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0225 | Central Block Foundation ADD. Bottom Reinforcement Plan In X Direction Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0225 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0226 | Central Block Foundation ADD. Bottom Reinforcement Plan In Y Direction Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0226 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0227 | Central Block Foundation ADD. Top Reinforcement Plan In X Direction Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0227 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0228 | Central Block Foundation ADD. TopReinforcement Plan In Y Direction Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0228 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0229 | Central Block Foundation Side Bars and AAO Reinforcement Plan Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0229 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0230 | Central Block Foundation Shear Reinforcement Plan Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0230 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0231 | Central Block Foundation Bottom Reinforcement Plan In X Direction Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0231 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0232 | Central Block Foundation Bottom Reinforcement Plan In Y Direction Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0232 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0233 | Central Block Foundation Top Reinforcement Plan In X Direction Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0233 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0234 | Central Block Foundation Top Reinforcement Plan In Y Direction Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0234 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0235 | Central Block Foundation ADD. Bottom Reinforcement Plan In X Direction Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0235 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0236 | Central Block Foundation ADD. Bottom Reinforcement Plan In Y Direction Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0236 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0237 | Central Block Foundation ADD. Top Reinforcement Plan In X Direction Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0237 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0238 | Central Block Foundation ADD. TopReinforcement Plan In Y Direction Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0238 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0239 | Central Block Foundation Side Bars and AAO Reinforcement Plan Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0239 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0240 | Central Block Foundation Shear Reinforcement Plan Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0240 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0241 | Central Block Foundation Bottom Reinforcement Plan In X Direction Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0241 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0242 | Central Block Foundation Bottom Reinforcement Plan In Y Direction Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0242 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0243 | Central Block Foundation Top Reinforcement Plan In X Direction Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0243 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0244 | Central Block Foundation Top Reinforcement Plan In Y Direction Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0244 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0245 | Central Block Foundation ADD. Bottom Reinforcement Plan In X Direction Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0245 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0246 | Central Block Foundation ADD. Bottom Reinforcement Plan In Y Direction Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0246 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0247 | Central Block Foundation ADD. Top Reinforcement Plan In X Direction Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0247 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0248 | Central Block Foundation ADD. TopReinforcement Plan In Y Direction Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0248 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0249 | Central Block Foundation Side Bars and AAO Reinforcement Plan Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0249 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0250 | Central Block Foundation Shear Reinforcement Plan Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0250 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0251 | Central Block Foundation Bottom Reinforcement Plan In X Direction Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0251 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0252 | Central Block Foundation Bottom Reinforcement Plan In Y Direction Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0252 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0253 | Central Block Foundation Top Reinforcement Plan In X Direction Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0253 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0254 | Central Block Foundation Top Reinforcement Plan In Y Direction Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0254 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0255 | Central Block Foundation ADD. Bottom Reinforcement Plan In X Direction Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0255 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0256 | Central Block Foundation ADD. Bottom Reinforcement Plan In Y Direction Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0256 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0257 | Central Block Foundation ADD. Top Reinforcement Plan In X Direction Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0257 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0258 | Central Block Foundation ADD. TopReinforcement Plan In Y Direction Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0258 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0259 | Central Block Foundation Side Bars and AAO Reinforcement Plan Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0259 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0260 | Central Block Foundation Shear Reinforcement Plan Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0260 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0128 | Central Block Amphitheatre Foundation Sections and Details Concrete Dim. Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0128 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0129 | Central Block Amphitheatre Foundation Sections and Details Concrete Dim. Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation GA | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0129 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0261 | Central Block Foundation Sections and Reinforcement Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0261 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0262 | Central Block Foundation Sections and Reinforcement Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0262 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0263 | Central Block Foundation Sections and Reinforcement Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0263 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0264 | Central Block Foundation Sections and Reinforcement Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0264 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0265 | Central Block Foundation Sections and Reinforcement Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0265 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0266 | Central Block Foundation Sections and Reinforcement Details Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0266 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0267 | Central Block Foundation Sections and Reinforcement Details Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0267 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0268 | Central Block Foundation Sections and Reinforcement Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0268 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0280 | CENTRAL BLOCK FOUNDATION SECTIONS AND REINFORCMENT DETAILS SHEET 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0280 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0281 | CENTRAL BLOCK FOUNDATION SECTIONS AND REINFORCMENT DETAILS SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0281 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0282 | CENTRAL BLOCK TANK FOUNDATION BOTTOM REINFORCEMENT PLAN B1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0282 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0283 | CENTRAL BLOCK TANK FOUNDATION BOTTOM REINFORCEMENT PLAN B2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0283 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0284 | CENTRAL BLOCK TANK FOUNDATION TOP REINFORCEMENT PLAN T1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0284 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0285 | CENTRAL BLOCK TANK FOUNDATION TOP REINFORCEMENT PLAN T2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0285 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0286 | CENTRAL BLOCK TANK FOUNDATION BOTTOM REINFORCEMENT PLAN ADD. B1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0286 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0287 | CENTRAL BLOCK TANK FOUNDATION BOTTOM REINFORCEMENT PLAN ADD. B2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0287 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0288 | CENTRAL BLOCK TANK FOUNDATION TOP REINFORCEMENT PLAN ADD. T1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0288 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0289 | CENTRAL BLOCK TANK FOUNDATION TOP REINFORCEMENT PLAN ADD. T2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0289 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0290 | CENTRAL BLOCK TANK FOUNDATION SIDE BAR REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0290 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0291 | CENTRAL BLOCK TANK FOUNDATION SHEAR REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0291 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0292 | CENTRAL BLOCK TANK FOUNDATION REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0292 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0279 | CENTRAL BLOCK FOUNDATION BBS SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0279 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0269 | Central Block Foundation BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0269 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0270 | Central Block Foundation BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0270 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0271 | Central Block Foundation BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0271 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0272 | Central Block Foundation BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0272 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0273 | Central Block Foundation BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0273 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0274 | Central Block Foundation BBS Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0274 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0275 | Central Block Foundation BBS Sheet 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0275 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0276 | Central Block Foundation BBS Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0276 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0277 | Central Block Foundation BBS Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0277 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0278 | Central Block Foundation BBS Sheet 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Foundation RFT | QP.E.CV.MBL.GEN.3020 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0278 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-CENT01-1FL0300 | Central Block Tie Beams - Key plan |  | Structure | Revit | .dwg,.pdf | 1:150 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 1 | FL | 0300 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0301 | Central Block Tie Beams Sections and Reinforcement Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0301 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0302 | Central Block Tie Beams Sections and Reinforcement Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0302 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0303 | Central Block Tie Beams Sections and Reinforcement Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0303 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0304 | Central Block Tie Beams Sections and Reinforcement Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0304 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0305 | Central Block Tie Beams Sections and Reinforcement Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0305 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0306 | Central Block Tie Beams Sections and Reinforcement Details Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0306 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0307 | Central Block Tie Beams Sections and Reinforcement Details Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0307 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0308 | Central Block Tie Beams Sections and Reinforcement Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0308 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0309 | Central Block Tie Beams Sections and Reinforcement Details Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0309 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0310 | Central Block Tie Beams Sections and Reinforcement Details Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0310 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0311 | Central Block Tie Beams Sections and Reinforcement Details Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0311 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0312 | Central Block Tie Beams Sections and Reinforcement Details Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0312 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0313 | Central Block Tie Beams BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0313 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0314 | CENTRAL BLOCK TIE BEAMS BBS SHEET 02 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0314 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL0315 | AMPHITHEATRE - TIE BEAMS KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITEATURE - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 0315 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0316 | AMPHITHEATRE - TIE BEAMS SECTIONS AND REINFORCEMENT DETAILS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITEATURE - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0316 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0317 | AMPHITHEATRE - TIE BEAMS SECTIONS AND REINFORCEMENT DETAILS SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITEATURE - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0317 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0318 | AMPHITHEATRE - TIE BEAMS BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | AMPHITEATURE - Tie Beams RFT | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0318 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2FL0401 | Central Block Columns Starter Bars RFT Plans Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | FL | 0401 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0402 | Central Block Columns Starter Bars RFT Plans Sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0402 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-05-CENT01-2FL0403 | Central Block Columns Starter Bars RFT Plans Sheet 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | FL | 0403 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-06-CENT01-2FL0404 | Central Block Columns Starter Bars RFT Plans Sheet 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | FL | 0404 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-08-CENT01-2FL0405 | Central Block Columns Starter Bars RFT Plans Sheet 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | FL | 0405 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-09-CENT01-2FL0406 | Central Block Columns Starter Bars RFT Plans Sheet 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | FL | 0406 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0407 | Central Block Columns Starter Bars RFT Sections & Details Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0407 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0408 | Central Block Columns Starter Bars RFT Sections & Details Sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0408 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0409 | BLADE 2 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 1 OF 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0409 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0410 | BLADE 2 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 2 OF 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0410 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0411 | BLADE 2 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 3 OF 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0411 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0412 | BLADE 2 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 4 OF 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0412 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0413 | Central Block Columns Starter Bars RFT Sections & Details Sheet 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0413 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0414 | Central Block Columns Starter Bars RFT Sections & Details Sheet 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0414 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0415 | Central Block Columns Starter Bars RFT Sections & Details Sheet 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0415 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0416 | Central Block Columns Starter Bars RFT Sections & Details Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0416 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0417 | Central Block Columns Starter Bars BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0417 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0418 | Central Block Columns Starter Bars BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0418 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0419 | Central Block Columns Starter Bars RFT Sections & Details Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0419 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0420 | Central Block Columns Starter Bars RFT Sections & Details Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0420 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0421 | Central Block Columns Starter Bars RFT Sections & Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0421 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL0500 | Central Block Walls & Cores Starter Bars Key plan |  | Structure | Revit | .dwg,.pdf | 1:300 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 0500 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0501 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0501 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0502 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0502 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0503 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0503 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0504 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0504 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0505 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0505 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0506 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0506 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0507 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0507 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0508 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0508 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0509 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0509 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0510 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0510 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0511 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0511 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0512 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0512 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL0513 | Central Block Walls & Cores Starter Bars Enlarged plan Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 0513 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0514 | Central Block Shear Walls Starter Bars Sections & Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0514 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0515 | Central Block Shear Walls Starter Bars Sections & Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0515 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0516 | Central Block Shear Walls Starter Bars Sections & Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0516 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0517 | Central Block Shear Walls Starter Bars Sections & Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0517 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0518 | Central Block Shear Walls Starter Bars Sections & Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0518 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0519 | Central Block Shear Walls Starter Bars Sections & Details Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0519 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0520 | Central Block Shear Walls Starter Bars Sections & Details Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0520 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0521 | Central Block Shear Walls Starter Bars Sections & Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0521 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0522 | Central Block Shear Walls Starter Bars Sections & Details Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0522 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0523 | Central Block Cores Walls Starter Bars Sections & Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0523 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0524 | Central Block Cores Walls Starter Bars Sections & Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0524 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0525 | Central Block Cores Walls Starter Bars Sections & Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0525 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0526 | Central Block Cores Walls Starter Bars Sections & Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0526 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0527 | Central Block Cores Walls Starter Bars Sections & Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0527 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0528 | Central Block Cores Walls Starter Bars Sections & Details Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0528 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0529 | Central Block Cores Walls Starter Bars Sections & Details Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0529 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0530 | Central Block Cores Walls Starter Bars Sections & Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0530 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0531 | Central Block Cores Walls Starter Bars Sections & Details Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0531 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0532 | Central Block Cores Walls Starter Bars Sections & Details Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0532 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0533 | Central Block Cores Walls Starter Bars Sections & Details Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0533 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0534 | Central Block Cores Walls Starter Bars Sections & Details Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0534 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0535 | Central Block Cores Walls Starter Bars Sections & Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0535 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0536 | Central Block Retaning Walls Starter Bars Sections & Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0536 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0537 | Central Block Retaning Walls Starter Bars Sections & Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0537 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0538 | Central Block Retaning Walls Starter Bars Sections & Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0538 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0539 | Central Block Retaning Walls Starter Bars Sections & Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0539 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0540 | Central Block Retaning Walls Starter Bars Sections & Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0540 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0541 | Central Block Retaning Walls Starter Bars Sections & Details Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0541 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0542 | Central Block Retaining Walls Starter Bars Sections & Details Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0542 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0543 | Central Block Retaning Walls Starter Bars Sections & Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0543 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0544 | Central Block Retaning Walls Starter Bars Sections & Details Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0544 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0545 | Central Block Upstand Starter Bars Sections & Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0545 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0546 | Central Block Upstand Starter Bars Sections & Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0546 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0547 | Central Block Upstand Starter Bars Sections & Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0547 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0548 | Central Block Sum Pit Starter Bars Sections & Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0548 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL0549 | Central Block Tank Starter Bars Sections & Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 0549 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0550 | Central Block Shear Walls Starter Bars BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0550 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0551 | Central Block Retaining Walls Starter Bars BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0551 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0552 | Central Block Retaining Walls Starter Bars BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0552 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0553 | Central Block Retaining Walls Starter Bars BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0553 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0554 | Central Block Upstand Walls Starter Bars BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0554 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0555 | Central Block Cores Starter Bars BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0555 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL0556 | Central Block Cores Starter Bars BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Cores & Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 0556 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-2FL0557 | AMPHITHEATRE-LEVEL B3-STARTER BARS KEY PLANS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | FL | 0557 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-4FL0558 | AMPHITHEATRE-LEVEL B3-CORE WALL STARTER BARS REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 4 | FL | 0558 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-4FL0559 | AMPHITHEATRE-LEVEL B3-CORE WALL STARTER BARS REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 4 | FL | 0559 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-4FL0560 | AMPHITHEATRE-LEVEL B3-CORE WALL STARTER BARS REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 4 | FL | 0560 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-4FL0561 | AMPHITHEATRE-LEVEL B3-CORE WALL STARTER BARS REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 4 | FL | 0561 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-4FL0562 | AMPHITHEATRE-LEVEL B3-CORE WALL STARTER BARS REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 4 | FL | 0562 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-4FL0563 | AMPHITHEATRE-LEVEL B3-CORE WALL STARTER BARS REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 4 | FL | 0563 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-3FL0564 | AMPHITHEATRE-LEVEL B3-COLUMNS STARTER BARS RFT SECTIONS & DETAILS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | FL | 0564 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-3FL0565 | AMPHITHEATRE-LEVEL B3-COLUMNS STARTER BARS RFT SECTIONS & DETAILS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | FL | 0565 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-3FL0566 | AMPHITHEATRE-LEVEL B3-WALL STARTER BARS RFT SECTIONS & DETAILS SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | FL | 0566 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-3FL0567 | AMPHITHEATRE-LEVEL B3-WALL STARTER BARS RFT SECTIONS & DETAILS SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | FL | 0567 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-3FL0568 | AMPHITHEATRE-LEVEL B3-WALL STARTER BARS RFT SECTIONS & DETAILS SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | FL | 0568 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-3FL0569 | AMPHITHEATRE-LEVEL B3-WALL STARTER BARS RFT SECTIONS & DETAILS SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | FL | 0569 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-3FL0570 | AMPHITHEATRE-LEVEL B3-WALL STARTER BARS RFT SECTIONS & DETAILS SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | FL | 0570 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-3FL0571 | AMPHITHEATRE-LEVEL B3-WALL STARTER BARS RFT SECTIONS & DETAILS SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | FL | 0571 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-3FL0572 | AMPHITHEATRE-LEVEL B3-WALL STARTER BARS RFT SECTIONS & DETAILS SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | FL | 0572 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-3FL0573 | AMPHITHEATRE-LEVEL B3-WALL STARTER BARS RFT SECTIONS & DETAILS SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | FL | 0573 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-6FL0574 | AMPHITHEATRE-LEVEL B3-COLUMNS STARTER & TANK WALL STARTER BARS BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 6 | FL | 0574 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-02-CENT01-6FL0575 | AMPHITHEATRE-LEVEL B3-CORE WALL STARTER BARS BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Amphitheater Walls Starter Bars | QP.E.CV.MBL.GEN.3000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 6 | FL | 0575 | Structural | Nesma & Partners |  |  |  |  | 2025-12-14
QF01012-NES-C04518-SDW-STR-01-CENT01-2B30601 | Central Block B3 (SOG) Plan Sheet 1 (1/4) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B3 | 0601 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B30602 | Central Block B3 (SOG) Plan Sheet 2 (2/4) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B3 | 0602 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-05-CENT01-2B30603 | Central Block B3 (SOG) Plan Sheet 5 (3/4) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B3 | 0603 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-11-CENT01-2B30604 | Central Block B3 (SOG) Plan Sheet 11 (4/4) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 11 | CENT01 | 2 | B3 | 0604 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-3B30605 | Central Block B3 (SOG) Sections and Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - B3 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 3 | B3 | 0605 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-3B30606 | Central Block B3 (SOG) Sections and Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - B3 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | B3 | 0606 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-05-CENT01-3B30607 | Central Block B3 (SOG) Sections and Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - B3 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 3 | B3 | 0607 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-11-CENT01-3B30608 | Central Block B3 (SOG) Sections and Details Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - B3 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 11 | CENT01 | 3 | B3 | 0608 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B30609 | Central Block B3 (SOG) BOTTOM REINFORCEMENT B1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B3 | 0609 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B30610 | Central Block B3 (SOG) BOTTOM REINFORCEMENT B2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B3 | 0610 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B30611 | Central Block B3 (SOG) TOP REINFORCEMENT T1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B3 | 0611 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B30612 | Central Block B3 (SOG) TOP REINFORCEMENT T2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B3 | 0612 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B30613 | Central Block B3 (SOG) BOTTOM REINFORCEMENT B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B3 | 0613 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B30614 | Central Block B3 (SOG) BOTTOM REINFORCEMENT B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B3 | 0614 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B30615 | Central Block B3 (SOG) TOP REINFORCEMENT T1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B3 | 0615 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B30616 | Central Block B3 (SOG) TOP REINFORCEMENT T2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B3 | 0616 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B30617 | Central Block B3 (SOG) BOTTOM REINFORCEMENT B1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B3 | 0617 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B30618 | Central Block B3 (SOG) BOTTOM REINFORCEMENT B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B3 | 0618 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-3B30619 | Central Block B3 (SOG) TOP REINFORCEMENT T1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B3 | 0619 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B30620 | Central Block B3 (SOG) TOP REINFORCEMENT T2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B3 | 0620 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-11-CENT01-2B30621 | Central Block B3 (SOG) BOTTOM REINFORCEMENT B1 Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 11 | CENT01 | 2 | B3 | 0621 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-11-CENT01-2B30622 | Central Block B3 (SOG) BOTTOM REINFORCEMENT B2 Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 11 | CENT01 | 2 | B3 | 0622 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-11-CENT01-2B30623 | Central Block B3 (SOG) TOP REINFORCEMENT T1 Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 11 | CENT01 | 2 | B3 | 0623 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-11-CENT01-2B30624 | Central Block B3 (SOG) TOP REINFORCEMENT T2 Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 11 | CENT01 | 2 | B3 | 0624 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-3B30625 | Central Block B3 (SOG) Sections and Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 3 | B3 | 0625 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-3B30626 | Central Block B3 (SOG) Sections and Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 3 | B3 | 0626 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-05-CENT01-3B30627 | Central Block B3 (SOG) Sections and Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 3 | B3 | 0627 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-11-CENT01-3B30628 | Central Block B3 (SOG) Sections and Details Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 11 | CENT01 | 3 | B3 | 0628 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B30629 | Central Block B3 (SOG) RFT BBS - Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B3 | 0629 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B30630 | Central Block B3 (SOG) RFT BBS - Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B3 | 0630 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B30631 | Central Block B3 (SOG) RFT BBS - Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B3 | 0631 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B30632 | Central Block B3 (SOG) RFT BBS - Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B3 | 0632 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B30633 | Central Block B3 (SOG) RFT BBS - Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B3 | 0633 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B30634 | Central Block B3 (SOG) RFT BBS - Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B3 | 0634 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B20701 | CENTRAL BLOCK B2 SERVICE COLUMNS AND WALLS PLAN SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B3 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B2 | 0701 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B20702 | CENTRAL BLOCK B2 SERVICE COLUMNS AND WALLS PLAN SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B2 | 0702 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-05-CENT01-2B20703 | CENTRAL BLOCK B2 SERVICE COLUMNS AND WALLS PLAN SHEET 5 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B2 | 0703 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-06-CENT01-2B20704 | CENTRAL BLOCK B2 SERVICE COLUMNS AND WALLS PLAN SHEET 6 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B2 | 0704 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-08-CENT01-2B20705 | CENTRAL BLOCK B2 SERVICE COLUMNS AND WALLS PLAN SHEET 8 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B2 | 0705 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-09-CENT01-2B20706 | CENTRAL BLOCK B2 SERVICE COLUMNS AND WALLS PLAN SHEET 9 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B2 | 0706 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-4B20707 | CENTRAL BLOCK B2 SERVICE SLAB GA OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B2 | 0707 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B20708 | CENTRAL BLOCK B2 SERVICE SLAB GA PLAN SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B2 | 0708 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B20709 | CENTRAL BLOCK B2 SERVICE SLAB GA PLAN SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B2 | 0709 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-05-CENT01-2B20710 | CENTRAL BLOCK B2 SERVICE SLAB GA PLAN SHEET 5 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B2 | 0710 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-06-CENT01-2B20711 | CENTRAL BLOCK B2 SERVICE SLAB GA PLAN SHEET 6 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B2 | 0711 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-08-CENT01-2B20712 | CENTRAL BLOCK B2 SERVICE SLAB GA PLAN SHEET 8 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 SOG GA | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B2 | 0712 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-09-CENT01-2B20713 | CENTRAL BLOCK B2 SERVICE SLAB GA PLAN SHEET 9 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B2 | 0713 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20714 | CENTRAL BLOCK B2 SERVICE SLAB GA SECTIONS SHEET 1 (1/4) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0714 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20715 | CENTRAL BLOCK B2 SERVICE SLAB GA SECTIONS SHEET 2 (2/4) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0715 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20716 | CENTRAL BLOCK B2 SERVICE SLAB GA SECTIONS SHEET 3 (3/4) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0716 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20717 | CENTRAL BLOCK B2 SERVICE SLAB GA SECTIONS SHEET 4 (4/4) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0717 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B20718 | CENTRAL BLOCK B2 BOTTOM REINFORCEMENT B1 Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B2 | 0718 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B20719 | CENTRAL BLOCK B2 BOTTOM REINFORCEMENT B2 Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B2 | 0719 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B20720 | CENTRAL BLOCK B2 TOP REINFORCEMENT T1 Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B2 | 0720 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B20721 | CENTRAL BLOCK B2 TOP REINFORCEMENT T2 Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B2 | 0721 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B20722 | Central Block B2 ADD. BOTTOM REINFORCEMENT Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B2 | 0722 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B20723 | CENTRAL BLOCK B2 ADD. TOP REINFORCEMENT Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B2 | 0723 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B20724 | CENTRAL BLOCK B2 A.A.O. BOTTOM REINFORCEMENT PLAN Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B2 | 0724 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-01-CENT01-2B20725 | CENTRAL BLOCK B2 A.A.O. TOP REINFORCEMENT PLAN Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B2 | 0725 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B20726 | Central Block B2 BOTTOM REINFORCEMENT B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B2 | 0726 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B20727 | Central Block B2 BOTTOM REINFORCEMENT B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B2 | 0727 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B20728 | Central Block B2 TOP REINFORCEMENT T1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B2 | 0728 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B20729 | Central Block B2 TOP REINFORCEMENT T2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B2 | 0729 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B20730 | Central Block B2 ADD BOTTOM REINFORCEMENT Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B2 | 0730 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-02-CENT01-2B20731 | Central Block B2 ADD TOP REINFORCEMENT Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B2 | 0731 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-05-CENT01-2B20732 | CENTRAL BLOCK B2 SERVICE BOTTOM REINFORCEMENT B1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B2 | 0732 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-05-CENT01-2B20733 | CENTRAL BLOCK B2 SERVICE BOTTOM REINFORCEMENT B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B2 | 0733 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-05-CENT01-2B20734 | CENTRAL BLOCK B2 SERVICE TOP REINFORCEMENT T1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B2 | 0734 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-05-CENT01-2B20735 | CENTRAL BLOCK B2 SERVICE TOP REINFORCEMENT T2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B2 | 0735 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-05-CENT01-2B20736 | CENTRAL BLOCK B2 SERVICE A.A.O. BOTTOM REINFORCEMENT Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B2 | 0736 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-05-CENT01-2B20737 | CENTRAL BLOCK B2 SERVICE A.A.O. TOP REINFORCEMENT Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B2 | 0737 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-06-CENT01-2B20738 | CENTRAL BLOCK B2 SERVICE BOTTOM REINFORCEMENT B1 Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B2 | 0738 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-06-CENT01-2B20739 | CENTRAL BLOCK B2 SERVICE BOTTOM REINFORCEMENT B2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B2 | 0739 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-06-CENT01-2B20740 | CENTRAL BLOCK B2 SERVICE TOP REINFORCEMENT T1 Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B2 | 0740 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-06-CENT01-2B20741 | CENTRAL BLOCK B2 SERVICE TOP REINFORCEMENT T2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B2 | 0741 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-06-CENT01-2B20742 | CENTRAL BLOCK B2 SERVICE A.A.O. BOTTOM REINFORCEMENT Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B2 | 0742 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-06-CENT01-2B20743 | CENTRAL BLOCK B2 SERVICE A.A.O. TOP REINFORCEMENT Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B2 | 0743 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-4B20746 | Central Block B2 – Bottom Reinforcement Plan for B1 & B2 Tank Slabs (Enlarged Plan) |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B2 | 0746 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-4B20747 | Central Block B2 – TOP Reinforcement Plan for T1 & T2 Tank Slabs (Enlarged Plan) |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B2 | 0747 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-4B20748 | Central Block B2 – Add Bottom Reinforcement Plan for B1 & B2 Tank Slabs (Enlarged Plan) |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B2 | 0748 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-4B20749 | Central Block B2 – Add TOP Reinforcement Plan for T1 & T2 Tank Slabs (Enlarged Plan) |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B2 | 0749 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20750 | Central Block B2 - Sections and Details |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0750 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20751 | Central Block B2 -Tank Slabs RFT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0751 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20754 | CENTRAL BLOCK B2 SERVICE SECTIONS AND DETAILS Sheet 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0754 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20755 | Central Block B2 SERVICE Sections and Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0755 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20759 | CENTRAL BLOCK B2 SERVICE RFT BBS - Sheet 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0759 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20760 | Central Block B2 SERVICE RFT BBS - Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0760 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-08-CENT01-2B20761 | CENTRAL BLOCK B2 SERVICE BOTTOM REINFORCEMENT B1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B2 | 0761 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-08-CENT01-2B20762 | CENTRAL BLOCK B2 SERVICE BOTTOM REINFORCEMENT B2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B2 | 0762 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-08-CENT01-2B20763 | CENTRAL BLOCK B2 SERVICE TOP REINFORCEMENT T1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B2 | 0763 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-08-CENT01-2B20764 | CENTRAL BLOCK B2 SERVICE TOP REINFORCEMENT T2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B2 | 0764 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-08-CENT01-2B20765 | CENTRAL BLOCK B2 SERVICE A.A.O. BOTTOM REINFORCEMENT Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B2 | 0765 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-08-CENT01-2B20766 | CENTRAL BLOCK B2 SERVICE A.A.O. TOP REINFORCEMENT Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B2 | 0766 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20767 | CENTRAL BLOCK B2 SERVICE SECTIONS AND DETAILS Sheet 03 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0767 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20768 | CENTRAL BLOCK B2 SERVICE SECTIONS AND DETAILS Sheet 04 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0768 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20769 | CENTRAL BLOCK B2 SERVICE RFT BBS - Sheet 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0769 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20770 | CENTRAL BLOCK B2 SERVICE RFT BBS - Sheet 02 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0770 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20771 | CENTRAL BLOCK B2 SERVICE RFT BBS - Sheet 03 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0771 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20772 | CENTRAL BLOCK B2 SERVICE RFT BBS - Sheet 04 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0772 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20773 | CENTRAL BLOCK B2 SERVICE RFT BBS - Sheet 05 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0773 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20774 | CENTRAL BLOCK B2 SERVICE RFT BBS - Sheet 06 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 SOG RFT | QP.E.CV.MBL.GEN.3640 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0774 | Structural | Nesma & Partners |  |  |  |  | 2026-04-02
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20800 | Central Block B2 Beams key plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0800 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20801 | Central Block B2 Beams Reinforcement Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0801 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20802 | Central Block B2 Beams Reinforcement Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0802 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20803 | Central Block B2 Beams Reinforcement Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0803 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20804 | Central Block B2 Beams Reinforcement Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0804 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20805 | Central Block B2 Beams Reinforcement Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0805 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20806 | Central Block B2 Beams Reinforcement Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0806 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20807 | Central Block B2 Beams Reinforcement Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0807 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20808 | Central Block B2 Beams Reinforcement Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0808 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20809 | Central Block B2 Beams Reinforcement Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0809 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20810 | Central Block B2 Beams Reinforcement Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0810 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20811 | Central Block B2 Beams Reinforcement Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0811 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20812 | Central Block B2 Beams Reinforcement Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0812 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20813 | Central Block B2 Beams Reinforcement Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0813 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20814 | Central Block B2 Beams Reinforcement Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0814 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20815 | Central Block B2 Beams Reinforcement Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0815 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20816 | Central Block B2 Beams RFT BBS - Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0816 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20817 | Central Block B2 Beams RFT BBS - Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0817 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20818 | Central Block B2 Beams RFT BBS - Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0818 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20819 | Central Block B2 Beams RFT BBS - Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0819 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20820 | Central Block B2 Beams RFT BBS - Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0820 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20821 | Central Block B2 Beams Reinforcement Sheet 16 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0821 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20822 | Central Block B2 Beams Reinforcement Sheet 17 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0822 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20823 | Central Block B2 UPSTAND REINFOREMENT SHEET 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0823 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20824 | Central Block B2 UPSTAND REINFOREMENT SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0824 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20825 | Central Block B2 UPSTAND REINFOREMENT SHEET 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0825 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20826 | Central Block B2 UPSTAND REINFOREMENT SHEET 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0826 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20827 | Central Block B2 UPSTAND REINFOREMENT SHEET 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0827 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20828 | Central Block B2 UPSTAND REINFOREMENT SHEET 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0828 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B20829 | Central Block B2 UPSTAND REINFOREMENT SHEET 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 0829 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6B20830 | Central Block B2 UPSTAND REINFOREMENT BBS SHEET1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-06 | Central - B2 Beams RFT Detail | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 0830 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-01-CENT01-2B30901 | CENTRAL BLOCK COLUMNS PLAN SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B2 Column & Axes | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B3 | 0901 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-02-CENT01-2B30902 | CENTRAL BLOCK COLUMNS PLAN SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B2 Column & Axes | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B3 | 0902 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-05-CENT01-2B30903 | CENTRAL BLOCK COLUMNS PLAN SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B2 Column & Axes | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B3 | 0903 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-06-CENT01-2B30904 | CENTRAL BLOCK COLUMNS PLAN SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B2 Column & Axes | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B3 | 0904 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-08-CENT01-2B30905 | CENTRAL BLOCK COLUMNS PLAN SHEET 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B2 Column & Axes | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B3 | 0905 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-09-CENT01-2B30906 | CENTRAL BLOCK COLUMNS PLAN SHEET 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - B2 Column & Axes | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B3 | 0906 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B30907 | CENTRAL BLOCK COLUMNS ELEVATION RFT FROM B3 TO B2 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B3 | 0907 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B30908 | CENTRAL BLOCK COLUMNS ELEVATION RFT FROM B3 TO B2 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B3 | 0908 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B30909 | CENTRAL BLOCK COLUMNS ELEVATION RFT FROM B3 TO B2 SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B3 | 0909 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B30910 | CENTRAL BLOCK COLUMNS ELEVATION RFT FROM B3 TO B2 SHEET 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B3 | 0910 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B30911 | CENTRAL BLOCK COLUMNS ELEVATION RFT FROM B3 TO B2 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B3 | 0911 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B30912 | CENTRAL BLOCK COLUMNS ELEVATION RFT FROM B3 TO B2 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B3 | 0912 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B30913 | CENTRAL BLOCK COLUMNS ELEVATION RFT FROM B3 TO B2 SHEET 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B3 | 0913 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B30914 | CENTRAL BLOCK COLUMNS ELEVATION RFT FROM B3 TO B2 SHEET 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B3 | 0914 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B30915 | CENTRAL BLOCK COLUMNS ELEVATION RFT FROM B3 TO B2 SHEET 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B3 | 0915 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6B30916 | CENTRAL BLOCK COLUMNS ELEVATION RFT BBS - SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B3 | 0916 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B30917 | CENTRAL BLOCK COLUMNS ELEVATION RFT FROM B3 TO B2 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B3 | 0917 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-01-CENT01-2B21001 | CENTRAL BLOCK COLUMNS PLAN at B2 LEVEL SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B2 | 1001 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-02-CENT01-2B21002 | CENTRAL BLOCK COLUMNS PLAN at B2 LEVEL SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B2 | 1002 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-05-CENT01-2B21003 | CENTRAL BLOCK COLUMNS PLAN at B2 LEVELSHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B2 | 1003 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-06-CENT01-2B21004 | CENTRAL BLOCK COLUMNS PLAN at B2 LEVELSHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B2 | 1004 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-08-CENT01-2B21005 | CENTRAL BLOCK COLUMNS PLAN at B2 LEVELSHEET 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B2 | 1005 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-09-CENT01-2B21006 | CENTRAL BLOCK COLUMNS PLAN at B2 LEVELSHEET 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B2 | 1006 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21007 | Central Block Column Elevation RFT from B2to B1 - Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1007 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21008 | Central Block Column Elevation RFT from B2 to B1 - Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1008 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21009 | Central Block Column Elevation RFT from B2 to B1 - Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1009 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21010 | Central Block Column Elevation RFT from B2 to B1 - Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1010 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21011 | Central Block Column Elevation RFT from B2 to B1 - Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1011 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21012 | Central Block Column Elevation RFT from B2 to B1 - Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1012 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21013 | Central Block Column Elevation RFT from B2 to B1 - Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1013 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21014 | Central Block Column Elevation RFT from B2 to B1 - Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1014 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21015 | Central Block Column Elevation RFT from B2 to B1 - Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1015 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21016 | Central Block Column Elevation RFT from B2 to B1 - Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1016 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21017 | Central Block Column Elevation RFT from B2 to B1 - Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1017 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21018 | Central Block Column Elevation RFT from B2 to B1 - Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1018 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21019 | Central Block Column Elevation RFT from B2 to B1 - Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1019 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21020 | Central Block Column Elevation RFT from B2 to B1 - Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1020 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21021 | Central Block Column Elevation RFT from B2 to B1 - Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1021 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21022 | Central Block Column Elevation RFT from B2 to B1 - Sheet 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1022 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21023 | Central Block Column Elevation RFT from B2 to B1 - Sheet 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1023 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21024 | Central Block Column Elevation RFT from B2to B1 - Sheet 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1024 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21025 | Central Block Column Elevation RFT from B2 to B1 - Sheet 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1025 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21026 | Central Block Column Elevation RFT from B2 to B1 - Sheet 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1026 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21027 | Central Block Column Elevation RFT from B2 to B1 - Sheet 21 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1027 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21028 | Central Block Column Elevation RFT from B2 to B1 - Sheet 22 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1028 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21029 | Central Block Column Elevation RFT from B2 to B1 - Sheet 23 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1029 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21030 | Central Block Column Elevation RFT from B2 to B1 - Sheet 24 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1030 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21031 | Central Block Column Elevation RFT from B2 to B1 - Sheet 25 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1031 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6B21032 | Central Block Column Elevation RFT from B2 to B1 BBS - Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 1032 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6B21033 | Central Block Column Elevation RFT from B2 to B1 BBS - Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 1033 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21034 | Central Block Column Elevation RFT from B2 to B1 - Sheet 26 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1034 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3B21035 | Central Block Column Elevation RFT from B2 to B1 - Sheet 27 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-06 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B2 | 1035 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6B21036 | Central Block Column Elevation RFT from B2 to B1 BBS - Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Column RFT Elevation up to B1 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B2 | 1036 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1101 | CENTRAL BLOCK TANK FOUNDATION ENLARGED PLAN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1101 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1102 | CENTRAL BLOCK WATER TANK-07 TOP SLAB ENLARGED PLAN GA |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1102 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1103 | CENTRAL BLOCK WATER TANK-07 SECTIONS & DETAILS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1103 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1104 | CENTRAL BLOCK WATER TANK-07 SECTIONS & DETAILS SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1104 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1105 | CENTRAL BLOCK - UNDER GROUND TANK-07 WALL REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1105 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1106 | CENTRAL BLOCK - UNDER GROUND TANK-07 SLAB BOTTOM REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1106 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1107 | CENTRAL BLOCK - UNDER GROUND TANK-07 SLAB TOP REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1107 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1108 | CENTRAL BLOCK - UNDER GROUND TANK-07 SLAB AAO REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1108 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1109 | CENTRAL BLOCK - UNDER GROUND TANK-07 WALL REINFORCEMENT ELEVATION |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1109 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1110 | CENTRAL BLOCK - UNDER GROUND TANK-07 SLAB & WALL RFT BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1110 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1111 | AMPHITHEATRE - LEVEL B3-BOTTOM REINFORCEMENT B1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1111 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1112 | AMPHITHEATRE - LEVEL B3-BOTTOM REINFORCEMENT B2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1112 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1113 | AMPHITHEATRE - LEVEL B3-TOP REINFORCEMENT T1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1113 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1114 | AMPHITHEATRE - LEVEL B3-TOP REINFORCEMENT T2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1114 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1115 | AMPHITHEATRE - LEVEL B3-BOTTOM REINFORCEMENT ADDITIONAL B1 & ADDITIONAL B3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1115 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1116 | AMPHITHEATRE - LEVEL B3-BOTTOM REINFORCEMENT ADDITIONAL B2 & ADDITIONAL B4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1116 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1117 | AMPHITHEATRE - LEVEL B3-TOP REINFORCEMENT ADDITIONAL T1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1117 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1118 | AMPHITHEATRE - LEVEL B3-TOP REINFORCEMENT ADDITIONAL T2 & ADDITIONAL T4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1118 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1119 | AMPHITHEATRE - LEVEL B3-SHEAR LINK & SIDE BAR REINFORCEMENT |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1119 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1120 | AMPHITHEATRE -LEVEL B3-FOUNDATION SECTIONS AND DETAILS - SHEET 1 OF SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1120 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1121 | AMPHITHEATRE -LEVEL B3-FOUNDATION SECTIONS AND DETAILS - SHEET 2 OF SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1121 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1122 | AMPHITHEATRE-LEVEL B3-FOUNDATION REINFORCEMENT BBS - SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1122 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1123 | AMPHITHEATRE-LEVEL B3-FOUNDATION REINFORCEMENT BBS - SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | AMPHITHEATRE FOUNDATION RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1123 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1124 | CENTRAL BLOCK TANKS – AMPHITHEATRE TANKS KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1124 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1125 | CENTRAL BLOCK AMPHITHEATRE TANK WALLS GA ENLARGED PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1125 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1126 | CENTRAL BLOCK TANKS – AMPHITHEATRE TANKS SECTIONS - SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1126 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1127 | CENTRAL BLOCK TANKS – AMPHITHEATRE TANKS SECTIONS - SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1127 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1128 | CENTRAL BLOCK TANKS – AMPHITHEATRE TANKS SECTIONS - SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1128 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1129 | CENTRAL BLOCK TANKS – AMPHITHEATRE TANKS SECTIONS - SHEET 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1129 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1130 | CENTRAL BLOCK TANKS – AMPHITHEATRE TANKS SECTIONS - SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1130 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1131 | CENTRAL BLOCK TANKS – AMPHITHEATRE TANKS SECTIONS - SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1131 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1132 | CENTRAL BLOCK TANKS – AMPHITHEATRE TANKS SECTIONS - SHEET 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1132 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1133 | Central Block Tanks AMPHITHEATRE Tanks Sections Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1133 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1134 | Central Block Tanks AMPHITHEATRE Tanks RFT key plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1134 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1135 | Central Block Tanks AMPHITHEATRE Tanks RFT Sections Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1135 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1136 | Central Block Tanks AMPHITHEATRE Tanks RFT Sections Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1136 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1137 | Central Block Tanks AMPHITHEATRE Tanks RFT Sections Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1137 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1138 | Central Block Tanks AMPHITHEATRE Tanks RFT Sections Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1138 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1139 | Central Block Tanks AMPHITHEATRE Tanks RFT Sections Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1139 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1140 | Central Block Tanks AMPHITHEATRE Tanks RFT Sections Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1140 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1141 | Central Block Tanks AMPHITHEATRE Tanks RFT Sections Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1141 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1142 | Central Block Tanks AMPHITHEATRE Tanks RFT BBS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Tanks GA & RFT | QP.E.CV.MBL.GEN.3030 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1142 | Structural | Nesma & Partners |  |  |  |  | 2026-02-17
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1200 | CENTRAL BLOCK RETAINING WALLS GENERAL ARRANGEMENT UP TO B1 - KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - RW GA Plans Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1200 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1201 | CENTRAL BLOCK RETAINING WALLS GENERAL ARRANGEMENT UP TO B1 PLAN- SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - RW GA Plans Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1201 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1202 | CENTRAL BLOCK RETAINING WALLS GENERAL ARRANGEMENT UP TO B1 PLAN- SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - RW GA Plans Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1202 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1203 | CENTRAL BLOCK RETAINING WALLS GENERAL ARRANGEMENT UP TO B1 PLAN- SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - RW GA Plans Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1203 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1204 | CENTRAL BLOCK RETAINING WALLS GENERAL ARRANGEMENT UP TO B1 PLAN- SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - RW GA Plans Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1204 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1205 | CENTRAL BLOCK RETAINING WALLS GENERAL ARRANGEMENT UP TO B1 PLAN- SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - RW GA Plans Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1205 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1206 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1206 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1207 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1207 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1208 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1208 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1209 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1209 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1210 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1210 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1211 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1211 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1212 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1212 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1213 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1213 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1214 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1214 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1215 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1215 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1216 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1216 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1217 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1217 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1218 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1218 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1219 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1219 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1220 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1220 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1221 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1221 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1222 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1222 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1223 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1223 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1224 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1224 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1225 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1225 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1226 | CENTRAL BLOCK RETAINING WALLS GA ELEVATION UP TO B1- SHEET 21 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW GA Elevation Up to B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1226 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1300 | Central Block Shear wall GA key plan |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central -Shear Walls GA Plans Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1300 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1301 | Central Block Shear wall GA Enlarged plan Part 1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central -Shear Walls GA Plans Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1301 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1302 | Central Block Shear wall GA Enlarged plan Part 2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central -Shear Walls GA Plans Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1302 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1303 | Central Block Shear wall GA Enlarged plan Part 3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1303 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1304 | Central Block Shear wall GA Section Elevation Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1304 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1305 | Central Block Shear wall GA Section Elevation Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1305 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1306 | Central Block Shear wall GA Section Elevation Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1306 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1307 | Central Block Shear wall GA Section Elevation Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1307 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1308 | Central Block Shear wall GA Section Elevation Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1308 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1309 | Central Block Shear wall GA Section Elevation Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1309 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1310 | Central Block Shear wall GA Section Elevation Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1310 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1311 | Central Block Shear wall GA Section Elevation Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1311 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1312 | Central Block Shear wall GA Section Elevation Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1312 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1313 | Central Block Shear wall GA Section Elevation Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1313 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1314 | Central Block Shear wall GA Section Elevation Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1314 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1315 | Central Block Shear wall GA Section Elevation Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Elevation Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1315 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1316 | Central Block Shear wall GA Section Elevation Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central -Shear Walls GA Plans Up To B1 level | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1316 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1400 | Central Block Core Walls GA key plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1400 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1401 | Central Block Core Walls GA Enlarged plan Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1401 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1402 | Central Block Core Walls GA Enlarged plan Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1402 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1403 | Central Block Core Walls GA Enlarged plan Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1403 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1405 | Central Block Core Walls GA Elevation Up to B1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1405 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1406 | Central Block Core Walls GA Elevation Up to B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1406 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1407 | Central Block Core Walls GA Elevation Up to B1 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1407 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1408 | Central Block Core Walls GA Elevation Up to B1 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1408 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1409 | Central Block Core Walls GA Elevation Up to B1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1409 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1410 | Central Block Core Walls GA Elevation Up to B1 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1410 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1411 | Central Block Core Walls GA Elevation Up to B1 Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1411 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1412 | Central Block Core Walls GA Elevation Up to B1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1412 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1413 | Central Block Core Walls GA Elevation Up to B1 Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1413 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1414 | Central Block Core Walls GA Elevation Up to B1 Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1414 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1415 | Central Block Core Walls GA Elevation Up to B1 Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1415 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1416 | Central Block Core Walls GA Elevation Up to B1 Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1416 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1417 | Central Block Core Walls GA Elevation Up to B1 Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1417 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1418 | Central Block Core Walls GA Elevation Up to B1 Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1418 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1419 | Central Block Core Walls GA Elevation Up to B1 Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1419 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1420 | Central Block Core Walls GA Elevation Up to B1 Sheet 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1420 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1421 | Central Block Core Walls GA Elevation Up to B1 Sheet 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1421 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1422 | Central Block Core Walls GA Elevation Up to B1 Sheet 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1422 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1423 | Central Block Core Walls GA Elevation Up to B1 Sheet 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1423 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1424 | Central Block Core Walls GA Elevation Up to B1 Sheet 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1424 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1425 | Central Block Core Walls GA Elevation Up to B1 Sheet 21 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1425 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1426 | Central Block Core Walls GA Elevation Up to B1 Sheet 22 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1426 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1427 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA UP TO B2 KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1427 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1428 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA UP TO B2 ENLARGED PLAN PART-01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1428 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1429 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA UP TO B2 ENLARGED PLAN PART-02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1429 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1430 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA UP TO B2 ENLARGED PLAN PART-03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1430 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1431 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA UP TO B2 ENLARGED PLAN PART-04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1431 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1432 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1432 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1433 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1433 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1434 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1434 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1435 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1435 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1436 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1436 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1437 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1437 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1438 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1438 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1439 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1439 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1440 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1440 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1441 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1441 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1442 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1442 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1443 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1443 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1444 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1444 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1445 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1445 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1446 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1446 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1447 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1447 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1448 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1448 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1449 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1449 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1450 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1450 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1451 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1451 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1452 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 21 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1452 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1453 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION UP TO B2 SHEET 22 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1453 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1454 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA UP TO B1 KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1454 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1455 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA UP TO B1 ENLARGED PLAN PART-01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1455 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1456 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA UP TO B1 ENLARGED PLAN PART-02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1456 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1457 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA UP TO B1 ENLARGED PLAN PART-03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1457 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1458 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA UP TO B1 ENLARGED PLAN PART-04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1458 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1459 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1459 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1460 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1460 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1461 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1461 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1462 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1462 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1463 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1463 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1464 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1464 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1465 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1465 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1466 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1466 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1467 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1467 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1468 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1468 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1469 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1469 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1470 | CENTRAL BLOCK AMPHITHEATRE CORE WALLS GA ELEVATION & SECTION UP TO B1 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1470 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1471 | Central Block Amphitheatre Core Walls CW( 05 TO 10) Reinforcement Key Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1471 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1472 | Central Block Amphitheatre Core Walls CW-05 & CW-10 Reinforcement Plan- PART 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1472 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1473 | Central Block Amphitheatre Core Walls CW-05 & CW-10 Reinforcement Plan- PART 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1473 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1474 | Central Block Amphitheatre Core Walls CW 05 Reinforcement Elevation SECTION Up to L01 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1474 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1475 | Central Block Amphitheatre Core Walls CW 05 Reinforcement Elevation SECTION Up to L01 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1475 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1476 | Central Block Amphitheatre Core Walls CW 05 Reinforcement Elevation SECTION Up to L01 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1476 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1477 | Central Block Amphitheatre Core Walls CW 05 Reinforcement Elevation SECTION Up to L01 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1477 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1478 | Central Block Amphitheatre Core Walls CW 05 Reinforcement Elevation SECTION Up to L01 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1478 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1479 | Central Block Amphitheatre Core Walls CW 05 Reinforcement Elevation SECTION Up to L01 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1479 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1480 | Central Block Amphitheatre Core Walls CW 05 Reinforcement Elevation SECTION Up to L01 Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1480 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1481 | Central Block Amphitheatre Core Walls CW 10 Reinforcement Elevation SECTION Up to L01 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1481 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1482 | Central Block Amphitheatre Core Walls CW-06 & CW-08 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1482 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1483 | Central Block Amphitheatre Core Walls CW 06 Reinforcement Elevation SECTION Up to L01 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1483 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1484 | Central Block Amphitheatre Core Walls CW 06 Reinforcement Elevation SECTION Up to L01 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1484 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1485 | Central Block Amphitheatre Core Walls CW 06 Reinforcement Elevation SECTION Up to L01 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1485 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1486 | Central Block Amphitheatre Core Walls CW 08 Reinforcement Elevation SECTION Up to L01 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1486 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1487 | Central Block Amphitheatre Core Walls 05 Bar Bending Schedule sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1487 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1488 | Central Block Amphitheatre Core Walls 06-08 & 10 Bar Bending Schedule sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central- AMPHITHEATRE CORE WALLS GA up to B1 | QP.E.CV.MBL.GEN.3200 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1488 | Structural | Nesma & Partners |  |  |  |  | 2026-06-23
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1500 | Central Block Core Walls RFT key plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1500 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1501 | Central Block Shear Walls from B3 to B2 Enlarged Plan RFT sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1501 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1502 | Central Block Shear Walls from B2 to B1 Enlarged Plan RFT sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1502 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1503 | Central Block Shear Walls from B2 to B1 Enlarged Plan RFT sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1503 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1504 | Central Block Shear Walls from B2 to B1 Enlarged Plan RFT sheet 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1504 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1505 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT - KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1505 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1506 | CENTRAL BLOCK RETAINING WALLS FROM B3 TO B2 ENLARGED PLAN REINFORCEMENT - SHEET-01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1506 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1507 | CENTRAL BLOCK RETAINING WALLS FROM B3 TO B2 ENLARGED PLAN REINFORCEMENT - SHEET-02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1507 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1508 | CENTRAL BLOCK RETAINING WALLS FROM B3 TO B2 ENLARGED PLAN REINFORCEMENT - SHEET-03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1508 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1509 | CENTRAL BLOCK RETAINING WALLS FROM B3 TO B2 ENLARGED PLAN REINFORCEMENT - SHEET-04 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1509 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1510 | CENTRAL BLOCK RETAINING WALLS FROM B3 TO B2 ENLARGED PLAN REINFORCEMENT - SHEET-05 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core Walls GA Elevation Up to B1 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1510 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1511 | CENTRAL BLOCK RETAINING WALLS FROM B3 TO B2 ENLARGED PLAN REINFORCEMENT - SHEET-06 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1511 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1512 | CENTRAL BLOCK RETAINING WALLS FROM B3 TO B2 ENLARGED PLAN REINFORCEMENT - SHEET-07 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1512 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1513 | CENTRAL BLOCK RETAINING WALLS FROM B3 TO B2 ENLARGED PLAN REINFORCEMENT - SHEET-08 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1513 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1514 | CENTRAL BLOCK RETAINING WALLS FROM B2 TO B1 ENLARGED PLAN REINFORCEMENT - SHEET-01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1514 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1515 | CENTRAL BLOCK RETAINING WALLS FROM B2 TO B1 ENLARGED PLAN REINFORCEMENT - SHEET-02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1515 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1516 | CENTRAL BLOCK RETAINING WALLS FROM B2 TO B1 ENLARGED PLAN REINFORCEMENT - SHEET-03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1516 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1517 | CENTRAL BLOCK RETAINING WALLS FROM B2 TO B1 ENLARGED PLAN REINFORCEMENT - SHEET-04 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1517 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1518 | CENTRAL BLOCK RETAINING WALLS FROM B2 TO B1 ENLARGED PLAN REINFORCEMENT - SHEET-05 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1518 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1519 | CENTRAL BLOCK RETAINING WALLS FROM B2 TO B1 ENLARGED PLAN REINFORCEMENT - SHEET-06 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1519 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1520 | CENTRAL BLOCK RETAINING WALLS FROM B2 TO B1 ENLARGED PLAN REINFORCEMENT - SHEET-07 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1520 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1521 | CENTRAL BLOCK RETAINING WALLS FROM B2 TO B1 ENLARGED PLAN REINFORCEMENT - SHEET-08 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1521 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1522 | Central Block Core Walls CW-02 Reinforcement plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1522 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1523 | Central Block Core Walls CW-04 Reinforcement plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1523 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1524 | Central Block Core Walls CW-01 Reinforcement plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1524 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1525 | Central Block Core Walls CW-03 Reinforcement plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1525 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1601 | Central Block Shear Walls RFT Elevation Up to B1 sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1601 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1602 | Central Block Shear Walls RFT Elevation Up to B1 sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1602 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1603 | Central Block Shear Walls RFT Elevation Up to B1 sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1603 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1604 | Central Block Shear Walls RFT Elevation Up to B1 sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1604 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1605 | Central Block Shear Walls RFT Elevation Up to B1 sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1605 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1606 | Central Block Shear Walls RFT Elevation Up to B1 sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1606 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1607 | Central Block Shear Walls RFT Elevation Up to B1 sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1607 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1608 | Central Block Shear Walls RFT Elevation Up to B1 sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1608 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1609 | Central Block Shear Walls RFT Elevation Up to B1 sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1609 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1610 | Central Block Shear Walls RFT Elevation Up to B1 sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1610 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1611 | Central Block Shear Walls RFT Elevation Up to B1 sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1611 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1612 | Central Block Shear Walls RFT Elevation Up to B1 sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1612 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1613 | Central Block Shear Walls RFT Elevation Up to B1 sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1613 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1614 | Central Block Shear Walls RFT Elevation Up to B1 sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1614 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1615 | Central Block Shear Walls RFT Elevation Up to B1 sheet 15 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1615 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1616 | Central Block Shear Walls RFT BBS - Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1616 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1617 | Central Block Shear Walls RFT BBS - Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1617 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1618 | Central Block Shear Walls RFT BBS - Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1618 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1619 | Central Block Shear Walls RFT BBS - Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Shear Wall RFT Up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1619 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1701 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1701 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1702 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1702 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1703 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1703 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1704 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1704 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1705 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1705 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1706 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1706 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1707 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1707 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1708 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1708 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1709 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1709 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1710 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1710 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1711 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1711 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1712 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1712 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1713 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1713 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1714 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1714 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1715 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1715 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1716 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1716 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1717 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1717 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1718 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1718 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1719 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1719 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1720 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1720 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1721 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT ELEVATION SECTION- SHEET 21 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1721 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1722 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT BBS FROM B3 TO B2 - SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1722 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1723 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT BBS FROM B3 TO B2 - SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1723 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1724 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT BBS FROM B3 TO B2 - SHEET 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1724 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1725 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT BBS FROM B2 TO B1 - SHEET 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1725 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1726 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT BBS FROM B2 TO B1 - SHEET 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1726 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1727 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT BBS FROM B1 TO L01 - SHEET 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1727 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1728 | CENTRAL BLOCK RETAINING WALLS REINFORCEMENT BBS FROM B1 TO L01 - SHEET 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1728 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1729 | Central Block Tank 04 Walls Enlarged Plan RFT |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1729 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1730 | Central Block Tanks 04 RFT Elevation and Sections Details |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - RW RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1730 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1801 | Central Block Core Walls CW-01 Reinforcement plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1801 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1802 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to B2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1802 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1803 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1803 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1804 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to B2 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1804 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1805 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to B2 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1805 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1806 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1806 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1807 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to B2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1807 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1808 | Central Block Core Walls CW-02 Reinforcement plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1808 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1809 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to B2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1809 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1810 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1810 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1811 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to B2 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1811 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1812 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to B2 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1812 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1813 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1813 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1814 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to B2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1814 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1815 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1815 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1816 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1816 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1817 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to B1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1817 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1818 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1818 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1819 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to B1 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1819 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1820 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to B1 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1820 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1821 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to B1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1821 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1822 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1822 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1823 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to B1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1823 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1824 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1824 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1825 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to B1 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1825 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1826 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to B1 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1826 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1827 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to B1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1827 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1828 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1828 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1829 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to B1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1829 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1830 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1830 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1831 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to B1 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1831 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1832 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to B1 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1832 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1833 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to B1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1833 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1834 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1834 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1835 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to B1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1835 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1836 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1836 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1837 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1837 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1837 | CENTRAL BLOCK CORE WALLS REINFORCEMENT SECTION DETAILS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1837 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1838 | CENTRAL BLOCK CORE WALLS REINFORCEMENT SECTION DETAILS SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1838 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2FL1839 | Central Block Amphitheatre Core Walls CW( 05 TO 10) Reinforcement Key Plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | FL | 1839 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1840 | Central Block Amphitheatre Core Walls CW-05 & CW-10 Reinforcement Plan- PART 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1840 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1841 | Central Block Amphitheatre Core Walls CW-05 & CW-10 Reinforcement Plan- PART 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1841 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1842 | Central Block Amphitheatre Core Walls CW 05 &10 Reinforcement Elevation SECTION Up to B2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1842 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1843 | Central Block Amphitheatre Core Walls CW 05 &10 Reinforcement Elevation SECTION Up to B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1843 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1844 | Central Block Amphitheatre Core Walls CW 05 &10 Reinforcement Elevation SECTION Up to B2 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1844 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1845 | Central Block Amphitheatre Core Walls CW 05 &10 Reinforcement Elevation SECTION Up to B2 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1845 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1846 | Central Block Amphitheatre Core Walls CW 05 &10 Reinforcement Elevation SECTION Up to B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1846 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1847 | Central Block Amphitheatre Core Walls CW 05 &10 Reinforcement Elevation SECTION Up to B2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1847 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1848 | Central Block Amphitheatre Core Walls CW-07 & 08 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1848 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1849 | Central Block Amphitheatre Core Walls CW 07 & 08 Reinforcement Elevation SECTION Up to B2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1849 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1850 | Central Block Amphitheatre Core Walls CW 07 & 08 Reinforcement Elevation SECTION Up to B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1850 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1851 | Central Block Amphitheatre Core Walls CW-06 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1851 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1852 | Central Block Amphitheatre Core Walls CW 06 Reinforcement Elevation SECTION Up to B2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1852 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1853 | Central Block Amphitheatre Core Walls CW 06 Reinforcement Elevation SECTION Up to B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1853 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1854 | Central Block Amphitheatre Core Walls CW 06 Reinforcement Elevation SECTION Up to B2 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1854 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1855 | Central Block Amphitheatre Core Walls CW-09 Reinforcement Plan-PART 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1855 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL1856 | Central Block Amphitheatre Core Walls CW-09 Reinforcement Plan-PART 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 1856 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1857 | Central Block Amphitheatre Core Walls CW 09 Reinforcement Elevation SECTION Up to B2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1857 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1858 | Central Block Amphitheatre Core Walls CW 09 Reinforcement Elevation SECTION Up to B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1858 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1859 | Central Block Amphitheatre Core Walls CW 09 Reinforcement Elevation SECTION Up to B2 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1859 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL1860 | Central Block Amphitheatre Core Walls CW 09 Reinforcement Elevation SECTION Up to B2 Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 1860 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1861 | Central Block Amphitheatre Core Walls Bar bending Schedule sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1861 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL1862 | Central Block Amphitheatre Core Walls Bar bending Schedule sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Core RFT up to B01 | QP.E.CV.MBL.GEN.3070 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 1862 | Structural | Nesma & Partners |  |  |  |  | 2026-03-15
QF01012-NES-C04518-SDW-STR-00-CENT01-2B11900 | CENTRAL BLOCK B1 SERVICE SLAB GA OVERALL PLAN SHEET 1 (1/1) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | B1 | 1900 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B11901 | CENTRAL BLOCK B1 SERVICE COLUMNS AND WALLS PLAN SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 1901 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B11902 | CENTRAL BLOCK B1 SERVICE COLUMNS AND WALLS PLAN SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 1902 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B11903 | CENTRAL BLOCK B1 SERVICE COLUMNS AND WALLS PLAN SHEET 5 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 1903 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B11904 | CENTRAL BLOCK B1 SERVICE COLUMNS AND WALLS PLAN SHEET 6 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 1904 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B11905 | CENTRAL BLOCK B1 SERVICE COLUMNS AND WALLS PLAN SHEET 8 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 1905 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B11906 | CENTRAL BLOCK B1 SERVICE COLUMNS AND WALLS PLAN SHEET 9 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 1906 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B11907 | CENTRAL BLOCK B1 SERVICE SLAB GA PLAN SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 1907 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B11908 | CENTRAL BLOCK B1 SERVICE SLAB GA PLAN SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 1908 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B11909 | CENTRAL BLOCK B1 SERVICE SLAB GA PLAN SHEET 5 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 1909 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B11910 | CENTRAL BLOCK B1 SERVICE SLAB GA PLAN SHEET 6 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 1910 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B11911 | CENTRAL BLOCK B1 SERVICE SLAB GA PLAN SHEET 8 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 1911 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B11912 | CENTRAL BLOCK B1 SERVICE SLAB GA PLAN SHEET 9 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 1912 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B11913 | CENTRAL BLOCK B1 SERVICE SLAB GA SECTIONS SHEET 1 (1/3) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 1913 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B11914 | CENTRAL BLOCK B1 SERVICE SLAB GA SECTIONS SHEET 2 (2/3) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 1914 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B11915 | CENTRAL BLOCK B1 SERVICE SLAB GA SECTIONS SHEET 3 (3/3) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Slab GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 1915 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B12001 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 2001 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B12002 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 2002 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B12003 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 2003 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B12004 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 2004 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B12005 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 2005 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B12006 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 2006 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B12007 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 2007 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B12008 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 2008 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B12009 | CENTRAL BLOCK - LEVEL B1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 2009 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B12010 | CENTRAL BLOCK - LEVEL B1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 2010 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B12011 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 2011 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B12012 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 2012 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B12013 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 2013 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B12014 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 2014 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B12015 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 2015 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B12016 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 2016 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B12017 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 2017 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B12018 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 2018 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B12019 | CENTRAL BLOCK - LEVEL B1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 2019 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B12020 | CENTRAL BLOCK - LEVEL B1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 2020 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B12021 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 2021 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B12022 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 2022 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B12023 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 2023 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B12024 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 2024 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B12025 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 2025 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B12026 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 2026 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B12027 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 2027 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B12028 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 2028 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B12029 | CENTRAL BLOCK - LEVEL B1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 2029 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B12030 | CENTRAL BLOCK - LEVEL B1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 2030 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B12031 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B1 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 2031 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B12032 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 2032 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B12033 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T1 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 2033 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B12034 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 2034 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B12035 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B1 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 2035 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B12036 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 2036 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B12037 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T1 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 2037 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B12038 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 2038 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B12039 | CENTRAL BLOCK - LEVEL B1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 2039 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B12040 | CENTRAL BLOCK - LEVEL B1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 2040 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B12041 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 2041 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B12042 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 2042 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B12043 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 2043 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B12044 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 2044 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B12045 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 2045 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B12046 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 2046 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B12047 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 2047 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B12048 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 2048 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B12049 | CENTRAL BLOCK - LEVEL B1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 2049 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B12050 | CENTRAL BLOCK - LEVEL B1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 2050 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B12051 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B1 Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 2051 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B12052 | CENTRAL BLOCK - LEVEL B1-BOTTOM REINFORCEMENT B2 Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 2052 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B12053 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T1 Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 2053 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B12054 | CENTRAL BLOCK - LEVEL B1-TOP REINFORCEMENT T2 Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 2054 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B12055 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B1 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 2055 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B12056 | CENTRAL BLOCK - LEVEL B1-BOTTOM ADDITIONAL REINFORCEMENT B2 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 2056 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B12057 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T1 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 2057 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B12058 | CENTRAL BLOCK - LEVEL B1-TOP ADDITIONAL REINFORCEMENT T2 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 2058 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B12059 | CENTRAL BLOCK - LEVEL B1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 2059 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B12060 | CENTRAL BLOCK - LEVEL B1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 2060 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12061 | CENTRAL BLOCK - LEVEL B1-SLAB SECTIONS AND DETAILS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2061 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12062 | CENTRAL BLOCK - LEVEL B1-SLAB SECTIONS AND DETAILS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2062 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12063 | CENTRAL BLOCK - LEVEL B1 SLAB RFT BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2063 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12064 | CENTRAL BLOCK - LEVEL B1 SLAB RFT BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2064 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12065 | CENTRAL BLOCK - LEVEL B1 SLAB RFT BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2065 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12066 | CENTRAL BLOCK - LEVEL B1 SLAB RFT BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2066 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12067 | CENTRAL BLOCK - LEVEL B1 SLAB RFT BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2067 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12068 | CENTRAL BLOCK - LEVEL B1 SLAB RFT BBS Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2068 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12069 | CENTRAL BLOCK - LEVEL B1 SLAB RFT BBS Sheet 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2069 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12070 | CENTRAL BLOCK - LEVEL B1 SLAB RFT BBS Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Slab RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2070 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12100 | CENTRAL BLOCK LEVEL B1 BEAMS - KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2100 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12101 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2101 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12102 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2102 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12103 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2103 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12104 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2104 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12105 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2105 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12106 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2106 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12107 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2107 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12108 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2108 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12109 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2109 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12110 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2110 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12111 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2111 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12112 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2112 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12113 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2113 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12114 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2114 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12115 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2115 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12116 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2116 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12117 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2117 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12118 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2118 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12119 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2119 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12120 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2120 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12121 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 21 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2121 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12122 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 22 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2122 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12123 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 23 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2123 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12124 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 24 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2124 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12125 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 25 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2125 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12126 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 26 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2126 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12127 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 27 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2127 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12128 | CENTRAL BLOCK LEVEL B1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 28 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2128 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12129 | CENTRAL BLOCK LEVEL B1 BEAMS BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2129 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12130 | CENTRAL BLOCK LEVEL B1 BEAMS BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2130 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12131 | CENTRAL BLOCK LEVEL B1 BEAMS BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2131 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12132 | CENTRAL BLOCK LEVEL B1 BEAMS BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2132 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12133 | CENTRAL BLOCK LEVEL B1 BEAMS BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2133 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12134 | CENTRAL BLOCK LEVEL B1 BEAMS BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 Beams RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2134 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-01-CENT01-2B12201 | CENTRAL BLOCK COLUMNS PLAN at B1 LEVEL SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | B1 | 2201 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-02-CENT01-2B12202 | CENTRAL BLOCK COLUMNS PLAN at B1 LEVEL SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | B1 | 2202 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-05-CENT01-2B12203 | CENTRAL BLOCK COLUMNS PLAN at B1 LEVELSHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | B1 | 2203 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-06-CENT01-2B12204 | CENTRAL BLOCK COLUMNS PLAN at B1 LEVELSHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | B1 | 2204 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-08-CENT01-2B12205 | CENTRAL BLOCK COLUMNS PLAN at B1 LEVELSHEET 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | B1 | 2205 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-09-CENT01-2B12206 | CENTRAL BLOCK COLUMNS PLAN at B1 LEVELSHEET 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | B1 | 2206 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12207 | Central Block From B1 to L1 Columns Elevation & Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2207 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12208 | Central Block From B1 to L1 Columns Elevation & Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2208 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12209 | Central Block From B1 to L1 Columns Elevation & Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2209 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12210 | Central Block From B1 to L1 Columns Elevation & Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2210 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12211 | Central Block From B1 to L1 Columns Elevation & Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2211 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12212 | Central Block From B1 to L1 Columns Elevation & Details Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2212 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12213 | Central Block From B1 to L1 Columns Elevation & Details Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2213 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12214 | Central Block From B1 to L1 Columns Elevation & Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2214 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12215 | Central Block From B1 to L1 Columns Elevation & Details Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2215 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12216 | Central Block From B1 to L1 Columns Elevation & Details Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2216 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12217 | Central Block From B1 to L1 Columns Elevation & Details Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2217 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12218 | Central Block From B1 to L1 Columns Elevation & Details Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2218 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12219 | Central Block From B1 to L1 Columns RFT BBS - Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2219 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12220 | Central Block From B1 to L1 Columns RFT BBS - Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - Column RFT Elevation B1-L1 | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2220 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-2B12301 | CENTRAL BLOCK CORE WALLS GA KEY PLAN FROM B01 TO L01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | B1 | 2301 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4B12302 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM B01 TO L01 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B1 | 2302 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4B12303 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM B01 TO L01 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B1 | 2303 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4B12304 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM B01 TO L01 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B1 | 2304 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12305 | CENTRAL BLOCK CORE WALLS GA ELEVATION FROM B01 TO L01 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2305 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12306 | CENTRAL BLOCK CORE WALLS GA ELEVATION FROM B01 TO L01 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2306 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12307 | CENTRAL BLOCK CORE WALLS GA ELEVATION FROM B01 TO L01 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2307 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12308 | CENTRAL BLOCK CORE WALLS GA ELEVATION FROM B01 TO L01 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2308 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12309 | CENTRAL BLOCK CORE WALLS GA ELEVATION FROM B01 TO L01 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2309 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12310 | CENTRAL BLOCK CORE WALLS GA ELEVATION FROM B01 TO L01 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2310 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12311 | CENTRAL BLOCK CORE WALLS GA ELEVATION FROM B01 TO L01 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2311 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12312 | CENTRAL BLOCK CORE WALLS GA ELEVATION FROM B01 TO L01 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2312 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12313 | CENTRAL BLOCK CORE WALLS GA ELEVATION FROM B01 TO L01 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2313 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12314 | CENTRAL BLOCK CORE WALLS GA ELEVATION FROM B01 TO L01 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1-L1 Core & Shear Walls GA | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2314 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-2B12400 | CENTRAL BLOCK SHEAR WALL B1 TO L1 GENERAL ARRANGEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | B1 | 2400 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4B12401 | CENTRAL BLOCK SHEAR WALL GA ENLARGED PLAN B1 TO L1 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B1 | 2401 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4B12402 | CENTRAL BLOCK SHEAR WALL GA ENLARGED PLAN B1 TO L1 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B1 | 2402 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4B12403 | CENTRAL BLOCK SHEAR WALL GA ENLARGED PLAN B1 TO L1 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B1 | 2403 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12404 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION B1 TO L1- SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2404 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12405 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION B1 TO L1- SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2405 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12406 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION B1 TO L1- SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2406 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12407 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION B1 TO L1- SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2407 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12408 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION B1 TO L1- SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2408 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12409 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION B1 TO L1- SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2409 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12410 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION B1 TO L1- SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2410 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12411 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION B1 TO L1- SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2411 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12412 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION B1 TO L1- SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-08-27 | Central - B1 - L1 Core & Shear Walls RFT Plans | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2412 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-2B12501 | Central Block Core Walls CW-01 Reinforcement plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | B1 | 2501 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12502 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2502 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12503 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2503 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12504 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L1 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2504 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12505 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L1 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2505 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12506 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2506 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-2B12507 | Central Block Core Walls CW-02 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | B1 | 2507 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12508 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2508 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12509 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2509 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12510 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L1 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2510 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12511 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L1 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2511 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12512 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2512 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-2B12513 | Central Block Core Walls CW-03 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | B1 | 2513 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12514 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to L1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2514 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12515 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to L1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2515 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12516 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2516 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-2B12517 | Central Block Core Walls CW-04 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | B1 | 2517 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12518 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2518 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12519 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2519 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12520 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L1 Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2520 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12521 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2521 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-2B12600 | CENTRAL BLOCK SHEAR WALLS RFT-B1 TO L1 KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | B1 | 2600 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4B12601 | CENTRAL BLOCK SHEAR WALLS FROM B1 TO L1 ENLARGED PLAN RFT SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B1 | 2601 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4B12602 | CENTRAL BLOCK SHEAR WALLS FROM B1 TO L1 ENLARGED PLAN RFT SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B1 | 2602 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4B12603 | CENTRAL BLOCK SHEAR WALLS FROM B1 TO L1 ENLARGED PLAN RFT SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | B1 | 2603 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12604 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2604 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12605 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2605 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12606 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2606 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12607 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2607 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12608 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2608 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12609 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2609 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12610 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2610 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12611 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2611 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12612 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-27 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2612 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12613 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2613 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12614 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2614 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12615 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 12 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2615 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3B12616 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM B1 TO L1 SHEET 13 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | B1 | 2616 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12617 | CENTRAL BLOCK SHEAR WALLS RFT B1 TO L1 BBS SHEET- 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2617 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12618 | CENTRAL BLOCK SHEAR WALLS RFT B1 TO L1 BBS SHEET- 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2618 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6B12619 | CENTRAL BLOCK SHEAR WALLS RFT B1 TO L1 BBS SHEET- 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - B1 - L1 Core Walls RFT | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | B1 | 2619 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2701 | STAIR-A - CENTRAL BLOCK - STAIR GA PLAN B3 TO B2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2701 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2702 | STAIR-A - CENTRAL BLOCK - STAIR GA PLAN B2 TO B1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2702 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2703 | STAIR-A - CENTRAL BLOCK - STAIR GA PLAN B1 TO L1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2703 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2704 | STAIR-A - CENTRAL BLOCK - STAIR SECTION ELEVATION B3 TO L1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2704 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2705 | STAIR-B - CENTRAL BLOCK - STAIR GA PLAN B3 TO B2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2705 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2706 | STAIR-B - CENTRAL BLOCK - STAIR GA PLAN B2 TO B1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2706 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2707 | STAIR-B - CENTRAL BLOCK - STAIR GA PLAN B1 TO L1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2707 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2708 | STAIR-B - CENTRAL BLOCK - STAIR SECTION ELEVATION B3 TO B2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2708 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2709 | STAIR-B - CENTRAL BLOCK - STAIR SECTION ELEVATION B2 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2709 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2710 | STAIR-C - CENTRAL BLOCK - STAIR GA PLAN B2 TO B1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2710 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2711 | STAIR-C - CENTRAL BLOCK - STAIR GA PLAN B1 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2711 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2712 | STAIR-C - CENTRAL BLOCK - STAIR SECTION ELEVATION B2 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2712 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2713 | STAIR-D - CENTRAL BLOCK - STAIR GA PLAN B2 TO B1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2713 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2714 | STAIR-D - CENTRAL BLOCK - STAIR GA PLAN B1 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2714 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2715 | STAIR-D - CENTRAL BLOCK - STAIR SECTION ELEVATION B2 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2715 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2716 | STAIR-F - CENTRAL BLOCK - STAIR GA PLAN B3 TO B2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2716 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2717 | STAIR-F - CENTRAL BLOCK - STAIR GA PLAN B2 TO B1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2717 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2718 | STAIR-F - CENTRAL BLOCK - STAIR SECTION ELEVATION B3 TO B1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2718 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2719 | STAIR-A - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B3 TO B2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2719 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2720 | STAIR-A - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B2 TO B1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2720 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2721 | STAIR-A - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B1 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2721 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2722 | STAIR-A - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION B3 TO B2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2722 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2723 | STAIR-A - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION B2 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2723 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL2724 | STAIR A - B3 TO L1 - CENTRAL BLOCK - STAIR REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 2724 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2725 | STAIR-B - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B3 TO B2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2725 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2726 | STAIR-B - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B2 TO B1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2726 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2727 | STAIR-B - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B1 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2727 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2728 | STAIR-B - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION B3 TO B2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2728 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2729 | STAIR-B - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION B2 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2729 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL2730 | STAIR B - B3 TO L1 - CENTRAL BLOCK - STAIR REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 2730 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2731 | STAIR-C - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B2 TO B1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2731 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2732 | STAIR-C - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B1 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2732 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2733 | STAIR-C - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION B2 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2733 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL2734 | STAIR C - B2 TO L1 - CENTRAL BLOCK - STAIR REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 2734 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2735 | STAIR-D - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B2 TO B1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-07-23 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2735 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2736 | STAIR-D - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B1 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2736 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2737 | STAIR-D - CENTRAL BLOCK - STAIR SECTION ELEVATION B2 TO L1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2737 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL2738 | STAIR D - B3 TO L1 - CENTRAL BLOCK - STAIR REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 2738 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2739 | STAIR-F - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B3 TO B2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2739 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-4FL2740 | STAIR-F - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN B2 TO B1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | FL | 2740 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-3FL2741 | STAIR-F - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION B3 TO B1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | FL | 2741 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-6FL2742 | STAIR-F - B3 TO B1 - CENTRAL BLOCK - STAIR REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Stairs Details B1- L1 | QP.E.CV.MBL.GEN.3100 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | FL | 2742 | Structural | Nesma & Partners |  |  |  |  | 2026-04-19
QF01012-NES-C04518-SDW-STR-00-CENT01-2L12800 | CENTRAL BLOCK L1 LOBBY & PLAZA SLAB GA OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L1 | 2800 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12801 | CENTRAL BLOCK L1 LOBBY & PLAZA COLUMNS AND WALLS PLAN SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2801 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12802 | CENTRAL BLOCK L1 LOBBY & PLAZA COLUMNS AND WALLS PLAN SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2802 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12803 | CENTRAL BLOCK L1 LOBBY & PLAZA COLUMNS AND WALLS PLAN SHEET 3 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2803 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12804 | CENTRAL BLOCK L1 LOBBY & PLAZA COLUMNS AND WALLS PLAN SHEET 4 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2804 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12805 | CENTRAL BLOCK L1 LOBBY & PLAZA COLUMNS AND WALLS PLAN SHEET 5 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2805 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12806 | CENTRAL BLOCK L1 LOBBY & PLAZA COLUMNS AND WALLS PLAN SHEET 6 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2806 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12807 | CENTRAL BLOCK L1 LOBBY & PLAZA SLAB GA PLAN SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2807 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12808 | CENTRAL BLOCK L1 LOBBY & PLAZA SLAB GA PLAN SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2808 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12809 | CENTRAL BLOCK L1 LOBBY & PLAZA SLAB GA PLAN SHEET 3 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2809 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12810 | CENTRAL BLOCK L1 LOBBY & PLAZA SLAB GA PLAN SHEET 4 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2810 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12811 | CENTRAL BLOCK L1 LOBBY & PLAZA SLAB GA PLAN SHEET 5 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2811 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12812 | CENTRAL BLOCK L1 LOBBY & PLAZA SLAB GA PLAN SHEET 6 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2812 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L12813 | CENTRAL BLOCK L1 LOBBY & PLAZA SLAB GA SECTIONS SHEET 1 (1/4) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 2813 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L12814 | CENTRAL BLOCK L1 LOBBY & PLAZA SLAB GA SECTIONS SHEET 2 (2/4) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 2814 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L12815 | CENTRAL BLOCK L1 LOBBY & PLAZA SLAB GA SECTIONS SHEET 3 (3/4) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 2815 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L12816 | CENTRAL BLOCK L1 LOBBY & PLAZA SLAB GA SECTIONS SHEET 4 (4/4) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Slab GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 2816 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12901 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2901 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12902 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2902 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12903 | Central Block - LEVEL 1-TOP REINFORCEMENT T1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2903 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12904 | Central Block - LEVEL 1-TOP REINFORCEMENT T2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2904 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12905 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2905 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12906 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2906 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12907 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T1 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2907 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12908 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2908 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12909 | Central Block - LEVEL 1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2909 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-01-CENT01-2L12910 | Central Block - LEVEL 1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L1 | 2910 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12911 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2911 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12912 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2912 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12913 | Central Block - LEVEL 1-TOP REINFORCEMENT T1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2913 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12914 | Central Block - LEVEL 1-TOP REINFORCEMENT T2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2914 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12915 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2915 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12916 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2916 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12917 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2917 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12918 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2918 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12919 | Central Block - LEVEL 1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2919 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L12920 | Central Block - LEVEL 1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 2920 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12921 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2921 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12922 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2922 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12923 | Central Block - LEVEL 1-TOP REINFORCEMENT T1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2923 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12924 | Central Block - LEVEL 1-TOP REINFORCEMENT T2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2924 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12925 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2925 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12926 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2926 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12927 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2927 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12928 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2928 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12929 | Central Block - LEVEL 1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2929 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L12930 | Central Block - LEVEL 1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 2930 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12931 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B1 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2931 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12932 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2932 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12933 | Central Block - LEVEL 1-TOP REINFORCEMENT T1 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2933 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12934 | Central Block - LEVEL 1-TOP REINFORCEMENT T2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2934 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12935 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B1 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2935 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12936 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2936 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12937 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T1 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2937 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12938 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2938 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12939 | Central Block - LEVEL 1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2939 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L12940 | Central Block - LEVEL 1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 2940 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12941 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2941 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12942 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2942 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12943 | Central Block - LEVEL 1-TOP REINFORCEMENT T1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2943 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12944 | Central Block - LEVEL 1-TOP REINFORCEMENT T2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2944 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12945 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2945 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12946 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2946 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12947 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T1 Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2947 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12948 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T2 Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2948 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12949 | Central Block - LEVEL 1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2949 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-08-CENT01-2L12950 | Central Block - LEVEL 1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 08 | CENT01 | 2 | L1 | 2950 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12951 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B1 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2951 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12952 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT B2 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2952 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12953 | Central Block - LEVEL 1-TOP REINFORCEMENT T1 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2953 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12954 | Central Block - LEVEL 1-TOP REINFORCEMENT T2 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2954 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12955 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B1 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2955 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12956 | Central Block - LEVEL 1-BOTTOM REINFORCEMENT ADDITIONAL B2 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2956 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12957 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T1 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2957 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12958 | Central Block - LEVEL 1-TOP REINFORCEMENT ADDITIONAL T2 Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2958 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12959 | Central Block - LEVEL 1-ADD BOTTOM REINFORCEMENT AROUND OPENING Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2959 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-09-CENT01-2L12960 | Central Block - LEVEL 1-ADD TOP REINFORCEMENT AROUND OPENING Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 09 | CENT01 | 2 | L1 | 2960 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L12961 | Central Block - LEVEL 1-SLAB SECTIONS AND DETAILS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 2961 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L12962 | CENTRAL BLOCK - LEVEL L1 SLAB REINFORCEMENT BBS - SHEET 1 OF 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 2962 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L12963 | CENTRAL BLOCK - LEVEL L1 SLAB REINFORCEMENT BBS - SHEET 2 OF 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 2963 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L12964 | CENTRAL BLOCK - LEVEL L1 SLAB REINFORCEMENT BBS - SHEET 3 OF 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 2964 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L12965 | CENTRAL BLOCK - LEVEL L1 SLAB REINFORCEMENT BBS - SHEET 4 OF 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Slab RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 2965 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-2L13000 | CENTRAL BLOCK LEVEL L1 BEAMS - KEY PLAN |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L1 | 3000 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13001 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3001 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13002 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3002 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13003 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3003 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13004 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3004 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13005 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3005 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13006 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3006 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13007 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3007 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13008 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3008 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13009 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3009 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13010 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3010 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13011 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3011 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13012 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3012 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13013 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3013 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13014 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3014 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13015 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3015 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13016 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3016 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13017 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3017 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13018 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3018 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13019 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3019 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13020 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3020 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13021 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 21 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3021 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13022 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 22 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3022 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13023 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 23 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3023 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13024 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 24 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3024 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13025 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 25 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3025 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13026 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 26 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3026 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13027 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 27 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3027 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13028 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 28 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3028 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13029 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 29 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3029 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13030 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 30 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3030 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13031 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 31 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3031 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13032 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 32 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3032 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13033 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 33 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3033 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13034 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 34 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3034 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13035 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 35 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3035 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13036 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 36 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3036 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13037 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 37 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3037 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13038 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 38 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3038 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13039 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 39 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3039 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13040 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 40 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3040 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13041 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 41 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3041 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13042 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 42 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3042 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13043 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 43 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3043 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13044 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 44 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3044 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13045 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 45 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3045 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13046 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 46 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3046 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13047 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 47 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3047 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13048 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 48 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3048 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13049 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 49 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3049 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13050 | CENTRAL BLOCK LEVEL L1 BEAMS SECTION AND REINFORCEMENT DETAILS SHEET 50 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3050 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13051 | CENTRAL BLOCK LEVEL L1 BEAMS BBS SHEET 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3051 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13052 | CENTRAL BLOCK LEVEL L1 BEAMS BBS SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3052 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13053 | CENTRAL BLOCK LEVEL L1 BEAMS BBS SHEET 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3053 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13054 | CENTRAL BLOCK LEVEL L1 BEAMS BBS SHEET 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3054 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13055 | CENTRAL BLOCK LEVEL L1 BEAMS BBS SHEET 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3055 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13056 | CENTRAL BLOCK LEVEL L1 BEAMS BBS SHEET 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3056 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13057 | CENTRAL BLOCK LEVEL L1 BEAMS BBS SHEET 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3057 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13058 | CENTRAL BLOCK LEVEL L1 BEAMS BBS SHEET 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 Beams RFT Details | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3058 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-02-CENT01-2L13101 | CENTRAL BLOCK COLUMNS KEY PLAN SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Column RFT Elevations L1-L1M | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L1 | 3101 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-05-CENT01-2L13102 | CENTRAL BLOCK COLUMNS KEY PLAN SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Column RFT Elevations L1-L1M | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L1 | 3102 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-06-CENT01-2L13103 | CENTRAL BLOCK COLUMNS KEY PLAN SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Column RFT Elevations L1-L1M | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L1 | 3103 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13104 | CENTRAL BLOCK FROM L1 UP TO L4 COLUMNS SECTIONS AND DETAILS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Column RFT Elevations L1-L1M | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3104 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13105 | CENTRAL BLOCK FROM L2 UP TO L4 COLUMNS SECTIONS AND DETAILS SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Column RFT Elevations L1-L1M | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3105 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13106 | CENTRAL BLOCK FROM L1 UP TO L4 COLUMNS SECTIONS AND DETAILS SHEET 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Column RFT Elevations L1-L1M | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3106 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13107 | CENTRAL BLOCK COLUMN RFT BBS SHEET 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Column RFT Elevations L1-L1M | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3107 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-2L13200 | CENTRAL BLOCK CORE WALLS GA KEY PLAN FROM L01 TO MIZZANINE |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L1 | 3200 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13201 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L01 TO L1MIZZ SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3201 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13202 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L01 TO L1MIZZ SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3202 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13203 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L01 TO L1MIZZ SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3203 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13204 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1 TO L1MIZZ SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3204 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13205 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1 TO L1MIZZ SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3205 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13206 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1 TO L1MIZZ SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3206 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13207 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1 TO L1MIZZ SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3207 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13208 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1 TO L1MIZZ SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3208 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13209 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1 TO L1MIZZ SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3209 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13210 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1 TO L1MIZZ SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3210 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13211 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1 TO L1MIZZ SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3211 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13212 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1 TO L1MIZZ SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3212 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13213 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1 TO L1MIZZ SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3213 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-2L13300 | CENTRAL BLOCK SHEAR WALL L1 TO L1M MEZZANINE GENERAL ARRANGEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L1 | 3300 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13301 | CENTRAL BLOCK SHEAR WALL GA ENLARGED PLAN L1 TO L1M MEZZANINE PART-1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3301 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13302 | CENTRAL BLOCK SHEAR WALL GA ENLARGED PLAN L1 TO L1M MEZZANINE PART-2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3302 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13303 | CENTRAL BLOCK SHEAR WALL GA ENLARGED PLAN L1 TO L1M MEZZANINE PART-3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3303 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13304 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1 TO L1M MEZZANINE- SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3304 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13305 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1 TO L1M MEZZANINE- SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3305 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13306 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1 TO L1M MEZZANINE- SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3306 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13307 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1 TO L1M MEZZANINE- SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3307 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13308 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1 TO L1M MEZZANINE- SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3308 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13309 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1 TO L1M MEZZANINE- SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3309 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13310 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1 TO L1M MEZZANINE- SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3310 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13311 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1 TO L1M MEZZANINE- SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3311 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13312 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1 TO L1M MEZZANINE- SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - L1 -M1 Shear Walls GA | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3312 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-2L13401 | Central Block Core Walls CW-01 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L1 | 3401 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13402 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L1MZZ Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3402 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13403 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L1MZZ Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3403 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13404 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L1MZZ Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3404 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13405 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L1MZZ Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3405 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13406 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3406 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-2L13407 | Central Block Core Walls CW-02 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L1 | 3407 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13408 | Central Block Core Walls CW-02 Reinforcement Elevation Section from L1 to MZZ Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3408 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13409 | Central Block Core Walls CW-02 Reinforcement Elevation Section from L1 to MZZ Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3409 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13410 | Central Block Core Walls CW-02 Reinforcement Elevation Section from L1 to MZZ Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3410 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13411 | Central Block Core Walls CW-02 Reinforcement Elevation Section from L1 to MZZ Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3411 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13412 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3412 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-2L13413 | Central Block Core Walls CW-03 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L1 | 3413 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13414 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to L1MZZ Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3414 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13415 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3415 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-2L13416 | Central Block Core Walls CW-04 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L1 | 3416 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13417 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L1MZZ Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3417 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13418 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L1MZZ Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3418 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13419 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L1MZZ Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3419 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13420 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Core Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3420 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-2L13500 | CENTRAL BLOCK SHEAR WALLS RFT-L1 TO L1M MEZZANINE KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L1 | 3500 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13501 | CENTRAL BLOCK SHEAR WALLS FROM L1 TO L1M MEZZANINE ENLARGED PLAN RFT SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3501 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13502 | CENTRAL BLOCK SHEAR WALLS FROM L1 TO L1M MEZZANINE ENLARGED PLAN RFT SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3502 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13503 | CENTRAL BLOCK SHEAR WALLS FROM L1 TO L1M MEZZANINE ENLARGED PLAN RFT SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3503 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13504 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3504 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13505 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO MEZZANINE SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3505 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13506 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3506 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13507 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3507 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13508 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3508 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13509 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3509 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13510 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3510 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13511 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3511 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13512 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3512 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13513 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3513 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13514 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3514 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13515 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3515 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13516 | CENTRAL BLOCK SHEAR WALLS RFT ELEVATION FROM L1 TO L1M MEZZANINE SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3516 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13517 | CENTRAL BLOCK SHEAR WALLS RFT L1 TO L1M MEZZANINE BBS SHEET- 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3517 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13518 | CENTRAL BLOCK SHEAR WALLS RFT L1 TO L1M MEZZANINE BBS SHEET-0 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3518 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13519 | CENTRAL BLOCK SHEAR WALLS RFT L1 TO L1M MEZZANINE BBS SHEET- 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3519 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13520 | CENTRAL BLOCK SHEAR WALLS RFT L1 TO L1M MEZZANINE BBS SHEET- 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Shear Walls RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3520 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13601 | STAIR-A - CENTRAL BLOCK - STAIR GA PLAN L1 TO L1M |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3601 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13602 | STAIR-A - CENTRAL BLOCK - STAIR GA PLAN L1M TO L2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3602 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13603 | STAIR-A - CENTRAL BLOCK - STAIR SECTION ELEVATION L1 TO L2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3603 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13604 | STAIR-B - CENTRAL BLOCK - STAIR GA PLAN L1 TO L1M |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3604 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13605 | STAIR-B - CENTRAL BLOCK - STAIR GA PLAN L1M TO L2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3605 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13606 | STAIR-B - CENTRAL BLOCK - STAIR SECTION ELEVATION L1 TO L2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3606 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13607 | STAIR-C - CENTRAL BLOCK - STAIR GA PLAN L1 TO L1M |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3607 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13608 | STAIR-C - CENTRAL BLOCK - STAIR GA PLAN L1M TO L2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3608 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13609 | STAIR-C - CENTRAL BLOCK - STAIR SECTION ELEVATION L1 TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3609 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13610 | STAIR-D - CENTRAL BLOCK - STAIR GA PLAN L1 TO L1M |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3610 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13611 | STAIR-D - CENTRAL BLOCK - STAIR GA PLAN L1M TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3611 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13612 | STAIR-D - CENTRAL BLOCK - STAIR SECTION ELEVATION L1 TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3612 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13613 | STAIR-A - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L1 TO L1M |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3613 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13614 | STAIR-A - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L1M TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3614 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13615 | STAIR-A - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION L1 TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3615 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13616 | STAIR A - CENTRAL BLOCK - STAIR REINFORCEMENT BBS FROM L1 TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3616 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13617 | STAIR-B - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L1 TO L1M |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3617 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13618 | STAIR-B - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L1M TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3618 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13619 | STAIR-B - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION L1 TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3619 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13620 | STAIR B - CENTRAL BLOCK - STAIR REINFORCEMENT BBS FROM L1 TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3620 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13621 | STAIR-C - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L1 TO L1M |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3621 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13622 | STAIR-C - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L1M TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3622 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13623 | STAIR-C - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION L1 TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3623 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13624 | STAIR C - CENTRAL BLOCK - STAIR REINFORCEMENT BBS FROM L1 TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3624 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13625 | STAIR-D - CENTRAL BLOCK - STAIR STAIR REINFORCEMENT PLAN L1 TO L1M |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3625 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L13626 | STAIR-D - CENTRAL BLOCK - STAIR STAIR REINFORCEMENT PLAN L1M TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L1 | 3626 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L13627 | STAIR-D - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION L1 TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L1 | 3627 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L13628 | STAIR D - CENTRAL BLOCK - STAIR REINFORCEMENT BBS FROM L1 TO L2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1 -M1 Stairs RFT | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L1 | 3628 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-2M13700 | CENTRAL BLOCK L1M MEZZANINE SLAB GA OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M GA | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | M1 | 3700 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-01-CENT01-2M13701 | CENTRAL BLOCK COLUMNS & WALLS LAYOUT - L1M MEZZANINE SHEET 1 (1/4) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M GA | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | M1 | 3701 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-02-CENT01-2M13702 | CENTRAL BLOCK COLUMNS & WALLS LAYOUT - L1M MEZZANINE SHEET 2 (2/4) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M GA | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | M1 | 3702 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-05-CENT01-2M13703 | CENTRAL BLOCK COLUMNS & WALLS LAYOUT - L1M MEZZANINE SHEET 3 (3/4) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M GA | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | M1 | 3703 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-06-CENT01-2M13704 | CENTRAL BLOCK COLUMNS & WALLS LAYOUT - L1M MEZZANINE SHEET 4 (4/4) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M GA | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | M1 | 3704 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-01-CENT01-2M13705 | CENTRAL BLOCK L1M MEZZANINE SLAB GA PLAN SHEET 1 (1/4) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M GA | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | M1 | 3705 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-02-CENT01-2M13706 | CENTRAL BLOCK L1M MEZZANINE SLAB GA PLAN SHEET 2 (2/4) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M GA | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | M1 | 3706 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-05-CENT01-2M13707 | CENTRAL BLOCK L1M MEZZANINE SLAB GA PLAN SHEET 3 (3/4) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M GA | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | M1 | 3707 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-06-CENT01-2M13708 | CENTRAL BLOCK L1M MEZZANINE SLAB GA PLAN SHEET 4 (4/4) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M GA | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | M1 | 3708 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13709 | CENTRAL BLOCK L1M MEZZANINE SLAB GA SECTIONS SHEET 1 (1/2) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M GA | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3709 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13710 | CENTRAL BLOCK L1M MEZZANINE SLAB GA SECTIONS SHEET 2 (2/2) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M GA | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3710 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-02-CENT01-2M13801 | CENTRAL BLOCK L1-MEZZ- +909M BOTTOM REINFORCEMENT B1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | M1 | 3801 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-02-CENT01-2M13802 | CENTRAL BLOCK L1-MEZZ- +909M BOTTOM REINFORCEMENT B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | M1 | 3802 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-02-CENT01-2M13803 | CENTRAL BLOCK L1-MEZZ- +909M TOP REINFORCEMENT T1 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | M1 | 3803 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-02-CENT01-2M13804 | CENTRAL BLOCK L1-MEZZ- +909M TOP REINFORCEMENT T2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | M1 | 3804 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-02-CENT01-2M13805 | CENTRAL BLOCK L1-MEZZ- +909M BOTTOM RFT ADDITIONAL B1 AND A.A.O Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | M1 | 3805 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-02-CENT01-2M13806 | CENTRAL BLOCK L1-MEZZ- +909M BOTTOM RFT ADDITIONAL B2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | M1 | 3806 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-02-CENT01-2M13807 | CENTRAL BLOCK L1-MEZZ- +909M TOP RFT ADDITIONAL T1 AND A.A.O Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | M1 | 3807 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-02-CENT01-2M13808 | CENTRAL BLOCK L1-MEZZ- +909M TOP RFT ADDITIONAL T2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | M1 | 3808 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-05-CENT01-2M13809 | CENTRAL BLOCK L1-MEZZ- +909M BOTTOM REINFORCEMENT B1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | M1 | 3809 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-05-CENT01-2M13810 | CENTRAL BLOCK L1-MEZZ- +909M BOTTOM REINFORCEMENT B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | M1 | 3810 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-05-CENT01-2M13811 | CENTRAL BLOCK L1-MEZZ- +909M TOP REINFORCEMENT T1 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | M1 | 3811 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-05-CENT01-2M13812 | CENTRAL BLOCK L1-MEZZ- +909M TOP REINFORCEMENT T2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | M1 | 3812 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-05-CENT01-2M13813 | CENTRAL BLOCK L1-MEZZ- +909M BOTTOM RFT ADDITIONAL B1 AND A.A.O Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | M1 | 3813 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-05-CENT01-2M13814 | CENTRAL BLOCK L1-MEZZ- +909M BOTTOM RFT ADDITIONAL B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | M1 | 3814 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-05-CENT01-2M13815 | CENTRAL BLOCK L1-MEZZ- +909M TOP RFT ADDITIONAL T1 AND A.A.O Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | M1 | 3815 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-05-CENT01-2M13816 | CENTRAL BLOCK L1-MEZZ- +909M TOP RFT ADDITIONAL T2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | M1 | 3816 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13817 | CENTRAL BLOCK L1-MEZZ- +909M SECTIONS AND DETAILS Sheet 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3817 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M13818 | CENTRAL BLOCK L1-MEZZ- +909M RFT BBS - Sheet 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 3818 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M13819 | CENTRAL BLOCK L1-MEZZ- +909M RFT BBS - Sheet 02 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 3819 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M13820 | CENTRAL BLOCK L1-MEZZ- +909M RFT BBS - Sheet 03 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-01 | Central - L1M Slab RFT | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 3820 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-2M13900 | CENTRAL BLOCK LEVEL L1-MEZZ BEAMS - KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | M1 | 3900 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13901 | Central Block L1-MEZZ Beams Sections and Reinforcement Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3901 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13902 | Central Block L1-MEZZ Beams Sections and Reinforcement Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3902 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13903 | Central Block L1-MEZZ Beams Sections and Reinforcement Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3903 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13904 | Central Block L1-MEZZ Beams Sections and Reinforcement Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3904 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13905 | Central Block L1-MEZZ Beams Sections and Reinforcement Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3905 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13906 | Central Block L1-MEZZ Beams Sections and Reinforcement Details Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3906 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13907 | Central Block L1-MEZZ Beams Sections and Reinforcement Details Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3907 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13908 | Central Block L1-MEZZ Beams Sections and Reinforcement Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3908 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M13909 | Central Block L1-MEZZ Beams RFT BBS - Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 3909 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M13910 | Central Block L1-MEZZ Beams RFT BBS - Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 3910 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13911 | Central Block L1 MEZZANINE UPSTAND REINFOREMENT SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3911 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13912 | Central Block L1 MEZZANINE UPSTAND REINFOREMENT SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3912 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M13913 | Central Block L1 MEZZANINE UPSTAND REINFOREMENT SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 3913 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M13914 | Central Block L1 MEZZANINE UPSTAND REINFOREMENT BBS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - L1M Beam RFT | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 3914 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-2M14000 | CENTRAL BLOCK CORE WALLS GA KEY PLAN FROM L1MIZZ TO L2 STAGE |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | M1 | 4000 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14001 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L1MIZZ TO L2 STAGE SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4001 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14002 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L1MIZZ TO L2 STAGE SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4002 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14003 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L1MIZZ TO L2 STAGE SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4003 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14004 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1MIZZ TO L2 STAGE SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4004 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14005 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1MIZZ TO L2 STAGE SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4005 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14006 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1MIZZ TO L2 STAGE SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4006 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14007 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1MIZZ TO L2 STAGE SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4007 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14008 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1MIZZ TO L2 STAGE SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4008 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14009 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1MIZZ TO L2 STAGE SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4009 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14010 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1MIZZ TO L2 STAGE SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4010 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14011 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1MIZZ TO L2 STAGE SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4011 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14012 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1MIZZ TO L2 STAGE SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4012 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14013 | CENTRAL BLOCK CORE WALLS GA ELEVATION L1MIZZ TO L2 STAGE SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4013 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-2M14101 | Central Block Core Walls CW-01 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | M1 | 4101 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14102 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4102 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14103 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4103 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14104 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L2 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4104 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14105 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L2 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4105 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M14106 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 4106 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-2M14107 | Central Block Core Walls CW-02 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | M1 | 4107 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14108 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4108 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14109 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L2 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4109 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14110 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L2 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4110 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M14111 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 4111 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-2M14112 | Central Block Core Walls CW-03 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | M1 | 4112 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14113 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to L2 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4113 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M14114 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 4114 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-2M14115 | Central Block Core Walls CW-04 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | M1 | 4115 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14116 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L02 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4116 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14117 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L02 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4117 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14118 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L02 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4118 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M14119 | CENTRAL BLOCK CORES WALLS REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Core Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 4119 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-2M14200 | CENTRAL BLOCK SHEAR WALLS L1M MEZZANINE TO L2 GENERAL ARRANGEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | M1 | 4200 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14201 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L1M MEZZANINE TO L2 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4201 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14202 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L1M MEZZANINE TO L2 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4202 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14203 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L1M MEZZANINE TO L2 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4203 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-2M14204 | CENTRAL BLOCK SHEAR WALLS L1M MEZZANINE TO L2 UPPER LEVEL GENERAL ARRANGEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | M1 | 4204 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14205 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4205 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14206 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4206 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14207 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4207 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14208 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4208 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14209 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4209 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14210 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4210 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14211 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4211 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14212 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4212 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14213 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4213 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14214 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4214 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14215 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4215 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14216 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4216 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14217 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4217 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14218 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4218 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14219 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4219 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14220 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4220 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14221 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4221 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14222 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4222 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14223 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4223 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14224 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4224 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14225 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L1M MEZZANINE TO L2 SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall GA from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4225 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-2M14300 | CENTRAL BLOCK SHEAR WALLS L1M MEZZANINE TO L2 RFT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | M1 | 4300 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14301 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L1M MEZZANINE TO L2 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4301 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14302 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L1M MEZZANINE TO L2 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4302 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14303 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L1M MEZZANINE TO L2 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4303 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-2M14304 | CENTRAL BLOCK SHEAR WALLS L1M TO L2 MEZZANINE UPPER LEVEL RFT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | M1 | 4304 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14305 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4305 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14306 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4306 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14307 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4307 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14308 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4308 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14309 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4309 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-4M14310 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L1M MEZZANINE TO L2 UPPER LEVEL PART-6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | M1 | 4310 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14311 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4311 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14312 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4312 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14313 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4313 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14314 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4314 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14315 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4315 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14316 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4316 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14317 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4317 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14318 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4318 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14319 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4319 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14320 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4320 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14321 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4321 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14322 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4322 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14323 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4323 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14324 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4324 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14325 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4325 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14326 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-01 | Central - Shear Wall RFT from L1M to L2 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4326 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14327 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 17 |  | Structure | Revit | .dwg,.pdf | 1:26 | 2026-10-22 | Central - Shear Wall RFT from L1M to L3 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4327 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14328 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 18 |  | Structure | Revit | .dwg,.pdf | 1:27 | 2026-10-22 | Central - Shear Wall RFT from L1M to L4 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4328 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-3M14329 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L1M MEZZANINE TO L2 SHEET 19 |  | Structure | Revit | .dwg,.pdf | 1:28 | 2026-10-22 | Central - Shear Wall RFT from L1M to L5 | QP.E.CV.MBL.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | M1 | 4329 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M14330 | CENTRAL BLOCK SHEAR WALLS RFT L1M MEZZANINE TO L2 BBS SHEET- 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-22 | Central - Shear Wall RFT from L1M to L6 | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 4330 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M14331 | CENTRAL BLOCK SHEAR WALLS RFT L1M MEZZANINE TO L2 BBS SHEET- 02 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-22 | Central - Shear Wall RFT from L1M to L7 | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 4331 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M14332 | CENTRAL BLOCK SHEAR WALLS RFT L1M MEZZANINE TO L2 BBS SHEET- 03 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-22 | Central - Shear Wall RFT from L1M to L8 | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 4332 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-6M14333 | CENTRAL BLOCK SHEAR WALLS RFT L1M MEZZANINE TO L2 BBS SHEET- 04 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-22 | Central - Shear Wall RFT from L1M to L9 | QP.E.CV.MBL.GEN.3140 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | M1 | 4333 | Structural | Nesma & Partners |  |  |  |  | 2026-06-08
QF01012-NES-C04518-SDW-STR-00-CENT01-2L24400 | CENTRAL BLOCK L2 SLAB GA OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L2 | 4400 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24401 | CENTRAL BLOCK L2 COLUMNS AND WALLS PLAN SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4401 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24402 | CENTRAL BLOCK L2 COLUMNS AND WALLS PLAN SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4402 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-03-CENT01-2L24403 | CENTRAL BLOCK L2 COLUMNS AND WALLS PLAN SHEET 3 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 03 | CENT01 | 2 | L2 | 4403 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-04-CENT01-2L24404 | CENTRAL BLOCK L2 COLUMNS AND WALLS PLAN SHEET 4 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 04 | CENT01 | 2 | L2 | 4404 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24405 | CENTRAL BLOCK L2 COLUMNS AND WALLS PLAN SHEET 5 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4405 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24406 | CENTRAL BLOCK L2 COLUMNS AND WALLS PLAN SHEET 6 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4406 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24407 | CENTRAL BLOCK L2 SLAB GA PLAN SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4407 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24408 | CENTRAL BLOCK L2 SLAB GA PLAN SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4408 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-03-CENT01-2L24409 | CENTRAL BLOCK L2 SLAB GA PLAN SHEET 3 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 03 | CENT01 | 2 | L2 | 4409 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-04-CENT01-2L24410 | CENTRAL BLOCK L2 SLAB GA PLAN SHEET 4 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 04 | CENT01 | 2 | L2 | 4410 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24411 | CENTRAL BLOCK L2 SLAB GA PLAN SHEET 5 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4411 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24412 | CENTRAL BLOCK L2 SLAB GA PLAN SHEET 6 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4412 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24413 | CENTRAL BLOCK L2 SLAB GA SECTIONS SHEET 1 (1/2) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4413 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24414 | CENTRAL BLOCK L2 SLAB GA SECTIONS SHEET 2 (2/2) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 GA | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4414 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24501 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT B1 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4501 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24502 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT B2 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4502 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24503 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT T1 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4503 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24504 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT T2 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4504 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24505 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT ADDITIONAL B1 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4505 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24506 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT ADDITIONAL B2 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4506 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24507 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT ADDITIONAL T1 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4507 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24508 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT ADDITIONAL T2 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4508 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24509 | CENTRAL BLOCK - LEVEL 2-ADD BOTTOM REINFORCEMENT AROUND OPENING SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4509 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L24510 | CENTRAL BLOCK - LEVEL 2-ADD TOP REINFORCEMENT AROUND OPENING SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L2 | 4510 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24511 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT B1 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4511 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24512 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT B2 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4512 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24513 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT T1 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4513 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24514 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT T2 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4514 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24515 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT ADDITIONAL B1 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4515 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24516 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT ADDITIONAL B2 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4516 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24517 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT ADDITIONAL T1 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4517 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24518 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT ADDITIONAL T2 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4518 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24519 | CENTRAL BLOCK - LEVEL 2-ADD BOTTOM REINFORCEMENT AROUND OPENING SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4519 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L24520 | CENTRAL BLOCK - LEVEL 2-ADD TOP REINFORCEMENT AROUND OPENING SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L2 | 4520 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24521 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT B1 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4521 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24522 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT B2 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4522 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24523 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT T1 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4523 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24524 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT T2 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4524 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24525 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT ADDITIONAL B1 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4525 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24526 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT ADDITIONAL B2 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4526 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24527 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT ADDITIONAL T1 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4527 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24528 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT ADDITIONAL T2 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4528 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24529 | CENTRAL BLOCK - LEVEL 2-ADD BOTTOM REINFORCEMENT AROUND OPENING SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4529 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L24530 | CENTRAL BLOCK - LEVEL 2-ADD TOP REINFORCEMENT AROUND OPENING SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L2 | 4530 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24531 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT B1 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4531 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24532 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT B2 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4532 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24533 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT T1 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4533 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24534 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT T2 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4534 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24535 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT ADDITIONAL B1 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4535 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24536 | CENTRAL BLOCK - LEVEL 2-BOTTOM REINFORCEMENT ADDITIONAL B2 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4536 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24537 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT ADDITIONAL T1 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4537 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24538 | CENTRAL BLOCK - LEVEL 2-TOP REINFORCEMENT ADDITIONAL T2 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4538 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24539 | CENTRAL BLOCK - LEVEL 2-ADD BOTTOM REINFORCEMENT AROUND OPENING SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4539 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L24540 | CENTRAL BLOCK - LEVEL 2-ADD TOP REINFORCEMENT AROUND OPENING SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L2 | 4540 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24541 | CENTRAL BLOCK - LEVEL 2-SLAB SECTIONS AND DETAILS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4541 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24542 | CENTRAL BLOCK - LEVEL 2-SLAB REINFORCEMENT BBS - SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4542 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24543 | CENTRAL BLOCK - LEVEL 2-SLAB REINFORCEMENT BBS - SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-22 | Central - L2 Slab RFT | QP.E.CV.MBL.GEN.3180 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4543 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L24600 | CENTRAL BLOCK LEVEL L2 BEAMS - KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:200 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L2 | 4600 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24601 | Central Block L2 Beams Sections and Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4601 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24602 | Central Block L2 Beams Sections and Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4602 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24603 | Central Block L2 Beams Sections and Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4603 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24604 | Central Block L2 Beams Sections and Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4604 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24605 | Central Block L2 Beams Sections and Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4605 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24606 | Central Block L2 Beams Sections and Details Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4606 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24607 | Central Block L2 Beams Sections and Details Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4607 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24608 | Central Block L2 Beams Sections and Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4608 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24609 | Central Block L2 Beams Sections and Details Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4609 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24610 | Central Block L2 Beams Sections and Details Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4610 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24611 | Central Block L2 Beams Sections and Details Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4611 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24612 | CENTRAL BLOCK LEVEL L2 BEAMS BBS SHEET 1 OF 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4612 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24613 | CENTRAL BLOCK LEVEL L2 BEAMS BBS SHEET 2 OF 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4613 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24614 | CENTRAL BLOCK LEVEL L2 BEAMS BBS SHEET 3 OF 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-22 | Central - L2 Beams RFT | QP.E.CV.MBL.GEN.3180 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4614 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L24800 | CENTRAL BLOCK SHEAR WALLS L2 TO L3 GENERAL ARRANGEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:200 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L2 | 4800 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24801 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L2 TO L3 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4801 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24802 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L2 TO L3 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4802 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24803 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L2 TO L3 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4803 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24804 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L2 TO L3 PART-4 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4804 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24805 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L2 TO L3 PART-5 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4805 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24806 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L2 TO L3 PART-6 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4806 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24807 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4807 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24808 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4808 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24809 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4809 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24810 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4810 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24811 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4811 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24812 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4812 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24813 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4813 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24814 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4814 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24815 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4815 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24816 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4816 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24817 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4817 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24818 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4818 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24819 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4819 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24820 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4820 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24821 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L2 TO L3 SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4821 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L24822 | CENTRAL BLOCK SHEAR WALLS L2 TO L3 REINFORCEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L2 | 4822 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24823 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L2 TO L3 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4823 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24824 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L2 TO L3 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4824 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24825 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L2 TO L3 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4825 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24826 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L2 TO L3 PART-4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4826 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24827 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L2 TO L3 PART-5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4827 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24828 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L2 TO L3 PART-6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4828 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24829 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4829 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24830 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4830 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24831 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4831 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24832 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4832 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24833 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4833 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24834 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4834 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24835 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4835 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24836 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4836 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24837 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4837 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24838 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4838 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24839 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4839 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24840 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4840 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24841 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4841 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24842 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4842 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24843 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4843 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24844 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4844 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24845 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4845 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24846 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4846 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24847 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION FROM L2 TO L3 SHEET 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4847 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24848 | CENTRAL BLOCK SHEAR WALLS RFT L2 TO L3 BBS SHEET- 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4848 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24849 | CENTRAL BLOCK SHEAR WALLS RFT L2 TO L3 BBS SHEET- 02 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-22 | Central - Shear Walls RFT from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4849 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L24900 | CENTRAL BLOCK CORE WALLS GA KEY PLAN FROM L2 STAGE TO L3 STALLS MEZZANINE |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L2 | 4900 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24901 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L2 STAGE TO L3 STALLS MEZZANINE SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4901 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24902 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L2 STAGE TO L3 STALLS MEZZANINE SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4902 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24903 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L2 STAGE TO L3 STALLS MEZZANINE SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4903 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24904 | CENTRAL BLOCK CORE WALLS GA ELEVATION L2 STAGE TO L3 STALLS MEZZANINE SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4904 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24905 | CENTRAL BLOCK CORE WALLS GA ELEVATION L2 STAGE TO L3 STALLS MEZZANINE SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4905 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24906 | CENTRAL BLOCK CORE WALLS GA ELEVATION L2 STAGE TO L3 STALLS MEZZANINE SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4906 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24907 | CENTRAL BLOCK CORE WALLS GA ELEVATION L2 STAGE TO L3 STALLS MEZZANINE SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4907 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24908 | CENTRAL BLOCK CORE WALLS GA ELEVATION L2 STAGE TO L3 STALLS MEZZANINE SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4908 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24909 | CENTRAL BLOCK CORE WALLS GA ELEVATION L2 STAGE TO L3 STALLS MEZZANINE SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4909 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24910 | CENTRAL BLOCK CORE WALLS GA ELEVATION L2 STAGE TO L3 STALLS MEZZANINE SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4910 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24911 | CENTRAL BLOCK CORE WALLS GA ELEVATION L2 STAGE TO L3 STALLS MEZZANINE SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4911 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24912 | CENTRAL BLOCK CORE WALLS GA ELEVATION L2 STAGE TO L3 STALLS MEZZANINE SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4912 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24913 | CENTRAL BLOCK CORE WALLS GA ELEVATION L2 STAGE TO L3 STALLS MEZZANINE SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Cores GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4913 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L24914 | CW01 Central Block Core Walls CW-01 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L2 | 4914 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24915 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L3 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4915 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24916 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L3 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4916 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24917 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L3 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4917 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24918 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L3 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4918 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24919 | CENTRAL BLOCK CORE WALL CW-01 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4919 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L24920 | Central Block Core Walls CW-02 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L2 | 4920 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24921 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L3 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4921 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24922 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L3 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4922 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24923 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L3 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4923 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24924 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L3 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4924 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24925 | CENTRAL BLOCK CORE WALL CW-02 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4925 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L24926 | Central Block Core Walls CW-03 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L2 | 4926 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24927 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to L3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4927 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24928 | CENTRAL BLOCK CORE WALL CW-03 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4928 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L24929 | Central Block Core Walls CW-04 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L2 | 4929 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24930 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L3 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4930 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24931 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L3 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4931 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24932 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L3 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4932 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24933 | CENTRAL BLOCK CORE WALL CW-04 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 |  | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4933 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L25001 | STAIR-A - CENTRAL BLOCK - STAIR GA PLAN L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair GA from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 5001 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L25002 | STAIR-A - CENTRAL BLOCK - STAIR SECTION ELEVATION L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair GA from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 5002 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L25003 | STAIR-B - CENTRAL BLOCK - STAIR GA PLAN L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair GA from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 5003 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L25004 | STAIR-B - CENTRAL BLOCK - STAIR SECTION ELEVATION L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair GA from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 5004 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L25005 | STAIR-C - CENTRAL BLOCK - STAIR GA PLAN L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair GA from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 5005 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L25006 | STAIR-C - CENTRAL BLOCK - STAIR SECTION ELEVATION L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair GA from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 5006 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L25007 | STAIR-D - CENTRAL BLOCK - STAIR GA PLAN L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair GA from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 5007 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L25008 | STAIR-D - CENTRAL BLOCK - STAIR SECTION ELEVATION L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair GA from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 5008 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L25009 | STAIR A - CENTRAL BLOCK - STAIR RFT PLAN L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 5009 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L25010 | STAIR A - CENTRAL BLOCK - STAIR SECTION ELEVATION RFT L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 5010 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L25011 | STAIR A - CENTRAL BLOCK - STAIR REINFORCEMENT BBS FROM L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 5011 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L25012 | STAIR B - CENTRAL BLOCK - STAIR RFT PLAN L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 5012 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L25013 | STAIR B - CENTRAL BLOCK - STAIR SECTION ELEVATION RFT L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-22 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 5013 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L25014 | STAIR B - CENTRAL BLOCK - STAIR REINFORCEMENT BBS FROM L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 5014 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L25015 | STAIR C - CENTRAL BLOCK - STAIR RFT PLAN L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 5015 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L25016 | STAIR C - CENTRAL BLOCK - STAIR SECTION ELEVATION RFT L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 5016 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L25017 | STAIR C - CENTRAL BLOCK - STAIR REINFORCEMENT BBS FROM L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 5017 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-4L25018 | STAIR D - CENTRAL BLOCK - STAIR RFT PLAN L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 5018 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-3L25019 | STAIR D - CENTRAL BLOCK - STAIR SECTION ELEVATION RFT L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 5019 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-6L25020 | STAIR D - CENTRAL BLOCK - STAIR REINFORCEMENT BBS FROM L2 TO L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Stair RFT from L2 to L4 | QP.E.CV.MBL.GEN.3120 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 5020 | Structural | Nesma & Partners |  |  |  |  | 2026-05-18
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35101 | Central Block L3- STALL MEZZANINE Plan Col & Axes Plan Overall |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5101 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-01-CENT01-2L35102 | Central Block L3- STALL MEZZANINE Plan Col & Axes Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L3 | 5102 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-02-CENT01-2L35103 | Central Block L3- STALL MEZZANINE Plan Col & Axes Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L3 | 5103 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-03-CENT01-2L35104 | Central Block L3- STALL MEZZANINE Plan Col & Axes Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 03 | CENT01 | 2 | L3 | 5104 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-04-CENT01-2L35105 | Central Block L3- STALL MEZZANINE Plan Col & Axes Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 04 | CENT01 | 2 | L3 | 5105 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-05-CENT01-2L35106 | Central Block L3- STALL MEZZANINE Plan Col & Axes Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L3 | 5106 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-06-CENT01-2L35107 | Central Block L3- STALL MEZZANINE Plan Col & Axes Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L3 | 5107 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35108 | Central Block L3- STALL MEZZANINE +917.5M Overall Plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5108 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-01-CENT01-2L35109 | Central Block L3- STALL MEZZANINE +917.5M Plan Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L3 | 5109 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-02-CENT01-2L35110 | Central Block L3- STALL MEZZANINE +917.5M Plan Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L3 | 5110 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-03-CENT01-2L35111 | Central Block L3- STALL MEZZANINE +917.5M Plan Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 03 | CENT01 | 2 | L3 | 5111 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-04-CENT01-2L35112 | Central Block L3- STALL MEZZANINE +917.5M Plan Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 04 | CENT01 | 2 | L3 | 5112 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-05-CENT01-2L35113 | Central Block L3- STALL MEZZANINE +917.5M Plan Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L3 | 5113 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-06-CENT01-2L35114 | Central Block L3- STALL MEZZANINE +917.5M Plan Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L3 | 5114 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35115 | CENTRAL BLOCK L3 SLAB GA SECTIONS SHEET 1 (1/1) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - L3 STALL MEZZANINE GA | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5115 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35200 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:150 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5200 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-01-CENT01-2L35201 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC BOTTOM SLAB REINFORCEMENT B1 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L3 | 5201 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-01-CENT01-2L35202 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC BOTTOM SLAB REINFORCEMENT B2 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L3 | 5202 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-01-CENT01-2L35203 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC TOP SLAB REINFORCEMENT T1 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L3 | 5203 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-01-CENT01-2L35204 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC TOP SLAB REINFORCEMENT T2 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L3 | 5204 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-02-CENT01-2L35205 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC BOTTOM SLAB REINFORCEMENT B1 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L3 | 5205 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-02-CENT01-2L35206 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC BOTTOM SLAB REINFORCEMENT B2 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L3 | 5206 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-02-CENT01-2L35207 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC TOP SLAB REINFORCEMENT T1 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L3 | 5207 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-02-CENT01-2L35208 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC TOP SLAB REINFORCEMENT T2 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L3 | 5208 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-05-CENT01-2L35209 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC BOTTOM SLAB REINFORCEMENT B1 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L3 | 5209 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-05-CENT01-2L35210 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC BOTTOM SLAB REINFORCEMENT B2 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L3 | 5210 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-05-CENT01-2L35211 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC TOP SLAB REINFORCEMENT T1 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L3 | 5211 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-05-CENT01-2L35212 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC TOP SLAB REINFORCEMENT T2 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L3 | 5212 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-05-CENT01-2L35213 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC ADD. TOP SLAB REINFORCEMENT T1 & T2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L3 | 5213 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-06-CENT01-2L35214 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC BOTTOM SLAB REINFORCEMENT B1 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L3 | 5214 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-06-CENT01-2L35215 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC BOTTOM SLAB REINFORCEMENT B2 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L3 | 5215 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-06-CENT01-2L35216 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC TOP SLAB REINFORCEMENT T1 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L3 | 5216 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-06-CENT01-2L35217 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC TOP SLAB REINFORCEMENT T2 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L3 | 5217 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-06-CENT01-2L35218 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC ADD. BOTTOM SLAB REINF. B1 & B2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L3 | 5218 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-06-CENT01-2L35219 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC ADD. TOP SLAB REINF. T1 & T2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L3 | 5219 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-06-CENT01-2L35220 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC ADD. BOT. SLAB REINF. AROUND OPENING SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L3 | 5220 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-06-CENT01-2L35221 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC ADD. TOP SLAB REINF. AROUND OPENING SHEET 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L3 | 5221 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-01-CENT01-2L35222 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC METAL DECK DOWEL BAR REINF. PLAN T1 & T2 - SHEET 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L3 | 5222 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-02-CENT01-2L35223 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC METAL DECK DOWEL BAR REINF. PLAN T1 & T2 - SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L3 | 5223 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-05-CENT01-2L35224 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC METAL DECK DOWEL BAR REINF. PLAN T1 & T2 - SHEET 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L3 | 5224 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35225 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC SLAB SECTIONS AND DETAILS SHEET 1/2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5225 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35226 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC SLAB SECTIONS AND DETAILS SHEET 2/2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5226 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35227 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC SLAB BBS SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5227 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35228 | CENTRAL BLOCK L3- STALL MEZZANINE +917.5M RC SLAB BBS SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 STALL MEZZANINE Slab RFT | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5228 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35301 | CENTRAL BLOCK LEVEL 3 BEAMS - KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5301 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35302 | CENTRAL BLOCK LEVEL 3 BEAMS SECTION AND DETAILS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5302 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35303 | CENTRAL BLOCK LEVEL 3 BEAMS SECTION AND DETAILS SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5303 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35304 | CENTRAL BLOCK LEVEL 3 BEAMS SECTION AND DETAILS SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5304 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35305 | CENTRAL BLOCK LEVEL 3 BEAMS SECTION AND DETAILS SHEET 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5305 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35306 | CENTRAL BLOCK LEVEL 3 BEAMS SECTION AND DETAILS SHEET 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5306 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35307 | CENTRAL BLOCK LEVEL 3 BEAMS SECTION AND DETAILS SHEET 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5307 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35308 | CENTRAL BLOCK LEVEL 3 BEAMS SECTION AND DETAILS SHEET 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5308 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35309 | CENTRAL BLOCK LEVEL 3 BEAMS SECTION AND DETAILS SHEET 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5309 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35310 | CENTRAL BLOCK LEVEL 3 BEAMS SECTION AND DETAILS SHEET 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5310 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35311 | CENTRAL BLOCK LEVEL L3 BEAMS BBS SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5311 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35312 | CENTRAL BLOCK LEVEL L3 BEAMS BBS SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - L3 Beams RFT | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5312 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35400 | CENTRAL BLOCK SHEAR WALLS L3 TO L4 GENERAL ARRANGEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5400 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35401 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L3 TO L4 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5401 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35402 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L3 TO L4 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5402 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35403 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L3 TO L4 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5403 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35404 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L3 TO L4 PART-4 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5404 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35405 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L3 TO L4 PART-5 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5405 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35406 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L3 TO L4 PART-6 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5406 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35407 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5407 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35408 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5408 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35409 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5409 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35410 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5410 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35411 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5411 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35412 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5412 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35413 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5413 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35414 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5414 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35415 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATIONL3 TO L4 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5415 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35416 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5416 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35417 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5417 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35418 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5418 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35419 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATIONL3 TO L4 SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5419 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35420 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5420 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35421 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L3 TO L4 SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5421 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35422 | CENTRAL BLOCK CORE WALLS GA KEY PLAN FROM L3 STAGE TO L4 1ST CIRCLE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5422 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35423 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L3 STALLS TO L4 1ST CIRCLE SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5423 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35424 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L3 STALLS TO L4 1ST CIRCLE SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5424 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35425 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L3 STALLS TO L4 1ST CIRCLE SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5425 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35426 | CENTRAL BLOCK CORE WALLS GA ELEVATION L3 STALLS MEZZ TO L4 1ST CIRCLE SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5426 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35427 | CENTRAL BLOCK CORE WALLS GA ELEVATION L3 STALLS MEZZ TO L4 1ST CIRCLE SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5427 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35428 | CENTRAL BLOCK CORE WALLS GA ELEVATION L3 STALLS MEZZ TO L4 1ST CIRCLE SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5428 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35429 | CENTRAL BLOCK CORE WALLS GA ELEVATION L3 STALLS MEZZ TO L4 1ST CIRCLE SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5429 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35430 | CENTRAL BLOCK CORE WALLS GA ELEVATION L3 STALLS MEZZ TO L4 1ST CIRCLE SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5430 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35431 | CENTRAL BLOCK CORE WALLS GA ELEVATION L3 STALLS MEZZ TO L4 1ST CIRCLE SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5431 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35432 | CENTRAL BLOCK CORE WALLS GA ELEVATION L3 STALLS MEZZ TO L4 1ST CIRCLE SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5432 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35433 | CENTRAL BLOCK CORE WALLS GA ELEVATION L3 STALLS MEZZ TO L4 1ST CIRCLE SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5433 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35434 | CENTRAL BLOCK CORE WALLS GA ELEVATION L3 STALLS MEZZ TO L4 1ST CIRCLE SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5434 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35435 | CENTRAL BLOCK CORE WALLS GA ELEVATION L3 STALLS MEZZ TO L4 1ST CIRCLE SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores Walls GA from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5435 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35501 | Central Block Core Walls CW-01 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5501 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35502 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L4 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5502 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35503 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L4 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5503 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35504 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L4 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5504 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35505 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L4 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5505 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35506 | CENTRAL BLOCK CORE WALL CW-01 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5506 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35507 | Central Block Core Walls CW-02 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5507 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35508 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L4 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5508 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35509 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L4 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5509 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35510 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L4 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5510 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35511 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L4 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5511 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35512 | CENTRAL BLOCK CORE WALL CW-02 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5512 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35513 | Central Block Core Walls CW-03 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5513 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35514 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to L4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5514 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35515 | CENTRAL BLOCK CORE WALL CW-03 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5515 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35516 | Central Block Core Walls CW-04 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5516 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35517 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L4 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5517 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35518 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L4 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5518 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35519 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L4 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5519 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35520 | CENTRAL BLOCK CORE WALL CW-04 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Cores RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5520 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L35521 | CENTRAL BLOCK SHEAR WALLS L3 TO L4 REINFORCEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L3 | 5521 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35522 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L3 TO L4 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5522 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35523 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L3 TO L4 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5523 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35524 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L3 TO L4 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5524 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35525 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L3 TO L4 PART-4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5525 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35526 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L3 TO L4 PART-5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5526 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35527 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L3 TO L4 PART-6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5527 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35528 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5528 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35529 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5529 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35530 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5530 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35531 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5531 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35532 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5532 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35533 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5533 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35534 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5534 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35535 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5535 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35536 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5536 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35537 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5537 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35538 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5538 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35539 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5539 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35540 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5540 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L35541 | Central Block up to L4 Shear Walls RFT Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L3 | 5541 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35542 | CENTRAL BLOCK SHEAR WALLS RFT L3 TO L4 BBS SHEET- 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5542 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35543 | CENTRAL BLOCK SHEAR WALLS RFT L3 TO L4 BBS SHEET- 02 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5543 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35544 | Central Block up to L4 Cores & Shear Walls RFT BBS - Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5544 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35545 | Central Block up to L4 Cores & Shear Walls RFT BBS - Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5545 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35546 | Central Block up to L4 Cores & Shear Walls RFT BBS - Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5546 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35547 | Central Block up to L4 Cores & Shear Walls RFT BBS - Sheet 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5547 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35548 | Central Block up to L4 Cores & Shear Walls RFT BBS - Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Shear Walls RFT from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5548 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35601 | Central Block L3- STALL MEZZANINE +917.5M Stairs Sections and Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs Details from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5601 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35602 | Central Block L3- STALL MEZZANINE +917.5M Stairs Sections and Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs Details from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5602 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35603 | Central Block L3- STALL MEZZANINE +917.5M Stairs Sections and Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs Details from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5603 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L35604 | Central Block L3- STALL MEZZANINE +917.5M Stairs Sections and Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs Details from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L3 | 5604 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L35605 | L3- STALL MEZZANINE +917.5M Stairs RFT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Stairs Details from L3 to L4 | QP.E.CV.MBL.GEN.3220 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L3 | 5605 | Structural | Nesma & Partners |  |  |  |  | 2026-08-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L45701 | CENTRAL BLOCK L4 COL & AXES PLAN OVERALL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L4 | 5701 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-01-CENT01-2L45702 | CENTRAL BLOCK L4 COLUMNS AND WALLS PLAN SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L4 | 5702 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-02-CENT01-2L45703 | CENTRAL BLOCK L4 COLUMNS AND WALLS PLAN SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L4 | 5703 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-03-CENT01-2L45704 | CENTRAL BLOCK L4 COLUMNS AND WALLS PLAN SHEET 3 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 03 | CENT01 | 2 | L4 | 5704 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-04-CENT01-2L45705 | CENTRAL BLOCK L4 COLUMNS AND WALLS PLAN SHEET 4 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 04 | CENT01 | 2 | L4 | 5705 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-05-CENT01-2L45706 | CENTRAL BLOCK L4 COLUMNS AND WALLS PLAN SHEET 5 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L4 | 5706 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-06-CENT01-2L45707 | CENTRAL BLOCK L4 COLUMNS AND WALLS PLAN SHEET 6 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L4 | 5707 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L45708 | CENTRAL BLOCK L4 SLAB GA OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L4 | 5708 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-01-CENT01-2L45709 | CENTRAL BLOCK L4 SLAB GA PLAN PART 1 SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L4 | 5709 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-02-CENT01-2L45710 | CENTRAL BLOCK L4 SLAB GA PLAN PART 1 SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L4 | 5710 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-03-CENT01-2L45711 | CENTRAL BLOCK L4 SLAB GA PLAN PART 1 SHEET 3 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 03 | CENT01 | 2 | L4 | 5711 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-04-CENT01-2L45712 | CENTRAL BLOCK L4 SLAB GA PLAN PART 1 SHEET 4 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 04 | CENT01 | 2 | L4 | 5712 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-05-CENT01-2L45713 | CENTRAL BLOCK L4 SLAB GA PLAN PART 1 SHEET 5 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L4 | 5713 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-06-CENT01-2L45714 | CENTRAL BLOCK L4 SLAB GA PLAN PART 1 SHEET 6 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L4 | 5714 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L45715 | CENTRAL BLOCK L4 SLAB GA SECTIONS SHEET 1 (1/1) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 GA plan | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 5715 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L45800 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L4 | 5800 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-01-CENT01-2L45801 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC BOTTOM SLAB REINFORCEMENT B1 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L4 | 5801 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-01-CENT01-2L45802 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC BOTTOM SLAB REINFORCEMENT B2 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L4 | 5802 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-01-CENT01-2L45803 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC TOP SLAB REINFORCEMENT T1 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L4 | 5803 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-01-CENT01-2L45804 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC TOP SLAB REINFORCEMENT T2 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L4 | 5804 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-02-CENT01-2L45805 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC BOTTOM SLAB REINFORCEMENT B1 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L4 | 5805 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-02-CENT01-2L45806 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC BOTTOM SLAB REINFORCEMENT B2 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L4 | 5806 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-02-CENT01-2L45807 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC TOP SLAB REINFORCEMENT T1 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L4 | 5807 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-02-CENT01-2L45808 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC TOP SLAB REINFORCEMENT T2 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L4 | 5808 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-02-CENT01-2L45809 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC ADD. BOTTOM SLAB REINFORCEMENT AROUND OPENING SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L4 | 5809 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-05-CENT01-2L45810 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC BOTTOM SLAB REINFORCEMENT B1 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L4 | 5810 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-05-CENT01-2L45811 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC BOTTOM SLAB REINFORCEMENT B2 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L4 | 5811 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-05-CENT01-2L45812 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC TOP SLAB REINFORCEMENT T1 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L4 | 5812 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-05-CENT01-2L45813 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC TOP SLAB REINFORCEMENT T2 SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L4 | 5813 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-05-CENT01-2L45814 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC ADD. BOTTOM SLAB REINFORCEMENT B1 & B2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L4 | 5814 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-05-CENT01-2L45815 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC ADD. TOP SLAB REINFORCEMENT T1 & T2 Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L4 | 5815 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-06-CENT01-2L45816 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC BOTTOM SLAB REINFORCEMENT B1 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L4 | 5816 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-06-CENT01-2L45817 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC BOTTOM SLAB REINFORCEMENT B2 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L4 | 5817 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-06-CENT01-2L45818 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC TOP SLAB REINFORCEMENT T1 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L4 | 5818 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-06-CENT01-2L45819 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC TOP SLAB REINFORCEMENT T2 SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L4 | 5819 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-06-CENT01-2L45820 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC ADD. BOTTOM SLAB REINFORCEMENT B1 & B2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L4 | 5820 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-06-CENT01-2L45821 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC ADD. TOP SLAB REINFORCEMENT T1 & T2 Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L4 | 5821 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-01-CENT01-2L45822 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC METAL DECK DOWEL BAR REINF. PLAN T1 & T2 - SHEET 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L4 | 5822 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-02-CENT01-2L45823 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC METAL DECK DOWEL BAR REINF. PLAN T1 & T2 - SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L4 | 5823 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-05-CENT01-2L45824 | CENTRAL BLOCK L4 - 1ST CIRCLE +921.0M RC METAL DECK DOWEL BAR REINF. PLAN T1 & T2 - SHEET 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L4 | 5824 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L45825 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC SLAB SECTIONS AND DETAILS SHEET 1/2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 5825 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L45826 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC SLAB SECTIONS AND DETAILS SHEET 2/2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 5826 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L45827 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC SLAB BBS SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_90_76 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 5827 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L45828 | CENTRAL BLOCK L4- 1ST CIRCLE +921.0M RC SLAB BBS SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - L4 Slab RFT | QP.E.CV.MBL.GEN.3240 | FI_90_77 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 5828 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L45900 | CENTRAL BLOCK L4- FIRST CIRCLE +921M RC BEAMS - KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:150 | 2026-11-19 | Central - L4 Beam RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L4 | 5900 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L45901 | CENTRAL BLOCK L4- FIRST CIRCLE +921M RC BEAMS SECTION AND DETAILS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - L4 Beam RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 5901 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L45902 | CENTRAL BLOCK L4- FIRST CIRCLE +921M RC BEAMS SECTION AND DETAILS SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Central - L4 Beam RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 5902 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L45903 | CENTRAL BLOCK L4- FIRST CIRCLE +921M RC BEAMS SECTION AND DETAILS SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-06-24 | Central - L4 Beam RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 5903 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L45904 | CENTRAL BLOCK L4- FIRST CIRCLE +921M RC BEAMS SECTION AND DETAILS SHEET 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-06-24 | Central - L4 Beam RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 5904 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L45905 | CENTRAL BLOCK L4- FIRST CIRCLE +921M RC BEAMS SECTION AND DETAILS SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-06-24 | Central - L4 Beam RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 5905 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L45906 | CENTRAL BLOCK L4- FIRST CIRCLE +921M RC BEAMS BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - L4 Beam RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 5906 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L45907 | CENTRAL BLOCK L4- FIRST CIRCLE +921M RC BEAMS BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - L4 Beam RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 5907 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L45908 | Central Block-L4-FIRST CIRCLE +921M RC Beams Sections and Details Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - L4 Beam RFT | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 5908 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L45909 | Central Block-L4-FIRST CIRCLE +921M RC Beams RFT BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - L4 Beam RFT | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 5909 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L45910 | Central Block-L4-FIRST CIRCLE +921M RC Beams RFT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - L4 Beam RFT | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 5910 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L46100 | CENTRAL BLOCK SHEAR WALLS L4 TO L5 GENERAL ARRANGEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L4 | 6100 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46101 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L4 TO L5 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6101 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46102 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L4 TO L5 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6102 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46103 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L4 TO L5 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6103 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46104 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L4 TO L5 PART-4 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6104 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46105 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L4 TO L5 PART-5 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6105 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46106 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L4 TO L5 PART-6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6106 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46107 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6107 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46108 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6108 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46109 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6109 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46110 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6110 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46111 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6111 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46112 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6112 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46113 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6113 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46114 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6114 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46115 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6115 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46116 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6116 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46117 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6117 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46118 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6118 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46119 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6119 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46120 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6120 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46121 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION L4 TO L5 SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6121 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L46122 | CENTRAL BLOCK SHEAR WALLS L4 TO L5 REINFORCEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L4 | 6122 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46123 | Central Block Up to L5 Shear Walls RFT plan 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6123 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46124 | Central Block Up to L5 Shear Walls RFT plan 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6124 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46125 | Central Block Up to L5 Shear Walls RFT plan 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6125 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46126 | Central Block Up to L5 Shear Walls RFT plan 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6126 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46127 | Central Block Up to L5 Shear Walls RFT plan 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6127 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46128 | Central Block Up to L5 Shear Walls RFT plan 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6128 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46129 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6129 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46130 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6130 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46131 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6131 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46132 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6132 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46133 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6133 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46134 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6134 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46135 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6135 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46136 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6136 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46137 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6137 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46138 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6138 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46139 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6139 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46140 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6140 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46141 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6141 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46142 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6142 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46143 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6143 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46144 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6144 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46145 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6145 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46146 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6146 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46147 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6147 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46148 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6148 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46149 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 21 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6149 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46150 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 22 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6150 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46151 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 23 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6151 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46152 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 24 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6152 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46153 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 25 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6153 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46154 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 26 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6154 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46155 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 27 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6155 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46156 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 28 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6156 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46157 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 29 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6157 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46158 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 30 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6158 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46159 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 31 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6159 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46160 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 32 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6160 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46161 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 33 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6161 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46162 | Central Block Up to L5 Shear Walls RFT Section Elevation Sheet 34 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6162 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46163 | Central Block Up to L5 Shear Walls RFT BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6163 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46164 | Central Block Up to L5 Shear Walls RFT BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6164 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46165 | Central Block Up to L5 Shear Walls RFT BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Shear Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6165 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L46201 | CENTRAL BLOCK CORE WALLS GA KEY PLAN FROM L4 1ST CIRCLE TO L5 LOFT |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L4 | 6201 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46202 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L4 1ST CIRCLE TO L5 LOFT SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6202 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46203 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L4 1ST CIRCLE TO L5 LOFT SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6203 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46204 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L4 1ST CIRCLE TO L5 LOFT SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6204 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46205 | CENTRAL BLOCK CORE WALLS GA ELEVATION L4 1ST CIRCLE TO L5 LOFT SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6205 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46206 | CENTRAL BLOCK CORE WALLS GA ELEVATION L4 1ST CIRCLE TO L5 LOFT SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6206 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46207 | CENTRAL BLOCK CORE WALLS GA ELEVATION L4 1ST CIRCLE TO L5 LOFT SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6207 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46208 | CENTRAL BLOCK CORE WALLS GA ELEVATION L4 1ST CIRCLE TO L5 LOFT SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6208 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46209 | CENTRAL BLOCK CORE WALLS GA ELEVATION L4 1ST CIRCLE TO L5 LOFT SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6209 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46210 | CENTRAL BLOCK CORE WALLS GA ELEVATION L4 1ST CIRCLE TO L5 LOFT SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6210 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46211 | CENTRAL BLOCK CORE WALLS GA ELEVATION L4 1ST CIRCLE TO L5 LOFT SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6211 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46212 | CENTRAL BLOCK CORE WALLS GA ELEVATION L4 1ST CIRCLE TO L5 LOFT SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6212 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46213 | CENTRAL BLOCK CORE WALLS GA ELEVATION L4 1ST CIRCLE TO L5 LOFT SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6213 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46214 | CENTRAL BLOCK CORE WALLS GA ELEVATION L4 1ST CIRCLE TO L5 LOFT SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls GA From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6214 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L46215 | Central Block Core Walls CW-01 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L4 | 6215 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46216 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L5 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6216 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46217 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L5 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6217 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46218 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L5 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6218 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46219 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L5 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6219 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46220 | CENTRAL BLOCK CORE WALL CW-01 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6220 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L46221 | Central Block Core Walls CW-02 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L4 | 6221 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46222 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L5 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6222 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46223 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L5 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6223 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46224 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L5 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6224 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46225 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L5 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6225 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46226 | CENTRAL BLOCK CORE WALL CW-02 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6226 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L46227 | Central Block Core Walls CW-03 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L4 | 6227 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46228 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to L5 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6228 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46229 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to L5 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6229 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46230 | CENTRAL BLOCK CORE WALL CW-03 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6230 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L46231 | Central Block Core Walls CW-04 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L4 | 6231 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46232 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L5 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6232 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46233 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L5 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6233 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46234 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L5 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6234 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46235 | CENTRAL BLOCK CORE WALL CW-04 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central -Core Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6235 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46236 | Central Block Up to L5 Shear Walls RFT Sections and Details Sheet 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6236 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46237 | Central Block Up to L5 Core & Shear Walls RFT BBS - Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6237 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46238 | Central Block Up to L5 Core & Shear Walls RFT BBS - Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6238 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46239 | Central Block Up to L5 Core & Shear Walls RFT BBS - Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6239 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46240 | Central Block Up to L5 Core & Shear Walls RFT BBS - Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6240 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46241 | Central Block Up to L5 Core & Shear Walls RFT BBS - Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6241 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46242 | Central Block Up to L5 Core & Shear Walls RFT BBS - Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6242 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46243 | Central Block Up to L5 Core & Shear Walls RFT BBS - Sheet 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6243 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46244 | Central Block Up to L5 Core & Shear Walls RFT BBS - Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Walls RFT From L4 to L5 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6244 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46245 | STAIR-A - CENTRAL BLOCK - STAIR GA PLAN L4 TO L5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs GA From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6245 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46246 | STAIR-A - CENTRAL BLOCK - STAIR GA PLAN L5 TO L6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs GA From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6246 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46247 | STAIR-A - CENTRAL BLOCK - STAIR SECTION ELEVATION L4 TO L6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs GA From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6247 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46248 | STAIR-B - CENTRAL BLOCK - STAIR GA PLAN L4 TO L5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs GA From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6248 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46249 | STAIR-B - CENTRAL BLOCK - STAIR GA PLAN L5 TO L6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Stairs GA From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6249 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46250 | STAIR-B - CENTRAL BLOCK - STAIR SECTION ELEVATION L4 TO L6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Stairs GA From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6250 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46251 | STAIR-C - CENTRAL BLOCK - STAIR GA PLAN L4 TO L6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Stairs GA From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6251 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46252 | STAIR-C - CENTRAL BLOCK - STAIR SECTION ELEVATION L4 TO L6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Stairs GA From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6252 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46253 | STAIR-D - CENTRAL BLOCK - STAIR GA PLAN L4 TO L5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Stairs GA From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6253 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46254 | STAIR-D - CENTRAL BLOCK - STAIR GA PLAN L5 TO L6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Stairs GA From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6254 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46255 | STAIR-D - CENTRAL BLOCK - STAIR SECTION ELEVATION L4 TO L6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Stairs GA From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6255 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46256 | STAIR A - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L4 TO L5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6256 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46257 | STAIR A - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L5 TO L6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6257 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46258 | STAIR A - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION L4 TO L6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6258 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46259 | STAIR A - CENTRAL BLOCK - L4 TO L6 - STAIR REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-19 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6259 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46260 | STAIR B - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L4 TO L5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6260 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46261 | STAIR B - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L5 TO L6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6261 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46262 | STAIR B - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION L4 TO L6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-19 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6262 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46263 | STAIR B - CENTRAL BLOCK - L4 TO L6 - STAIR REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6263 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46264 | STAIR C - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L4 TO L5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6264 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46265 | STAIR C - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L5 TO L6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6265 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46266 | STAIR C - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION L4 TO L6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6266 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46267 | STAIR C - CENTRAL BLOCK - L4 TO L6 - STAIR REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6267 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46268 | STAIR D - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L4 TO L5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6268 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-4L46269 | STAIR D - CENTRAL BLOCK - STAIR REINFORCEMENT PLAN L5 TO L6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L4 | 6269 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-3L46270 | STAIR D - CENTRAL BLOCK - STAIR REINFORCEMENT SECTION ELEVATION L4 TO L6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L4 | 6270 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-6L46271 | STAIR D - CENTRAL BLOCK - L4 TO L6 - STAIR REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Stairs RFT From L4 to L6 | QP.E.CV.MBL.GEN.3240 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L4 | 6271 | Structural | Nesma & Partners |  |  |  |  | 2026-09-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L56301 | CENTRAL BLOCK L5 COL & AXES OVERALL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L5 | 6301 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L56302 | CENTRAL BLOCK L5 COL & AXES PART PLAN SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L5 | 6302 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L56303 | CENTRAL BLOCK L5 COL & AXES PART PLAN SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L5 | 6303 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-03-CENT01-2L56304 | CENTRAL BLOCK L5 COL & AXES PART PLAN SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 03 | CENT01 | 2 | L5 | 6304 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-04-CENT01-2L56305 | CENTRAL BLOCK L5 COL & AXES PART PLAN SHEET 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 04 | CENT01 | 2 | L5 | 6305 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L56306 | CENTRAL BLOCK L5 COL & AXES PART PLAN SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L5 | 6306 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L56307 | CENTRAL BLOCK L5 COL & AXES PART PLAN SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L5 | 6307 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L56308 | CENTRAL BLOCK L5 SLAB GA OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L5 | 6308 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L56309 | CENTRAL BLOCK L5 SLAB GA PART PLAN SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L5 | 6309 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L56310 | CENTRAL BLOCK L5 SLAB GA PART PLAN SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L5 | 6310 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-03-CENT01-2L56311 | CENTRAL BLOCK L5 SLAB GA PART PLAN SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 03 | CENT01 | 2 | L5 | 6311 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-04-CENT01-2L56312 | CENTRAL BLOCK L5 SLAB GA PART PLAN SHEET 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 04 | CENT01 | 2 | L5 | 6312 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L56313 | CENTRAL BLOCK L5 SLAB GA PART PLAN SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L5 | 6313 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L56314 | CENTRAL BLOCK L5 SLAB GA PART PLAN SHEET 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L5 | 6314 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56315 | CENTRAL BLOCK L5 SLAB GA SECTION SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6315 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L56401 | CENTRAL BLOCK L5.5 COL & AXES PLAN OVERALL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L5 | 6401 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L56402 | CENTRAL BLOCK L5.5 COLUMNS AND WALLS PLAN SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L5 | 6402 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L56403 | CENTRAL BLOCK L5.5 COLUMNS AND WALLS PLAN SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L5 | 6403 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-03-CENT01-2L56404 | CENTRAL BLOCK L5.5 COLUMNS AND WALLS PLAN SHEET 3 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 03 | CENT01 | 2 | L5 | 6404 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-04-CENT01-2L56405 | CENTRAL BLOCK L5.5 COLUMNS AND WALLS PLAN SHEET 4 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 04 | CENT01 | 2 | L5 | 6405 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L56406 | CENTRAL BLOCK L5.5 COLUMNS AND WALLS PLAN SHEET 5 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L5 | 6406 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L56407 | CENTRAL BLOCK L5.5 COLUMNS AND WALLS PLAN SHEET 6 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L5 | 6407 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L56408 | CENTRAL BLOCK L5.5 SLAB GA OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L5 | 6408 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-01-CENT01-2L56409 | CENTRAL BLOCK L5.5 SLAB GA PLAN PART 1 SHEET 1 (1/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 01 | CENT01 | 2 | L5 | 6409 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-02-CENT01-2L56410 | CENTRAL BLOCK L5.5 SLAB GA PLAN PART 2 SHEET 2 (2/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 02 | CENT01 | 2 | L5 | 6410 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-03-CENT01-2L56411 | CENTRAL BLOCK L5.5 SLAB GA PLAN PART 3 SHEET 3 (3/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 03 | CENT01 | 2 | L5 | 6411 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-04-CENT01-2L56412 | CENTRAL BLOCK L5.5 SLAB GA PLAN PART 4 SHEET 4 (4/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 04 | CENT01 | 2 | L5 | 6412 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-05-CENT01-2L56413 | CENTRAL BLOCK L5.5 SLAB GA PLAN PART 5 SHEET 5 (5/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 05 | CENT01 | 2 | L5 | 6413 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-06-CENT01-2L56414 | CENTRAL BLOCK L5.5 SLAB GA PLAN PART 6 SHEET 6 (6/6) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 06 | CENT01 | 2 | L5 | 6414 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56415 | CENTRAL BLOCK L5.5 SLAB GA SECTION SHEET 1(1/1) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Central - L5.5 - GA | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6415 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56501 | Central Block - L5.5 RC Slab Reinforcement |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L5.5 Slab RFT | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6501 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56502 | Central Block - L5.5 RC Slab Reinforcement |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L5.5 Slab RFT | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6502 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56503 | Central Block - L5.5 RC Slab Reinforcement |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L5.5 Slab RFT | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6503 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56504 | Central Block - L5.5 RC Beams Sections and Details |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - L5.5 Slab RFT | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6504 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56505 | Central Block - L5.5 Slab RFT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - L5.5 Slab RFT | QP.E.CV.MBL.GEN.3260 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6505 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L56600 | CENTRAL BLOCK SHEAR WALLS L5 TO L6 GENERAL ARRANGEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L5 | 6600 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56601 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L5 TO L6 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6601 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56602 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L5 TO L6 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6602 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56603 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L5 TO L6 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6603 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56604 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L5 TO L6 PART-4 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6604 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56605 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L5 TO L6 PART-5 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6605 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56606 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L5 TO L6 PART-6 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6606 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56607 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW1 L5 TO L6 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6607 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56608 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW1 L5 TO L6 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6608 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56609 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW1 L5 TO L6 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6609 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56610 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW2 L5 TO L6 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6610 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56611 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW2 L5 TO L6 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6611 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56612 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW2 L5 TO L6 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6612 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56613 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW2 L5 TO L6 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6613 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56614 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW3 L5 TO L6 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6614 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56615 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW3 L5 TO L6 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6615 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56616 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW3 L5 TO L6 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6616 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56617 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW3 L5 TO L6 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6617 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56618 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW4 L5 TO L6 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6618 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56619 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW4 L5 TO L6 SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6619 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L56620 | CENTRAL BLOCK SHEAR WALLS L5 TO L6 REINFORCEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L5 | 6620 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56621 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L5 TO L6 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6621 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56622 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L5 TO L6 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6622 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56623 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L5 TO L6 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6623 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56624 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L5 TO L6 PART-4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6624 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56625 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L5 TO L6 PART-5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6625 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56626 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L5 TO L6 PART-6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6626 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56627 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L5 TO L6 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6627 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56628 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L5 TO L6 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6628 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56629 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L5 TO L6 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6629 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56630 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L5 TO L6 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6630 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56631 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L5 TO L6 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6631 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56632 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L5 TO L6 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6632 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56633 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L5 TO L6 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6633 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56634 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW2 L5 TO L6 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6634 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56635 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW2 L5 TO L6 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6635 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56636 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW2 L5 TO L6 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6636 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56637 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW2 L5 TO L6 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6637 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56638 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW2 L5 TO L6 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6638 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56639 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW2 L5 TO L6 SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6639 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56640 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW2 L5 TO L6 SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6640 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56641 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW2 L5 TO L6 SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6641 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56642 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW2 L5 TO L6 SHEET 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6642 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56643 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW3 L5 TO L6 SHEET 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6643 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56644 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW3 L5 TO L6 SHEET 18 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6644 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56645 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW3 L5 TO L6 SHEET 19 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6645 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56646 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW3 L5 TO L6 SHEET 20 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6646 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56647 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW3 L5 TO L6 SHEET 21 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6647 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56648 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW3 L5 TO L6 SHEET 22 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6648 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56649 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW3 L5 TO L6 SHEET 23 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6649 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56650 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW3 L5 TO L6 SHEET 24 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6650 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56651 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW4 L5 TO L6 SHEET 25 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6651 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56652 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW4 L5 TO L6 SHEET 26 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6652 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56653 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW4 L5 TO L6 SHEET 27 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6653 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56654 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW4 L5 TO L6 SHEET 28 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6654 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56655 | CENTRAL BLOCK SHEAR WALLS RFT L5 TO L6 BBS SHEET- 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6655 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56656 | CENTRAL BLOCK SHEAR WALLS RFT L5 TO L6 BBS SHEET- 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6656 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L56701 | CENTRAL BLOCK CORE WALLS GA KEY PLAN FROM L5 LOFT TO L6 SKY GARDN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L5 | 6701 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56702 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L5 LOFT TO L6 SKY GARDN SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6702 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56703 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L5 LOFT TO L6 SKY GARDN SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6703 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L56704 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN FROM L5 LOFT TO L6 SKY GARDN SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L5 | 6704 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56705 | CENTRAL BLOCK CORE WALLS GA ELEVATION L5 LOFT TO L6 SKY GARDN SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6705 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56706 | CENTRAL BLOCK CORE WALLS GA ELEVATION L5 LOFT TO L6 SKY GARDN SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6706 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56707 | CENTRAL BLOCK CORE WALLS GA ELEVATION L5 LOFT TO L6 SKY GARDN SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6707 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56708 | CENTRAL BLOCK CORE WALLS GA ELEVATION L5 LOFT TO L6 SKY GARDN SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6708 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56709 | CENTRAL BLOCK CORE WALLS GA ELEVATION L5 LOFT TO L6 SKY GARDN SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6709 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56710 | CENTRAL BLOCK CORE WALLS GA ELEVATION L5 LOFT TO L6 SKY GARDN SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6710 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56711 | CENTRAL BLOCK CORE WALLS GA ELEVATION L5 LOFT TO L6 SKY GARDN SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6711 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56712 | CENTRAL BLOCK CORE WALLS GA ELEVATION L5 LOFT TO L6 SKY GARDN SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6712 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56713 | CENTRAL BLOCK CORE WALLS GA ELEVATION L5 LOFT TO L6 SKY GARDN SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6713 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56714 | CENTRAL BLOCK CORE WALLS GA ELEVATION L5 LOFT TO L6 SKY GARDN SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6714 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56715 | CENTRAL BLOCK CORE WALLS GA ELEVATION L5 LOFT TO L6 SKY GARDN SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6715 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L56715 | Central Block Core Walls CW-01 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Core Walls GA From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L5 | 6715 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56716 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L6 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6716 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56717 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L6 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6717 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56718 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L6 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6718 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56719 | Central Block Core Walls CW-01 Reinforcement Elevation SECTION Up to L6 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6719 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56720 | CENTRAL BLOCK CORE WALL CW-01 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6720 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L56721 | Central Block Core Walls CW-02 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L5 | 6721 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56722 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L6 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6722 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56723 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L6 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6723 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56724 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L6 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6724 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56725 | Central Block Core Walls CW-02 Reinforcement Elevation SECTION Up to L6 Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6725 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56726 | CENTRAL BLOCK CORE WALL CW-02 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6726 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L56727 | Central Block Core Walls CW-03 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L5 | 6727 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56728 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to L6 SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6728 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56729 | Central Block Core Walls CW-03 Reinforcement Elevation SECTION Up to L6 SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6729 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56730 | CENTRAL BLOCK CORE WALL CW-03 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6730 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L56731 | Central Block Core Walls CW-04 Reinforcement Plan |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L5 | 6731 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56732 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L6 Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6732 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56733 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L6 Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6733 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56734 | Central Block Core Walls CW-04 Reinforcement Elevation SECTION Up to L6 Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6734 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56735 | CENTRAL BLOCK CORE WALL CW-04 REINFORCEMENT BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6735 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L56736 | Central Block - Shear Wall RFT Elevations From L5 to L6- Sheet 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L5 | 6736 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56737 | Central Block - Cores & Shear Wall RFT BBS From L5 to L6 - Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6737 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56738 | Central Block - Cores & Shear Wall RFT BBS From L5 to L6 - Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6738 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56739 | Central Block - Cores & Shear Wall RFT BBS From L5 to L6 - Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6739 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56740 | Central Block - Cores & Shear Wall RFT BBS From L5 to L6 - Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6740 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56741 | Central Block - Cores & Shear Wall RFT BBS From L5 to L6 - Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6741 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56742 | Central Block - Cores & Shear Wall RFT BBS From L5 to L6 - Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6742 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56743 | Central Block - Cores & Shear Wall RFT BBS From L5 to L6 - Sheet 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6743 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L56744 | Central Block - Cores & Shear Wall RFT BBS From L5 to L6 - Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-05 | Central - Walls FRT From L5 to L6 | QP.E.CV.MBL.GEN.3260 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L5 | 6744 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-2L66801 | CENTRAL BLOCK GA CORE WALLS KEY PLAN L6 SKY GARDEN B |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3260 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L6 | 6801 | Structural | Nesma & Partners |  |  |  |  | 2026-10-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66802 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN L6 SKY GARDEN |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6802 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66803 | CENTRAL BLOCK CORE WALLS GA ENLARGED PLAN L8 SIGNATURE RESTAURANT |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6803 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66804 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW1 L6 TO L8 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6804 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66805 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW1 L6 TO L8 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6805 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66806 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW1 L6 TO L8 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6806 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66807 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW1 L6 TO L8 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6807 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66808 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW1 L6 TO L8 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6808 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66809 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW1 L6 TO L8 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6809 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66810 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW2 L6 TO L8 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6810 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66811 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW2 L6 TO L8 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6811 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66812 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW2 L6 TO L8 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6812 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66813 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW2 L6 TO L8 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6813 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66814 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW2 L6 TO L8 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6814 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66815 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW4 L6 TO L8 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6815 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66816 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW4 L6 TO L8 SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6816 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66817 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW4 L6 TO L8 SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6817 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66818 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW4 L6 TO L8 SHEET 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6818 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66819 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW4 L6 TO L8 SHEET 16 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6819 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66820 | CENTRAL BLOCK CORE WALLS GA SECTION ELEVATION CW4 L6 TO L8 SHEET 17 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6820 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66821 | Central Block - Cores Wall GA Elevations From L6 to L8 - Sheet 15 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6821 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66822 | Central Block - Shear Wall GA Elevations From L6 to L8- Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6822 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66823 | Central Block - Shear Wall GA Elevations From L6 to L8- Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6823 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66824 | Central Block - Shear Wall GA Elevations From L6 to L8- Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6824 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66825 | Central Block - Shear Wall GA Elevations From L6 to L8- Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3300 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6825 | Structural | Nesma & Partners |  |  |  |  | 2027-04-13
QF01012-NES-C04518-SDW-STR-00-CENT01-2L66900 | CENTRAL BLOCK SHEAR WALLS L6 TO L8 GENERAL ARRANGEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:150 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L6 | 6900 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66901 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L6 TO L8 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6901 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66902 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L6 TO L8 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6902 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66903 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L6 TO L8 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6903 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66904 | CENTRAL BLOCK SHEAR WALLS GA ENLARGED PLAN L6 TO L8 PART-4 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6904 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66905 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW1 L6 TO L8 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6905 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66906 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW1 L6 TO L8 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6906 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66907 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW1 L6 TO L8 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6907 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66908 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW1 L6 TO L8 SHEET 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6908 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66909 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW1 L6 TO L8 SHEET 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6909 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66910 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW2 L6 TO L8 SHEET 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6910 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66911 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW2 L6 TO L8 SHEET 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6911 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66912 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW3 L6 TO L8 SHEET 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6912 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66913 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW3 L6 TO L8 SHEET 09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6913 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66914 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW4 L6 TO L8 SHEET 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6914 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66915 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW4 L6 TO L8 SHEET 11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6915 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66916 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW4 L6 TO L8 SHEET 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6916 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66917 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW4 L6 TO L8 SHEET 13 |  | Structure | Revit | .dwg,.pdf | 1:26 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6917 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66918 | CENTRAL BLOCK SHEAR WALLS GA SECTION ELEVATION SW4 L6 TO L8 SHEET 14 |  | Structure | Revit | .dwg,.pdf | 1:27 | 2026-11-05 | Central - Walls GA From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6918 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-2L66919 | CENTRAL BLOCK SHEAR WALLS L6 TO L8 REINFORCEMENT KEY PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L6 | 6919 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66920 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L6 TO L8 PART-1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6920 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66921 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L6 TO L8 PART-2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6921 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66922 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L6 TO L8 PART-3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6922 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66923 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L6 TO L8 PART-4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-05 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6923 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66924 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L6 TO L8 PART-5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6924 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-4L66925 | CENTRAL BLOCK SHEAR WALLS RFT ENLARGED PLAN L6 TO L8 PART-6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L6 | 6925 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66926 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6926 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66927 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 02 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6927 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66928 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 03 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6928 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66929 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 04 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6929 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66930 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 05 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6930 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66931 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 06 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6931 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66932 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 07 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6932 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66933 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 08 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6933 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0101 | BLADE 1 COLUMN & AXES PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Foundation GA | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0101 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0102 | BLADE 1 FOUNDATION GA PLAN - PART 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Foundation GA | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0102 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0103 | BLADE 1 FOUNDATION GA PLAN - PART 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Foundation GA | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0103 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0104 | BLADE 1 - FOUNDATION SECTION DETAILS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Foundation GA | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0104 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0201 | BLADE 1 FOUNDATION BOTTOM REINFORCEMENT PLAN-B1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0201 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0202 | BLADE 1 FOUNDATION BOTTOM REINFORCEMENT PLAN-B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0202 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0203 | BLADE 1 FOUNDATION TOP REINFORCEMENT PLAN-T1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0203 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0204 | BLADE 1 FOUNDATION TOP REINFORCEMENT PLAN-T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0204 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0205 | BLADE 1 FOUNDATION BOTTOM ADDITIONAL REINFORCEMENT PLAN-B3,B5 & B7 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0205 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0206 | BLADE 1 FOUNDATION BOTTOM ADDITIONAL REINFORCEMENT PLAN-B4,B6 & B8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0206 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0207 | BLADE 1 FOUNDATION TOP ADDITIONAL REINFORCEMENT PLAN-T3 & T5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0207 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0208 | BLADE 1 FOUNDATION TOP ADDITIONAL REINFORCEMENT PLAN-T4 & T6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0208 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0209 | BLADE 1 FOUNDATION RFT SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0209 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0210 | BLADE 1 FOUNDATION RFT BBS - SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0210 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0211 | BLADE 1 FOUNDATION RFT BBS - SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0211 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0212 | BLADE 1 FOUNDATION REINFORCEMENT PLAN-SHEAR LINK & SIDE BAR |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0212 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0213 | BLADE 1 COLUMN STARTER BAR PLANS & SECTIONS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0213 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0214 | BLADE 1 WALL STARTER BAR PLANS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0214 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0215 | BLADE 1 WALL STARTER BAR ELEVATIONS & SECTIONS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0215 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0216 | BLADE 1 COLUMN & WALL STARTER BAR BBS SHEET 1 OF 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0216 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0217 | BLADE 1 FOUNDATION ADDITIONAL U BAR REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0217 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0218 | BLADE 1 FOUNDATION ADDITIONAL U BAR REINFORCEMENT SECTION DETAILS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Foundation RFT | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0218 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0301 | BLADE 1 COLUMN REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Column RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0301 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0302 | BLADE 1 COLUMN REINFORCEMENT ELEVATIONS AND SECTIONS -SHEET 1 OF 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Column RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0302 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0303 | BLADE 1 COLUMN REINFORCEMENT ELEVATIONS AND SECTIONS -SHEET 2 OF 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Column RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0303 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0304 | BLADE 1 COLUMN REINFORCEMENT ELEVATIONS AND SECTIONS -SHEET 3 OF 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Column RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0304 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0305 | BLADE 1 COLUMN REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Column RFT | QP.E.CV.BL1.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0305 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0401 | BLADE 1 - RETAINING WALL PLAN (PART-01) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0401 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0402 | BLADE 1 - RETAINING WALL PLAN (PART-02) |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0402 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0403 | BLADE 1 - RETAINING WALL ELEVATION & SECTION - SHEET 1 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0403 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0404 | BLADE 1 - RETAINING WALL ELEVATION & SECTION - SHEET 2 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0404 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0405 | BLADE 1 - RETAINING WALL ELEVATION & SECTION - SHEET 3 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0405 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0406 | BLADE 1 - RETAINING WALL ELEVATION & SECTION - SHEET 4 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0406 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0407 | BLADE 1 - RETAINING WALL ELEVATION & SECTION - SHEET 5 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0407 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0408 | BLADE 1 - RETAINING WALL ELEVATION & SECTION - SHEET 6 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0408 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0409 | BLADE 1 - RETAINING WALL ELEVATION & SECTION - SHEET 7 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0409 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0410 | BLADE 1 - RETAINING WALL ELEVATION & SECTION - SHEET 8 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0410 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0411 | BLADE 1 - RETAINING WALL ELEVATION & SECTION - SHEET 9 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0411 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0412 | BLADE 1 - RETAINING WALL ELEVATION & SECTION - SHEET 10 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0412 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0413 | BLADE 1 - RETAINING WALL REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0413 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0414 | BLADE 1 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 1 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0414 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0415 | BLADE 1 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 2 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0415 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0416 | BLADE 1 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 3 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0416 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0417 | BLADE 1 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 4 OF 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0417 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0418 | BLADE 1 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 5 OF 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0418 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0419 | BLADE 1 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 6 OF 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0419 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0420 | BLADE 1 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 7 OF 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0420 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0421 | BLADE 1 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 8 OF 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0421 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0422 | BLADE 1 - RETAINING WALL BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0422 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0423 | BLADE 1 - RETAINING WALL BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0423 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0424 | BLADE 1 - GENERAL ARRANGEMENT SLAB PLAN EL.893.86m |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-08 | Blade 1 - Walls RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0424 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0425 | BLADE 1 - EXTERIOR WALL ELEVATION & SECTION SHEET 1 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0425 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0426 | BLADE 1 - EXTERIOR WALL ELEVATION & SECTION SHEET 2 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0426 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0427 | BLADE 1 - EXTERIOR WALL ELEVATION & SECTION SHEET 3 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0427 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0428 | BLADE 1 - EXTERIOR WALL ELEVATION & SECTION SHEET 4 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0428 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0429 | BLADE 1 - EXTERIOR WALL ELEVATION & SECTION SHEET 5 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0429 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0430 | BLADE 1 - EXTERIOR WALL ELEVATION & SECTION SHEET 6 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0430 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0431 | BLADE 1 - EXTERIOR WALL ELEVATION & SECTION SHEET 7 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0431 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0432 | BLADE 1 - EXTERIOR WALL ELEVATION & SECTION SHEET 8 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0432 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0433 | BLADE 1 EXTERNAL STAIR & EXTERNAL WALL KEY PLANS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0433 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0434 | BLADE 1 EXTERNAL STAIR REINFORCEMENT SECTIONS - SHEET 1 OF 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0434 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0435 | BLADE 1 EXTERNAL STAIR REINFORCEMENT SECTIONS - SHEET 2 OF 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0435 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0436 | BLADE 1 EXTERNAL STAIR REINFORCEMENT SECTIONS - SHEET 3 OF 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0436 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0437 | BLADE 1 EXTERNAL STAIR REINFORCEMENT SECTIONS - SHEET 4 OF 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0437 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0438 | BLADE 1 EXTERNAL STAIR REINFORCEMENT SECTIONS - SHEET 5 OF 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0438 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0439 | BLADE 1 EXTERNAL WALL REINFORCEMENT ELEVATIONS AND SECTIONS - SHEET 1 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0439 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0440 | BLADE 1 EXTERNAL WALL REINFORCEMENT ELEVATIONS AND SECTIONS - SHEET 2 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0440 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0441 | BLADE 1 EXTERNAL WALL REINFORCEMENT ELEVATIONS AND SECTIONS - SHEET 3 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0441 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0442 | BLADE 1 EXTERNAL WALL REINFORCEMENT ELEVATIONS AND SECTIONS - SHEET 4 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0442 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0443 | BLADE 1 EXTERNAL WALL REINFORCEMENT ELEVATIONS AND SECTIONS - SHEET 5 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0443 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0444 | BLADE 1 EXTERNAL WALL REINFORCEMENT ELEVATIONS AND SECTIONS - SHEET 6 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0444 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0445 | BLADE 1 EXTERNAL WALL REINFORCEMENT ELEVATIONS AND SECTIONS - SHEET 7 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0445 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0446 | BLADE 1 EXTERNAL WALL REINFORCEMENT ELEVATIONS AND SECTIONS - SHEET 8 OF 8 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0446 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0447 | BLADE 1 EXTERNAL STAIR REINFORCEMENT BBS - SHEET 1 OF 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0447 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0448 | BLADE 1 EXTERNAL STAIR REINFORCEMENT BBS - SHEET 2 OF 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0448 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0449 | BLADE 1 EXTERNAL STAIR REINFORCEMENT BBS - SHEET 3 OF 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0449 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0450 | BLADE 1 EXTERNAL STAIR REINFORCEMENT BBS - SHEET 4 OF 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0450 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0451 | BLADE 1 EXTERNAL WALL REINFORCEMENT BBS - SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0451 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0452 | BLADE 1 EXTERNAL WALL REINFORCEMENT BBS - SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 -EXTERIOR WALL GA | QP.E.CV.BL1.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0452 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0461 | BLADE 1 - TANK ROOM PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -Tank Room GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0461 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0462 | BLADE 1 - TANK ROOM WALL ELEVATIONS & SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -Tank Room GA | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0462 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-2FL0463 | BLADE 1 - TANK ROOM REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -Tank Room RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | FL | 0463 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-3FL0464 | BLADE 1 - TANK ROOM REINFORCEMNT ELEVATIONS & SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-10-08 | Blade 1 -Tank Room RFT | QP.E.CV.BL1.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 3 | FL | 0464 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-6FL0465 | BLADE 1 - TANK ROOM REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Blade 1 -Tank Room RFT | QP.E.CV.BL1.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 6 | FL | 0465 | Structural | Nesma & Partners |  |  |  |  | 2026-06-04
QF01012-NES-C04518-SDW-STR-00-BLAD01-2000601 | Blade 1 Slabs GA Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Blade 1 - GA Plans | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | 00 | 0601 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2000602 | Blade 1 Slabs GA Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Blade 1 - GA Plans | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | 00 | 0602 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2000603 | Blade 1 Slabs GA Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Blade 1 - GA Plans | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | 00 | 0603 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2000604 | Blade 1 Slabs GA Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Blade 1 - GA Plans | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | 00 | 0604 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2000605 | Blade 1 Slabs GA Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Blade 1 - GA Plans | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | 00 | 0605 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2000606 | Blade 1 Slabs GA Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Blade 1 - GA Plans | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | 00 | 0606 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2000607 | Blade 1 Slabs GA Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Blade 1 - GA Plans | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | 00 | 0607 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2000608 | Blade 1 Slabs GA Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Blade 1 - GA Plans | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | 00 | 0608 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD01-2000609 | Blade 1 Slabs GA Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-07 | Blade 1 - GA Plans | QP.E.CV.BL1.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD01 | 2 | 00 | 0609 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0101 | BLADE 2 - WALL & COLUMN AXES PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Foundation GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0101 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0102 | BLADE 2 - FOUNDATION PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Foundation GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0102 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0103 | BLADE 2- FOUNDATION SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Foundation GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0103 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0201 | BLADE 2 FOUNDATION BOTTOM REINFORCEMENT PLAN-B1 & B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0201 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0202 | BLADE2 FOUNDATION TOP REINFORCEMENT PLAN-T1 & T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0202 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0203 | BLADE 2 FOUNDATION BOTTOM ADDNL REINFORCEMENT PLAN-B3,B4,B5,B6,B7 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0203 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0204 | BLADE 2 FOUNDATION TOP REINFORCEMENT PLAN ADDITIONAL T3,T4 &T6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0204 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0205 | BLADE 2 FOUNDATION REINFORCEMENT PLAN-SHEAR LINK & SIDE BAR |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0205 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0206 | BLADE 2 FOUNDATION REINFORCEMENT SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0206 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0207 | BLADE 2 WALL STARTER BAR PLAN & ELEVATIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0207 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0208 | BLADE 2 WALL STARTER BAR SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0208 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-6FL0209 | BLADE 2 WALL STARTER BAR BBS SHEET 1 OF 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 6 | FL | 0209 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-6FL0210 | BLADE 2 FOUNDATION BBS - SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 6 | FL | 0210 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-6FL0211 | BLADE 2 FOUNDATION BBS - SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 6 | FL | 0211 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0212 | BLADE 2 FOUNDATION ADDITIONAL REINFORCEMENT PLAN & SECTIONS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Blade 2 - Foundation RFT | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0212 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0401 | BLADE 2 - RETANING WALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0401 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0402 | BLADE 2 - RETAINING WALL ELEVATION & SECTION - SHEET 1 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0402 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0403 | BLADE 2 - RETAINING WALL ELEVATION & SECTION - SHEET 2 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0403 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0404 | BLADE 2 - RETAINING WALL ELEVATION & SECTION - SHEET 3 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0404 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0405 | BLADE 2 - RETAINING WALL ELEVATION & SECTION - SHEET 4 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0405 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0406 | BLADE 2 - RETAINING WALL ELEVATION & SECTION - SHEET 5 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0406 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0407 | BLADE 2 - RETAINING WALL ELEVATION & SECTION - SHEET 6 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0407 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0408 | BLADE 2 RETINING WALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0408 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0409 | Blades 2-Walls Elevation RFT sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0409 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0410 | Blades 2-Walls Elevation RFT sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0410 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0411 | Blades 2-Walls Elevation RFT sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0411 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0412 | Blades 2-Walls Elevation RFT sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0412 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-6FL0413 | BLADE 2 - RETAINING WALL BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 6 | FL | 0413 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0414 | BLADE 2 - GENERAL ARRANGEMENT SLAB PLAN EL.882.00m |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0414 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0415 | BLADE 2 - EXTERIOR WALL ELEVATION & SECTION - SHEET 1 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0415 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0416 | BLADE 2 - EXTERIOR WALL ELEVATION & SECTION - SHEET 2 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0416 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0417 | BLADE 2 - EXTERIOR WALL ELEVATION & SECTION - SHEET 3 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0417 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0418 | BLADE 2 - EXTERIOR WALL ELEVATION & SECTION - SHEET 4 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0418 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0419 | BLADE 2 - EXTERIOR WALL ELEVATION & SECTION - SHEET 5 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0419 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0420 | BLADE 2 - EXTERIOR WALL ELEVATION & SECTION - SHEET 6 OF 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0420 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0421 | BLADE 2 - EXTERIOR SLAB & STAIR PLAN EL.882.00m |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0421 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0422 | BLADE 2 - EXTERIOR SLAB & STAIR SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0422 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0423 | BLADE 2 - EXTERIOR WALL REINFORCEMENT ELEVATIONS & SECTIONS - SHEET 1 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0423 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0424 | BLADE 2 - EXTERIOR WALL REINFORCEMENT ELEVATIONS & SECTIONS - SHEET 2 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0424 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0425 | BLADE 2 - EXTERIOR WALL REINFORCEMENT ELEVATIONS & SECTIONS - SHEET 3 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0425 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0426 | BLADE 2 - EXTERIOR WALL REINFORCEMENT ELEVATIONS & SECTIONS - SHEET 4 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0426 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0427 | BLADE 2 - EXTERIOR WALL REINFORCEMENT ELEVATIONS & SECTIONS - SHEET 5 OF 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0427 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0428 | BLADE 2 - EXTERIOR WALL REINFORCEMENT ELEVATIONS & SECTIONS - SHEET 6 OF 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0428 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-6FL0429 | BLADE 2 - EXTERIOR SLAB & STAIR REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 6 | FL | 0429 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-6FL0430 | BLADE 2 - EXTERIOR WALL REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 6 | FL | 0430 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0431 | BLADE 2 - TANK ROOM PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0431 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0432 | BLADE 2 - TANK ROOM ELEVATIONS & SECTIONS SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0432 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0433 | BLADE 2 - TANK ROOM ELEVATIONS & SECTIONS SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0433 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0434 | BLADE 2 - INTERNAL WALL REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0434 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0435 | BLADE 2 - INTERNAL WALL REINFORCEMENT ELEVATIONS & SECTIONS - SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0435 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-3FL0436 | BLADE 2 - INTERNAL WALL REINFORCEMENT ELEVATIONS & SECTIONS - SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 3 | FL | 0436 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0437 | BLADE 2 - TANK SLAB REINFORCEMENT PLANS - B1 & B2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0437 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0438 | BLADE 2 - TANK SLAB REINFORCEMENT PLANS - T1 & T2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0438 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-2FL0439 | BLADE 2 - TANK SLAB ADDITIONAL REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | FL | 0439 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-6FL0440 | BLADE 2 - INTERNAL WALL REINFORCEMET BBS - SHEET 1 OF 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 6 | FL | 0440 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-6FL0441 | BLADE 2 - TANK SLAB REINFORCEMENT BBS - SHEET 1 OF 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | Blade 2 - Walls GA & RFT | QP.E.CV.BL2.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 6 | FL | 0441 | Structural | Nesma & Partners |  |  |  |  | 2026-05-11
QF01012-NES-C04518-SDW-STR-00-BLAD02-2000601 | Blade 2 Slabs GA Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-01 | Blade 2 - Plans GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | 00 | 0601 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2000602 | Blade 2 Slabs GA Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-01 | Blade 2 - Plans GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | 00 | 0602 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2000603 | Blade 2 Slabs GA Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-01 | Blade 2 - Plans GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | 00 | 0603 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2000604 | Blade 2 Slabs GA Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-01 | Blade 2 - Plans GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | 00 | 0604 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2000605 | Blade 2 Slabs GA Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-01 | Blade 2 - Plans GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | 00 | 0605 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2000606 | Blade 2 Slabs GA Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-01 | Blade 2 - Plans GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | 00 | 0606 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2000607 | Blade 2 Slabs GA Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-01 | Blade 2 - Plans GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | 00 | 0607 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2000608 | Blade 2 Slabs GA Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-01 | Blade 2 - Plans GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | 00 | 0608 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD02-2000609 | Blade 2 Slabs GA Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-01 | Blade 2 - Plans GA | QP.E.CV.BL2.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD02 | 2 | 00 | 0609 | Structural | Nesma & Partners |  |  |  |  | 2026-03-28
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0101 | Blade 3 Column & axes |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Foundation GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0101 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0102 | Blade 3 Foundation Plan Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Foundation GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0102 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0103 | Blade 3 Foundation Section Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - Foundation GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0103 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0201 | BLADE 3 - COLUMN REINFORCEMENT PLAN - STARTER BAR |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0201 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0202 | BLADE 3 - COLUMN REINFORCEMENT SECTIONS - STARTER BAR |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0202 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0203 | BLADE 3 - WALL REINFORCEMENT PLAN-STARTER BAR |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0203 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0204 | BLADE 3 - WALL STARTER BAR SECTION-SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0204 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0205 | BLADE 3 - WALL STARTER BAR SECTION-SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0205 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0206 | BLADE 3 - FOUNDATION BOTTOM REINFORCEMENT PLAN B1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0206 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0207 | BLADE 3 - FOUNDATION BOTTOM REINFORCEMENT PLAN B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0207 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0208 | BLADE 3 - FOUNDATION TOP REINFORCEMENT PLAN T1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0208 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0209 | BLADE 3 - FOUNDATION TOP REINFORCEMENT PLAN T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0209 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0210 | BLADE 3 - FOUNDATION BOTTOM ADD REINFORCEMENT PLAN B3 & B5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0210 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0211 | BLADE 3 - FOUNDATION BOTTOM ADD REINFORCEMENT PLAN B4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0211 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0212 | BLADE 3 - FOUNDATION TOP ADD REINFORCEMENT PLAN T3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0212 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0213 | BLADE 3 - FOUNDATION TOP ADD REINFORCEMENT PLAN T4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0213 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0214 | BLADE 3 - FOUNDATION REINFORCEMENT PLAN - SHEAR LINK & SIDE BAR |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0214 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0215 | BLADE 3 - FOUNDATION REINFORCEMENT SECTIONS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0215 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-6FL0216 | BLADE 3 -COLUMN AND WALL BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 6 | FL | 0216 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-6FL0217 | BLADE 3 - FOUNDATION REINFORCEMENTBAR BENDING SCHEDULE SHEET 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 6 | FL | 0217 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-6FL0218 | BLADE 3 - FOUNDATION REINFORCEMENTBAR BENDING SCHEDULE SHEET 02 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-24 | Blade 3 - Foundation RFT | QP.E.CV.BL3.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 6 | FL | 0218 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0301 | BLADE 3 - INTERNAL WALLS GENERAL ARRANGEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Col Elevation GA and Internal wall RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0301 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0302 | BLADE 3 - INTERNAL WALL GA ELEVATION SHEET-01 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Col Elevation GA and Internal wall RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0302 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0303 | BLADE 3 - COLUMN REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Col Elevation RFT and Internal wall RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0303 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0304 | BLADE 3 - COLUMN REINFORCEMENT SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Col Elevation RFT and Internal wall RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0304 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0305 | BLADE 3 - INTERNAL WALL REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Col Elevation RFT and Internal wall RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0305 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0306 | BLADE 3 - INTERNAL WALL REINFORCEMENT ELEVATION AND SECTION -SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Col Elevation RFT and Internal wall RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0306 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0307 | BLADE 3 - INTERNAL WALL REINFORCEMENT ELEVATION AND SECTION -SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Col Elevation RFT and Internal wall RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0307 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-6FL0308 | BLADE 3 - COLUMN AND INTERNAL WALL BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Col Elevation RFT and Internal wall RFT | QP.E.CV.BL3.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 6 | FL | 0308 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0401 | BLADE 3 - RETAINING WALLS GENERAL ARRANGEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0401 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0402 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0402 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0403 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0403 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0404 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0404 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0405 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0405 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0406 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0406 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0407 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0407 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0408 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0408 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0409 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0409 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0410 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-09 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0410 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0411 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0411 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0412 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-11 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0412 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0413 | BLADE 3 - RETAINING WALLS GA ELEVATION SECTION SHEET-12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW GA & RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0413 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0414 | BLADE 3 - RETANING WALL REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0414 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0415 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 1 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0415 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0416 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 2 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0416 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0417 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 3 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0417 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0418 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 4 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0418 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0419 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 5 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0419 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0420 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 6 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0420 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0421 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 7 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0421 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0422 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 8 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0422 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0423 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 9 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0423 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0424 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 10 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0424 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0425 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 11 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0425 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0426 | BLADE 3 - RETAINING WALL ELEVATION & SECTION SHEET 12 OF 12 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0426 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-6FL0427 | BLADE 3 - RETAINING WALL BBS - SHEET 1 OF 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 6 | FL | 0427 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-6FL0428 | BLADE 3 - RETAINING WALL BBS - SHEET 2 OF 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 6 | FL | 0428 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-6FL0429 | BLADE 3 - RETAINING WALL BBS - SHEET 3 OF 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 6 | FL | 0429 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0430 | BLADE 3 - STAIR REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0430 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0431 | BLADE 3 - STAIR SECTION - SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0431 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0432 | BLADE 3 - STAIR SECTION - SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0432 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-6FL0433 | BLADE 3 - EXT. SLAB BBS - SHEET 1 OF 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 6 | FL | 0433 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-6FL0434 | BLADE 3 - EXT. STAIR BBS - SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 6 | FL | 0434 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-6FL0435 | BLADE 3 - EXT. STAIR BBS - SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 6 | FL | 0435 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0436 | BLADE 3 - GENERAL ARRANGEMENT STAIR PLAN EL. 847.50m |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - RW RFT | QP.E.CV.BL3.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0436 | Structural | Nesma & Partners |  |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0501 | BLADE 3 - TANK ROOF SLAB GENERAL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Plans GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0501 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0502 | BLADE 3 - TANK ROOF SLAB SECTION DETAILS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Plans GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0502 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0503 | BLADE 3 - TANK ROOF SLAB BOTTOM REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Plans RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0503 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0504 | BLADE 3 - TANK ROOF SLAB TOP REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Plans RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0504 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2FL0505 | BLADE 3 - TANK ROOF SLAB ADDITIONAL REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-24 | Blade 3 - Plans RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | FL | 0505 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-3FL0506 | BLADE 3 - TANK ROOF SLAB SECTION DETAILS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-24 | Blade 3 - Plans RFT | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 3 | FL | 0506 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-6FL0507 | BLADE 3 - TANK ROOF SLAB BAR BENDING SCHEDULE |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-24 | Blade 3 - Plans RFT | QP.E.CV.BL3.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 6 | FL | 0507 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2000601 | Blade 3 Slabs GA sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Blade 3 - Plans GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | 00 | 0601 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2000602 | Blade 3 Slabs GA sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Blade 3 - Plans GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | 00 | 0602 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2000603 | Blade 3 Slabs GA sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Blade 3 - Plans GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | 00 | 0603 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2000604 | Blade 3 Slabs GA sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Blade 3 - Plans GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | 00 | 0604 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2000605 | Blade 3 Slabs GA sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Blade 3 - Plans GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | 00 | 0605 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2000606 | Blade 3 Slabs GA sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Blade 3 - Plans GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | 00 | 0606 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2000607 | Blade 3 Slabs GA sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Blade 3 - Plans GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | 00 | 0607 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2000608 | Blade 3 Slabs GA sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Blade 3 - Plans GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | 00 | 0608 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD03-2000609 | Blade 3 Slabs GA sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-17 | Blade 3 - Plans GA | QP.E.CV.BL3.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD03 | 2 | 00 | 0609 | Structural | Nesma & Partners |  |  |  |  | 2026-03-03
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0101 | Blade 4 Column & axes |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Foundation GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0101 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0102 | Blade 4 Foundation Plan Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Foundation GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0102 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0103 | Blade 4 Foundation Section Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Foundation GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0103 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0201 | BLADE 4 FOUNDATION BOTTOM REINFORCEMENT PLAN-B1 & B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Foundation RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0201 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0202 | BLADE 4 FOUNDATION TOP REINFORCEMENT PLAN-T1 & T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Foundation RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0202 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0203 | BLADE 4 FOUNDATION BOTTOM ADDITIONAL REINFORCEMENT PLAN-ADDN.B3,B4,B5,B6,B7,B8,B9,B10 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Foundation RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0203 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0204 | BLADE 4 FOUNDATION TOP ADDITIONAL REINFORCEMENT PLAN-ADDN.T3,T4,T5,T6,T7,T8,T9,T10 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Foundation RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0204 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0205 | BLADE 4 FOUNDATION ADDITIONAL REINFORCEMENT PLAN-SHEAR LINKS & SIDE BARS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Foundation RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0205 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0206 | BLADE 4 - FOUNDATION RFT SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Foundation RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0206 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0207 | BLADE 4 COLUMN STARTER BAR PLAN & SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Foundation RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0207 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0208 | BLADE 4 RETAINING WALL STARTER BAR PLAN & SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Foundation RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0208 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-6FL0209 | BLADE 4 - FOUNDATION RFT BBS - SHEET 1 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Foundation RFT | QP.E.CV.BL4.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 6 | FL | 0209 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-6FL0210 | BLADE 4 - FOUNDATION RFT BBS - SHEET 2 OF 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Foundation RFT | QP.E.CV.BL4.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 6 | FL | 0210 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-6FL0211 | BLADE 4 COLUMN & RETAINING WALL STARTER BAR BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Foundation RFT | QP.E.CV.BL4.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 6 | FL | 0211 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0401 | BLADE 4 - RETAINING WALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0401 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0402 | BLADE 4 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 1 OF 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0402 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0403 | BLADE 4 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 2 OF 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0403 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0404 | BLADE 4 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 3 OF 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0404 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0405 | BLADE 4 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 4 OF 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0405 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0406 | BLADE 4 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 5 OF 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0406 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0407 | BLADE 4 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 6 OF 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0407 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0408 | BLADE 4 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 7 OF 7 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0408 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0409 | BLADE 4 - RETAINING WALL REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0409 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0410 | BLADE 4 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 1 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0410 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0411 | BLADE 4 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 2 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0411 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0412 | BLADE 4 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 3 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0412 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0413 | BLADE 4 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 4 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0413 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0414 | BLADE 4 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 5 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0414 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0415 | BLADE 4 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 6 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0415 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0416 | BLADE 4 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 6 OF 10 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0416 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0417 | BLADE 4 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 6 OF 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0417 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0418 | BLADE 4 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 6 OF 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0418 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0419 | BLADE 4 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 6 OF 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0419 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-6FL0420 | BLADE 4 - RETAINING WALL BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 6 | FL | 0420 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0421 | BLADE 4 COLUMN REINFORCEMENT PLAN & SECTIONS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0421 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0422 | BLADE 4 WALL REINFORCEMNT PLAN |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0422 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0423 | BLADE 4 WALL REINFORCEMNT ELEVATION & SECTIONS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0423 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0424 | BLADE 4 WALL REINFORCEMNT ELEVATION & SECTIONS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0424 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-6FL0425 | BLADE 4 COLUMN & INTERNAL WALL REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - RW GA & RFT | QP.E.CV.BL4.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 6 | FL | 0425 | Structural | Nesma & Partners |  |  |  |  | 2026-04-16
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0501 | BLADE 4 - TANK ROOF SLAB GENERAL ARRANGEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0501 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0502 | BLADE 4 - TANK ROOF SLAB GENERAL ARRANGEMENT SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0502 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0503 | BLADE 4 - TANK ROOF SLAB BOTTOM REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0503 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0504 | BLADE 4 - TANK ROOF SLAB TOP REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0504 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0505 | BLADE 4 - TANK ROOF SLAB AROUND OPENING REINFORCEMENT PLANS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0505 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0506 | BLADE 4 - TANK ROOF SLAB REINFORCEMENT SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0506 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-6FL0507 | BLADE 4 - TANK ROOF SLAB REINFORCEMENT BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 6 | FL | 0507 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0508 | Blade 4 - Exterior Wall & Stair Slab GA PALN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0508 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0509 | Blade 4 - Exterior Wall & Stair Slab GA SECTION SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0509 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0510 | Blade 4 - Exterior Wall & Stair Slab GA SECTION SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0510 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0511 | Blade 4 - Exterior Wall & Stair Slab GA SECTION SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0511 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0512 | Blade 4 - Exterior Wall & Stair Slab GA SECTION SHEET 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0512 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0513 | Blade 4 - Exterior Wall & Stair Slab GA SECTION SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0513 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2FL0514 | Blade 4 - Exterior Wall & Stair Slab RFT PALN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | FL | 0514 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0515 | Blade 4 - Exterior Wall & Stair Slab RFT SECTIONS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0515 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0516 | Blade 4 - Exterior Wall & Stair Slab RFT SECTIONS SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0516 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0517 | Blade 4 - Exterior Wall & Stair Slab RFT SECTIONS SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0517 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0518 | Blade 4 - Exterior Wall & Stair Slab RFT SECTIONS SHEET 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0518 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-3FL0519 | Blade 4 - Exterior Wall & Stair Slab RFT SECTIONS SHEET 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 3 | FL | 0519 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-6FL0520 | Blade 4 - Exterior Wall & Stair Slab BBS SHEET 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 6 | FL | 0520 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-6FL0521 | Blade 4 - Exterior Wall & Stair Slab BBS SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | Blade 4 - Plans RFT | QP.E.CV.BL4.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 6 | FL | 0521 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2000601 | Blade 4 Slabs GA sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | 00 | 0601 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2000602 | Blade 4 Slabs GA sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | 00 | 0602 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2000603 | Blade 4 Slabs GA sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | 00 | 0603 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2000604 | Blade 4 Slabs GA sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | 00 | 0604 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2000605 | Blade 4 Slabs GA sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | 00 | 0605 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2000606 | Blade 4 Slabs GA sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | 00 | 0606 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2000607 | Blade 4 Slabs GA sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | 00 | 0607 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2000608 | Blade 4 Slabs GA sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | 00 | 0608 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD04-2000609 | Blade 4 Slabs GA sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-19 | Blade 4 - Plans GA | QP.E.CV.BL4.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD04 | 2 | 00 | 0609 | Structural | Nesma & Partners |  |  |  |  | 2026-02-05
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0101 | BLADE 5 - GENERAL ARRANGEMENT FOUNDATION PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - Foundation GA | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0101 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0102 | BLADE 5 - GENERAL ARRANGEMENT WALL & COLUMN AXES PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - Foundation GA | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0102 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0103 | BLADE 5- GENERAL ARRANGEMENT FOUNDATION SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - Foundation GA | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0103 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0201 | BLADE 5 FOUNDATION BOTTOM REINFORCEMENT PLAN-B1 & B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0201 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0202 | BLADE 5 FOUNDATION TOP REINFORCEMENT PLAN-T1 & T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0202 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0203 | BLADE 5 FOUNDATION BOTTOM ADDN. REINFORCEMENT PLAN-B1 & B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0203 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0204 | BLADE 5 FOUNDATION TOP ADDN. REINFORCEMENT PLAN-T1 & T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0204 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0205 | BLADE 5 FOUNDATION REINFORCEMENT PLAN-SHEAR LINK & SIDE BAR |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0205 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0206 | BLADE 5 FOUNDATION REINFORCEMENT SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0206 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0207 | BLADE 5 COLUMN STARTER BAR PLAN & SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0207 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0208 | BLADE 5 WALL STARTER BAR PLAN & ELEVATION |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0208 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0209 | BLADE 5 WALL STARTER BAR SECTION |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0209 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-6FL0210 | BLADE 5 FOUNDATION BBS - SHEET 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 6 | FL | 0210 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-6FL0211 | BLADE 5 FOUNDATION BBS - SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 6 | FL | 0211 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-6FL0212 | BLADE 5 COLUMN & WALL STARTER BBS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 6 | FL | 0212 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0213 | BLADE 5 FOUNDATION REINFORCEMENT PLAN-ADD. REBAR AT BASE CONNECTION DETAILS |  | Structure | Revit | .dwg,.pdf | NTS | 2026-08-13 | Blade 5 - Foundation RFT | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0213 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0301 | Blades 5 -Column Elevation RFT - Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - Column Elevation RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0301 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0302 | Blades 5 -Column Elevation RFT - Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - Column Elevation RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0302 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-6FL0303 | Blades 5 -Column Elevation RFT - Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - Column Elevation RFT | QP.E.CV.BL5.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 6 | FL | 0303 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0401 | BLADE 5 - GENERAL ARRANGEMENT RETAINING WALL PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0401 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0402 | BLADE 5 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 1 OF 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0402 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0403 | BLADE 5 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 2 OF 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0403 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0404 | BLADE 5 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 3 OF 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0404 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0405 | BLADE 5 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 4 OF 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0405 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0406 | BLADE 5 - RETAINING WALL ELEVATIONS & SECTIONS-SHEET 5 OF 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0406 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0407 | BLADE 5 - RETAINING WALL REINFORCEMENT PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0407 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0408 | BLADE 5 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 1 OF 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0408 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0409 | BLADE 5 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 2 OF 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0409 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0410 | BLADE 5 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 3 OF 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0410 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0411 | BLADE 5 - RETAINING WALL REINFORCEMENT ELEVATIONS - SHEET 4 OF 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0411 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-6FL0412 | BLADE 5 - RETAINING WALL BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 6 | FL | 0412 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0413 | BLADE 5 WALL REINFORCEMENT PLAN TOW 899.350m & 899.300m |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0413 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0414 | BLADE 5 SLAB REINFORCEMENT PLAN EL.898.400m |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0414 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-6FL0415 | BLADE 5 SLAB RFT & WALL UPSTAND BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 6 | FL | 0415 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0501 | BLADE 5 - GENERAL ARRANGEMENT SLAB PLAN EL. 898.440m |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0501 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-2FL0502 | BLADE 5 - GENERAL ARRANGEMENT SLAB PLAN @ WATER TANK |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | FL | 0502 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-3FL0503 | BLADE 5 - SLAB SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 3 | FL | 0503 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-2000601 | Blade 5 Slabs GA Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-08-13 | Blade 5 - RW GA & RFT | QP.E.CV.BL5.GEN.1080 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | 00 | 0601 | Structural | Nesma & Partners |  |  |  |  | 2026-04-20
QF01012-NES-C04518-SDW-STR-00-BLAD05-2000602 | Blade 5 Slabs GA Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Blade 5 - Plans GA | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | 00 | 0602 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2000603 | Blade 5 Slabs GA Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Blade 5 - Plans GA | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | 00 | 0603 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2000604 | Blade 5 Slabs GA Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Blade 5 - Plans GA | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | 00 | 0604 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2000605 | Blade 5 Slabs GA Sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Blade 5 - Plans GA | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | 00 | 0605 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2000606 | Blade 5 Slabs GA Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Blade 5 - Plans GA | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | 00 | 0606 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2000607 | Blade 5 Slabs GA Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Blade 5 - Plans GA | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | 00 | 0607 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2000608 | Blade 5 Slabs GA Sheet 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Blade 5 - Plans GA | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | 00 | 0608 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-BLAD05-2000609 | Blade 5 Slabs GA Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-10-29 | Blade 5 - Plans GA | QP.E.CV.BL5.GEN.1000 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | BLAD05 | 2 | 00 | 0609 | Structural | Nesma & Partners |  |  |  |  | 2026-01-15
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2100 | TUNNEL FOUNDATION OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL FOUNDATION GA | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2100 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2101 | TUNNEL-FDN- Foundation GA Part 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION GA | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2101 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2102 | TUNNEL-FDN- Foundation GA Part 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION GA | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2102 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2103 | TUNNEL-FDN- Foundation GA Part 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION GA | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2103 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2104 | TUNNEL-FDN-SECTION DETAIL-1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION GA | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2104 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2105 | TUNNEL-FDN-SECTION DETAIL-2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION GA | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2105 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2106 | TUNNEL-FDN-SECTION DETAIL-3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION GA | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2106 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2107 | TUNNEL-FDN-SECTION DETAIL-4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION GA | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2107 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2201 | TUNNEL-FDN- BOTTOM REINFORCEMENT B1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2201 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2202 | TUNNEL-FDN- BOTTOM REINFORCEMENT B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2202 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2203 | TUNNEL-FDN- TOP REINFORCEMENT T1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2203 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2204 | TUNNEL-FDN- TOP REINFORCEMENT T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2204 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2205 | TUNNEL-FDN-BOTTOM RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2205 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2206 | TUNNEL-FDN-TOP RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2206 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2207 | TUNNEL-FDN-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2207 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2208 | TUNNEL-FDN-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2208 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2209 | TUNNEL-FDN- BOTTOM REINFORCEMENT B1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2209 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2210 | TUNNEL-FDN- BOTTOM REINFORCEMENT B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2210 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2211 | TUNNEL-FDN- TOP REINFORCEMENT T1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2211 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2212 | TUNNEL-FDN- TOP REINFORCEMENT T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2212 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2213 | TUNNEL-FDN-BOTTOM RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2213 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2214 | TUNNEL-FDN-TOP RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2214 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2215 | TUNNEL-FDN-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2215 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2216 | TUNNEL-FDN-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2216 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2217 | TUNNEL-FDN- BOTTOM REINFORCEMENT B1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2217 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2218 | TUNNEL-FDN- BOTTOM REINFORCEMENT B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2218 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2219 | TUNNEL-FDN- TOP REINFORCEMENT T1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2219 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2220 | TUNNEL-FDN- TOP REINFORCEMENT T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2220 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2221 | TUNNEL-FDN-BOTTOM RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2221 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2222 | TUNNEL-FDN-TOP RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2222 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2223 | TUNNEL-FDN-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2223 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2224 | TUNNEL-FDN-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2224 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2225 | TUNNEL(trench)-FDN- BOTTOM REINFORCEMENT B1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2225 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2226 | TUNNEL(trench)-FDN- BOTTOM REINFORCEMENT B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2226 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2227 | TUNNEL(trench)-FDN- TOP REINFORCEMENT T1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2227 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2228 | TUNNEL(trench)-FDN- TOP REINFORCEMENT T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2228 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2229 | TUNNEL(trench)-FDN-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2229 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2230 | TUNNEL(trench)-FDN- BOTTOM REINFORCEMENT B1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2230 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2231 | TUNNEL(trench)-FDN- BOTTOM REINFORCEMENT B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2231 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2232 | TUNNEL(trench)-FDN- TOP REINFORCEMENT T1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2232 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2233 | TUNNEL(trench)-FDN- TOP REINFORCEMENT T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2233 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2234 | TUNNEL(trench)-FDN-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2234 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2235 | TUNNEL FOUNDATION RFT BBS SHEET 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2235 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2236 | TUNNEL FOUNDATION RFT BBS SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2236 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2237 | TUNNEL FOUNDATION RFT BBS SHEET 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2237 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2238 | TUNNEL FOUNDATION RFT BBS SHEET 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2238 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2239 | TUNNEL FOUNDATION RFT BBS SHEET 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2239 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2240 | TUNNEL FOUNDATION RFT BBS SHEET 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2240 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2241 | TUNNEL FOUNDATION RFT BBS SHEET 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2241 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2242 | TUNNEL FOUNDATION RFT BBS SHEET 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2242 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2243 | TUNNEL FOUNDATION RFT BBS SHEET 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2243 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2244 | TUNNEL FOUNDATION RFT BBS SHEET 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL FOUNDATION RFT | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2244 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2301 | TUNNEL-Wall Starter Bars RFT Enlarged Plan Part 1 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2301 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2302 | TUNNEL-Wall Starter Bars RFT Enlarged Plan Part 2 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2302 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2303 | TUNNEL-Wall Starter Bars RFT Enlarged Plan Part 3 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2303 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2304 | TUNNEL-Wall Starter Bars RFT Enlarged Plan Part 4 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2304 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2305 | TUNNEL-Wall Starter Bars RFT Enlarged Plan Part 5 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2305 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2306 | TUNNEL-Wall Starter Bars RFT Enlarged Plan Part 6 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2306 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2307 | TUNNEL-Wall Starter Bars RFT Enlarged Plan Part 7 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2307 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2308 | TUNNEL-Wall Stater Bars Section Detail -1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2308 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2309 | TUNNEL-Wall Stater Bars Section Detail -2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2309 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2310 | TUNNEL-Wall Stater Bars Section Detail -3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2310 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2311 | TUNNEL-Wall Stater Bars RFT BBS - Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2311 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2312 | TUNNEL-Wall Stater Bars RFT BBS - Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2312 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2313 | TUNNEL-Wall Stater Bars RFT BBS - Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2313 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2314 | TUNNEL-Wall Stater Bars RFT BBS - Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-11-26 | TUNNAL WALL STARTER BARS | QP.E.CV.MBL.GEN.3480 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2314 | Structural | Nesma & Partners |  |  |  |  | 2027-05-19
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL2401 | TUNNEL WALL OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 2401 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2402 | TUNNEL- Wall-1 Elevation Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2402 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2403 | TUNNEL- Wall-1 Elevation Sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2403 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2404 | TUNNEL- Wall-1 Elevation Sheet 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2404 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2405 | TUNNEL- Wall-1 Elevation Sheet 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2405 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2406 | TUNNEL- Wall-1 Elevation Sheet 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2406 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2407 | TUNNEL- Wall-2 Elevation Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2407 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2408 | TUNNEL- Wall-2 Elevation Sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2408 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2409 | TUNNEL- Wall-2 Elevation Sheet 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2409 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2410 | TUNNEL- Wall-2 Elevation Sheet 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2410 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2411 | TUNNEL- Wall-2 Elevation Sheet 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2411 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2412 | TUNNEL- Wall-2 Elevation Sheet 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2412 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2413 | TUNNEL- Wall-2 Elevation Sheet 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2413 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2414 | TUNNEL- Wall-2 Elevation Sheet 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2414 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2415 | TUNNEL- Wall-3 Elevation Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2415 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2416 | TUNNEL- Wall-3 Elevation Sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2416 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2417 | TUNNEL- Wall-3 Elevation Sheet 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2417 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2418 | TUNNEL- Wall-3 Elevation Sheet 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2418 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2419 | TUNNEL- Wall-3 Elevation Sheet 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2419 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2420 | TUNNEL- Wall-3 Elevation Sheet 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2420 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2421 | TUNNEL- Wall-3 Elevation Sheet 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2421 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2422 | TUNNEL- Wall-4 Elevation Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2422 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2423 | TUNNEL- Wall-4 Elevation Sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2423 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2424 | TUNNEL- Wall-4 Elevation Sheet 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2424 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2425 | TUNNEL- Wall-4 Elevation Sheet 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2425 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2426 | TUNNEL- Walls sections Details sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2426 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2427 | TUNNEL- Walls sections Details sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2427 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2428 | TUNNEL- Walls sections Details sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2428 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2429 | TUNNEL- Walls sections Details sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2429 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2430 | TUNNEL- Walls sections Details sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2430 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2431 | TUNNEL- Walls sections Details sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2431 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2501 | TUNNEL- Wall RFT Enlarged Plan Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2501 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2502 | TUNNEL- Wall RFT Enlarged Plan Sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2502 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2503 | TUNNEL- Wall RFT Enlarged Plan Sheet 03 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2503 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2504 | TUNNEL- Wall RFT Enlarged Plan Sheet 04 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2504 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2505 | TUNNEL- Wall RFT Enlarged Plan Sheet 05 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2505 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-4FL2506 | TUNNEL- Wall RFT Enlarged Plan Sheet 06 |  | Structure | Revit | .dwg,.pdf | 1:50 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 4 | FL | 2506 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2507 | TUNNEL- Wall-1 Elevation RFT Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2507 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2508 | TUNNEL- Wall-1 Elevation RFT Sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2508 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2509 | TUNNEL- Wall-1 Elevation RFT Sheet 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2509 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2510 | TUNNEL- Wall-1 Elevation RFT Sheet 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2510 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2511 | TUNNEL- Wall-1 Elevation RFT Sheet 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2511 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2512 | TUNNEL- Wall-2 Elevation RFT Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2512 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2513 | TUNNEL- Wall-2 Elevation RFT Sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2513 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2514 | TUNNEL- Wall-2 Elevation RFT Sheet 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2514 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2515 | TUNNEL- Wall-2 Elevation RFT Sheet 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2515 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2516 | TUNNEL- Wall-2 Elevation RFT Sheet 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2516 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2517 | TUNNEL- Wall-2 Elevation RFT Sheet 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2517 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2518 | TUNNEL- Wall-2 Elevation RFT Sheet 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2518 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2519 | TUNNEL- Wall-2 Elevation RFT Sheet 08 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2519 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2520 | TUNNEL- Wall-3 Elevation RFT Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2520 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2521 | TUNNEL- Wall-3 Elevation RFT Sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2521 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2522 | TUNNEL- Wall-3 Elevation RFT Sheet 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2522 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2523 | TUNNEL- Wall-3 Elevation RFT Sheet 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2523 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2524 | TUNNEL- Wall-3 Elevation RFT Sheet 05 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2524 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2525 | TUNNEL- Wall-3 Elevation RFT Sheet 06 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2525 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2526 | TUNNEL- Wall-3 Elevation RFT Sheet 07 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2526 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2527 | TUNNEL- Wall-4 Elevation RFT Sheet 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2527 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2528 | TUNNEL- Wall-4 Elevation RFT Sheet 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2528 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2529 | TUNNEL- Wall-4 Elevation RFT Sheet 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-11-26 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2529 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2530 | TUNNEL- Wall-4 Elevation RFT Sheet 04 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2530 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2531 | TUNNEL- Walls sections Details sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2531 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2532 | TUNNEL- Walls sections Details sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2532 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2533 | TUNNEL- Walls sections Details sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2533 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2534 | TUNNEL- Walls sections Details sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2534 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2535 | TUNNEL- Walls sections Details sheet 5 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2535 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL2536 | TUNNEL- Walls sections Details sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 2536 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2537 | TUNNEL- WALL RFT BBS - SHEET 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2537 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2538 | TUNNEL- WALL RFT BBS - SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2538 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2539 | TUNNEL- WALL RFT BBS - SHEET 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2539 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2540 | TUNNEL- WALL RFT BBS - SHEET 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2540 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2541 | TUNNEL- WALL RFT BBS - SHEET 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2541 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2542 | TUNNEL- WALL RFT BBS - SHEET 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2542 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2543 | TUNNEL- WALL RFT BBS - SHEET 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2543 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL2544 | TUNNEL- WALL RFT BBS - SHEET 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL WALL ELEVATIONS RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 2544 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2601 | TUNNEL ROOF OVERALL PLAN |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2026-12-10 | TUNNAL ROOF GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2601 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2602 | TUNNEL-RF- Roof GA Part 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2602 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2603 | TUNNEL-RF- Roof GA Part 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2603 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2604 | TUNNEL-RF- Roof GA Part 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2604 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3RF2605 | TUNNEL-RF-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL ROOF GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | RF | 2605 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3RF2606 | TUNNEL-RF-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL ROOF GA | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | RF | 2606 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2701 | TUNNEL-RF- BOTTOM REINFORCEMENT B1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2701 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2702 | TUNNEL-RF- BOTTOM REINFORCEMENT B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2702 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2703 | TUNNEL-RF- TOP REINFORCEMENT T1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2703 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2704 | TUNNEL-RF- TOP REINFORCEMENT T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2704 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2705 | TUNNEL-RF-BOTTOM RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2705 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2706 | TUNNEL-RF-TOP RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2706 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3RF2707 | TUNNEL-RF-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | RF | 2707 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2708 | TUNNEL-RF- BOTTOM REINFORCEMENT B1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2708 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2709 | TUNNEL-RF- BOTTOM REINFORCEMENT B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2709 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2710 | TUNNEL-RF- TOP REINFORCEMENT T1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2710 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2711 | TUNNEL-RF- TOP REINFORCEMENT T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2711 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2712 | TUNNEL-RF-BOTTOM RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2712 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2713 | TUNNEL-RF-TOP RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2713 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3RF2714 | TUNNEL-RF-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | RF | 2714 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2715 | TUNNEL-RF- BOTTOM REINFORCEMENT B1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2715 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2716 | TUNNEL-RF- BOTTOM REINFORCEMENT B2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2716 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2717 | TUNNEL-RF- TOP REINFORCEMENT T1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2717 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2718 | TUNNEL-RF- TOP REINFORCEMENT T2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2718 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2719 | TUNNEL-RF-BOTTOM RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2719 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2RF2720 | TUNNEL-RF-TOP RFT ADDITIONAIL |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | RF | 2720 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-3RF2721 | TUNNEL-RF-SECTION DETAIL |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | RF | 2721 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6RF2722 | TUNNELROOF SLAB RFT BBS- SHEET 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | RF | 2722 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6RF2723 | TUNNELROOF SLAB RFT BBS- SHEET 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | RF | 2723 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6RF2724 | TUNNELROOF SLAB RFT BBS- SHEET 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | RF | 2724 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6RF2725 | TUNNELROOF SLAB RFT BBS- SHEET 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | RF | 2725 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6RF2726 | TUNNELROOF SLAB RFT BBS- SHEET 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | RF | 2726 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6RF2727 | TUNNELROOF SLAB RFT BBS- SHEET 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | RF | 2727 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6RF2728 | TUNNELROOF SLAB RFT BBS- SHEET 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | RF | 2728 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6RF2729 | TUNNELROOF SLAB RFT BBS- SHEET 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | RF | 2729 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6RF2730 | TUNNELROOF SLAB RFT BBS- SHEET 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | RF | 2730 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-6RF2731 | TUNNELROOF SLAB RFT BBS- SHEET 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-12-10 | TUNNAL ROOF RFT | QP.E.CV.MBL.GEN.3520 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | RF | 2731 | Structural | Nesma & Partners |  |  |  |  | 2027-07-05
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3101 | LS External RW-FDN - KEY PLAN SHEET 1 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3101 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3102 | LS External Foundation Plan Sheet 1 (1/10) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3102 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3103 | LS External Foundation Plan Sheet 2 (2/10) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3103 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3104 | LS External Foundation Plan Sheet 3 (3/10) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3104 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3105 | LS External Foundation Plan Sheet 4 (4/10) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3105 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3106 | LS External Foundation Plan Sheet 6 (5/10) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3106 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3107 | LS External Foundation Plan Sheet 7 (6/10) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3107 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3108 | LS External Foundation Plan Sheet 9 (7/10) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3108 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3109 | LS External Foundation Plan Sheet 11 (8/10) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3109 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3110 | LS External Foundation Plan Sheet 28 (9/10) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3110 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3111 | LS External Foundation Plan Sheet 29 (10/10) |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3111 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3112 | LS External RW Foundation SECTION DETAIL-1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3112 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3113 | LS External RW Foundation SECTION DETAIL-2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3113 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3114 | LS External RW Foundation SECTION DETAIL-3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3114 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3115 | LS External RW Foundation SECTION DETAIL-4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3115 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3116 | LS External RW Foundation SECTION DETAIL-5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation GA | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3116 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3201 | LS External RW Foundation Bottom RFT Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3201 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3202 | LS External RW Foundation TOP RFT Sheet 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3202 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3203 | LS External RW Foundation Bottom RFT Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3203 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3204 | LS External RW Foundation TOP RFT Sheet 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3204 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3205 | LS External RW Foundation Bottom RFT Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3205 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3206 | LS External RW Foundation TOP RFT Sheet 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3206 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3207 | LS External RW Foundation Bottom RFT Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3207 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3208 | LS External RW Foundation TOP RFT Sheet 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3208 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3209 | LS External RW Foundation Bottom RFT Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3209 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3210 | LS External RW Foundation TOP RFT Sheet 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3210 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3211 | LS External RW Foundation Bottom RFT Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3211 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3212 | LS External RW Foundation TOP RFT Sheet 7 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3212 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3213 | LS External RW Foundation Bottom RFT Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3213 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3214 | LS External RW Foundation TOP RFT Sheet 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3214 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3215 | LS External RW Foundation Bottom RFT Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3215 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3216 | LS External RW Foundation TOP RFT Sheet 11 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3216 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3217 | LS External RW Foundation Bottom RFT Sheet 28 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3217 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3218 | LS External RW Foundation TOP RFT Sheet 28 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3218 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3219 | LS External RW Foundation Bottom RFT Sheet 29 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3219 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3220 | LS External RW Foundation TOP RFT Sheet 29 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3220 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3221 | LS External RW Foundation SECTION DETAIL-1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3221 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3222 | LS External RW Foundation SECTION DETAIL-2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3222 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3223 | LS External RW Foundation SECTION DETAIL-3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3223 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3224 | LS External RW Foundation SECTION DETAIL-4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3224 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3225 | LS External RW Foundation SECTION DETAIL-5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3225 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3226 | LS External RW Foundation RFT BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3226 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3227 | LS External RW Foundation RFT BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3227 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3228 | LS External RW Foundation RFT BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3228 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3229 | LS External RW Foundation RFT BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3229 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3230 | LS External RW Foundation RFT BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3230 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3231 | LS External RW Foundation RFT BBS Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3231 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3232 | LS External RW Foundation RFT BBS Sheet 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3232 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3233 | LS External RW Foundation RFT BBS Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3233 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3234 | LS External RW Foundation RFT BBS Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3234 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3235 | LS External RW Foundation RFT BBS Sheet 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-03 | LS External RW-Foundation RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3235 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3301 | LS External RW- Wall Starter Bars Part 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3301 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3302 | LS External RW- Wall Starter Bars Part 2 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3302 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3303 | LS External RW- Wall Starter Bars Part 3 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3303 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3304 | LS External RW- Wall Starter Bars Part 4 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3304 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3305 | LS External RW- Wall Starter Bars Part 5 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-03 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3305 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3306 | LS External RW- Wall Starter Bars Part 6 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3306 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3307 | LS External RW- Wall Starter Bars Part 7 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3307 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3308 | LS External RW- Wall Starter Bars Part 8 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3308 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3309 | LS External RW- Wall Starter Bars Part 9 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3309 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3310 | LS External RW- Wall Starter Bars Part 10 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3310 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3311 | LS External RW- Wall Starter Bars Section Details -1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3311 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3312 | LS External RW- Wall Starter Bars Section Details -2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3312 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3313 | LS External RW- Wall Starter Bars Section Details -3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3313 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3314 | LS External RW- Wall Starter Bars Section Details -4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3314 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3315 | LS External RW- Wall Starter Bars Section Details -5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3315 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3316 | LS External RW- Wall Starter Bars RFT BBS Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3316 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3317 | LS External RW- Wall Starter Bars RFT BBS Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3317 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3318 | LS External RW- Wall Starter Bars RFT BBS Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3318 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3319 | LS External RW- Wall Starter Bars RFT BBS Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3319 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3320 | LS External RW- Wall Starter Bars RFT BBS Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Starter Bars | QP.E.CV.MBL.GEN.3060 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3320 | Structural | Nesma & Partners |  |  |  |  | 2026-09-07
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL3401 | LS External RW- KEY PLAN SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:100 | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 3401 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3402 | LS External RW- Wall Elevation sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3402 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3403 | LS External RW- Wall Elevation sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3403 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3404 | LS External RW- Wall Elevation sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3404 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3405 | LS External RW- Wall Elevation sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3405 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3406 | LS External RW- Wall Elevation sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3406 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3407 | LS External RW- Wall Elevation sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3407 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3408 | LS External RW- Wall Elevation sheet 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3408 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3409 | LS External RW- Wall Elevation sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3409 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3410 | LS External RW- Wall Elevation sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3410 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3411 | LS External RW- Wall Elevation sheet 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3411 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3412 | LS External RW- Wall Elevation sheet 11 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3412 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3413 | LS External RW- Wall Elevation sheet 12 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3413 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3414 | LS External RW- Wall Elevation sheet 13 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3414 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3415 | LS External RW- Wall Elevation sheet 14 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3415 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3416 | LS External RW- Wall Elevation sheet 15 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3416 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3417 | LS External RW- Wall Elevation sheet 16 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3417 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3418 | LS External RW- Wall Elevation sheet 17 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3418 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3419 | LS External RW- Wall Elevation sheet 18 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3419 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3420 | LS External RW- Wall Elevation sheet 19 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3420 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3421 | LS External RW- Wall Elevation sheet 20 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3421 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3422 | LS External RW- Wall Elevation sheet 21 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3422 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3423 | LS External RW- Wall Elevation sheet 22 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3423 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3424 | LS External RW- Wall Elevation sheet 23 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3424 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3425 | LS External RW- Wall Elevation sheet 24 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3425 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3426 | LS External RW- Wall Elevation sheet 25 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3426 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3427 | LS External RW- Wall GA Section Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3427 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3428 | LS External RW- Wall GA Section Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3428 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3429 | LS External RW- Wall GA Section Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3429 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3430 | LS External RW- Wall GA Section Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3430 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3431 | LS External RW- Wall GA Section Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall Elevation GA | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3431 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3501 | LS External RW RFT- KEY PLAN SHEET 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3501 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3502 | LS External RW- Wall RFT Sheet 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3502 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3503 | LS External RW- Wall RFT Sheet 02 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3503 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3504 | LS External RW- Wall RFT Sheet 03 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3504 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3505 | LS External RW- Wall RFT Sheet 04 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3505 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3506 | LS External RW- Wall RFT Sheet 05 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3506 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3507 | LS External RW- Wall RFT Sheet 06 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3507 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3508 | LS External RW- Wall RFT Sheet 07 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3508 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3509 | LS External RW- Wall RFT Sheet 08 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3509 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3510 | LS External RW- Wall RFT Sheet 09 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3510 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3511 | LS External RW- Wall RFT Sheet 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3511 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3512 | LS External RW- Wall RFT Sheet 11 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3512 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3513 | LS External RW- Wall RFT Sheet 12 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3513 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3514 | LS External RW- Wall RFT Sheet 13 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3514 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3515 | LS External RW- Wall RFT Sheet 14 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3515 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3516 | LS External RW- Wall RFT Sheet 15 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3516 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3517 | LS External RW- Wall RFT Sheet 16 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3517 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3518 | LS External RW- Wall RFT Sheet 17 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3518 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3519 | LS External RW- Wall RFT Sheet 18 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3519 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3520 | LS External RW- Wall RFT Sheet 19 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3520 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3521 | LS External RW- Wall RFT Sheet 20 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3521 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3522 | LS External RW- Wall RFT Sheet 21 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3522 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3523 | LS External RW- Wall RFT Sheet 22 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3523 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3524 | LS External RW- Wall RFT Sheet 23 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3524 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3525 | LS External RW- Wall RFT Sheet 24 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3525 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3526 | LS External RW- Wall RFT Sheet 25 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-17 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3526 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3527 | LS External RW- Wall RFT section Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3527 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3528 | LS External RW- Wall RFT section Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3528 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3529 | LS External RW- Wall RFT section Details Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3529 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3530 | LS External RW- Wall RFT section Details Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3530 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL3531 | LS External RW- Wall RFT section Details Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 3531 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3532 | LS External RW- Wall RFT BBS - Sheet 1 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3532 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3533 | LS External RW- Wall RFT BBS - Sheet 2 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3533 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3534 | LS External RW- Wall RFT BBS - Sheet 3 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3534 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3535 | LS External RW- Wall RFT BBS - Sheet 4 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3535 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3536 | LS External RW- Wall RFT BBS - Sheet 5 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3536 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3537 | LS External RW- Wall RFT BBS - Sheet 6 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3537 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3538 | LS External RW- Wall RFT BBS - Sheet 7 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3538 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3539 | LS External RW- Wall RFT BBS - Sheet 8 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3539 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3540 | LS External RW- Wall RFT BBS - Sheet 9 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-09-16 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3540 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-6FL3541 | LS External RW- Wall RFT BBS - Sheet 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2027-01-14 | LS External RW-Wall RFT | QP.E.CV.MBL.GEN.3560 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 6 | FL | 3541 | Structural | Nesma & Partners |  |  |  |  | 2026-11-30
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL4001 | SEC MRMU ROOM FOUNDATION PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 4001 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL4002 | SEC MRMU ROOM TRENCH FOUNDATION PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 4002 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL4003 | SEC MRMU ROOM TRENCH WALL LAYOUT PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 4003 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL4004 | SEC MRMU ROOM FLOOR PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 4004 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-2FL4005 | SEC MRMU ROOM ROOF SLAB PLAN |  | Structure | Revit | .dwg,.pdf | 1:100 | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 2 | FL | 4005 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4006 | SEC MRMU ROOM FOUNDATION SECTIONS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4006 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4007 | SEC MRMU ROOM RFT Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4007 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4008 | SEC MRMU ROOM RFT Details Sheet 2 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4008 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4009 | SEC MRMU ROOM RFT Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4009 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4010 | SEC MRMU ROOM RFT Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4010 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4011 | SEC MRMU ROOM RFT Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4011 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4012 | SEC MRMU ROOM RFT Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4012 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4013 | SEC MRMU ROOM RFT Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4013 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4014 | SEC MRMU ROOM RFT Details Sheet 1 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4014 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4015 | LS & External Work Package 1 - Details 15 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4015 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4016 | LS & External Work Package 1 - Details 16 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4016 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4017 | LS & External Work Package 1 - Details 17 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4017 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4018 | LS & External Work Package 1 - Details 18 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4018 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4019 | LS & External Work Package 1 - Details 19 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4019 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4020 | LS & External Work Package 1 - Details 20 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4020 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4021 | LS & External Work Package 1 - Details 21 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4021 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4022 | LS & External Work Package 1 - Details 22 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4022 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4023 | LS & External Work Package 1 - Details 23 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4023 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4024 | LS & External Work Package 1 - Details 24 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4024 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4025 | LS & External Work Package 1 - Details 25 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4025 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4026 | LS & External Work Package 1 - Details 26 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4026 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4027 | LS & External Work Package 1 - Details 27 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4027 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4028 | LS & External Work Package 1 - Details 28 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4028 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4029 | LS & External Work Package 1 - Details 29 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4029 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4030 | LS & External Work Package 1 - Details 30 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4030 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4031 | LS & External Work Package 1 - Details 31 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4031 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4032 | LS & External Work Package 1 - Details 32 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4032 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4033 | LS & External Work Package 1 - Details 33 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4033 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4034 | LS & External Work Package 1 - Details 34 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4034 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4035 | LS & External Work Package 1 - Details 35 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4035 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4036 | LS & External Work Package 1 - Details 36 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4036 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4037 | LS & External Work Package 1 - Details 37 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4037 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4038 | LS & External Work Package 1 - Details 38 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4038 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4039 | LS & External Work Package 1 - Details 39 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4039 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4040 | LS & External Work Package 1 - Details 40 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4040 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4041 | LS & External Work Package 1 - Details 41 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4041 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4042 | LS & External Work Package 1 - Details 42 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4042 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4043 | LS & External Work Package 1 - Details 43 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4043 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4044 | LS & External Work Package 1 - Details 44 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4044 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4045 | LS & External Work Package 1 - Details 45 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4045 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4046 | LS & External Work Package 1 - Details 46 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4046 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4047 | LS & External Work Package 1 - Details 47 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4047 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4048 | LS & External Work Package 1 - Details 48 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4048 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4049 | LS & External Work Package 1 - Details 49 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4049 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4050 | LS & External Work Package 1 - Details 50 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4050 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4051 | LS & External Work Package 1 - Details 51 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4051 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4052 | LS & External Work Package 1 - Details 52 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4052 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4053 | LS & External Work Package 1 - Details 53 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4053 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4054 | LS & External Work Package 1 - Details 54 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4054 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4055 | LS & External Work Package 1 - Details 55 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4055 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4056 | LS & External Work Package 1 - Details 56 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4056 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4057 | LS & External Work Package 1 - Details 57 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4057 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4058 | LS & External Work Package 1 - Details 58 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4058 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4059 | LS & External Work Package 1 - Details 59 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4059 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4060 | LS & External Work Package 1 - Details 60 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4060 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4061 | LS & External Work Package 1 - Details 61 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4061 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4062 | LS & External Work Package 1 - Details 62 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4062 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4063 | LS & External Work Package 1 - Details 63 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4063 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4064 | LS & External Work Package 1 - Details 64 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4064 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4065 | LS & External Work Package 1 - Details 65 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4065 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4066 | LS & External Work Package 1 - Details 66 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4066 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4067 | LS & External Work Package 1 - Details 67 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4067 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4068 | LS & External Work Package 1 - Details 68 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4068 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4069 | LS & External Work Package 1 - Details 69 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4069 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4070 | LS & External Work Package 1 - Details 70 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4070 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4071 | LS & External Work Package 1 - Details 71 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4071 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4072 | LS & External Work Package 1 - Details 72 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4072 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4073 | LS & External Work Package 1 - Details 73 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4073 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4074 | LS & External Work Package 1 - Details 74 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4074 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4075 | LS & External Work Package 1 - Details 75 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4075 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4076 | LS & External Work Package 1 - Details 76 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4076 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4077 | LS & External Work Package 1 - Details 77 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4077 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4078 | LS & External Work Package 1 - Details 78 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4078 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4079 | LS & External Work Package 1 - Details 79 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4079 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4080 | LS & External Work Package 1 - Details 80 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4080 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4081 | LS & External Work Package 1 - Details 81 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4081 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4082 | LS & External Work Package 1 - Details 82 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4082 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4083 | LS & External Work Package 1 - Details 83 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4083 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4084 | LS & External Work Package 1 - Details 84 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4084 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4085 | LS & External Work Package 1 - Details 85 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-01-14 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4085 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4086 | LS & External Work Package 1 - Details 86 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4086 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4087 | LS & External Work Package 1 - Details 87 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4087 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4088 | LS & External Work Package 1 - Details 88 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4088 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4089 | LS & External Work Package 1 - Details 89 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4089 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4090 | LS & External Work Package 1 - Details 90 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4090 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4091 | LS & External Work Package 1 - Details 91 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4091 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4092 | LS & External Work Package 1 - Details 92 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4092 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4093 | LS & External Work Package 1 - Details 93 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4093 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4094 | LS & External Work Package 1 - Details 94 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4094 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4095 | LS & External Work Package 1 - Details 95 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4095 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4096 | LS & External Work Package 1 - Details 96 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4096 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4097 | LS & External Work Package 1 - Details 97 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4097 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4098 | LS & External Work Package 1 - Details 98 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4098 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4099 | LS & External Work Package 1 - Details 99 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4099 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL4100 | LS & External Work Package 1 - Details 100 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 4100 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5001 | LS & External Work Package 2 - Details 01 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5001 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5002 | LS & External Work Package 2 - Details 02 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5002 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5003 | LS & External Work Package 2 - Details 03 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5003 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5004 | LS & External Work Package 2 - Details 04 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5004 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5005 | LS & External Work Package 2 - Details 05 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5005 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5006 | LS & External Work Package 2 - Details 06 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5006 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5007 | LS & External Work Package 2 - Details 07 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5007 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5008 | LS & External Work Package 2 - Details 08 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5008 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5009 | LS & External Work Package 2 - Details 09 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5009 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5010 | LS & External Work Package 2 - Details 10 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5010 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5011 | LS & External Work Package 2 - Details 11 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5011 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5012 | LS & External Work Package 2 - Details 12 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5012 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5013 | LS & External Work Package 2 - Details 13 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5013 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5014 | LS & External Work Package 2 - Details 14 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5014 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5015 | LS & External Work Package 2 - Details 15 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5015 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5016 | LS & External Work Package 2 - Details 16 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5016 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5017 | LS & External Work Package 2 - Details 17 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5017 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5018 | LS & External Work Package 2 - Details 18 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5018 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5019 | LS & External Work Package 2 - Details 19 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5019 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5020 | LS & External Work Package 2 - Details 20 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5020 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5021 | LS & External Work Package 2 - Details 21 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5021 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5022 | LS & External Work Package 2 - Details 22 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5022 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5023 | LS & External Work Package 2 - Details 23 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5023 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5024 | LS & External Work Package 2 - Details 24 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5024 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5025 | LS & External Work Package 2 - Details 25 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5025 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5026 | LS & External Work Package 2 - Details 26 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5026 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5027 | LS & External Work Package 2 - Details 27 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5027 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5028 | LS & External Work Package 2 - Details 28 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5028 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5029 | LS & External Work Package 2 - Details 29 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5029 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5030 | LS & External Work Package 2 - Details 30 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5030 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5031 | LS & External Work Package 2 - Details 31 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5031 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5032 | LS & External Work Package 2 - Details 32 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5032 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5033 | LS & External Work Package 2 - Details 33 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5033 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5034 | LS & External Work Package 2 - Details 34 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5034 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5035 | LS & External Work Package 2 - Details 35 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5035 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5036 | LS & External Work Package 2 - Details 36 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5036 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5037 | LS & External Work Package 2 - Details 37 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5037 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5038 | LS & External Work Package 2 - Details 38 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5038 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5039 | LS & External Work Package 2 - Details 39 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5039 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5040 | LS & External Work Package 2 - Details 40 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5040 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5041 | LS & External Work Package 2 - Details 41 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5041 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5042 | LS & External Work Package 2 - Details 42 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5042 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5043 | LS & External Work Package 2 - Details 43 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5043 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5044 | LS & External Work Package 2 - Details 44 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5044 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5045 | LS & External Work Package 2 - Details 45 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5045 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5046 | LS & External Work Package 2 - Details 46 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5046 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5047 | LS & External Work Package 2 - Details 47 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5047 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5048 | LS & External Work Package 2 - Details 48 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5048 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5049 | LS & External Work Package 2 - Details 49 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5049 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5050 | LS & External Work Package 2 - Details 50 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5050 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5051 | LS & External Work Package 2 - Details 51 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5051 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5052 | LS & External Work Package 2 - Details 52 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5052 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5053 | LS & External Work Package 2 - Details 53 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5053 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5054 | LS & External Work Package 2 - Details 54 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5054 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5055 | LS & External Work Package 2 - Details 55 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5055 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5056 | LS & External Work Package 2 - Details 56 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5056 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5057 | LS & External Work Package 2 - Details 57 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5057 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5058 | LS & External Work Package 2 - Details 58 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5058 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5059 | LS & External Work Package 2 - Details 59 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5059 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5060 | LS & External Work Package 2 - Details 60 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5060 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5061 | LS & External Work Package 2 - Details 61 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5061 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5062 | LS & External Work Package 2 - Details 62 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5062 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5063 | LS & External Work Package 2 - Details 63 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5063 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5064 | LS & External Work Package 2 - Details 64 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5064 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5065 | LS & External Work Package 2 - Details 65 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5065 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5066 | LS & External Work Package 2 - Details 66 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5066 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5067 | LS & External Work Package 2 - Details 67 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5067 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5068 | LS & External Work Package 2 - Details 68 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5068 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5069 | LS & External Work Package 2 - Details 69 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5069 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5070 | LS & External Work Package 2 - Details 70 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5070 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5071 | LS & External Work Package 2 - Details 71 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5071 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5072 | LS & External Work Package 2 - Details 72 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5072 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5073 | LS & External Work Package 2 - Details 73 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5073 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5074 | LS & External Work Package 2 - Details 74 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5074 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5075 | LS & External Work Package 2 - Details 75 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5075 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5076 | LS & External Work Package 2 - Details 76 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5076 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5077 | LS & External Work Package 2 - Details 77 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5077 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5078 | LS & External Work Package 2 - Details 78 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3580 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5078 | Structural | Nesma & Partners |  |  |  |  | 2027-01-02
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5079 | LS & External Work Package 2 - Details 79 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5079 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5080 | LS & External Work Package 2 - Details 80 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5080 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5081 | LS & External Work Package 2 - Details 81 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5081 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5082 | LS & External Work Package 2 - Details 82 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5082 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5083 | LS & External Work Package 2 - Details 83 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5083 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5084 | LS & External Work Package 2 - Details 84 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5084 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5085 | LS & External Work Package 2 - Details 85 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-11 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5085 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5086 | LS & External Work Package 2 - Details 86 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5086 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5087 | LS & External Work Package 2 - Details 87 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5087 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5088 | LS & External Work Package 2 - Details 88 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5088 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5089 | LS & External Work Package 2 - Details 89 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5089 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5090 | LS & External Work Package 2 - Details 90 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5090 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5091 | LS & External Work Package 2 - Details 91 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5091 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5092 | LS & External Work Package 2 - Details 92 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5092 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5093 | LS & External Work Package 2 - Details 93 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5093 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5094 | LS & External Work Package 2 - Details 94 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5094 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5095 | LS & External Work Package 2 - Details 95 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5095 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5096 | LS & External Work Package 2 - Details 96 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5096 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5097 | LS & External Work Package 2 - Details 97 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5097 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5098 | LS & External Work Package 2 - Details 98 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5098 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5099 | LS & External Work Package 2 - Details 99 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5099 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL5100 | LS & External Work Package 2 - Details 100 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 5100 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6001 | LS & External Work Package 3 - Details 01 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6001 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6002 | LS & External Work Package 3 - Details 02 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6002 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6003 | LS & External Work Package 3 - Details 03 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6003 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6004 | LS & External Work Package 3 - Details 04 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6004 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6005 | LS & External Work Package 3 - Details 05 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6005 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6006 | LS & External Work Package 3 - Details 06 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6006 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6007 | LS & External Work Package 3 - Details 07 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6007 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6008 | LS & External Work Package 3 - Details 08 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6008 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6009 | LS & External Work Package 3 - Details 09 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6009 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6010 | LS & External Work Package 3 - Details 10 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6010 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6011 | LS & External Work Package 3 - Details 11 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6011 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6012 | LS & External Work Package 3 - Details 12 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6012 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6013 | LS & External Work Package 3 - Details 13 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6013 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6014 | LS & External Work Package 3 - Details 14 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6014 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6015 | LS & External Work Package 3 - Details 15 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6015 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6016 | LS & External Work Package 3 - Details 16 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6016 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6017 | LS & External Work Package 3 - Details 17 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6017 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6018 | LS & External Work Package 3 - Details 18 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6018 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6019 | LS & External Work Package 3 - Details 19 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6019 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6020 | LS & External Work Package 3 - Details 20 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6020 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6021 | LS & External Work Package 3 - Details 21 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6021 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6022 | LS & External Work Package 3 - Details 22 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6022 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6023 | LS & External Work Package 3 - Details 23 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6023 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6024 | LS & External Work Package 3 - Details 24 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6024 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6025 | LS & External Work Package 3 - Details 25 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6025 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6026 | LS & External Work Package 3 - Details 26 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6026 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6027 | LS & External Work Package 3 - Details 27 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6027 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6028 | LS & External Work Package 3 - Details 28 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6028 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6029 | LS & External Work Package 3 - Details 29 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6029 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6030 | LS & External Work Package 3 - Details 30 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6030 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6031 | LS & External Work Package 3 - Details 31 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6031 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6032 | LS & External Work Package 3 - Details 32 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6032 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6033 | LS & External Work Package 3 - Details 33 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6033 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6034 | LS & External Work Package 3 - Details 34 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6034 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6035 | LS & External Work Package 3 - Details 35 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6035 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6036 | LS & External Work Package 3 - Details 36 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6036 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6037 | LS & External Work Package 3 - Details 37 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6037 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6038 | LS & External Work Package 3 - Details 38 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6038 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6039 | LS & External Work Package 3 - Details 39 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6039 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6040 | LS & External Work Package 3 - Details 40 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6040 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6041 | LS & External Work Package 3 - Details 41 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6041 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6042 | LS & External Work Package 3 - Details 42 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6042 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6043 | LS & External Work Package 3 - Details 43 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6043 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6044 | LS & External Work Package 3 - Details 44 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6044 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6045 | LS & External Work Package 3 - Details 45 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6045 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6046 | LS & External Work Package 3 - Details 46 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6046 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6047 | LS & External Work Package 3 - Details 47 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6047 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6048 | LS & External Work Package 3 - Details 48 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6048 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6049 | LS & External Work Package 3 - Details 49 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6049 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6050 | LS & External Work Package 3 - Details 50 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6050 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6051 | LS & External Work Package 3 - Details 51 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6051 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6052 | LS & External Work Package 3 - Details 52 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6052 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6053 | LS & External Work Package 3 - Details 53 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6053 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6054 | LS & External Work Package 3 - Details 54 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6054 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6055 | LS & External Work Package 3 - Details 55 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6055 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6056 | LS & External Work Package 3 - Details 56 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6056 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6057 | LS & External Work Package 3 - Details 57 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6057 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6058 | LS & External Work Package 3 - Details 58 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6058 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6059 | LS & External Work Package 3 - Details 59 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6059 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6060 | LS & External Work Package 3 - Details 60 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6060 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6061 | LS & External Work Package 3 - Details 61 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6061 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6062 | LS & External Work Package 3 - Details 62 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6062 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6063 | LS & External Work Package 3 - Details 63 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6063 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6064 | LS & External Work Package 3 - Details 64 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6064 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6065 | LS & External Work Package 3 - Details 65 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6065 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6066 | LS & External Work Package 3 - Details 66 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6066 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6067 | LS & External Work Package 3 - Details 67 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6067 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6068 | LS & External Work Package 3 - Details 68 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6068 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6069 | LS & External Work Package 3 - Details 69 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6069 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6070 | LS & External Work Package 3 - Details 70 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6070 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6071 | LS & External Work Package 3 - Details 71 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6071 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6072 | LS & External Work Package 3 - Details 72 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6072 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6073 | LS & External Work Package 3 - Details 73 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6073 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6074 | LS & External Work Package 3 - Details 74 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6074 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6075 | LS & External Work Package 3 - Details 75 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6075 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6076 | LS & External Work Package 3 - Details 76 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6076 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6077 | LS & External Work Package 3 - Details 77 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6077 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6078 | LS & External Work Package 3 - Details 78 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6078 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6079 | LS & External Work Package 3 - Details 79 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6079 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6080 | LS & External Work Package 3 - Details 80 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6080 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6081 | LS & External Work Package 3 - Details 81 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6081 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6082 | LS & External Work Package 3 - Details 82 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6082 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6083 | LS & External Work Package 3 - Details 83 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6083 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6084 | LS & External Work Package 3 - Details 84 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6084 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6085 | LS & External Work Package 3 - Details 85 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6085 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6086 | LS & External Work Package 3 - Details 86 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6086 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6087 | LS & External Work Package 3 - Details 87 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6087 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6088 | LS & External Work Package 3 - Details 88 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6088 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6089 | LS & External Work Package 3 - Details 89 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6089 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6090 | LS & External Work Package 3 - Details 90 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6090 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6091 | LS & External Work Package 3 - Details 91 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6091 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6092 | LS & External Work Package 3 - Details 92 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6092 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6093 | LS & External Work Package 3 - Details 93 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6093 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6094 | LS & External Work Package 3 - Details 94 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6094 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6095 | LS & External Work Package 3 - Details 95 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6095 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6096 | LS & External Work Package 3 - Details 96 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6096 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6097 | LS & External Work Package 3 - Details 97 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6097 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6098 | LS & External Work Package 3 - Details 98 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6098 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6099 | LS & External Work Package 3 - Details 99 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6099 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-Z00000-3FL6100 | LS & External Work Package 3 - Details 100 |  | Structure | Revit | .dwg,.pdf | AS INDICATED | 2027-02-25 | LS & External Work | QP.E.CV.MBL.GEN.3600 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | Z00000 | 3 | FL | 6100 | Structural | Nesma & Partners |  |  |  |  | 2027-02-03
QF01012-NES-C04518-SDW-STR-00-CENT01-2L24820 | CENTRAL BLOCK L2 TO L5 WALLS GA ENLARGED PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-05-20 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 2 | L2 | 4820 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24823 | CENTRAL BLOCK L2 TO L5 WALLS GA SECTION ELEVATION L2 TO L3 SHEET 01 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-05-20 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4823 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24824 | CENTRAL BLOCK L2 TO L5 WALLS GA SECTION ELEVATION L2 TO L3 SHEET 02 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-05-20 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4824 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24825 | CENTRAL BLOCK L2 TO L5 WALLS GA SECTION ELEVATION L2 TO L3 SHEET 03 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-05-20 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4825 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-4L24850 | CENTRAL BLOCK L2 TO L5 DEEP BEAM ENLARGED PLAN |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-05-20 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 4 | L2 | 4850 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24851 | L2-L5 - DEEP BEAMS SECTIONS AND REINFORCEMENT DETAILS SHEET 1 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-05-20 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4851 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24852 | L2-L5 - DEEP BEAMS SECTIONS AND REINFORCEMENT DETAILS SHEET 2 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-05-20 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4852 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L24853 | L2-L5 - DEEP BEAMS SECTIONS AND REINFORCEMENT DETAILS SHEET 3 |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-05-20 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L2 | 4853 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-6L24854 | DEEP BEAMS BBS |  | Structure | Revit | .dwg,.pdf | 1:25 | 2026-05-20 | Central - Shear Walls GA from L2 to L3 | QP.E.CV.MBL.GEN.3180 | FI_60_25 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L2 | 4854 | Structural | Nesma & Partners |  |  |  |  | 2026-07-07
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66934 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 09 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6934 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66935 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 10 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6935 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66936 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 11 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6936 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66937 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 12 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6937 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66938 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 13 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6938 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66939 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 14 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6939 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66940 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 15 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6940 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66941 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 16 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6941 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66942 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 17 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6942 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66943 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 18 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6943 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66944 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 19 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6944 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66945 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 20 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6945 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66946 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 21 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6946 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66947 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 22 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6947 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66948 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 23 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6948 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66949 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 24 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6949 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66950 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 25 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6950 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66951 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 26 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6951 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66952 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 27 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6952 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-3L66953 | CENTRAL BLOCK SHEAR WALLS RFT SECTION ELEVATION SW1 L6 TO L8 SHEET 28 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 3 | L6 | 6953 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L66954 | CENTRAL BLOCK SHEAR WALLS RFT L6 TO L8 BBS SHEET- 01 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L6 | 6954 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L66955 | CENTRAL BLOCK SHEAR WALLS RFT L6 TO L8 BBS SHEET- 02 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L6 | 6955 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05
QF01012-NES-C04518-SDW-STR-00-CENT01-6L66956 | CENTRAL BLOCK SHEAR WALLS RFT L6 TO L8 BBS SHEET- 03 |  | Structure | Revit | .dwg,.pdf | NTS | 2026-10-08 | Central - Walls RFT From L6 to L8 | QP.E.CV.MBL.GEN.3280 | FI_90_75 | QF01012 | NES | C04518 | SDW | STR | 00 | CENT01 | 6 | L6 | 6956 | Structural | Nesma & Partners |  |  |  |  | 2026-11-05

## Baseline (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | Package | Activity Code | Activity | Original Duration | Start | Finish
Shop Drawings | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Shop Drawings ¦ Mobilization | QP.M.GN.GEN.GEN.1400 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Shop Drawings ¦ Mobilization ¦ Tower Crane Foundation - Concrete Works | QP.M.GN.GEN.GEN.1470 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Blades Below Loft | QP.M.GN.GEN.GEN.1540 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Loft | QP.M.GN.GEN.GEN.1560 | Submittal | 12 | 2026-08-29 | 2026-09-10
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Above Loft | QP.M.GN.GEN.GEN.1580 | Submittal | 12 | 2026-10-01 | 2026-10-14
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works | QP.E.CV.MBL.GEN.3460 | Submittal | 28 | 2025-10-11 | 2025-11-11
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works Outside Core Area | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works Outside Core Area | QP.E.CV.MBL.GEN.3540 | Submittal | 14 | 2025-11-12 | 2025-11-27
Shop Drawings | Civil | Blades | Blade 1 | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 1 | QP.E.CV.BL1.GEN.1060 | Submittal | 28 | 2026-02-21 | 2026-03-28
Shop Drawings | Civil | Blades | Blade 2 | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 2 | QP.E.CV.BL2.GEN.1060 | Submittal | 28 | 2026-01-19 | 2026-02-19
Shop Drawings | Civil | Blades | Blade 3 | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 3 | QP.E.CV.BL3.GEN.1060 | Submittal | 28 | 2025-12-17 | 2026-01-18
Shop Drawings | Civil | Blades | Blade 4 | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 4 | QP.E.CV.BL4.GEN.1060 | Submittal | 28 | 2025-12-03 | 2026-01-04
Shop Drawings | Civil | Blades | Blade 5 | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 5 | QP.E.CV.BL5.GEN.1060 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Civil | Parking | Parking | Parking | Parking | Parking | Shop Drawings ¦ Civil ¦ Parking | QP.E.CV.PAR.GEN.1000 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - Foundation Works Core Area | QP.E.CV.MBL.GEN.3000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 03 +887.750M | QP.E.CV.MBL.GEN.3030 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - SOG | QP.E.CV.MBL.GEN.3640 | Submittal | 14 | 2026-03-16 | 2026-04-02
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 02 - Foundation Works Outside Core Area | QP.E.CV.MBL.GEN.3020 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 02 +893.5M | QP.E.CV.MBL.GEN.3070 | Submittal | 21 | 2026-02-18 | 2026-03-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 01 +900.5M | QP.E.CV.MBL.GEN.3100 | Submittal | 28 | 2026-03-16 | 2026-04-19
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01- LOBBY LEVEL +905M | QP.E.CV.MBL.GEN.3120 | Submittal | 25 | 2026-04-20 | 2026-05-18
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01 - MEZZANINE +909M | QP.E.CV.MBL.GEN.3140 | Submittal | 15 | 2026-05-19 | 2026-06-08
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3180 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3380 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3220 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3400 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3240 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3420 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3260 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3440 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | QP.E.CV.MBL.GEN.3280 | Submittal | 25 | 2026-10-08 | 2026-11-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | QP.E.CV.MBL.GEN.3300 | Submittal | 28 | 2027-03-13 | 2027-04-13
Shop Drawings | Concrete | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Premium Theatre Concrete Works | QP.E.CV.MBL.GEN.3150 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Amphitheatre Concrete Works | QP.E.CV.MBL.GEN.3200 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Premium Theater | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Premium Theater | QP.E.CV.MBL.GEN.3660 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Loft and Adaptable Theatre | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Loft and Adaptable Theatre | QP.E.CV.MBL.GEN.3700 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Fly Tower | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Fly Tower | QP.E.CV.MBL.GEN.3710 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Lobby & Plaza | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Lobby & Plaza | QP.E.CV.MBL.GEN.3680 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Royal Majlis | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Royal Majlis | QP.E.CV.MBL.GEN.3740 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Foundation | QP.E.CV.BL1.GEN.1000 | Submittal | 25 | 2026-02-25 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL1.GEN.1040 | Submittal | 25 | 2026-03-29 | 2026-04-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL1.GEN.1080 | Submittal | 18 | 2026-05-12 | 2026-06-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL1.GEN.1020 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL1.GEN.1120 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL1.GEN.1100 | Submittal | 28 | 2026-10-27 | 2026-11-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Foundation | QP.E.CV.BL2.GEN.1000 | Submittal | 21 | 2026-03-02 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL2.GEN.1040 | Submittal | 21 | 2026-03-10 | 2026-04-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL2.GEN.1080 | Submittal | 18 | 2026-04-21 | 2026-05-11
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL2.GEN.1020 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL2.GEN.1140 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL2.GEN.1120 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Foundation | QP.E.CV.BL3.GEN.1000 | Submittal | 21 | 2026-02-07 | 2026-03-03
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Steel Composite Slab Including Embedded items Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Steel Composite Slab Including Embedded items Below Loft | QP.E.CV.BL3.GEN.1030 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL3.GEN.1080 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL3.GEN.1020 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Foundation | QP.E.CV.BL4.GEN.1000 | Submittal | 28 | 2026-01-05 | 2026-02-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL4.GEN.1030 | Submittal | 28 | 2026-02-24 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL4.GEN.1080 | Submittal | 15 | 2026-03-31 | 2026-04-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL4.GEN.1020 | Submittal | 28 | 2026-04-18 | 2026-05-19
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL4.GEN.1100 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL4.GEN.1120 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Foundation | QP.E.CV.BL5.GEN.1000 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL5.GEN.1030 | Submittal | 28 | 2026-03-23 | 2026-04-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL5.GEN.1080 | Submittal | 18 | 2026-03-31 | 2026-04-20
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL5.GEN.1020 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL5.GEN.1100 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL5.GEN.1120 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Foundation Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Foundation Including Embedded items | QP.E.CV.PAR.GEN.1020 | Submittal | 28 | 2027-04-28 | 2027-06-03
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Structural Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Structural Concrete Works Including Embedded items | QP.E.CV.PAR.GEN.1040 | Submittal | 28 | 2027-06-19 | 2027-07-20
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Below Loft | QP.E.ST.GEN.GEN.1090 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1100 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1110 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1050 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1060 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1070 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 3,4,5 | QP.E.ST.GEN.GEN.1000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | QP.E.ST.GEN.GEN.1010 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Truss below Auditorium, Side and Back Stage | QP.E.ST.GEN.GEN.2120 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1220 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1230 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1200 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1210 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1190 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Embedded part - Main Building Above Level 5 | QP.E.ST.GEN.GEN.1040 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Premium Theater - Frame Balconies and Back Stage Dressing | QP.E.ST.GEN.GEN.2140 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Loft and adaptable Theatre | QP.E.ST.GEN.GEN.1340 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1390 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1400 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1310 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1320 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1330 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1470 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ Truss above Auditorium Incl. Metal Deck | QP.E.ST.GEN.GEN.2100 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Temporay Tower ROYAL MAJLIS and Blades above loft | QP.E.ST.GEN.GEN.1490 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2160 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1520 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Truss above Flytower | QP.E.ST.GEN.GEN.2180 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1540 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ Blade 2 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2200 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ Adaptable Theatre Incl. Metal Deck | QP.E.ST.GEN.GEN.1560 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.2220 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Loft Truss and Infilled Beam North Side Incl. Metal Deck | QP.E.ST.GEN.GEN.1610 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1600 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Lobby and Plaza Incl. Metal Deck | QP.E.ST.GEN.GEN.1660 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Frame for Mezzanine | QP.E.ST.GEN.GEN.1670 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Link Bridge and Helix Stair | QP.E.ST.GEN.GEN.1570 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1680 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | Shop Drawings ¦ Structural Steel ¦ Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck ¦ ROYAL MAJLIS | QP.E.ST.GEN.GEN.1640 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1090 | Submittal | 21 | 2026-03-26 | 2026-04-19
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1120 | Submittal | 21 | 2026-09-15 | 2026-10-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Wall Cladding | QP.E.AF.MBL.GEN.4440 | Submittal | 21 | 2026-10-11 | 2026-11-03
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1100 | Submittal | 21 | 2026-11-04 | 2026-11-28
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ FFE | QP.E.AF.MBL.GEN.5260 | Submittal | 21 | 2026-11-29 | 2026-12-22
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1170 | Submittal | 21 | 2026-04-20 | 2026-05-13
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1200 | Submittal | 20 | 2026-11-04 | 2026-11-26
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5700 | Submittal | 21 | 2026-11-28 | 2026-12-21
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1180 | Submittal | 21 | 2026-12-23 | 2027-01-16
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ FFE | QP.E.AF.MBL.GEN.5280 | Submittal | 21 | 2027-01-17 | 2027-02-09
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1220 | Submittal | 21 | 2026-05-14 | 2026-06-10
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1250 | Submittal | 28 | 2026-11-28 | 2026-12-29
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5720 | Submittal | 21 | 2026-12-30 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1230 | Submittal | 21 | 2027-01-24 | 2027-02-16
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ FFE | QP.E.AF.MBL.GEN.5300 | Submittal | 21 | 2027-02-17 | 2027-03-16
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1310 | Submittal | 21 | 2026-06-11 | 2026-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1340 | Submittal | 28 | 2026-12-30 | 2027-01-31
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5800 | Submittal | 21 | 2027-02-01 | 2027-02-25
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1320 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ FFE | QP.E.AF.MBL.GEN.5320 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1400 | Submittal | 21 | 2026-07-06 | 2026-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1430 | Submittal | 20 | 2027-02-01 | 2027-02-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5740 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1410 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ FFE | QP.E.AF.MBL.GEN.5340 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1000 | Submittal | 21 | 2026-07-30 | 2026-08-23
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1030 | Submittal | 20 | 2027-02-25 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5760 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1010 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ FFE | QP.E.AF.MBL.GEN.5360 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1490 | Submittal | 21 | 2026-08-24 | 2026-09-16
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1520 | Submittal | 20 | 2027-03-23 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5820 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1500 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ FFE | QP.E.AF.MBL.GEN.5380 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1580 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1610 | Submittal | 20 | 2027-04-15 | 2027-05-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5840 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1590 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ FFE | QP.E.AF.MBL.GEN.5400 | Submittal | 21 | 2027-07-06 | 2027-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1670 | Submittal | 21 | 2026-12-20 | 2027-01-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1700 | Submittal | 20 | 2027-05-23 | 2027-06-14
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5860 | Submittal | 28 | 2027-06-15 | 2027-07-17
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1680 | Submittal | 28 | 2027-07-18 | 2027-08-18
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ FFE | QP.E.AF.MBL.GEN.5420 | Submittal | 28 | 2027-07-31 | 2027-08-31
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1760 | Submittal | 21 | 2027-01-19 | 2027-02-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1790 | Submittal | 21 | 2027-05-23 | 2027-06-15
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5880 | Submittal | 21 | 2027-07-18 | 2027-08-10
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1770 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ FFE | QP.E.AF.MBL.GEN.5440 | Submittal | 21 | 2027-09-01 | 2027-09-26
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1880 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1910 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5900 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1890 | Submittal | 21 | 2027-09-13 | 2027-10-07
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ FFE | QP.E.AF.MBL.GEN.5460 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1800 | Submittal | 21 | 2027-04-22 | 2027-05-20
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1830 | Submittal | 21 | 2027-07-25 | 2027-08-17
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5920 | Submittal | 21 | 2027-08-25 | 2027-09-18
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1810 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ FFE | QP.E.AF.MBL.GEN.5480 | Submittal | 21 | 2027-10-11 | 2027-11-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1110 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1140 | Submittal | 21 | 2027-05-31 | 2027-06-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1120 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1370 | Submittal | 21 | 2027-03-01 | 2027-03-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1360 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Wall Cladding | QP.E.AF.BL1.GEN.5940 | Submittal | 21 | 2027-07-19 | 2027-08-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1340 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1650 | Submittal | 21 | 2027-06-14 | 2027-07-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1680 | Submittal | 14 | 2027-09-01 | 2027-09-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1660 | Submittal | 21 | 2027-11-18 | 2027-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1080 | Submittal | 21 | 2027-05-26 | 2027-06-19
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1110 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Wall Cladding | QP.E.AF.BL2.GEN.5960 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1090 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1580 | Submittal | 21 | 2027-07-04 | 2027-07-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1610 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1590 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1670 | Submittal | 21 | 2027-07-28 | 2027-08-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1700 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1680 | Submittal | 14 | 2028-01-18 | 2028-02-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1000 | Submittal | 24 | 2026-11-15 | 2026-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1030 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL3.GEN.5980 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1010 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1340 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1370 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1350 | Submittal | 21 | 2027-12-22 | 2028-01-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1210 | Submittal | 24 | 2026-12-27 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1240 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL4.GEN.6000 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1220 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1820 | Submittal | 21 | 2027-04-24 | 2027-05-22
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1850 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1830 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1730 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1760 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1740 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.2280 | Submittal | 24 | 2027-02-07 | 2027-03-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.2340 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.2300 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1130 | Submittal | 21 | 2027-03-22 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1160 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1140 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1500 | Submittal | 28 | 2027-06-29 | 2027-07-31
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1530 | Submittal | 21 | 2027-10-10 | 2027-11-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Wall Cladding | QP.E.AF.BL5.GEN.6020 | Submittal | 21 | 2027-12-16 | 2028-01-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1510 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1000 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1020 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Doors / Openings | QP.E.AF.PAR.GEN.1010 | Submittal | 28 | 2027-12-22 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Specialities | QP.E.AF.MBL.GEN.5160 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1030 | Submittal | 28 | 2027-10-16 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1050 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Doors / Openings | QP.E.AF.PAR.GEN.1040 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Specialities | QP.E.AF.MBL.GEN.5200 | Submittal | 21 | 2028-01-09 | 2028-02-01
Shop Drawings | Architecture and Fitouts | Amphitheatre | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4040 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Architecture and Fitouts | Amphitheatre | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.4070 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Amphitheatre | Wall Cladding | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Wall Cladding | QP.E.AF.MBL.GEN.6040 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | Architecture and Fitouts | Amphitheatre | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4050 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | Shop Drawings ¦ External Building Works (Guard House, SEC Room) | QP.E.EX.GEN.GEN.1270 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Main Building | QP.E.AF.MBL.GEN.6060 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 5 | Water Proofing - Roof - Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 5 | QP.E.AF.BL5.GEN.6180 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 4 | Water Proofing - Roof - Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 4 | QP.E.AF.BL4.GEN.6160 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 3 | Water Proofing - Roof - Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 3 | QP.E.AF.BL3.GEN.6140 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 1 | Water Proofing - Roof - Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 1 | QP.E.AF.BL1.GEN.6100 | Submittal | 21 | 2027-12-09 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 2 | Water Proofing - Roof - Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 2 | QP.E.AF.BL2.GEN.6120 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Wet Areas | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Wet Areas ¦ Main Building | QP.E.AF.MBL.GEN.4400 | Submittal | 21 | 2027-08-08 | 2027-08-31
Shop Drawings | Specialist Systems | Doors/ Openings | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Main Building | QP.E.AF.MBL.GEN.1140 | Submittal | 20 | 2027-06-29 | 2027-07-21
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.1130 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 2 | QP.E.AF.BL2.GEN.1100 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.1020 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.1230 | Submittal | 21 | 2027-08-16 | 2027-09-08
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.2320 | Submittal | 21 | 2027-09-09 | 2027-10-04
Shop Drawings | Specialist Systems | Doors/ Openings | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Amphitheatre | QP.E.AF.MBL.GEN.4060 | Submittal | 28 | 2027-11-13 | 2027-12-14
Shop Drawings | Specialist Systems | Conveying System | Waste Management | Waste Management | Waste Management | Waste Management | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Waste Management | QP.E.CY.GEN.GEN.1280 | Submittal | 14 | 2027-12-02 | 2027-12-18
Shop Drawings | Specialist Systems | Conveying System | Escalators | Escalators | Escalators | Escalators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Escalators | QP.E.CY.GEN.GEN.1040 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | Specialist Systems | Conveying System | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | QP.E.CY.GEN.GEN.1020 | Submittal | 28 | 2026-10-22 | 2026-11-23
Shop Drawings | Specialist Systems | Conveying System | Truck Elevators | Truck Elevators | Truck Elevators | Truck Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Truck Elevators | QP.E.CY.GEN.GEN.1000 | Submittal | 28 | 2026-09-19 | 2026-10-21
Shop Drawings | Specialist Systems | Conveying System | Inclined Elevators | Inclined Elevators | Inclined Elevators | Inclined Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Inclined Elevators | QP.E.CY.GEN.GEN.1050 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Main Building | QP.E.CY.GEN.GEN.1090 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 1 | QP.E.CY.GEN.GEN.1130 | Submittal | 28 | 2027-10-17 | 2027-11-17
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 2 | QP.E.CY.GEN.GEN.1170 | Submittal | 28 | 2027-09-13 | 2027-10-16
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 3 | Balde 3 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 3 | QP.E.CY.GEN.GEN.1210 | Submittal | 28 | 2027-06-07 | 2027-07-08
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 4 | QP.E.CY.GEN.GEN.1110 | Submittal | 28 | 2027-07-10 | 2027-08-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 5 | Balde 5 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 5 | QP.E.CY.GEN.GEN.1150 | Submittal | 28 | 2027-08-11 | 2027-09-12
Shop Drawings | Specialist Systems | Joinery Works | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Main Building | QP.E.AF.MBL.GEN.5540 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.6120 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.6160 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.6180 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.6200 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Shop Drawings ¦ Specialist Systems ¦ Kitchen and Laundary | QP.E.AF.MBL.GEN.5500 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Specialist Systems | Water Features | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Specialist Systems ¦ Water Features | QP.E.AF.MBL.GEN.6100 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Mechanical | QP.E.ME.MBL.GEN.6780 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical | QP.E.ME.MBL.GEN.6800 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6840 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical | QP.E.ME.MBL.GEN.6850 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6860 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical | QP.E.ME.MBL.GEN.6870 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Mechanical | QP.E.ME.MBL.GEN.6900 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical | QP.E.ME.MBL.GEN.6910 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Mechanical | QP.E.ME.MBL.GEN.6940 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical | QP.E.ME.MBL.GEN.6950 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Mechanical | QP.E.ME.MBL.GEN.6980 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Electrical | QP.E.ME.MBL.GEN.6990 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Mechanical | QP.E.ME.MBL.GEN.7020 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical | QP.E.ME.MBL.GEN.7030 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7060 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical | QP.E.ME.MBL.GEN.7070 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7100 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical | QP.E.ME.MBL.GEN.7110 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Mechanical | QP.E.ME.MBL.GEN.7140 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical | QP.E.ME.MBL.GEN.7150 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Mechanical | QP.E.ME.MBL.GEN.7180 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Electrical | QP.E.ME.MBL.GEN.7190 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Mechanical | QP.E.ME.MBL.GEN.7220 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical | QP.E.ME.MBL.GEN.7230 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1320 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1330 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1340 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1350 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ ICT Containment | QP.E.ME.MBL.GEN.1360 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1420 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1430 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1440 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1450 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1460 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1740 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1750 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1760 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1770 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1780 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1590 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1600 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1610 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1620 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.1630 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2040 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2050 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2060 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2070 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ ICT Containment | QP.E.ME.MBL.GEN.2080 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2240 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2250 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2260 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2270 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ ICT Containment | QP.E.ME.MBL.GEN.2280 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2440 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2450 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2460 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2470 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.2480 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2640 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2650 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2660 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2670 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2680 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2850 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2860 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2870 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2880 | Submittal | 28 | 2026-12-08 | 2027-01-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2890 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3070 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3080 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3090 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3100 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ ICT Containment | QP.E.ME.MBL.GEN.3110 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3290 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3300 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3310 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3320 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ ICT Containment | QP.E.ME.MBL.GEN.3330 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3500 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3510 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3520 | Submittal | 28 | 2026-12-23 | 2027-01-24
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3530 | Submittal | 28 | 2027-02-11 | 2027-03-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ ICT Containment | QP.E.ME.MBL.GEN.3540 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.MBL.GEN.5000 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.MBL.GEN.5040 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.MBL.GEN.5060 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.MBL.GEN.5080 | Submittal | 28 | 2027-03-07 | 2027-04-10
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.MBL.GEN.7280 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.MBL.GEN.7300 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.MBL.GEN.7320 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.MBL.GEN.7260 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.MBL.GEN.7340 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | LPG System | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ LPG System | QP.E.ME.MBL.GEN.5100 | Submittal | 21 | 2027-09-22 | 2027-10-17
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.MBL.GEN.7360 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Fire Suppression | QP.E.ME.CBR.GEN.1000 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Plumbing | Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Plumbing | QP.E.ME.CBR.GEN.1011 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ LPG System | QP.E.ME.CBR.GEN.1055 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.CBR.GEN.1022 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Electrical | QP.E.ME.CBR.GEN.1033 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ ELV (Low Current System) | QP.E.ME.CBR.GEN.1044 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.MBL.GEN.7380 | Submittal | 28 | 2027-12-09 | 2028-01-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Diesel | Diesel | Diesel | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Diesel | QP.E.ME.MBL.GEN.7420 | Submittal | 21 | 2028-02-01 | 2028-02-26
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Water Features | Water Features | Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Water Features | QP.E.ME.MBL.GEN.7440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M | QP.E.ME.MBL.GEN.6520 | Submittal | 28 | 2026-06-14 | 2026-07-15
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Grey Water Treatment/ Sewage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Grey Water Treatment/ Sewage | QP.E.ME.MBL.GEN.1050 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Stromwater/ Drainage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Stromwater/ Drainage | QP.E.ME.MBL.GEN.1060 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1040 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M | QP.E.ME.MBL.GEN.6540 | Submittal | 28 | 2026-07-16 | 2026-08-17
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ AHU Room | QP.E.ME.MBL.GEN.1160 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Transformer/ Switchgear/ Panel Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Transformer/ Switchgear/ Panel Room | QP.E.ME.MBL.GEN.1240 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Generator Room/ Diesel Tank | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Generator Room/ Diesel Tank | QP.E.ME.MBL.GEN.1250 | Submittal | 14 | 2026-10-05 | 2026-10-20
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | ETS/ CWP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ ETS/ CWP Room | QP.E.ME.MBL.GEN.1170 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1030 | Submittal | 14 | 2026-09-24 | 2026-10-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1290 | Submittal | 28 | 2026-09-01 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M | QP.E.ME.MBL.GEN.6560 | Submittal | 14 | 2026-08-18 | 2026-09-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1020 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Domestic Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Domestic Water | QP.E.ME.MBL.GEN.1010 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Fire Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Fire Water | QP.E.ME.MBL.GEN.1000 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1280 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 LOBBY LEVEL +905.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 LOBBY LEVEL +905.00M | QP.E.ME.MBL.GEN.6640 | Submittal | 21 | 2026-09-03 | 2026-09-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 UPEER LOBBY LEVEL MEZZANINE +909M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M | QP.E.ME.MBL.GEN.6660 | Submittal | 21 | 2026-09-29 | 2026-10-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L2 THEATRE STALLS +913M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L2 THEATRE STALLS +913M | QP.E.ME.MBL.GEN.6680 | Submittal | 21 | 2026-10-24 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | QP.E.ME.MBL.GEN.6700 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | QP.E.ME.MBL.GEN.6720 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 SECOND CIRCLE AND LOFT +928.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 SECOND CIRCLE AND LOFT +928.00M | QP.E.ME.MBL.GEN.6740 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M | QP.E.ME.MBL.GEN.5540 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - AHU Room | QP.E.ME.MBL.GEN.1180 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Makeup Air Unit and Ecology | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Makeup Air Unit and Ecology | QP.E.ME.MBL.GEN.1190 | Submittal | 14 | 2027-01-06 | 2027-01-21
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Sky Garden Irrigation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Sky Garden Irrigation | QP.E.ME.MBL.GEN.1070 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L6 SKY GARDEN +935.85M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L6 SKY GARDEN +935.85M | QP.E.ME.MBL.GEN.6760 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M | QP.E.ME.MBL.GEN.6580 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | Plant Room - Fan Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M ¦ Plant Room - Fan Room | QP.E.ME.MBL.GEN.6600 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Kitchen and Laundry | Kitchen and Laundry | Kitchen and Laundry | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Kitchen and Laundry | QP.E.ME.MBL.GEN.7400 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | MEP | Panels | Panels | Panels | Panels | Panels | Shop Drawings ¦ MEP ¦ Panels | QP.E.ME.MBL.GEN.6510 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Mechanical | QP.E.ME.BL1.GEN.3720 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical | QP.E.ME.BL1.GEN.3740 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL1.GEN.3760 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL1.GEN.3780 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Mechanical | QP.E.ME.BL1.GEN.3800 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical | QP.E.ME.BL1.GEN.3820 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1020 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1030 | Submittal | 21 | 2027-02-25 | 2027-03-23
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1040 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1050 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ ICT Containment | QP.E.ME.BL1.GEN.1060 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL1.GEN.2940 | Submittal | 21 | 2027-04-11 | 2027-05-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.2950 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.2960 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.2970 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL1.GEN.2980 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1510 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1520 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1530 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1540 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ ICT Containment | QP.E.ME.BL1.GEN.1550 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.BL1.GEN.3280 | Submittal | 21 | 2027-08-30 | 2027-09-22
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL1.GEN.3320 | Submittal | 21 | 2027-10-07 | 2027-10-31
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL1.GEN.3340 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL1.GEN.3360 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL1.GEN.3580 | Submittal | 21 | 2027-11-15 | 2027-12-08
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL1.GEN.3600 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL1.GEN.3620 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL1.GEN.3680 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL1.GEN.3640 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL1.GEN.3660 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3480 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL1.GEN.1000 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL1.GEN.3700 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3400 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical | QP.E.ME.BL2.GEN.3420 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL2.GEN.3440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL2.GEN.3460 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3480 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical | QP.E.ME.BL2.GEN.3500 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1020 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1030 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1040 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1050 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.1060 | Submittal | 21 | 2027-04-18 | 2027-05-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1910 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1920 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1930 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1940 | Submittal | 21 | 2027-04-29 | 2027-05-27
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL2.GEN.1950 | Submittal | 21 | 2027-05-12 | 2027-06-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.2110 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.2120 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.2130 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.2140 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.2150 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL2.GEN.3160 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL2.GEN.3200 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL2.GEN.3220 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL2.GEN.3240 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL2.GEN.3260 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL2.GEN.3280 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL2.GEN.3300 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL2.GEN.3380 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL2.GEN.3320 | Submittal | 28 | 2027-11-22 | 2027-12-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL2.GEN.3340 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3500 | Submittal | 14 | 2028-02-17 | 2028-03-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL2.GEN.1000 | Submittal | 16 | 2028-02-17 | 2028-03-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL2.GEN.3360 | Submittal | 14 | 2028-04-09 | 2028-04-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Mechanical | QP.E.ME.BL3.GEN.3640 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical | QP.E.ME.BL3.GEN.3660 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical | QP.E.ME.BL3.GEN.3700 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Mechanical | QP.E.ME.BL3.GEN.3680 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1020 | Submittal | 21 | 2026-06-17 | 2026-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.1030 | Submittal | 21 | 2026-07-12 | 2026-08-04
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1040 | Submittal | 21 | 2026-08-05 | 2026-08-29
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1050 | Submittal | 21 | 2026-08-30 | 2026-09-22
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ ICT Containment | QP.E.ME.BL3.GEN.1060 | Submittal | 21 | 2026-10-07 | 2026-10-31
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1790 | Submittal | 21 | 2026-12-31 | 2027-01-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.3280 | Submittal | 21 | 2027-01-25 | 2027-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1810 | Submittal | 21 | 2027-02-18 | 2027-03-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1820 | Submittal | 21 | 2027-03-18 | 2027-04-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ ICT Containment | QP.E.ME.BL3.GEN.1830 | Submittal | 21 | 2027-04-12 | 2027-05-05
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL3.GEN.3400 | Submittal | 21 | 2027-06-23 | 2027-07-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL3.GEN.3440 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL3.GEN.3460 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL3.GEN.3480 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL3.GEN.3500 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL3.GEN.3540 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL3.GEN.3560 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL3.GEN.3620 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL3.GEN.3600 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL3.GEN.3580 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3520 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL3.GEN.1000 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL3.GEN.3520 | Submittal | 14 | 2028-04-04 | 2028-04-19
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Mechanical | QP.E.ME.BL4.GEN.6010 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical | QP.E.ME.BL4.GEN.6030 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Mechanical | QP.E.ME.BL4.GEN.6050 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Electrical | QP.E.ME.BL4.GEN.6070 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Mechanical | QP.E.ME.BL4.GEN.6090 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical | QP.E.ME.BL4.GEN.6110 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Fire Suppression | QP.E.ME.BL4.GEN.2110 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2120 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2130 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2140 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ ICT Containment | QP.E.ME.BL4.GEN.2150 | Submittal | 21 | 2026-11-01 | 2026-11-24
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2910 | Submittal | 21 | 2026-12-05 | 2026-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.5550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2930 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2940 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ ICT Containment | QP.E.ME.BL4.GEN.2950 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2810 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2820 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2830 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2840 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ ICT Containment | QP.E.ME.BL4.GEN.2850 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL4.GEN.5770 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL4.GEN.5810 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL4.GEN.5830 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL4.GEN.5850 | Submittal | 21 | 2027-09-29 | 2027-10-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL4.GEN.5870 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL4.GEN.5930 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL4.GEN.5950 | Submittal | 21 | 2027-12-05 | 2027-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL4.GEN.5890 | Submittal | 21 | 2028-01-12 | 2028-02-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL4.GEN.5970 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL4.GEN.5990 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3540 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL4.GEN.3110 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL4.GEN.5910 | Submittal | 14 | 2028-04-02 | 2028-04-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Mechanical | QP.E.ME.BL5.GEN.3040 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical | QP.E.ME.BL5.GEN.3060 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL5.GEN.3080 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL5.GEN.3100 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Mechanical | QP.E.ME.BL5.GEN.3120 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical | QP.E.ME.BL5.GEN.3140 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1020 | Submittal | 21 | 2026-10-29 | 2026-11-22
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1030 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1040 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1050 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ ICT Containment | QP.E.ME.BL5.GEN.1060 | Submittal | 21 | 2026-11-25 | 2026-12-19
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1560 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1570 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1580 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL5.GEN.1590 | Submittal | 21 | 2027-04-10 | 2027-05-03
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1750 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1760 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1770 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1780 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ ICT Containment | QP.E.ME.BL5.GEN.1790 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL5.GEN.2800 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL5.GEN.2840 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL5.GEN.2860 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL5.GEN.2880 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL5.GEN.3020 | Submittal | 14 | 2027-10-24 | 2027-11-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL5.GEN.2900 | Submittal | 14 | 2027-12-01 | 2027-12-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL5.GEN.2920 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL5.GEN.3000 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL5.GEN.2940 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL5.GEN.2960 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3560 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL5.GEN.1000 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL5.GEN.2980 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Mechanical | QP.E.ME.PAR.GEN.1459 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Electrical | QP.E.ME.PAR.GEN.1479 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Mechanical | QP.E.ME.PAR.GEN.1499 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Electrical | QP.E.ME.PAR.GEN.1519 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Fire Suppression | QP.E.ME.PAR.GEN.1000 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1011 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1022 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1033 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ ICT Containment | QP.E.ME.PAR.GEN.1044 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Fire Suppression | QP.E.ME.PAR.GEN.1055 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1066 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1077 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1088 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ ICT Containment | QP.E.ME.PAR.GEN.1099 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.PAR.GEN.1219 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.PAR.GEN.1259 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.PAR.GEN.1279 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.PAR.GEN.1299 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.PAR.GEN.1419 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.PAR.GEN.1319 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.PAR.GEN.1339 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.PAR.GEN.1439 | Submittal | 14 | 2028-02-07 | 2028-02-23
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.PAR.GEN.1359 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.PAR.GEN.1379 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.PAR.GEN.1399 | Submittal | 14 | 2028-03-09 | 2028-03-25
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3600 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3610 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3620 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.4430 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4440 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.4450 | Submittal | 14 | 2027-12-18 | 2028-01-02
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3960 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3970 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3980 | Submittal | 14 | 2028-01-01 | 2028-01-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Fire Suppression | QP.E.ME.MBL.GEN.3930 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3940 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Electrical | QP.E.ME.MBL.GEN.3950 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Fire Suppression | QP.E.ME.MBL.GEN.3810 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3820 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Electrical | QP.E.ME.MBL.GEN.3830 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4400 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4410 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4420 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4340 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4350 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4360 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4520 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4530 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4540 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4640 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4650 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4660 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3870 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3880 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3890 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3840 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3850 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3860 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.4550 | Submittal | 21 | 2028-02-08 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4560 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.4570 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 3, 4 & 5 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 3, 4 & 5 | QP.E.FA.GEN.GEN.1460 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 1 & 2 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 1 & 2 | QP.E.FA.GEN.GEN.2180 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Loft and Lobby | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Loft and Lobby | QP.E.FA.GEN.GEN.2140 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | QP.E.FA.GEN.GEN.2160 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Blades | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Blades | QP.E.FA.GEN.GEN.1820 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Lobby and Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Lobby and Loft | QP.E.FA.GEN.GEN.1770 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Above Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Above Loft | QP.E.FA.GEN.GEN.1780 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Blades | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Blades | QP.E.FA.GEN.GEN.1890 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Main Building | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Main Building | QP.E.FA.GEN.GEN.2230 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Facade | Facade | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 1 | QP.E.FA.GEN.GEN.1920 | Submittal | 28 | 2026-09-29 | 2026-10-31
Shop Drawings | Facade | Facade | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 2 | QP.E.FA.GEN.GEN.1930 | Submittal | 28 | 2026-08-26 | 2026-09-28
Shop Drawings | Facade | Facade | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 3 | QP.E.FA.GEN.GEN.1940 | Submittal | 28 | 2026-05-17 | 2026-06-21
Shop Drawings | Facade | Facade | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 4 | QP.E.FA.GEN.GEN.1950 | Submittal | 28 | 2026-06-22 | 2026-07-23
Shop Drawings | Facade | Facade | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 5 | QP.E.FA.GEN.GEN.1960 | Submittal | 28 | 2026-07-25 | 2026-08-25
Shop Drawings | Facade | Facade | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Facade ¦ Amphitheatre | QP.E.FA.GEN.GEN.2240 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Lobby | Lobby | Lobby | Lobby | Shop Drawings ¦ Facade ¦ Lobby | QP.E.FA.GEN.GEN.2090 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | Loft | Loft | Loft | Loft | Shop Drawings ¦ Facade ¦ Loft | QP.E.FA.GEN.GEN.2100 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Above Loft | Above Loft | Above Loft | Above Loft | Shop Drawings ¦ Facade ¦ Above Loft | QP.E.FA.GEN.GEN.1910 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | Link Bridges | Link Bridges | Link Bridges | Link Bridges | Shop Drawings ¦ Facade ¦ Link Bridges | QP.E.FA.GEN.GEN.2050 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Facade | Facade | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Shop Drawings ¦ Facade ¦ Facade Lighting Fixtures | QP.E.FA.GEN.GEN.1450 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | GRC Cladding | GRC Cladding | GRC Cladding | GRC Cladding | Shop Drawings ¦ Facade ¦ GRC Cladding | QP.E.FA.GEN.GEN.1390 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 1 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 1 | QP.E.CV.MBL.GEN.3060 | Submittal | 28 | 2026-08-06 | 2026-09-07
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 2 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 2 | QP.E.CV.MBL.GEN.3560 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 3 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 3 | QP.E.CV.MBL.GEN.3580 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 4 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 4 | QP.E.CV.MBL.GEN.3600 | Submittal | 28 | 2027-01-03 | 2027-02-03
Shop Drawings | External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Shop Drawings ¦ External Works ¦ Waterproofing for External Works | QP.E.EX.GEN.GEN.1040 | Submittal | 28 | 2026-06-25 | 2026-07-27
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Excavation | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Excavation | QP.E.CV.MBL.GEN.3320 | Submittal | 28 | 2027-01-06 | 2027-02-07
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Blinding Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Blinding Including Embedded Items | QP.E.CV.MBL.GEN.3500 | Submittal | 28 | 2027-02-23 | 2027-03-29
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Foundation Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Foundation Including Embedded Items | QP.E.CV.MBL.GEN.3480 | Submittal | 28 | 2027-04-13 | 2027-05-19
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Structural Concrete Works Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Structural Concrete Works Including Embedded Items | QP.E.CV.MBL.GEN.3520 | Submittal | 28 | 2027-06-03 | 2027-07-05
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4000 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Finishing | Finishing | Finishing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Finishing | QP.E.AF.MBL.GEN.4030 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4010 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Doors / Openings | QP.E.AF.MBL.GEN.4020 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Fire Suppression | QP.E.ME.MBL.GEN.1690 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Plumbing | Plumbing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Plumbing | QP.E.ME.MBL.GEN.1700 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.1710 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Electrical | Electrical | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Electrical | QP.E.ME.MBL.GEN.1720 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ ELV (Low Current System) | QP.E.ME.MBL.GEN.1730 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | External Utilities | Irrigation Works | Irrigation Works | Irrigation Works | Irrigation Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ Irrigation Works | QP.E.EX.GEN.GEN.1090 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Drainage Works | External Drainage Works | External Drainage Works | External Drainage Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Drainage Works | QP.E.EX.GEN.GEN.1110 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Lighting Works | External Lighting Works | External Lighting Works | External Lighting Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Lighting Works | QP.E.EX.GEN.GEN.1170 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | External Utilities | Low Current | Low Current | Low Current | Low Current | Shop Drawings ¦ External Works ¦ External Utilities ¦ Low Current | QP.E.EX.GEN.GEN.1100 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Shop Drawings ¦ External Works ¦ Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 | Submittal | 14 | 2027-08-07 | 2027-08-22
Shop Drawings | External Works | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Shop Drawings ¦ External Works ¦ Water and Environment | QP.E.EX.GEN.GEN.1220 | Submittal | 21 | 2026-11-23 | 2026-12-16
Shop Drawings | External Works | External Fixtures | External Fixtures | External Fixtures | External Fixtures | External Fixtures | Shop Drawings ¦ External Works ¦ External Fixtures | QP.E.EX.GEN.GEN.1260 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | External Works | LPG System | LPG System | LPG System | LPG System | LPG System | Shop Drawings ¦ External Works ¦ LPG System | QP.E.EX.GEN.GEN.1300 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Fit-out | Fit-out | Fit-out | Fit-out | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Fit-out | QP.C.PS.GEN.GEN.2590 | Submittal | 110 | 2026-07-30 | 2026-12-06
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Stage Engineering | Stage Engineering | Stage Engineering | Stage Engineering | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Stage Engineering | QP.C.PS.GEN.GEN.2560 | Submittal | 110 | 2026-12-07 | 2027-04-17
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | AV / Broadcast | AV / Broadcast | AV / Broadcast | AV / Broadcast | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ AV / Broadcast | QP.C.PS.GEN.GEN.1200 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ Technology (ICT) | QP.C.PS.GEN.GEN.1810 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Control Systems | Control Systems | Control Systems | Control Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Control Systems | QP.C.PS.GEN.GEN.1880 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Lighting Systems | Lighting Systems | Lighting Systems | Lighting Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Lighting Systems | QP.C.PS.GEN.GEN.1850 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Conveying System Finishes | QP.C.PS.GEN.GEN.2120 | Submittal | 150 | 2027-06-07 | 2027-11-29
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | HVAC System | HVAC System | HVAC System | HVAC System | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ HVAC System | QP.C.PS.GEN.GEN.2100 | Submittal | 90 | 2027-11-01 | 2028-02-13
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | ID Finishes | ID Finishes | ID Finishes | ID Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ ID Finishes | QP.C.PS.GEN.GEN.1930 | Submittal | 90 | 2027-07-18 | 2027-10-31
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Water Features | QP.C.PS.GEN.GEN.1960 | Submittal | 120 | 2027-02-16 | 2027-07-13
Shop Drawings | Provisional Sums | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | Shop Drawings ¦ Provisional Sums ¦ PS5 - Signage and Wayfinding | QP.C.PS.GEN.GEN.2140 | Submittal | 60 | 2028-07-29 | 2028-10-07
Shop Drawings | Provisional Sums | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | Shop Drawings ¦ Provisional Sums ¦ PS6 - Soft Landscaping | QP.C.PS.GEN.GEN.2180 | Submittal | 160 | 2027-08-30 | 2028-03-08
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Concrete Superstructure | QP.C.PS.GEN.GEN.2360 | Submittal | 30 | 2028-06-08 | 2028-07-12
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Foundation | Foundation | Foundation | Foundation | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Foundation | QP.C.PS.GEN.GEN.2260 | Submittal | 30 | 2028-05-01 | 2028-06-07
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Landscape | Landscape | Landscape | Landscape | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Landscape | QP.C.PS.GEN.GEN.2320 | Submittal | 30 | 2028-07-31 | 2028-09-03
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Promenade Bridge MEP | QP.C.PS.GEN.GEN.2340 | Submittal | 30 | 2028-06-26 | 2028-07-30
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Technology (ICT) | QP.C.PS.GEN.GEN.2400 | Submittal | 150 | 2027-04-11 | 2027-10-07
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Traffic & Car Parking | QP.C.PS.GEN.GEN.2500 | Submittal | 150 | 2027-07-12 | 2028-01-03

## Picklists (hidden)
| #VALUE! |  | Numbering System Document - Metadata Mapping
DOCUMENT NUMBERING DROPDOWN ATTRIBUTES | [18 empty] | QIC GENERAL DROPDOWN ATTRIBUTES
FIELD 01 - PROJECT CODE |  | FIELD 02 - ORIGINATOR |  | FIELD 03 - CONTRACT REFERENCE |  | FIELD 04 - DOCUMENT TYPES |  | FIELD 05 - DISCIPLINE |  | FIELD 06 - AREA/ZONE |  | FIELD 07 - VENUE/BUILDING |  | FIELD 08 - SERIAL NUMBER |  |  |  |  | DOCUMENT DETAILS |  |  | SUITABILITY STATUS |  | NAP GENERAL DROPDOWN ATTRIBUTES
Ab. 01 | 1 - Project Name | Ab. 02 | 2 - Originator Name | Ab. 03 | 3 - Contract Reference | Ab. 04 | 4 - Document Type | Ab. 05 | 5 - Discipline | Ab. 06 | 6 - Area/Zone | Ab. 07 | 7 - Venue/Building | Ab. 08A | 8A - Drawing Type | Ab. 08B | 8B - Level | 8C - Sequence Number | Authoring Software | File/Exchange Format | Scope Area | Code | Status | Scale | Classification ID | Classification | Corporate Discipline | Author
QF01012 | Qiddaya Performing Arts Center | NES | Nesma and Partners | C04518 | Contract Number | AGD | Agenda | ACO | Acoustic | 00 | Overall | Z00000 | Overall | 0 | General (General Notes, Abbreviations, Legends, Single Line Diagrams, General Detail) | 00 | Non-Specific ( For Blade ) | 4 Digit Sequence Number For Drawings/Models | Revit | .rvt | Design Management | S0 (WIP) | Initial status or WIP | NTS | FI_60_25 | Drawing | Architectural | Nesma & Partners
[6 empty] | AVV | Agreed Value of Variation | ADM | Administration | 01 | Zone Sheet 1 | CENT01 | Center Block | 1 | Elevations (Vertical View) | B1 | Basement 1 - Parking A +900.50 | 3 Digit Sequence Number For Documents | Civil3D | .nwc | Architecture / LDC | S1 (Shared) | Suitable for Coordination | AS INDICATED | FI_90_75 | Schedule or table | Electrical | JINGGONG
[6 empty] | ASB | As Built | ARC | Architectural | 02 | Zone Sheet 2 | GARD01 | Guard House | 2 | Plans (Overall, Horizontal View, Floor Plan, Ceiling Plan, Site Plan, Loading Plan) | B2 | Basement 2 - Service +893.50 |  | MicrosoftWord | .nwd | Landscape | S2 (Shared) | Suitable for Information | 1:1 | FI_60_53 | Model | Façade | ALUTEC
[6 empty] | AUR | Audit Report | ADT | Area Development | 03 | Zone Sheet 3 | BLAD01 | Blade 01 | 3 | Sections (Sectional View, Wall Section, Riser) | B3 | Basement 3 - Promenade +887.750 |  | MicrosoftExcel | .ifc | Interior Design | S3 (Shared) | Suitable for Review and Comment | 1:2 | FI_60_15 | Clash Rendition | Fire & Life Safety | AFCO
[6 empty] | BOQ | Bill of Quantities | ASM | Assets Management | 04 | Zone Sheet 4 | BLAD02 | Blade 02 | 4 | Large-scale Views (Enlarged Details) (Plans, Elevations, Stair Sections, etc) | FL | Foundation level |  | Navisworks | .pdf | Signage & Wayfinding | S4 (Shared) | Suitable for Review and Authorisation | 1:5 | FI_40_10 | Calculations | Interior Design | DOKA
[6 empty] | BEP | BIM Execution Plan | AVL | Audio Visual | 05 | Zone Sheet 5 | BLAD03 | Blade 03 | 5 | Details (Any detail view, such as Wall / Floor / Manhole Detail, etc) | L1 | Lobby Level +905.0 |  | inDesign | .jpg | Public Interaction & Activation | S5 (Shared) | Suitable for Review and Acceptance | 1:10 | FI_90_72 | Report | Infrastructure | RAWABI
[6 empty] | BIM | BIM Model | AUV | Audio/Video | 06 | Zone Sheet 6 | BLAD04 | Blade 04 | 6 | Schedules and Diagrams | L2 | Theater Stalls +913.0 |  | Inviso | .xls | Structure | A1 (Published) | Authorised and Accepted-Concept Design | 1:20 | FI_10_90 | Transmittal | Landscape | FALLPROTEC
[6 empty] | BRF | Brief | BRG | Bridges | 07 | Zone Sheet 7 | BLAD05 | Blade 05 | 7 | Combination of different views | L3 | Stalles Mezz & AD Theater +917.5 |  | JPG | .xer | Geotechnical Engineering | A2 (Published) | Authorised and Accepted-Schematic Design 100% | 1:25 | FI_90_47 | Log | Mechanical | TKE
[6 empty] | BUD | Budget | BRC | Broadcast | 08 | Zone Sheet 8 | MBLAD1 | Mini Blade 01 | 8 | User-Defined (For types that do not fall in other categories) | L4 | First Circle & AD Theater +921.0 |  | Recap | .dwf | Civil Engineering | A3 (Published) | Authorised and Accepted-Detailed Design 100% | 1:50 | FI_80_50 | Method statement | Structural | Subcontractor - Unassigned
[6 empty] | CAL | Calculation | BIM | Building Information Modelling | 09 | Zone Sheet 9 | MBLAD4 | Mini Blade 04 | 9 | 3D Representation (Isometric, Perspectives, Photographes) | L5 | Second Circle & Loft |  | Rhino | .dwg | MEP Engineering | A4 (Published) | Authorised and Accepted-Tender | 1:100 | FI_90_64 | Plan |  | Provisional Sum
[6 empty] | CER | Certificate | BMS | Building Management System | 10 | Zone Sheet 10 | SECE01 | SEC Room |  |  | L6 | SKY Garden +935.85 |  | Sketchup | .bcf | Fire & Life Safety | A5 (Published) | Authorised and Accepted-IFC | 1:150
[6 empty] | COR | Change Order | CWC | Chilled Water / Cooling | 11 | Zone Sheet 11 | PARK01 | Parking Building |  |  | L8 | Royal Majlis +948.10M |  | Autocad | .3ds | Pitch Design & Sports Playing Surfaces | A6 (Published) | Authorised and Accepted-Construction (Shop Drawing) | 1:200
[6 empty] | CRA | Change Request Authorization | CIV | Civil | 12 | Zone Sheet 12 |  |  |  |  | M1 | Mez Upper Lobby +909.0 |  | ArcGIS | .skp | Specialist Lighting (Services and Systems) | A7 (Published) | Authorised and Accepted-As Built | 1:250
[6 empty] | CDT | Clash Detection Report | CPM | Contracts & Procurement | 13 | Zone Sheet 13 |  |  |  |  | M2 | Mez Loft MEP +931.10 |  |  | .docx | Acoustics | A8(Published) | Authorised and Accepted-In Use | 1:300
[6 empty] | CLM | Claim | CIN | Controls & Instrumentation | 14 | Zone Sheet 14 |  |  |  |  | RL | Roof Level |  |  | .rvt,.nwd,.ifc | AV / Broadcast |  |  | 1:350
[6 empty] | CIN | Client Instruction | CRE | Creative Designer | 15 | Zone Sheet 15 |  |  |  |  | ZZ | Overall |  |  | .nwc,.nwd,.ifc | Security |  |  | 1:500
[6 empty] | CRS | Comments Resolution Sheet | CDM | Crowd Management | 16 | Zone Sheet 16 | [8 empty] | .dwg,.nwc,.ifc | Vertical Transport
[6 empty] | CON | Contract | CUL | Culvert | 17 | Zone Sheet 17 | [8 empty] | .docx,.pdf | Facade & Roof Envelope
[6 empty] | COS | Cost Estimate | DRN | Drainage | 18 | Zone Sheet 18 | [8 empty] | .xer,.pdf | Crowd Modelling / Pedestrian Flow
[6 empty] | DAB | Dashboard | ELP | Earthing & Lighting Protection | 19 | Zone Sheet 19 | [8 empty] | .xls,.pdf | Sustainability
[6 empty] | DOA | Delegation of Authority | ELE | Electrical | 20 | Zone Sheet 20 | [8 empty] | .msp,.pdf | Accessibility
[6 empty] | DES | Design | ELC | Electrical Containment | 21 | Zone Sheet 21 | [8 empty] | .dwg,.pdf | Architect of Record
[6 empty] | MTX | Distribution Matrix | ENV | Environmental | 22 | Zone Sheet 22 | [8 empty] | .indd | Food & Beverage & Operations
[6 empty] | DSS | Dossier | EQP | Equipment | 23 | Zone Sheet 23 | [8 empty] | .pdf, .indd | Utilities, Roads & Infrastructure
[6 empty] | DRW | Drawing | FAC | Facade | 24 | Zone Sheet 24 | [8 empty] | .rvt,.nwc,.ifc | Traffic & Car Parking
[6 empty] | ENI | Engineer Instruction | FED | Federated | 25 | Zone Sheet 25 | [8 empty] | .gdb | Technology (ICT)
[6 empty] | EXP | Expenses | FIN | Finance | 26 | Zone Sheet 26 | [9 empty] | Sports & Specialist Lighting
[6 empty] | HOC | Handover Certificate | FAE | Fire Alarm & Emergency Lighting | 27 | Zone Sheet 27 | [9 empty] | BMS & Access Control
[6 empty] | IRT | Incident Report | FLS | Fire Life Safety | 28 | Zone Sheet 28 | [9 empty] | Waste Management
[6 empty] | ITP | Inspection & Test Plan | FPR | Fire Protection | [11 empty] | Health & Safety in Design
[6 empty] | INS | Instruction | FFE | Furniture Fixture & Equipment | [11 empty] | Wind
[6 empty] | IAB | Insurance and Bonds | GEN | General
[6 empty] | INV | Invoice | GIS | Geospatial Information System
[6 empty] | LAR | Laydown Area Access Request | GEH | Geotechnical & Hydraulics
[6 empty] | LTR | Letter | GRA | Graphics
[6 empty] | LIC | License | HSE | Health and Safety
[6 empty] | LST | List | EHV | High Voltage
[6 empty] | MAN | Manual | HVC | HVAC
[6 empty] | MPL | Master Plan | ICT | Information & Communication Technology
[6 empty] | MAR | Material Approval Request | INF | Infrastructure
[6 empty] | MIR | Material Inspection Request | INS | Installation
[6 empty] | MST | Method Statement | ITS | Intelligent Transportation System
[6 empty] | MOM | Minutes of Meeting | INT | Interior Design
[6 empty] | MIX | Mix Design | IRR | Irrigation
[6 empty] | MOD | Model | KNL | Kitchen & Laundry
[6 empty] | MRP | Monthly Report | LSE | Landscape
[6 empty] | NOC | No Objection Certificate | ELL | Lighting
[6 empty] | NCR | Non-Conformance Report | LTC | Lighting Control
[6 empty] | NDA | Non-Disclosure Agreement | ELV | Low Voltage
[6 empty] | NTC | Notice | LPG | LPG
[6 empty] | OMM | Operation & Maintenance Manual | MAR | Marine Engineering
[6 empty] | ORC | Organizational Chart | MPL | Master Planning
[6 empty] | OTR | Overtime Request | MEC | Mechanical
[6 empty] | PAP | Payment Application | EMV | Medium Voltage
[6 empty] | PYC | Payment Certificate | MEP | MEPF
[6 empty] | PRM | Permit | NTD | Non-Technical Document
[6 empty] | PAF | Personnel Approval Form | OSE | Operating Supplies and Equipment
[6 empty] | PIV | Photographs, Images & Videos | OTH | Others
[6 empty] | PLN | Plan | PLB | Plumbing
[6 empty] | PLT | Plant | PTW | Potable Water
[6 empty] | PPG | Policy & Procedure | PJC | Project Control
[6 empty] | PQS | Prequalification Submittal | QMS | Quality Management
[6 empty] | PRE | Presentation | RID | Rides
[6 empty] | PRO | Procedure | ERL | Road Lighting
[6 empty] | PEP | Project Execution Plan | RKW | Rockwork
[6 empty] | PRS | Proposal | SEC | Security System
[6 empty] | POR | Purchase Order | SEW | Sewage
[6 empty] | REG | Register | SHW | Show
[6 empty] | REP | Report | SGN | Signage / Wayfinding
[6 empty] | RFC | Request For Change | ESP | Small Power
[6 empty] | RSM | Resume | SSC | Smart City
[6 empty] | SVR | Safety Violation Report | SPL | Specialist Lighting
[6 empty] | SMP | Sample | SWD | Storm Water Drainage
[6 empty] | SCH | Schedule | STR | Structural
[6 empty] | SDW | Shop Drawing | SUR | Surveying / Mapping
[6 empty] | SIN | Site Instruction | SUS | Sustainability
[6 empty] | SOR | Site Observation Report | TEL | Telecommunication
[6 empty] | SPE | Specification | TNC | Testing/Commissioning
[6 empty] | STD | Standard | TFC | Traffic System
[6 empty] | SFA | Statement of Final Account | UTI | Utilities
[6 empty] | STR | Strategy | VNT | Ventilation Ductwork
[6 empty] | TOC | Taking Over Certificate | VTR | Vertical Transportation
[6 empty] | TOR | Task Order | VES | Voice Evacuation
[6 empty] | TEM | Template | WSM | Waste Management
[6 empty] | TDC | Tender Document | WTR | Water
[6 empty] | TRP | Test Report | CTV | CCTV System
[6 empty] | TMS | Time Sheet | ACS | Access Control System
[6 empty] | VOR | Variation Order | EFL | Facade Lighting
[6 empty] | WAR | Warranty / Guarantees | DES | Diesel
[6 empty] | WRP | Weekly Report | SMK | Smoke Ductwork
[6 empty] | WIR | Work Inspection Request | STL | Steel Structure
[6 empty] | RLM | RedLine Mark Drawing | FWR | Formwork
[6 empty] | MDP | Master Information Delivery Plan | ELS | Emergency Lighting system
[6 empty] | TDP | Task Information Delivery Plan | EBW | Electrical Builder Works
[8 empty] | MBW | Mechanical Builder Works
[8 empty] | EBC | Electrical Busway
[8 empty] | WFT | Water Features
[8 empty] | LOG | Logistics