## TIDP_Sheet
TASK INFORMATION DELIVERY PLAN (TIDP)
CLIENT | Qiddiya | #VALUE!
PROJECT | Qiddiya Performing Arts Center (QPAC)
ORGANISATION | Nesma & Partners
DISCIPLINE | Electrical
APPROVER | BSBG
DATE CREATED
DATE LAST UPDATED
REVISION NUMBER | 00
DOCUMENT REFERENCE | QF01012-NES-C04518-TDP-ELE-00-000000-000001
This document shall be populated and kept up-to-date by the task team | [10 empty] | REFER TO THE FILE NAMING CONVENTION IN THE BIM EXECUTION PLAN | [10 empty] | DATA EXCHANGE #01 | [5 empty] | DATA EXCHANGE #02
[11 empty] | DOC REFERENCE GENERATOR | [10 empty] | STAGE: | CONSTRUCTION |  |  |  |  | STAGE: | HAND OVER
[22 empty] | PROGRAMME REF: | [5 empty] | PROGRAMME REF:
[5 empty] | EXCHANGE FORMATS | [5 empty] | FIELD 01 | FIELD 02 | FIELD 03 | FIELD 04 | FIELD 05 | FIELD 06 | FIELD 07 | FIELD 08 |  |  |  |  | LEVEL OF INFORMATION NEED | [5 empty] | LEVEL OF INFORMATION NEED
DOCUMENT NUMBER | DOCUMENT TITLE | EXTRACTED FROM MODEL | SCOPE AREA | AUTHORING SOFTWARE | EXCHANGE FORMAT | SCALE | DELIVERY MILESTONE | PACKAGE NAME | ACTIVITY ID | CLASSIFICATION CODE | PROJECT | ORIGINATOR | CONTRACT | DOCUMENT TYPE | DISCIPLINE | AREA/ZONE | VENUE/BUILDING | DRAWING TYPE | LEVEL | SEQUENCE NUMBER | CORPORATE DISCIPLINE | 01-AUTHOR | 01-GEOMETRICAL | 01-NON GEOMETRICAL | 01-DURATION (DAYS) | 01-PREDECESSOR | 01-EXCHANGE DATE | 02-AUTHOR | 02-GEOMETRICAL | 02-NON GEOMETRICAL | 02-DURATION (DAYS) | 02-PREDECESSOR | 02-EXCHANGE DATE
QF01012-NES-C04518-CAL-ELE-00-Z00000-000001 | B3 Supporting System Load Calculation |  | MEP Engineering | Revit | .rvt,.nwc,.ifc | AS INDICATED | 2026-04-15 | Power | QP.E.ME.MBL.GEN.1350 | FI_60_53 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-25
QF01012-NES-C04518-CAL-ELE-00-Z00000-000002 | BOH LIGHTING LUX CALCULATION REPORT | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2027-02-15 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELE-00-Z00000-000003 | BOH EMERGENCY LIGHTING LUX CALCULATION REPORT | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2027-02-15 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELE-00-Z00000-000004 | CENTRAL BATTERY SYSTEM SIZING CALCULATIONS | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2027-01-15 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELE-00-Z00000-000005 | CABLE CALCULATION - ETAP STUDY | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2027-02-15 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELE-00-Z00000-000006 | SEC MRMU ROOM LIGHTING LUX CALCULATION | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2027-01-15 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELE | 00 | Z00000 | 0 | 00 | 006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELP-00-Z00000-000001 | Calculation for Earthing and Lightning protection system | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2026-01-29 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELP | 00 | Z00000 | 0 | 00 | 001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ELP-00-Z00000-000002 | Calculation for Lightning Protection Risk Assessment | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .pdf | NTS | 2026-07-27 | Electrical Calculation | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ELP | 00 | Z00000 | 0 | 00 | 002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-ICT-00-Z00000-000001 | FIBER OPTIC CABLE LOSS CALCULATION | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | MicrosoftWord | .dwg,.pdf | NTS | 2027-04-22 | ICT | QP.E.ME.CBR.GEN.1033 | FI_40_10 | QF01012 | NES | C04518 | CAL | ICT | 00 | Z00000 | 0 | 00 | 001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-CAL-SEC-00-Z00000-000001 | CCTV COVERAGE AND STORAGE CALCULATION REPORT | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | MicrosoftWord | .dwg,.pdf | NTS | 2027-04-22 | SECURITY | QP.E.ME.CBR.GEN.1044 | FI_40_10 | QF01012 | NES | C04518 | CAL | SEC | 00 | Z00000 | 0 | 00 | 001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-AUV-00-Z00000-0ZZ0101 | AUDIO VISUAL INSTALLATION DETAILS - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 0 | ZZ | 0101 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-00-Z00000-0ZZ0102 | AUDIO VISUAL INSTALLATION DETAILS - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 0 | ZZ | 0102 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-00-Z00000-0ZZ0103 | AUDIO VISUAL INSTALLATION DETAILS - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 0 | ZZ | 0103 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-00-Z00000-0ZZ0104 | AUDIO VISUAL INSTALLATION DETAILS - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 0 | ZZ | 0104 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AUV-00-Z00000-0ZZ0105 | AUDIO VISUAL INSTALLATION DETAILS - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | AUDIO VISUAL | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AUV | 00 | Z00000 | 0 | ZZ | 0105 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-Z00000-0ZZ0101 | BACKGROUND MUSIC INSTALLATION DETAILS - SHEET 1 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 0 | ZZ | 0101 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-Z00000-0ZZ0102 | BACKGROUND MUSIC INSTALLATION DETAILS - SHEET 2 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 0 | ZZ | 0102 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-Z00000-0ZZ0103 | BACKGROUND MUSIC INSTALLATION DETAILS - SHEET 3 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 0 | ZZ | 0103 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-Z00000-0ZZ0104 | BACKGROUND MUSIC INSTALLATION DETAILS - SHEET 4 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 0 | ZZ | 0104 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-AVL-00-Z00000-0ZZ0105 | BACKGROUND MUSIC INSTALLATION DETAILS - SHEET 5 | QF01012-NES-C04518-MOD-AVL-00-Z00000-0000001 | AV / Broadcast | Revit | .dwg,.pdf | NTS | 2026-12-31 | BACKGROUND MUSIC | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | AVL | 00 | Z00000 | 0 | ZZ | 0105 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-00-Z00000-0ZZ0101 | STANDARD INSTALLATION DETAILS - CCTV SYSTEM - SHEET 1 | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | Z00000 | 0 | ZZ | 0101 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-CTV-00-Z00000-0ZZ0111 | STANDARD INSTALLATION DETAILS - VEHICLE ACCESS CONTROL TOTEM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | CTV | 00 | Z00000 | 0 | ZZ | 0111 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-EBW-01-BLAD01-2ZZ0001 | ELECTRICAL BUILDER WORK - BLADE-01-STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-15 | Electrical Builder Work | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD01 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-EBW-01-BLAD01-2ZZ0002 | ELECTRICAL BUILDER WORK - BLADE-01-STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-15 | Electrical Builder Work | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD01 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-EBW-01-BLAD01-2ZZ0003 | ELECTRICAL BUILDER WORK - BLADE-01-STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | Electrical Builder Work | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD01 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-EBW-01-BLAD01-2ZZ0004 | ELECTRICAL BUILDER WORK - BLADE-01-STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | Electrical Builder Work | QP.E.ME.BL1.GEN.3820 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD01 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-01
QF01012-NES-C04518-SDW-EBW-01-BLAD02-2ZZ0001 | ELECTRICAL BUILDER WORK - BLADE-02-STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-15 | Electrical Builder Work | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD02 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-EBW-01-BLAD02-2ZZ0002 | ELECTRICAL BUILDER WORK - BLADE-02-STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-15 | Electrical Builder Work | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD02 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-EBW-01-BLAD02-2ZZ0003 | ELECTRICAL BUILDER WORK - BLADE-02-STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | Electrical Builder Work | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD02 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-EBW-01-BLAD02-2ZZ0004 | ELECTRICAL BUILDER WORK - BLADE-02-STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | Electrical Builder Work | QP.E.ME.BL2.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD02 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-03-07
QF01012-NES-C04518-SDW-EBW-01-BLAD03-2ZZ0001 | ELECTRICAL BUILDER WORK - BLADE-03-STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-15 | Electrical Builder Work | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD03 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-EBW-01-BLAD03-2ZZ0002 | ELECTRICAL BUILDER WORK - BLADE-03-STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-15 | Electrical Builder Work | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD03 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-EBW-01-BLAD03-2ZZ0003 | ELECTRICAL BUILDER WORK - BLADE-03-STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | Electrical Builder Work | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD03 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-EBW-01-BLAD03-2ZZ0004 | ELECTRICAL BUILDER WORK - BLADE-03-STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | Electrical Builder Work | QP.E.ME.BL3.GEN.3700 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD03 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-05-24
QF01012-NES-C04518-SDW-EBW-01-BLAD04-2ZZ0001 | ELECTRICAL BUILDER WORK - BLADE-04-STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-15 | Electrical Builder Work | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD04 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-EBW-01-BLAD04-2ZZ0002 | ELECTRICAL BUILDER WORK - BLADE-04-STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-15 | Electrical Builder Work | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD04 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-EBW-01-BLAD04-2ZZ0003 | ELECTRICAL BUILDER WORK - BLADE-04-STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | Electrical Builder Work | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD04 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-EBW-01-BLAD04-2ZZ0004 | ELECTRICAL BUILDER WORK - BLADE-04-STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | Electrical Builder Work | QP.E.ME.BL4.GEN.6070 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD04 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-EBW-01-BLAD05-2ZZ0001 | ELECTRICAL BUILDER WORK - BLADE-05-STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-03-15 | Electrical Builder Work | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD05 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-EBW-01-BLAD05-2ZZ0002 | ELECTRICAL BUILDER WORK - BLADE-05-STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-03-15 | Electrical Builder Work | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD05 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-EBW-01-BLAD05-2ZZ0003 | ELECTRICAL BUILDER WORK - BLADE-05-STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-03-30 | Electrical Builder Work | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD05 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-EBW-01-BLAD05-2ZZ0004 | ELECTRICAL BUILDER WORK - BLADE-05-STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-03-30 | Electrical Builder Work | QP.E.ME.BL5.GEN.3140 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | BLAD05 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-14
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0005 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 3 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-15 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0006 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 3 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-15 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0007 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 4 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0008 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 4 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ELE-00-BLAD01-6ZZ0001 | ELECTRICAL DB SCHEDULE – BLADE-01- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD01 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD01-6ZZ0002 | ELECTRICAL DB SCHEDULE – BLADE-01- 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD01 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD01-6ZZ0003 | ELECTRICAL DB SCHEDULE – BLADE-01- 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD01 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD01-6ZZ0004 | ELECTRICAL CBS SCHEDULE – BLADE-01- 01 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL CBS SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD01 | 6 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD03-6ZZ0001 | ELECTRICAL DB SCHEDULE – BLADE-03- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD03 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD03-6ZZ0002 | ELECTRICAL DB SCHEDULE – BLADE-03- 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD03 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD03-6ZZ0003 | ELECTRICAL DB SCHEDULE – BLADE-03- 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-27 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD03 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD04-6ZZ0001 | ELECTRICAL DB SCHEDULE – BLADE-04- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD04 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD04-6ZZ0002 | ELECTRICAL DB SCHEDULE – BLADE-04- 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD04 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD04-6ZZ0003 | ELECTRICAL DB SCHEDULE – BLADE-04- 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD04 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD05-6ZZ0001 | ELECTRICAL DB SCHEDULE – BLADE-05- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD05 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD05-6ZZ0002 | ELECTRICAL DB SCHEDULE – BLADE-05- 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD05 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-BLAD05-6ZZ0003 | ELECTRICAL DB SCHEDULE – BLADE-05- 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-03 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | BLAD05 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0001 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0002 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0003 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0004 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 04 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0005 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 05 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0006 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 06 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-11-10 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0019 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 19 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0019 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0020 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 20 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0020 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0021 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 21 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0021 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0022 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 22 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0022 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0023 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 23 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0023 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0024 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 24 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-06 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0024 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0025 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 25 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0025 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0026 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 26 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0026 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0027 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 27 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0027 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0028 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 28 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0028 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0029 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 29 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0029 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0030 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 30 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-13 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0030 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0031 | ELECTRICAL CBS SCHEDULE – CENTER BLOCK - 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL CBS SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0031 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0032 | ELECTRICAL CBS SCHEDULE – CENTER BLOCK - 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL CBS SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0032 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-GARD01-6ZZ0001 | ELECTRICAL DB SCHEDULE – GUARD HOUSE- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-12-15 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | GARD01 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-PARK01-6ZZ0001 | ELECTRICAL DB SCHEDULE – PARKING- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-20 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | PARK01 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-PARK01-6ZZ0002 | ELECTRICAL DB SCHEDULE – PARKING- 02 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-20 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | PARK01 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-PARK01-6ZZ0003 | ELECTRICAL DB SCHEDULE – PARKING- 03 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-10-20 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | PARK01 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-SECE001-4ZZ0001 | ELECTRICAL ENLARGED PLAN-SEC MRMU-SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_71 | QF01012 | NES | C04518 | SDW | ELE | 00 | SECE001 | 4 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ELE-00-SECE001-4ZZ0002 | ELECTRICAL ENLARGED PLAN-SEC MRMU-SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_72 | QF01012 | NES | C04518 | SDW | ELE | 00 | SECE001 | 4 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ELE-00-SECE01-6ZZ0001 | ELECTRICAL DB SCHEDULE – SEC ROOM- 01 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-12-15 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | SECE01 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-Z00000-0ZZ0001 | ELECTRICAL STANDARD INSTALLATION DETAILS SHEET 1 | [5 empty] | 2026-08-30 | ELECTRICAL INSTALLATION DETAILS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 0 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-0ZZ0002 | ELECTRICAL STANDARD INSTALLATION DETAILS SHEET 2 | [5 empty] | 2026-08-31 | ELECTRICAL INSTALLATION DETAILS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 0 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-0ZZ0003 | ELECTRICAL STANDARD INSTALLATION DETAILS SHEET 3 | [5 empty] | 2026-08-30 | ELECTRICAL INSTALLATION DETAILS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 0 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0001 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 1 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-15 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0002 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 1 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-15 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0003 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 2 - SHEET 01 - (01 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-EBW-01-CENT01-2ZZ0004 | ELECTRICAL BUILDER WORK - STAIRCASE TYPE 2 - SHEET 02 - (02 OF 02) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | Electrical Builder Work | QP.E.ME.MBL.GEN.7230 | FI_60_25 | QF01012 | NES | C04518 | SDW | EBW | 01 | CENT01 | 2 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-11-26
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0007 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 07 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0008 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 08 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0009 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 09 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0009 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0010 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 10 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0010 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0011 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 11 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0011 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0012 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 12 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-22 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0012 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0013 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 13 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0013 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0014 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 14 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0014 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0015 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 15 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0015 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0016 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 16 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0016 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0017 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 17 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0017 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-ELE-00-CENT01-6ZZ0018 | ELECTRICAL DB SCHEDULE – CENTER BLOCK - 18 | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2026-09-29 | ELECTRICAL DB SCHEDULE | QP.E.ME.MBL.GEN.6510 | FI_90_75 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 6 | ZZ | 0018 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-05-20
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10008 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_UPS ROOM_(Z00-B01-116) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_51 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20006 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_LV PANEL RM_(Z00-B02-007) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_52 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50005 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELE.CP.R_(Z00-L05-322) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50006 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELE.CP.R_(Z00-L05-323) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50003 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELE.CP.R_(Z00-L05-368) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50004 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELE.CP.R_(Z00-L05-378) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0001 | MV - SCHEMATIC DIAGRAM |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0002 | LV - SCHEMATIC DIAGRAM FOR TX-01 & TX-02 - SHEET 01 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0003 | LV - SCHEMATIC DIAGRAM FOR TX-03 & TX-04 - SHEET 02 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0004 | LV - SCHEMATIC DIAGRAM FOR TX-05 & TX-06 - SHEET 03 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0005 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 04 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0006 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 05 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0007 | LV - SCHEMATIC DIAGRAM FOR TX-09 - SHEET 06 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0008 | LV - SCHEMATIC DIAGRAM FOR TX-10 - SHEET 07 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0009 | LV - SCHEMATIC DIAGRAM FOR TX-10 - SHEET 08 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0009 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0010 | LV - SCHEMATIC DIAGRAM FOR TX-11 - SHEET 09 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0010 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0011 | LV - SCHEMATIC DIAGRAM FOR TX-01 & TX-02 - SHEET 10 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0011 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0012 | LV - SCHEMATIC DIAGRAM FOR TX-03 & TX-04 - SHEET 11 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0012 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0013 | LV - SCHEMATIC DIAGRAM FOR TX-05 & TX-06 - SHEET 12 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0013 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0014 | LV - SCHEMATIC DIAGRAM FOR TX-05 & TX-06 - SHEET 13 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0014 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0015 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 14 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0015 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0016 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 15 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0016 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0017 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 16 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0017 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0018 | LV - SCHEMATIC DIAGRAM FOR TX-07 & TX-08 - SHEET 17 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0018 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0019 | LV - SCHEMATIC DIAGRAM FOR TX-09 - SHEET 18 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0019 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0020 | LV - SCHEMATIC DIAGRAM FOR TX-09 - SHEET 19 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0020 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0021 | LV - SCHEMATIC DIAGRAM FOR TX-09 - SHEET 20 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0021 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0022 | LV - SCHEMATIC DIAGRAM FOR TX-09 - SHEET 21 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0022 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0023 | LV - SCHEMATIC DIAGRAM FOR TX-10 - SHEET 22 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0023 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0024 | LV - SCHEMATIC DIAGRAM FOR TX-10 - SHEET 23 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0024 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0025 | LV - SCHEMATIC DIAGRAM FOR TX-10 - SHEET 24 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0025 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0026 | LV - SCHEMATIC DIAGRAM FOR TX-11 - SHEET 25 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0026 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0027 | LV - SCHEMATIC DIAGRAM FOR TX-11 - SHEET 26 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0027 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0028 | LV - SCHEMATIC DIAGRAM FOR TX-11 - SHEET 27 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0028 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0029 | LV - SCHEMATIC DIAGRAM FOR MFM DETAIL - SHEET 28 |  |  |  | .dwg,.pdf |  | 2026-08-25 | ELECTRICAL SCHEMATIC DIAGRAM | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0029 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0040 | MV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0040 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0041 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-01 - SHEET 01 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0041 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0042 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-02 - SHEET 02 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0042 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0043 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-03 - SHEET 03 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0043 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0044 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-04 - SHEET 04 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0044 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0045 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-05 - SHEET 05 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0045 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0046 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-06 - SHEET 06 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0046 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0047 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-07 - SHEET 07 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0047 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0048 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-08 - SHEET 08 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0048 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0049 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-09 - SHEET 09 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0049 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0050 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-09 - SHEET 10 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0050 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0051 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-10 - SHEET 11 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0051 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0052 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-10 - SHEET 12 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0052 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ELE-00-Z00000-6ZZ0053 | LV-FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS FOR TX-11 - SHEET 13 |  |  |  | .dwg,.pdf |  | 2026-08-25 | FEEDER SCHEDULE AND LOAD FLOW CALCULATIONS | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | Z00000 | 6 | ZZ | 0053 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50007 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELE.RIS_(Z00-L04-382) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4B30004 | ELECTRICAL ENLARGED PLAN-BLADE-4_ELE.RIS_(Z00-B03-452A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | B3 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L80001 | ELECTRICAL ENLARGED PLAN-L8 ROYAL MAJLIS+948.28M_UPS_(Z00-L08-054) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_81 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L8 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0130 | FAÇADE LIGHTING SYSTEM -VMU-01- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-01 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0130 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0131 | FAÇADE LIGHTING SYSTEM -VMU-01- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-01 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0131 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0132 | FAÇADE LIGHTING SYSTEM -VMU-01- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-09-01 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0132 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-ELP-00-Z00000-0ZZ0001 | EARTHING & LIGHTNING PROTECTION STANDARD INSTALLATION DETAILS - SHEET 1 | [5 empty] | 2027-01-24 | ELECTRICAL INSTALLATION DETAILS | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 0 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-0ZZ0002 | EARTHING & LIGHTNING PROTECTION STANDARD INSTALLATION DETAILS - SHEET 2 | [5 empty] | 2027-01-24 | ELECTRICAL INSTALLATION DETAILS | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 0 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-6ZZ0001 | EARTHING SCHEMATIC - SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Earthing & Lightning | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 6 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-6ZZ0002 | EARTHING SCHEMATIC - SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Earthing & Lightning | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 6 | ZZ | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-6ZZ0003 | EARTHING SCHEMATIC - SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Earthing & Lightning | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 6 | ZZ | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-6ZZ0004 | EARTHING SCHEMATIC - SHEET 4 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Earthing & Lightning | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 6 | ZZ | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ELP-00-Z00000-6ZZ0005 | EARTHING SCHEMATIC - SHEET 5 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | NTS | 2027-02-28 | Earthing & Lightning | QP.E.EX.GEN.GEN.1170 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELP | 00 | Z00000 | 6 | ZZ | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-ESP-00-CENT01-4B20001 | ELECTRICAL ENLARGED PLAN - B2 SERVICE +893.5M - RAW WASH / DEBOX | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.7380 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | B2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-01-10
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L10011 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-4) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L1 | 0011 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L20012 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-5) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-04 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L2 | 0012 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L30002 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-1) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-07 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6700 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L3 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-12-10
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L400013 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-6) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-11 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L4 | 00013 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L50009 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-2) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-12 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L5 | 0009 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ESP-00-CENT01-4L50010 | ELECTRICAL ENLARGED PLAN - KITCHEN EQUIPMET POWER (SHEET-3) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-21 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | ESP | 00 | CENT01 | 4 | L5 | 0010 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-ICT-00-Z00000-0ZZ0101 | ICT INSTALLATION DETAILS - SHEET 1 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2026-11-30 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 0 | ZZ | 0101 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-ICT-00-Z00000-0ZZ0102 | ICT INSTALLATION DETAILS - SHEET 2 | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | NTS | 2026-11-30 | ICT | QP.E.ME.CBR.GEN.1044 | FI_60_25 | QF01012 | NES | C04518 | SDW | ICT | 00 | Z00000 | 0 | ZZ | 0102 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000001 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +882M - BL1 - IDF (Z00-B03-153) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000002 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +905M - BL1 - IDF (Z00-L01-173) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000003 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +922.25M - BL1 - IDF (Z00-L04-158) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000004 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +935.85M - BL1 - IDF (Z00-L06-159) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000005 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +882M - BL1 - IDF (Z00-B03-153A) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-0000006 | IDF ROOM ENLARGED DETAIL - BLADE-01 LEVEL +928M - BL1 - IDF (Z00-L05-151) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 0 | 00 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4B30001 | ELECTRICAL ENLARGED PLAN-BLADE-1+870.5M_ELEC.RM_(Z00-B03-167E) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_30 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4L10001 | ELECTRICAL ENLARGED PLAN-BLADE-1+905M_ELEC.RM_(Z00-L01-171) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_32 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | L1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4L30001 | ELECTRICAL ENLARGED PLAN-BLADE-1+917.5M_ELEC.RM_(Z00-L03-151) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_42 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | L3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4L40001 | ELECTRICAL ENLARGED PLAN-BLADE-1+922.25M_ELEC.RM_(Z00-L04-169) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_35 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | L4 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4L50001 | ELECTRICAL ENLARGED PLAN-BLADE-1+928M_ELEC.RM_(Z00-L05-074B) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4L60001 | ELECTRICAL ENLARGED PLAN-BLADE-1+935.85M_ELEC.RM_(Z00-L06-158) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_102 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | L6 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4RL0001 | ELECTRICAL ENLARGED PLAN-BLADE-1+953.3M_ELEC.RM_(Z00-RF-160B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_82 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | RL | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD01-4RL0002 | ELECTRICAL ENLARGED PLAN-BLADE-1+953.3M_ELEC.RM_(Z00-RF-160C) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_83 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD01 | 4 | RL | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-0000001 | IDF ROOM ENLARGED DETAIL - BLADE-02 LEVEL +887.75M - BL2 - IDF (Z00-B03-235) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 0 | 00 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-MEP-00-BLAD02-0000003 | IDF ROOM ENLARGED DETAIL - BLADE-02 LEVEL +928M - BL2 - IDF (Z00-L05-210) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 0 | 00 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-MEP-00-BLAD02-0000004 | IDF ROOM ENLARGED DETAIL - BLADE-02 LEVEL +887.75M - BL2 - IDF (Z00-B03-221) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 0 | 00 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-MEP-00-BLAD02-0000005 | IDF ROOM ENLARGED DETAIL - BLADE-02 LEVEL +905M - BL2 - IDF (Z00-L01-211) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 0 | 00 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-MEP-00-BLAD02-0000006 | IDF ROOM ENLARGED DETAIL - BLADE-02 LEVEL +935.85M - BL2 - IDF (Z00-L06-212) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3500 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 0 | 00 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-08
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4B30001 | ELECTRICAL ENLARGED PLAN-BLADE-2+887.75M_ELEC.RM_(Z00-B03-211) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_89 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4B30002 | ELECTRICAL ENLARGED PLAN-BLADE-2+887.75M_ELEC.RM_(Z00-B03-240) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_90 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | B3 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4L10001 | ELECTRICAL ENLARGED PLAN-BLADE-2+905M_ELEC.RM_(Z00-L01-214) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_33 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | L1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4L50001 | ELECTRICAL ENLARGED PLAN-BLADE-2+928M_ELEC.RM_(Z00-L05-239) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_36 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4L50002 | ELECTRICAL ENLARGED PLAN-BLADE-2_ELEC.RM_(Z00-L05-246) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_100 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | L5 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4L50003 | ELECTRICAL ENLARGED PLAN-BLADE-2+928M_ELEC.RM_(Z00-L05-225) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_43 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | L5 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD02-4L60001 | ELECTRICAL ENLARGED PLAN-BLADE-2+935.85M_ELEC.RM_(Z00-L06-212) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_37 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD02 | 4 | L6 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000001 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +876.25M - IDF (Z00-B03-359) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000002 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +905M - IDF (Z00-L01-457) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000003 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +928M - BL3 - IDF (Z00-L05-396) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000004 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +867.62M - IDF (Z00-B03-354) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000005 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +905M - IDF (Z00-L01-390) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000006 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +910.75M - IDF (Z00-L01-330) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000007 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +916.5M - IDF (Z00-L02-391) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-0000008 | IDF ROOM ENLARGED DETAIL - BLADE-03 LEVEL +928M - BL3 - IDF (Z00-L05-395) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 0 | 00 | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4B30001 | ELECTRICAL ENLARGED PLAN-BLADE-3+859.0M_ELEC.RM_(Z00-B03-315) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_91 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4B30002 | ELECTRICAL ENLARGED PLAN-BLADE-3+859.0M_ELEC.RM_(Z00-B03-361) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_92 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | B3 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L20001 | ELECTRICAL ENLARGED PLAN-BLADE-3+916.5M_ELEC.RM_(Z00-L02-367) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_95 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L20002 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELEC.RM_(Z00-L02-335) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_96 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L20003 | ELECTRICAL ENLARGED PLAN-BLADE-3_ELEC.RM_(Z00-L02-336) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_97 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L2 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L20004 | ELECTRICAL ENLARGED PLAN-BLADE-3+910.75M_ELEC.RM_(Z00-L01-319) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_98 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L2 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50001 | ELECTRICAL ENLARGED PLAN-BLADE-3+928M_ELEC.CPB_(Z00-L05-376B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_70 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L50002 | ELECTRICAL ENLARGED PLAN-BLADE-3+928M_ELEC.RM_(Z00-L05-376A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L5 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-20
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000001 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +876.25M - IDF (Z00-B03-408) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000002 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +899.25M - BL4 - IDF (Z00-B01-467) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000003 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +916.5M - BL4 - IDF (Z00-L02-406) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000004 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +928M - BL4 - IDF (Z00-L05-426) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000005 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +887.75M - BL4 - IDF (Z00-B03-425) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000006 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +916.5M - BL4 - IDF (Z00-L02-319) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-03-18
QF01012-NES-C04518-SDW-MEP-00-BLAD04-0000007 | IDF ROOM ENLARGED DETAIL - BLADE-04 LEVEL +941.6M - BL4 - IDF (Z00-L06-407) | QF01012-NES-C04518-MOD-BMS-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | IDF | QP.E.ME.BL1.GEN.3540 | FI_90_72 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 0 | 00 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-10-25
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4B30001 | ELECTRICAL ENLARGED PLAN-BLADE-4_ELEC.RM_(Z00-B03-463) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_93 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4B30002 | ELECTRICAL ENLARGED PLAN-BLADE-4+876.25M_ELEC.RM_(Z00-B03-452) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_94 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | B3 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4B30003 | ELECTRICAL ENLARGED PLAN-BLADE-4+863.85M_ELEC.RM_(Z00-B03-447) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_31 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | B3 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4L20001 | ELECTRICAL ENLARGED PLAN-BLADE-4+916.5M_ELEC.RM_(Z00-L02-477) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_34 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | L2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4L50001 | ELECTRICAL ENLARGED PLANBLADE-4+928M_ELEC.CPB_(Z00-L05-427) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_101 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4L60001 | ELECTRICAL ENLARGED PLAN-BLADE-4+941.6M_ELEC.RM_(Z00-L06-489B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_39 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | L6 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4L60002 | ELECTRICAL ENLARGED PLAN-BLADE-4+935.85M_ELEC.RM_(Z00-L06-487A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_38 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | L6 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4L60003 | ELECTRICAL ENLARGED PLAN-BLADE-4+941.6M_ELEC.RM_(Z00-L06-489C) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_40 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | L6 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD05-0000001 | IDF ROOM ENLARGED DETAIL - BLADE-05 LEVEL +899.5M - BL5 - IDF (Z00-B01-506G) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 0 | 00 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-MEP-00-BLAD05-0000002 | IDF ROOM ENLARGED DETAIL - BLADE-05 LEVEL +935.85M - BL5-IDF (Z00-L06-510) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 0 | 00 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-MEP-00-BLAD05-0000003 | IDF ROOM ENLARGED DETAIL - BLADE-05 LEVEL +899.5M - BL5 - IDF (Z00-B01-506I) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.BL1.GEN.3560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 0 | 00 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2028-02-16
QF01012-NES-C04518-SDW-MEP-00-BLAD05-4B10001 | ELECTRICAL ENLARGED PLAN-BLADE-5+899.5M_ELEC.RM_(Z00-B01-523) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_29 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 4 | B1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-BLAD05-4L50001 | ELECTRICAL ENLARGED PLAN-BLADE-1+928M_ELEC.RM_(Z00-L05-524) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.BL1.GEN.3480 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 4 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-12-02
QF01012-NES-C04518-SDW-MEP-00-BLAD05-4L60001 | ELECTRICAL ENLARGED PLAN-BLAD05+941.16M_ELEC.RM_(Z00-L08-506U) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_41 | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD05 | 4 | L6 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10001 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-018) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_44 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10002 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-030) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_45 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10003 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.CB_(Z00-B01-042) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_46 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10004 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-050) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_47 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10005 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-051)-SHEET-01 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_48 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10006 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-084) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_49 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10007 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-090) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_50 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10010 | ELECTRICAL ENLARGED PLAN-CENTRAL-01 B01_ELEC.RM_(Z00-B01-050H) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_88 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0010 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B10011 | ELECTRICAL ENLARGED PLAN-B1 SERVICE+900.5M_ELEC.RM_(Z00-B01-051)-SHEET-02 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B1 | 0011 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20001 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_GEN_(Z00-B02-025)-SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_86 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20002 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_GEN_(Z00-B02-025)-SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_87 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ELE-00-CENT01-4B20003 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_TRANSFORMER_(Z00-B02-004)-SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 4 | B2 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-08-17
QF01012-NES-C04518-SDW-ELE-00-CENT01-4B20004 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_TRANSFORMER_(Z00-B02-004)-SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 4 | B2 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-08-17
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20005 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_ELEC.RM_(Z00-B02-026) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_53 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20007 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_ELEC.RM_(Z00-B02-034) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_54 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B20008 | ELECTRICAL ENLARGED PLAN-B2 SERVICE+893.5M_ELEC.RM_(Z00-B02-034A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-11-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_55 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B2 | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4B30001 | ELECTRICAL ENLARGED PLAN-B3 PROMENADE+887.750M_ELEC_(Z00-B03-017) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_56 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L10001 | ELECTRICAL ENLARGED PLAN-L1-LOBBY LEVEL+905M_ELEC.RM_(Z00-L01-033) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_57 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L10002 | ELECTRICAL ENLARGED PLAN-L1-LOBBY LEVEL+905M_ELEC.RM_(Z00-L01-036) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_58 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L1 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L20001 | ELECTRICAL ENLARGED PLAN-L2-THEATRE STALLS+913M_ELEC.RM_(Z00-L02-073) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_60 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L20002 | ELECTRICAL ENLARGED PLAN-L2-THEATRE STALLS+913M_ELEC.RM_(Z00-L02-090B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-12-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_61 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L30001 | ELECTRICAL ENLARGED PLAN-L3-STALL MEZZANINE&ADAPTIVE THEATRE+917.5M_ELEC.RM_(Z00-L03-055) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_63 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-ELE-00-CENT01-4L30004 | ELECTRICAL ENLARGED PLAN-L3-STALL MEZZANINE&ADAPTIVE THEATRE+917.5M_ELEC.RM_(Z00-L03-007A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_62 | QF01012 | NES | C04518 | SDW | ELE | 00 | CENT01 | 4 | L3 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L40001 | ELECTRICAL ENLARGED PLAN-L4-FIRST CIRCLE&ADAPTIVE THEATRE+921M_ELEC.CLST_(Z00-L04-018) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_65 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L4 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L40002 | ELECTRICAL ENLARGED PLAN-L4-FIRST CIRCLE&ADAPTIVE THEATRE+921M_ELEC.RM_(Z00-L04-011A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_64 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L4 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L40003 | ELECTRICAL ENLARGED PLAN-L4-FIRST CIRCLE&ADAPTIVE THEATRE+921M_ELEC.RM_(Z00-L04-020) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_28 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L4 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50002 | ELECTRICAL ENLARGED PLAN-L5 SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-052D) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_28 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50003 | ELECTRICAL ENLARGED PLAN-L5 SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-052C) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_27 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50004 | ELECTRICAL ENLARGED PLAN-L5 SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-052B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-01-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_26 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50005 | ELECTRICAL ENLARGED PLAN-L5-SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-074A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_68 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0005 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50007 | ELECTRICAL ENLARGED PLAN-L5-SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-071B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50008 | ELECTRICAL ENLARGED PLAN-L5-SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-071A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_67 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L50009 | ELECTRICAL ENLARGED PLAN-L5-SECOND CIRCLE&LOFT+928M_ELEC.RM_(Z00-L05-052A) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_66 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L5 | 0009 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L60001 | ELECTRICAL ENLARGED PLAN-L6-SKY GARDEN+935.85M_ELEC.RM_(Z00-L06-025) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-10-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_77 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L6 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L60002 | ELECTRICAL ENLARGED PLAN-L6-SKY GARDEN+935.85M_ELEC.RM_(Z00-L06-512) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_79 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L6 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L60003 | ELECTRICAL ENLARGED PLAN-L6-SKY GARDEN+935.85M_ELEC.CB_(Z00-L06-170) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_78 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L6 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L60004 | ELECTRICAL ENLARGED PLAN-L6-SKY GARDEN+935.85M_ELEC.RM_(Z00-L06-004D) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_73 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L6 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4L80002 | ELECTRICAL ENLARGED PLAN-L8 ROYAL MAJLIS+948.28M_ELEC.RM_(Z00-L08-021) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_80 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | L8 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4M10001 | ELECTRICAL ENLARGED PLAN-L1M+909.0M_ELEC.RM_(Z00-L01-051) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_59 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | M1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4M20001 | ELECTRICAL ENLARGED PLAN-L5.5 LOFT MEP LEVEL+931.1_ELEC.RM_(Z00-L05-110) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_73 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | M2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4M20002 | ELECTRICAL ENLARGED PLAN-L5.5 LOFT MEP LEVEL+931.1_ELEC.RM_(Z00-L05-145) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_74 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | M2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-00-CENT01-4M20003 | ELECTRICAL ENLARGED PLAN-L5.5 LOFT MEP LEVEL+931.1_ELEC.RM_(Z00-L05-149B) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2027-02-28 | ELECTRICAL ROOM DETAIL | QP.E.ME.MBL.GEN.6720 | FI_60_75 | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | M2 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-01-CENT01-0B10001 | IDF ROOM ENLARGED DETAIL - B1 SERVICE +900.5M - IDF(Z00-B01-039) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 01 | CENT01 | 0 | B1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-01-CENT01-0B30001 | IDF ROOM ENLARGED DETAIL - B3 PROMENADE +887.750M - IDF (Z00-B03-019) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 01 | CENT01 | 0 | B3 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-07-15
QF01012-NES-C04518-SDW-MEP-01-CENT01-0M20001 | IDF ROOM ENLARGED DETAIL - L5.5 LOFT +931.7M - IDF (Z00-L05-132) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.5540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 01 | CENT01 | 0 | M2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-23
QF01012-NES-C04518-SDW-MEP-01-CENT01-0M20003 | IDF ROOM ENLARGED DETAIL - L5.5 LOFT +931.7M - IDF (Z00-L05-142) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.5540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 01 | CENT01 | 0 | M2 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-23
QF01012-NES-C04518-SDW-MEP-02-CENT01-0B30002 | IDF ROOM ENLARGED DETAIL - B3 PROMENADE +887.750M - IDF (Z00-B03-021) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6520 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 02 | CENT01 | 0 | B3 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-07-15
QF01012-NES-C04518-SDW-MEP-02-CENT01-0M10001 | IDF ROOM ENLARGED DETAIL - L1 UPPER LOBBY MEZZANINE LEVEL +909M - IDF (Z00-L01-060) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6660 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 02 | CENT01 | 0 | M1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-22
QF01012-NES-C04518-SDW-MEP-02-CENT01-0M20002 | IDF ROOM ENLARGED DETAIL - L5.5 LOFT +931.7M - IDF (Z00-L05-130) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.5540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 02 | CENT01 | 0 | M2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-23
QF01012-NES-C04518-SDW-MEP-02-CENT01-0M20004 | IDF ROOM ENLARGED DETAIL - L5.5 LOFT +931.7M - IDF (Z00-L05-131) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.5540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 02 | CENT01 | 0 | M2 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-02-23
QF01012-NES-C04518-SDW-MEP-03-CENT01-0L50001 | IDF ROOM ENLARGED DETAIL - L5 SECOND CIRCLE & LOFT +928M - IDF (Z00-L05-098) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 03 | CENT01 | 0 | L5 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-MEP-04-CENT01-0B10006 | MAIN SECURITY CONTROL ENLARGED DETAILS- B1 SERVICE- MAIN SEC. CONTROL (Z00-B01-031) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 04 | CENT01 | 0 | B1 | 0006 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-MEP-04-CENT01-0B10007 | SECURITY EQUIPMENT ENLARGED DEATILS - B1 SERVICE - SEC.EQUIP (Z00-B01-029) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 04 | CENT01 | 0 | B1 | 0007 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-MEP-04-CENT01-0B10008 | TETRA ROOM ENLARGED DETAIL- B1 SERVICE +900.5M - TETRA (Z00-B01-139) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 04 | CENT01 | 0 | B1 | 0008 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-MEP-04-CENT01-0L40001 | IDF ROOM ENLARGED DETAIL - L4 FIRST CIRCLE & ADAPTIVE THEATRE +921M - IDF (Z00-L04-011) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6720 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 04 | CENT01 | 0 | L4 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-04
QF01012-NES-C04518-SDW-MEP-05-CENT01-0B10001 | IDF ROOM ENLARGED DETAIL - B1 SERVICE +900.5M - IDF (Z00-B01-064) | QF01012-NES-C04518-MOD-ELE-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | B1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-05-CENT01-0B10004 | SERVER ROOM / MDF ENLARGED DETAIL - B1 SERVICE +900.5M - SERVER RM / MDF (Z00-B01-041) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6560 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | B1 | 0004 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-02
QF01012-NES-C04518-SDW-MEP-05-CENT01-0B20001 | POE / MTR ROOM ENLARGED DETAIL - B2 SERVICE +893.5M - POE / MTR (Z00-B02-011) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | B2 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-08-17
QF01012-NES-C04518-SDW-MEP-05-CENT01-0B20002 | GSM ROOM ENLARGED DETAIL - B2 SERVICE +893.5M - GSM (Z00-B02-018) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2027-01-08 | ICT | QP.E.ME.MBL.GEN.6540 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | B2 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-08-17
QF01012-NES-C04518-SDW-MEP-05-CENT01-0B20003 | IDF ROOM ENLARGED DETAIL - B2 SERVICE +893.5M - IDF (Z00-B02-030) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1290 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | B2 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-05-CENT01-0L10001 | IDF ROOM ENLARGED DETAIL - L1 LOBBY LEVEL +905M - IDF (Z00-L01-034) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6640 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | L1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-09-28
QF01012-NES-C04518-SDW-MEP-05-CENT01-0L50002 | IDF ROOM ENLARGED DETAIL - L5 SECOND CIRCLE & LOFT +928M - IDF (Z00-L05-015) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | L5 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-MEP-05-CENT01-0L80001 | IDF ROOM ENLARGED DETAIL - L8 ROYAL MAJLIS +948.28M - IDF(Z00-L08-023) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6580 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | L8 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-04-24
QF01012-NES-C04518-SDW-MEP-05-CENT01-0M10002 | IDF ROOM ENLARGED DETAIL - L1 UPPER LOBBY MEZZANINE LEVEL +909M - IDF (Z00-L01-057) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6660 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | M1 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-22
QF01012-NES-C04518-SDW-MEP-05-CENT01-0M10003 | IDF ROOM ENLARGED DETAIL - L1 UPPER LOBBY MEZZANINE LEVEL +909M - IDF (Z00-L01-052) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6660 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 05 | CENT01 | 0 | M1 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-22
QF01012-NES-C04518-SDW-MEP-06-CENT01-0L50003 | IDF ROOM ENLARGED DETAIL - L5 LOFT +928M - IDF (Z00-L05-100) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.6740 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 06 | CENT01 | 0 | L5 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-01-28
QF01012-NES-C04518-SDW-MEP-13-PARK01-0B10001 | IDF ENLARGED DETAIL- B1 PARKING +900.5M - IDF (Z00-B01-109) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 13 | PARK01 | 0 | B1 | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-14-PARK01-0B10002 | IDF ROOM ENLARGED DETAIL - B1 PARKING +900.5M - IDF (Z00-B01-087) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 14 | PARK01 | 0 | B1 | 0002 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-15-PARK01-0B10003 | IDF ROOM ENLARGED DETAIL - B1 PARKING +900.5M - IDF (Z00-B01-070) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-08-30 | ICT | QP.E.ME.MBL.GEN.1280 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 15 | PARK01 | 0 | B1 | 0003 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-10-04
QF01012-NES-C04518-SDW-MEP-19-GARD01-2ZZ0001 | GUARDHOUSE ENLARGED DETAIL - L1 LOBBY LEVEL +905M - GUARDHOUSE (Z00-L01-047) | QF01012-NES-C04518-MOD-ICT-00-Z00000-0000001 | Technology (ICT) | Revit | .dwg,.pdf | AS INDICATED | 2026-09-30 | ICT | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | MEP | 19 | GARD01 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0101 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-01 AND ACS-02 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0101 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0102 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-03 AND ACS-04 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0102 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0103 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-05 AND ACS-06 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0103 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0104 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-08 AND ACS-09 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0104 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0105 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-10 AND ACS-11 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0105 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0106 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-12 AND ACS-14 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0106 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0107 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-16 AND ACS-17 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0107 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0108 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-18 AND ACS-19 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0108 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0109 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-20 AND ACS-21 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0109 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0110 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-22 AND ACS-23 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0110 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0111 | ACCESS CONTROL SYSTEM DOOR TYPES ACS-07 AND ACS-15 STANDARD INSTALLATION DETAILS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-11-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0111 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0116 | STANDARD INSTALLATION DETAILS - DISABLED TOILET ALARM SYSTEM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0116 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0117 | STANDARD INSTALLATION DETAILS - TYPICAL ANTENNA | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0117 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0118 | STANDARD INSTALLATION DETAILS - KEY MANAGEMENT SYSTEM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0118 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0119 | STANDARD INSTALLATION DETAILS - INTERCOM SYSTEM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0119 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0121 | STANDARD INSTALLATION DETAILS - FIXED BOLLARDS | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-09-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0121 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0123 | STANDARD INSTALLATION DETAILS - HYDRAULICS BOLLARDS SYSTEM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-09-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0123 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-00-Z00000-0ZZ0125 | STANDARD INSTALLATION DETAILS - GATE BARRIER | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | NTS | 2026-08-30 | SECURITY | QP.E.EX.GEN.GEN.1100 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 00 | Z00000 | 0 | ZZ | 0125 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-06-06
QF01012-NES-C04518-SDW-SEC-19-GARD01-2ZZ0001 | SECURITY SYSTEM PLAN - GUARD ROOM | QF01012-NES-C04518-MOD-SEC-00-Z00000-0000001 | Security | Revit | .dwg,.pdf | 1:100 | 2027-01-15 | SECURITY | QP.E.EX.GEN.GEN.1270 | FI_60_25 | QF01012 | NES | C04518 | SDW | SEC | 19 | GARD01 | 2 | ZZ | 0001 | Electrical | NAP PMO | LOD400 |  |  |  | 2027-07-22
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0430 | FAÇADE LIGHTING SYSTEM -VMU-04- SHEET 1 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-27 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0430 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0431 | FAÇADE LIGHTING SYSTEM -VMU-04- SHEET 2 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-27 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0431 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-VMU-FAC-00-CENT01-5ZZ0432 | FAÇADE LIGHTING SYSTEM -VMU-04- SHEET 3 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000001 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-08-27 | SPECIAL LIGHTING | QP.E.FA.GEN.GEN.1890 | FI_60_25 | QF01012 | NES | C04518 | VMU | FAC | 00 | CENT01 | 5 | ZZ | 0432 | Electrical | NAP PMO | LOD400 |  |  |  | 2026-03-30
QF01012-NES-C04518-SDW-MEP-00-BLAD03-4L10004 | ELECTRICAL ENLARGED PLAN-BLADE-3+910.75M_ELEC.RM_(Z00-L01-357) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000002 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-07-29 17:32 | ELECTRICAL ROOM DETAIL |  |  | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD03 | 4 | L1 | 0004 | Electrical | NAP PMO | LOD400
QF01012-NES-C04518-SDW-MEP-00-BLAD04-4L50002 | ELECTRICAL ENLARGED PLANBLADE-4+928M_ELEC.CPB_(Z00-L05-427) | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000003 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-07-29 17:34 | ELECTRICAL ROOM DETAIL |  |  | QF01012 | NES | C04518 | SDW | MEP | 00 | BLAD04 | 4 | L5 | 0002 | Electrical | NAP PMO | LOD400
QF01012-NES-C04518-SDW-MEP-00-CENT01-4M20004 | ELECTRICAL ENLARGED PLAN - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M_PREMIUM THEATRE ELEC_(Z00-L05-110) SHEET-02 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000004 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-07-30 17:37 | ELECTRICAL ROOM DETAIL |  |  | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | M2 | 0004 | Electrical | NAP PMO | LOD400
QF01012-NES-C04518-SDW-MEP-00-CENT01-4M20005 | ELECTRICAL ENLARGED PLAN - L5.5-MEZZ-LOFT MEP MEZZANINE +931.1M_PREMIUM THEATRE ELEC_(Z00-L05-110) SHEET-03 | QF01012-NES-C04518-MOD-ELC-00-Z00000-0000005 | MEP Engineering | Revit | .dwg,.pdf | AS INDICATED | 2026-07-30 17:37 | ELECTRICAL ROOM DETAIL |  |  | QF01012 | NES | C04518 | SDW | MEP | 00 | CENT01 | 4 | M2 | 0005 | Electrical | NAP PMO | LOD400

## Baseline
1 | 2 | 3 | 4 | 5 | 6 | 7 | Package | Activity Code | Activity | Original Duration | Start | Finish
Shop Drawings | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Mobilization | Shop Drawings ¦ Mobilization | QP.M.GN.GEN.GEN.1400 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Tower Crane Foundation - Concrete Works | Shop Drawings ¦ Mobilization ¦ Tower Crane Foundation - Concrete Works | QP.M.GN.GEN.GEN.1470 | Submittal | 25 | 2025-10-02 | 2025-10-30
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Temporary Tower For Steel Works Foundation - Blades Below Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Blades Below Loft | QP.M.GN.GEN.GEN.1540 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Temporary Tower For Steel Works Foundation - Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Loft | QP.M.GN.GEN.GEN.1560 | Submittal | 12 | 2026-08-29 | 2026-09-10
Shop Drawings | Mobilization | Temporary Tower For Steel Works Foundation | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Temporary Tower For Steel Works Foundation - Above Loft | Shop Drawings ¦ Mobilization ¦ Temporary Tower For Steel Works Foundation ¦ Temporary Tower For Steel Works Foundation - Above Loft | QP.M.GN.GEN.GEN.1580 | Submittal | 12 | 2026-10-01 | 2026-10-14
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works | QP.E.CV.MBL.GEN.3460 | Submittal | 28 | 2025-10-11 | 2025-11-11
Shop Drawings | Civil | Main Building | Main Building | Main Building | Main Building | Basement 03 & 02 Excavation and Blinding Works Outside Core Area | Shop Drawings ¦ Civil ¦ Main Building ¦ Basement 03 & 02 Excavation and Blinding Works Outside Core Area | QP.E.CV.MBL.GEN.3540 | Submittal | 14 | 2025-11-12 | 2025-11-27
Shop Drawings | Civil | Blades | Blade 1 | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 1 | QP.E.CV.BL1.GEN.1060 | Submittal | 28 | 2026-02-21 | 2026-03-28
Shop Drawings | Civil | Blades | Blade 2 | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 2 | QP.E.CV.BL2.GEN.1060 | Submittal | 28 | 2026-01-19 | 2026-02-19
Shop Drawings | Civil | Blades | Blade 3 | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 3 | QP.E.CV.BL3.GEN.1060 | Submittal | 28 | 2025-12-17 | 2026-01-18
Shop Drawings | Civil | Blades | Blade 4 | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 4 | QP.E.CV.BL4.GEN.1060 | Submittal | 28 | 2025-12-03 | 2026-01-04
Shop Drawings | Civil | Blades | Blade 5 | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Civil ¦ Blades ¦ Blade 5 | QP.E.CV.BL5.GEN.1060 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Civil | Parking | Parking | Parking | Parking | Parking | Shop Drawings ¦ Civil ¦ Parking | QP.E.CV.PAR.GEN.1000 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Basement 03 & 02 - Foundation Works Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - Foundation Works Core Area | QP.E.CV.MBL.GEN.3000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Floor Level - Basement 03 +887.750M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 03 +887.750M | QP.E.CV.MBL.GEN.3030 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Basement 03 & 02 - SOG | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 03 & 02 - SOG | QP.E.CV.MBL.GEN.3640 | Submittal | 14 | 2026-03-16 | 2026-04-02
Shop Drawings | Concrete | Concrete Structure - Main Building | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Basement 02 - Foundation Works Outside Core Area | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Basement 02 - Foundation Works Outside Core Area | QP.E.CV.MBL.GEN.3020 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Floor Level - Basement 02 +893.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 02 +893.5M | QP.E.CV.MBL.GEN.3070 | Submittal | 21 | 2026-02-18 | 2026-03-15
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Floor Level - Basement 01 +900.5M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - Basement 01 +900.5M | QP.E.CV.MBL.GEN.3100 | Submittal | 28 | 2026-03-16 | 2026-04-19
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Floor Level - L01- LOBBY LEVEL +905M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01- LOBBY LEVEL +905M | QP.E.CV.MBL.GEN.3120 | Submittal | 25 | 2026-04-20 | 2026-05-18
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Floor Level - L01 - MEZZANINE +909M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L01 - MEZZANINE +909M | QP.E.CV.MBL.GEN.3140 | Submittal | 15 | 2026-05-19 | 2026-06-08
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3180 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Floor Level - L02 - THEATRE STALLS +913M | Level 02 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L02 - THEATRE STALLS +913M ¦ Level 02 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3380 | Submittal | 25 | 2026-06-09 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3220 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Floor Level - L03 STALL MEZZANINE +917.5M | Level 03 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L03 STALL MEZZANINE +917.5M ¦ Level 03 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3400 | Submittal | 25 | 2026-07-08 | 2026-08-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3240 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L04 +921M | Floor Level - L04 +921M | Floor Level - L04 +921M | Level 04 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L04 +921M ¦ Level 04 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3420 | Submittal | 25 | 2026-08-06 | 2026-09-03
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Concrete Super Structure Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Concrete Super Structure Including Embedded items | QP.E.CV.MBL.GEN.3260 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Floor Level - L05 LOFT +928M | Level 05 Precast Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L05 LOFT +928M ¦ Level 05 Precast Concrete Works Including Embedded items | QP.E.CV.MBL.GEN.3440 | Submittal | 28 | 2026-09-05 | 2026-10-07
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L06 - MEP +931.7M & SKY GARDEN +935.85M | QP.E.CV.MBL.GEN.3280 | Submittal | 25 | 2026-10-08 | 2026-11-05
Shop Drawings | Concrete | Concrete Structure - Main Building | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | Shop Drawings ¦ Concrete ¦ Concrete Structure - Main Building ¦ Floor Level - L08 - L8 ROYAL MAJLIS +948.28M | QP.E.CV.MBL.GEN.3300 | Submittal | 28 | 2027-03-13 | 2027-04-13
Shop Drawings | Concrete | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Concrete Structure - Premium Theatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Premium Theatre Concrete Works | QP.E.CV.MBL.GEN.3150 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Concrete Structure - Amphitheatre Concrete Works | Shop Drawings ¦ Concrete ¦ Concrete Structure - Amphitheatre Concrete Works | QP.E.CV.MBL.GEN.3200 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Premium Theater | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Premium Theater | QP.E.CV.MBL.GEN.3660 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Loft and Adaptable Theatre | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Loft and Adaptable Theatre | QP.E.CV.MBL.GEN.3700 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Fly Tower | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Fly Tower | QP.E.CV.MBL.GEN.3710 | Submittal | 28 | 2026-08-10 | 2026-09-10
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Lobby & Plaza | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Lobby & Plaza | QP.E.CV.MBL.GEN.3680 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Concrete | Composite Slabs | Composite Slabs | Composite Slabs | Composite Slabs | Royal Majlis | Shop Drawings ¦ Concrete ¦ Composite Slabs ¦ Royal Majlis | QP.E.CV.MBL.GEN.3740 | Submittal | 28 | 2027-01-21 | 2027-02-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Foundation | QP.E.CV.BL1.GEN.1000 | Submittal | 25 | 2026-02-25 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL1.GEN.1040 | Submittal | 25 | 2026-03-29 | 2026-04-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL1.GEN.1080 | Submittal | 18 | 2026-05-12 | 2026-06-04
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL1.GEN.1020 | Submittal | 28 | 2026-06-06 | 2026-07-07
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL1.GEN.1120 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 1 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 1 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL1.GEN.1100 | Submittal | 28 | 2026-10-27 | 2026-11-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Foundation | QP.E.CV.BL2.GEN.1000 | Submittal | 21 | 2026-03-02 | 2026-03-28
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL2.GEN.1040 | Submittal | 21 | 2026-03-10 | 2026-04-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL2.GEN.1080 | Submittal | 18 | 2026-04-21 | 2026-05-11
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL2.GEN.1020 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL2.GEN.1140 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 2 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 2 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL2.GEN.1120 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Foundation | QP.E.CV.BL3.GEN.1000 | Submittal | 21 | 2026-02-07 | 2026-03-03
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Steel Composite Slab Including Embedded items Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Steel Composite Slab Including Embedded items Below Loft | QP.E.CV.BL3.GEN.1030 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL3.GEN.1080 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 3 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 3 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL3.GEN.1020 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Foundation | QP.E.CV.BL4.GEN.1000 | Submittal | 28 | 2026-01-05 | 2026-02-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL4.GEN.1030 | Submittal | 28 | 2026-02-24 | 2026-03-30
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL4.GEN.1080 | Submittal | 15 | 2026-03-31 | 2026-04-16
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL4.GEN.1020 | Submittal | 28 | 2026-04-18 | 2026-05-19
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL4.GEN.1100 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 4 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 4 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL4.GEN.1120 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Foundation | Foundation | Foundation | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Foundation | QP.E.CV.BL5.GEN.1000 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Below Loft | QP.E.CV.BL5.GEN.1030 | Submittal | 28 | 2026-03-23 | 2026-04-23
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Retaining Wall | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Retaining Wall | QP.E.CV.BL5.GEN.1080 | Submittal | 18 | 2026-03-31 | 2026-04-20
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Below Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Below Loft | QP.E.CV.BL5.GEN.1020 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Steel Composite Slab Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Steel Composite Slab Above Loft | QP.E.CV.BL5.GEN.1100 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Concrete | Concrete Structure - Blades | Blade 5 | Super Structure | Super Structure | Precast Stairs Above Loft | Shop Drawings ¦ Concrete ¦ Concrete Structure - Blades ¦ Blade 5 ¦ Super Structure ¦ Precast Stairs Above Loft | QP.E.CV.BL5.GEN.1120 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Foundation Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Foundation Including Embedded items | QP.E.CV.PAR.GEN.1020 | Submittal | 28 | 2027-04-28 | 2027-06-03
Shop Drawings | Concrete | Parking | Parking | Parking | Parking | Structural Concrete Works Including Embedded items | Shop Drawings ¦ Concrete ¦ Parking ¦ Structural Concrete Works Including Embedded items | QP.E.CV.PAR.GEN.1040 | Submittal | 28 | 2027-06-19 | 2027-07-20
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Temporay Tower Below Loft | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Below Loft | QP.E.ST.GEN.GEN.1090 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1100 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1110 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1050 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1060 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1070 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Embedded part - Blades Pile Cap - 3,4,5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 3,4,5 | QP.E.ST.GEN.GEN.1000 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Embedded part - Blades Pile Cap - 1,2 and Main Building Below Level 5 | QP.E.ST.GEN.GEN.1010 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Structural Steel | Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Truss below Auditorium, Side and Back Stage | Shop Drawings ¦ Structural Steel ¦ Batch 01 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Truss below Auditorium, Side and Back Stage | QP.E.ST.GEN.GEN.2120 | Submittal | 21 | 2026-02-24 | 2026-03-19
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1220 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1230 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1200 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1210 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1190 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Embedded part - Main Building Above Level 5 | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Embedded part - Main Building Above Level 5 | QP.E.ST.GEN.GEN.1040 | Submittal | 21 | 2026-01-17 | 2026-02-09
Shop Drawings | Structural Steel | Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Premium Theater - Frame Balconies and Back Stage Dressing | Shop Drawings ¦ Structural Steel ¦ Batch 02 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft and Premium Threater ¦ Premium Theater - Frame Balconies and Back Stage Dressing | QP.E.ST.GEN.GEN.2140 | Submittal | 21 | 2026-03-23 | 2026-04-15
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Temporay Tower Loft and adaptable Theatre | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Temporay Tower Loft and adaptable Theatre | QP.E.ST.GEN.GEN.1340 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Blade 01 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 01 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1390 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Blade 02 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 02 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1400 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Blade 03 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 03 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1310 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Blade 04 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 04 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1320 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Blade 05 - Below Loft Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 03 - Structural Steel and Metal Deck for Blade 1, 2, 3, 4, 5 Below Loft ¦ Blade 05 - Below Loft Incl. Metal Deck | QP.E.ST.GEN.GEN.1330 | Submittal | 28 | 2026-04-16 | 2026-05-18
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1470 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Truss above Auditorium Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 04 - Structural Steel for Loft truss, Infilled beam and Truss above Auditorium ¦ Truss above Auditorium Incl. Metal Deck | QP.E.ST.GEN.GEN.2100 | Submittal | 28 | 2026-05-19 | 2026-06-23
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Temporay Tower ROYAL MAJLIS and Blades above loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Temporay Tower ROYAL MAJLIS and Blades above loft | QP.E.ST.GEN.GEN.1490 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Blade 4 & 5 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2160 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | South Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ South Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1520 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Truss above Flytower | Shop Drawings ¦ Structural Steel ¦ Batch 05 - Structural Steel for Blade 4 & 5, Loft Truss, Infilled beam and Truss above Flytower ¦ Truss above Flytower | QP.E.ST.GEN.GEN.2180 | Submittal | 28 | 2026-06-24 | 2026-07-26
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.1540 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Blade 2 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 06 - Structural Steel for Blade 2, Loft truss and Infilled beam ¦ Blade 2 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.2200 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Adaptable Theatre Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ Adaptable Theatre Incl. Metal Deck | QP.E.ST.GEN.GEN.1560 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | North Loft Steel and Infilled Beams Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 07 - Structural Steel for Loft truss, Infilled beam and Adaptable theater ¦ North Loft Steel and Infilled Beams Incl. Metal Deck | QP.E.ST.GEN.GEN.2220 | Submittal | 28 | 2026-08-29 | 2026-09-30
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Loft Truss and Infilled Beam North Side Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Loft Truss and Infilled Beam North Side Incl. Metal Deck | QP.E.ST.GEN.GEN.1610 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 08 - Structural Steel for Blade 1, Loft truss and Infilled beam ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1600 | Submittal | 28 | 2026-10-01 | 2026-11-02
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Lobby and Plaza Incl. Metal Deck | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Lobby and Plaza Incl. Metal Deck | QP.E.ST.GEN.GEN.1660 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Frame for Mezzanine | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Frame for Mezzanine | QP.E.ST.GEN.GEN.1670 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Link Bridge and Helix Stair | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Link Bridge and Helix Stair | QP.E.ST.GEN.GEN.1570 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Blade 1 - Structural Steel and Metal Deck Above Loft | Shop Drawings ¦ Structural Steel ¦ Batch 09 - Structural Steel for Blade 1, Lobby & plaza, Link Bridge and Helix ¦ Blade 1 - Structural Steel and Metal Deck Above Loft | QP.E.ST.GEN.GEN.1680 | Submittal | 28 | 2026-11-03 | 2026-12-05
Shop Drawings | Structural Steel | Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | ROYAL MAJLIS | Shop Drawings ¦ Structural Steel ¦ Batch 10 - Structural Steel for Royal Majlis Incl. Metal Deck ¦ ROYAL MAJLIS | QP.E.ST.GEN.GEN.1640 | Submittal | 28 | 2026-12-06 | 2027-01-06
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1090 | Submittal | 21 | 2026-03-26 | 2026-04-19
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1120 | Submittal | 21 | 2026-09-15 | 2026-10-10
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Wall Cladding | QP.E.AF.MBL.GEN.4440 | Submittal | 21 | 2026-10-11 | 2026-11-03
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1100 | Submittal | 21 | 2026-11-04 | 2026-11-28
Shop Drawings | Architecture and Fitouts | Main Building | B3 PROMENADE LEVEL +887.750M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B3 PROMENADE LEVEL +887.750M ¦ FFE | QP.E.AF.MBL.GEN.5260 | Submittal | 21 | 2026-11-29 | 2026-12-22
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1170 | Submittal | 21 | 2026-04-20 | 2026-05-13
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1200 | Submittal | 20 | 2026-11-04 | 2026-11-26
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5700 | Submittal | 21 | 2026-11-28 | 2026-12-21
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1180 | Submittal | 21 | 2026-12-23 | 2027-01-16
Shop Drawings | Architecture and Fitouts | Main Building | B2 SERVICE LEVEL +893.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B2 SERVICE LEVEL +893.50M ¦ FFE | QP.E.AF.MBL.GEN.5280 | Submittal | 21 | 2027-01-17 | 2027-02-09
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1220 | Submittal | 21 | 2026-05-14 | 2026-06-10
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1250 | Submittal | 28 | 2026-11-28 | 2026-12-29
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5720 | Submittal | 21 | 2026-12-30 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1230 | Submittal | 21 | 2027-01-24 | 2027-02-16
Shop Drawings | Architecture and Fitouts | Main Building | B1 SERVICE LEVEL +900.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ B1 SERVICE LEVEL +900.50M ¦ FFE | QP.E.AF.MBL.GEN.5300 | Submittal | 21 | 2027-02-17 | 2027-03-16
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1310 | Submittal | 21 | 2026-06-11 | 2026-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1340 | Submittal | 28 | 2026-12-30 | 2027-01-31
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5800 | Submittal | 21 | 2027-02-01 | 2027-02-25
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1320 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 LOBBY LEVEL +905.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 LOBBY LEVEL +905.00M ¦ FFE | QP.E.AF.MBL.GEN.5320 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1400 | Submittal | 21 | 2026-07-06 | 2026-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1430 | Submittal | 20 | 2027-02-01 | 2027-02-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5740 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1410 | Submittal | 21 | 2027-03-25 | 2027-04-18
Shop Drawings | Architecture and Fitouts | Main Building | L1 UPEER LOBBY LEVEL MEZZANINE +909M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ FFE | QP.E.AF.MBL.GEN.5340 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1000 | Submittal | 21 | 2026-07-30 | 2026-08-23
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1030 | Submittal | 20 | 2027-02-25 | 2027-03-22
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5760 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1010 | Submittal | 21 | 2027-04-19 | 2027-05-12
Shop Drawings | Architecture and Fitouts | Main Building | L2 THEATRE STALLS +913M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L2 THEATRE STALLS +913M ¦ FFE | QP.E.AF.MBL.GEN.5360 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1490 | Submittal | 21 | 2026-08-24 | 2026-09-16
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1520 | Submittal | 20 | 2027-03-23 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5820 | Submittal | 21 | 2027-04-17 | 2027-05-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1500 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | Architecture and Fitouts | Main Building | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ FFE | QP.E.AF.MBL.GEN.5380 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1580 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1610 | Submittal | 20 | 2027-04-15 | 2027-05-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5840 | Submittal | 21 | 2027-05-11 | 2027-06-08
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1590 | Submittal | 21 | 2027-06-12 | 2027-07-05
Shop Drawings | Architecture and Fitouts | Main Building | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ FFE | QP.E.AF.MBL.GEN.5400 | Submittal | 21 | 2027-07-06 | 2027-07-29
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1670 | Submittal | 21 | 2026-12-20 | 2027-01-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1700 | Submittal | 20 | 2027-05-23 | 2027-06-14
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5860 | Submittal | 28 | 2027-06-15 | 2027-07-17
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1680 | Submittal | 28 | 2027-07-18 | 2027-08-18
Shop Drawings | Architecture and Fitouts | Main Building | L5 SECOND CIRCLE AND LOFT +928.00M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ FFE | QP.E.AF.MBL.GEN.5420 | Submittal | 28 | 2027-07-31 | 2027-08-31
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1760 | Submittal | 21 | 2027-01-19 | 2027-02-11
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1790 | Submittal | 21 | 2027-05-23 | 2027-06-15
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5880 | Submittal | 21 | 2027-07-18 | 2027-08-10
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1770 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Main Building | L5 LOFT MEP MEZZANINE +931.70M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ FFE | QP.E.AF.MBL.GEN.5440 | Submittal | 21 | 2027-09-01 | 2027-09-26
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1880 | Submittal | 21 | 2027-01-21 | 2027-02-14
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1910 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5900 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1890 | Submittal | 21 | 2027-09-13 | 2027-10-07
Shop Drawings | Architecture and Fitouts | Main Building | L6 SKY GARDEN +935.85M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L6 SKY GARDEN +935.85M ¦ FFE | QP.E.AF.MBL.GEN.5460 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.1800 | Submittal | 21 | 2027-04-22 | 2027-05-20
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.1830 | Submittal | 21 | 2027-07-25 | 2027-08-17
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Wall Cladding | QP.E.AF.MBL.GEN.5920 | Submittal | 21 | 2027-08-25 | 2027-09-18
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.1810 | Submittal | 21 | 2027-10-09 | 2027-11-01
Shop Drawings | Architecture and Fitouts | Main Building | L8 ROYAL MAJLIS +948.28M | FFE | FFE | FFE | Shop Drawings ¦ Architecture and Fitouts ¦ Main Building ¦ L8 ROYAL MAJLIS +948.28M ¦ FFE | QP.E.AF.MBL.GEN.5480 | Submittal | 21 | 2027-10-11 | 2027-11-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1110 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1140 | Submittal | 21 | 2027-05-31 | 2027-06-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +870.6M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1120 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1370 | Submittal | 21 | 2027-03-01 | 2027-03-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1360 | Submittal | 21 | 2027-06-24 | 2027-07-18
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Wall Cladding | QP.E.AF.BL1.GEN.5940 | Submittal | 21 | 2027-07-19 | 2027-08-11
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1340 | Submittal | 21 | 2027-08-19 | 2027-09-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL1.GEN.1650 | Submittal | 21 | 2027-06-14 | 2027-07-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL1.GEN.1680 | Submittal | 14 | 2027-09-01 | 2027-09-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-1 | BL1 - LEVEL +935.85M to +993.11M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-1 ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Non-Structural Metal works | QP.E.AF.BL1.GEN.1660 | Submittal | 21 | 2027-11-18 | 2027-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1080 | Submittal | 21 | 2027-05-26 | 2027-06-19
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1110 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Wall Cladding | QP.E.AF.BL2.GEN.5960 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +876.26M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +876.26M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1090 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1580 | Submittal | 21 | 2027-07-04 | 2027-07-27
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1610 | Submittal | 21 | 2027-12-08 | 2028-01-01
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1590 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL2.GEN.1670 | Submittal | 21 | 2027-07-28 | 2027-08-21
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL2.GEN.1700 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Architecture and Fitouts | Blades | Blade-2 | BL2 - LEVEL +935.85M to +957.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-2 ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Non-Structural Metal works | QP.E.AF.BL2.GEN.1680 | Submittal | 14 | 2028-01-18 | 2028-02-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1000 | Submittal | 24 | 2026-11-15 | 2026-12-12
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1030 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL3.GEN.5980 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +847.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1010 | Submittal | 14 | 2027-11-22 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL3.GEN.1340 | Submittal | 21 | 2027-02-27 | 2027-03-24
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL3.GEN.1370 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | Architecture and Fitouts | Blades | Blade-3 | BL3 - LEVEL +905.00M to +931.1M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-3 ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Non-Structural Metal works | QP.E.AF.BL3.GEN.1350 | Submittal | 21 | 2027-12-22 | 2028-01-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1210 | Submittal | 24 | 2026-12-27 | 2027-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1240 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Wall Cladding | QP.E.AF.BL4.GEN.6000 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +870.5M to +899.25M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +870.5M to +899.25M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1220 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1820 | Submittal | 21 | 2027-04-24 | 2027-05-22
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1850 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +905M to +928M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +905M to +928M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1830 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL4.GEN.1730 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL4.GEN.1760 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-4 | BL4 - LEVEL +935.85M to +975.82M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-4 ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Non-Structural Metal works | QP.E.AF.BL4.GEN.1740 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.2280 | Submittal | 24 | 2027-02-07 | 2027-03-07
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.2340 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +893.5M to +899.5M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.2300 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1130 | Submittal | 21 | 2027-03-22 | 2027-04-14
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1160 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +905.00M to +928.00M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1140 | Submittal | 14 | 2027-11-30 | 2027-12-15
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Rough Finishing (CMU & GA) | QP.E.AF.BL5.GEN.1500 | Submittal | 28 | 2027-06-29 | 2027-07-31
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.BL5.GEN.1530 | Submittal | 21 | 2027-10-10 | 2027-11-02
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Wall Cladding | QP.E.AF.BL5.GEN.6020 | Submittal | 21 | 2027-12-16 | 2028-01-09
Shop Drawings | Architecture and Fitouts | Blades | Blade-5 | BL5 - LEVEL +935.85M to +969.3M | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Blades ¦ Blade-5 ¦ BL5 - LEVEL +935.85M to +969.3M ¦ Non-Structural Metal works | QP.E.AF.BL5.GEN.1510 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1000 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1020 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Doors / Openings | QP.E.AF.PAR.GEN.1010 | Submittal | 28 | 2027-12-22 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone A | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone A ¦ Specialities | QP.E.AF.MBL.GEN.5160 | Submittal | 21 | 2027-12-30 | 2028-01-23
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Rough Finishing (CMU & GA) | QP.E.AF.PAR.GEN.1030 | Submittal | 28 | 2027-10-16 | 2027-11-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.PAR.GEN.1050 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Doors / Openings | QP.E.AF.PAR.GEN.1040 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Parking | Parking Zone B | Specialities | Specialities | Specialities | Shop Drawings ¦ Architecture and Fitouts ¦ Parking ¦ Parking Zone B ¦ Specialities | QP.E.AF.MBL.GEN.5200 | Submittal | 21 | 2028-01-09 | 2028-02-01
Shop Drawings | Architecture and Fitouts | Amphitheatre | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4040 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Architecture and Fitouts | Amphitheatre | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Finishing (Floor, Wall, Ceiling, Acoustic) | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Finishing (Floor, Wall, Ceiling, Acoustic) | QP.E.AF.MBL.GEN.4070 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Architecture and Fitouts | Amphitheatre | Wall Cladding | Wall Cladding | Wall Cladding | Wall Cladding | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Wall Cladding | QP.E.AF.MBL.GEN.6040 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | Architecture and Fitouts | Amphitheatre | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ Architecture and Fitouts ¦ Amphitheatre ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4050 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | External Building Works (Guard House, SEC Room) | Shop Drawings ¦ External Building Works (Guard House, SEC Room) | QP.E.EX.GEN.GEN.1270 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Main Building | QP.E.AF.MBL.GEN.6060 | Submittal | 21 | 2027-06-30 | 2027-07-24
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 5 | Water Proofing - Roof - Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 5 | QP.E.AF.BL5.GEN.6180 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 4 | Water Proofing - Roof - Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 4 | QP.E.AF.BL4.GEN.6160 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 3 | Water Proofing - Roof - Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 3 | QP.E.AF.BL3.GEN.6140 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 1 | Water Proofing - Roof - Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 1 | QP.E.AF.BL1.GEN.6100 | Submittal | 21 | 2027-12-09 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Roof Waterproofing | Blades | Water Proofing - Roof - Blade 2 | Water Proofing - Roof - Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Roof Waterproofing ¦ Blades ¦ Water Proofing - Roof - Blade 2 | QP.E.AF.BL2.GEN.6120 | Submittal | 28 | 2027-12-01 | 2028-01-02
Shop Drawings | Specialist Systems | Waterproofing | Wet Areas | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Waterproofing ¦ Wet Areas ¦ Main Building | QP.E.AF.MBL.GEN.4400 | Submittal | 21 | 2027-08-08 | 2027-08-31
Shop Drawings | Specialist Systems | Doors/ Openings | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Main Building | QP.E.AF.MBL.GEN.1140 | Submittal | 20 | 2027-06-29 | 2027-07-21
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.1130 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 2 | QP.E.AF.BL2.GEN.1100 | Submittal | 21 | 2027-10-05 | 2027-10-28
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.1020 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.1230 | Submittal | 21 | 2027-08-16 | 2027-09-08
Shop Drawings | Specialist Systems | Doors/ Openings | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.2320 | Submittal | 21 | 2027-09-09 | 2027-10-04
Shop Drawings | Specialist Systems | Doors/ Openings | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Specialist Systems ¦ Doors/ Openings ¦ Amphitheatre | QP.E.AF.MBL.GEN.4060 | Submittal | 28 | 2027-11-13 | 2027-12-14
Shop Drawings | Specialist Systems | Conveying System | Waste Management | Waste Management | Waste Management | Waste Management | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Waste Management | QP.E.CY.GEN.GEN.1280 | Submittal | 14 | 2027-12-02 | 2027-12-18
Shop Drawings | Specialist Systems | Conveying System | Escalators | Escalators | Escalators | Escalators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Escalators | QP.E.CY.GEN.GEN.1040 | Submittal | 28 | 2026-11-24 | 2026-12-26
Shop Drawings | Specialist Systems | Conveying System | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Elevators (Public / Freight / Service / Wheel Chair Platform / Platform Lift) | QP.E.CY.GEN.GEN.1020 | Submittal | 28 | 2026-10-22 | 2026-11-23
Shop Drawings | Specialist Systems | Conveying System | Truck Elevators | Truck Elevators | Truck Elevators | Truck Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Truck Elevators | QP.E.CY.GEN.GEN.1000 | Submittal | 28 | 2026-09-19 | 2026-10-21
Shop Drawings | Specialist Systems | Conveying System | Inclined Elevators | Inclined Elevators | Inclined Elevators | Inclined Elevators | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ Inclined Elevators | QP.E.CY.GEN.GEN.1050 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Main Building | QP.E.CY.GEN.GEN.1090 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 1 | QP.E.CY.GEN.GEN.1130 | Submittal | 28 | 2027-10-17 | 2027-11-17
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 2 | Blade 2 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 2 | QP.E.CY.GEN.GEN.1170 | Submittal | 28 | 2027-09-13 | 2027-10-16
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 3 | Balde 3 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 3 | QP.E.CY.GEN.GEN.1210 | Submittal | 28 | 2027-06-07 | 2027-07-08
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Blade 4 | QP.E.CY.GEN.GEN.1110 | Submittal | 28 | 2027-07-10 | 2027-08-10
Shop Drawings | Specialist Systems | Conveying System | BMU | Blades | Balde 5 | Balde 5 | Shop Drawings ¦ Specialist Systems ¦ Conveying System ¦ BMU ¦ Blades ¦ Balde 5 | QP.E.CY.GEN.GEN.1150 | Submittal | 28 | 2027-08-11 | 2027-09-12
Shop Drawings | Specialist Systems | Joinery Works | Main Building | Main Building | Main Building | Main Building | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Main Building | QP.E.AF.MBL.GEN.5540 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 1 | QP.E.AF.BL1.GEN.6120 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 3 | QP.E.AF.BL3.GEN.6160 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 4 | QP.E.AF.BL4.GEN.6180 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Joinery Works | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Specialist Systems ¦ Joinery Works ¦ Blades ¦ Blade 5 | QP.E.AF.BL5.GEN.6200 | Submittal | 14 | 2028-01-02 | 2028-01-17
Shop Drawings | Specialist Systems | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Kitchen and Laundary | Shop Drawings ¦ Specialist Systems ¦ Kitchen and Laundary | QP.E.AF.MBL.GEN.5500 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | Specialist Systems | Water Features | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Specialist Systems ¦ Water Features | QP.E.AF.MBL.GEN.6100 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Mechanical | QP.E.ME.MBL.GEN.6780 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B3 PROMENADE LEVEL +887.750M | B3 PROMENADE LEVEL +887.750M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical | QP.E.ME.MBL.GEN.6800 | Submittal | 14 | 2025-12-29 | 2026-01-13
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6840 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B2 SERVICE LEVEL +893.50M | B2 SERVICE LEVEL +893.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical | QP.E.ME.MBL.GEN.6850 | Submittal | 18 | 2026-02-23 | 2026-03-15
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Mechanical | QP.E.ME.MBL.GEN.6860 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | B1 SERVICE LEVEL +900.50M | B1 SERVICE LEVEL +900.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical | QP.E.ME.MBL.GEN.6870 | Submittal | 18 | 2026-03-30 | 2026-04-19
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Mechanical | QP.E.ME.MBL.GEN.6900 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 LOBBY LEVEL +905.00M | L1 LOBBY LEVEL +905.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical | QP.E.ME.MBL.GEN.6910 | Submittal | 18 | 2026-04-28 | 2026-05-18
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Mechanical | QP.E.ME.MBL.GEN.6940 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L1 UPEER LOBBY LEVEL MEZZANINE +909M | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical | QP.E.ME.MBL.GEN.6950 | Submittal | 18 | 2026-05-19 | 2026-06-11
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Mechanical | QP.E.ME.MBL.GEN.6980 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L2 THEATRE STALLS +913M | L2 THEATRE STALLS +913M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L2 THEATRE STALLS +913M ¦ Electrical | QP.E.ME.MBL.GEN.6990 | Submittal | 18 | 2026-06-17 | 2026-07-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Mechanical | QP.E.ME.MBL.GEN.7020 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical | QP.E.ME.MBL.GEN.7030 | Submittal | 18 | 2026-07-16 | 2026-08-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7060 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical | QP.E.ME.MBL.GEN.7070 | Submittal | 18 | 2026-08-15 | 2026-09-03
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Mechanical | QP.E.ME.MBL.GEN.7100 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 SECOND CIRCLE AND LOFT +928.00M | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical | QP.E.ME.MBL.GEN.7110 | Submittal | 18 | 2026-09-16 | 2026-10-07
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Mechanical | QP.E.ME.MBL.GEN.7140 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L5 LOFT MEP MEZZANINE +931.70M | L5 LOFT MEP MEZZANINE +931.70M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical | QP.E.ME.MBL.GEN.7150 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Mechanical | QP.E.ME.MBL.GEN.7180 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L6 SKY GARDEN +935.85M | L6 SKY GARDEN +935.85M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L6 SKY GARDEN +935.85M ¦ Electrical | QP.E.ME.MBL.GEN.7190 | Submittal | 18 | 2026-10-17 | 2026-11-05
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Mechanical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Mechanical | QP.E.ME.MBL.GEN.7220 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP Early Package and Builder's Work | L8 ROYAL MAJLIS +948.28M | L8 ROYAL MAJLIS +948.28M | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP Early Package and Builder's Work ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical | QP.E.ME.MBL.GEN.7230 | Submittal | 18 | 2026-11-07 | 2026-11-26
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1320 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1330 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1340 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1350 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B3 PROMENADE LEVEL +887.750M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B3 PROMENADE LEVEL +887.750M ¦ ICT Containment | QP.E.ME.MBL.GEN.1360 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1420 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1430 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1440 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1450 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B2 SERVICE LEVEL +893.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B2 SERVICE LEVEL +893.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1460 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1740 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1750 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1760 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1770 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | B1 SERVICE LEVEL +900.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ B1 SERVICE LEVEL +900.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.1780 | Submittal | 28 | 2026-04-28 | 2026-06-02
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.1590 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.1600 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.1610 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.1620 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 LOBBY LEVEL +905.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 LOBBY LEVEL +905.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.1630 | Submittal | 28 | 2026-06-03 | 2026-07-05
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2040 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2050 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2060 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2070 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L1 UPEER LOBBY LEVEL MEZZANINE +909M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M ¦ ICT Containment | QP.E.ME.MBL.GEN.2080 | Submittal | 28 | 2026-07-06 | 2026-08-06
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2240 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2250 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2260 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2270 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L2 THEATRE STALLS +913M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L2 THEATRE STALLS +913M ¦ ICT Containment | QP.E.ME.MBL.GEN.2280 | Submittal | 28 | 2026-08-08 | 2026-09-08
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2440 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2450 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2460 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2470 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M ¦ ICT Containment | QP.E.ME.MBL.GEN.2480 | Submittal | 28 | 2026-09-09 | 2026-10-12
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2640 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2650 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2660 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2670 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2680 | Submittal | 28 | 2026-10-13 | 2026-11-14
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Fire Suppression | QP.E.ME.MBL.GEN.2850 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.2860 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.2870 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.2880 | Submittal | 28 | 2026-12-08 | 2027-01-09
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 SECOND CIRCLE AND LOFT +928.00M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 SECOND CIRCLE AND LOFT +928.00M ¦ ICT Containment | QP.E.ME.MBL.GEN.2890 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3070 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3080 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3090 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3100 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L5 LOFT MEP MEZZANINE +931.70M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ ICT Containment | QP.E.ME.MBL.GEN.3110 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3290 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3300 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3310 | Submittal | 28 | 2026-11-21 | 2026-12-22
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3320 | Submittal | 28 | 2027-01-10 | 2027-02-10
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L6 SKY GARDEN +935.85M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L6 SKY GARDEN +935.85M ¦ ICT Containment | QP.E.ME.MBL.GEN.3330 | Submittal | 28 | 2026-12-17 | 2027-01-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Fire Suppression | QP.E.ME.MBL.GEN.3500 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Drainage & Plumbing | QP.E.ME.MBL.GEN.3510 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.MBL.GEN.3520 | Submittal | 28 | 2026-12-23 | 2027-01-24
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.MBL.GEN.3530 | Submittal | 28 | 2027-02-11 | 2027-03-18
Shop Drawings | MEP | Main Building | MEP 1st Deliverables | L8 ROYAL MAJLIS +948.28M | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 1st Deliverables ¦ L8 ROYAL MAJLIS +948.28M ¦ ICT Containment | QP.E.ME.MBL.GEN.3540 | Submittal | 28 | 2027-01-19 | 2027-02-20
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.MBL.GEN.5000 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.MBL.GEN.5040 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.MBL.GEN.5060 | Submittal | 28 | 2027-05-22 | 2027-06-22
Shop Drawings | MEP | Main Building | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.MBL.GEN.5080 | Submittal | 28 | 2027-03-07 | 2027-04-10
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.MBL.GEN.7280 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.MBL.GEN.7300 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.MBL.GEN.7320 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.MBL.GEN.7260 | Submittal | 21 | 2027-08-15 | 2027-09-07
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.MBL.GEN.7340 | Submittal | 21 | 2027-07-07 | 2027-07-31
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | LPG System | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ LPG System | QP.E.ME.MBL.GEN.5100 | Submittal | 21 | 2027-09-22 | 2027-10-17
Shop Drawings | MEP | Main Building | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.MBL.GEN.7360 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Fire Suppression | QP.E.ME.CBR.GEN.1000 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Plumbing | Plumbing | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Plumbing | QP.E.ME.CBR.GEN.1011 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | LPG System | LPG System | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ LPG System | QP.E.ME.CBR.GEN.1055 | Submittal | 21 | 2027-11-01 | 2027-11-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.CBR.GEN.1022 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ Electrical | QP.E.ME.CBR.GEN.1033 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Vertical Risers | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Vertical Risers ¦ ELV (Low Current System) | QP.E.ME.CBR.GEN.1044 | Submittal | 28 | 2027-09-22 | 2027-10-25
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.MBL.GEN.7380 | Submittal | 28 | 2027-12-09 | 2028-01-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Diesel | Diesel | Diesel | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Diesel | QP.E.ME.MBL.GEN.7420 | Submittal | 21 | 2028-02-01 | 2028-02-26
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Water Features | Water Features | Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Water Features | QP.E.ME.MBL.GEN.7440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M | QP.E.ME.MBL.GEN.6520 | Submittal | 28 | 2026-06-14 | 2026-07-15
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Grey Water Treatment/ Sewage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Grey Water Treatment/ Sewage | QP.E.ME.MBL.GEN.1050 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Stromwater/ Drainage | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Stromwater/ Drainage | QP.E.ME.MBL.GEN.1060 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B3 PROMENADE LEVEL +887.750M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B3 PROMENADE LEVEL +887.750M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1040 | Submittal | 21 | 2026-08-08 | 2026-08-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M | QP.E.ME.MBL.GEN.6540 | Submittal | 28 | 2026-07-16 | 2026-08-17
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ AHU Room | QP.E.ME.MBL.GEN.1160 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Transformer/ Switchgear/ Panel Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Transformer/ Switchgear/ Panel Room | QP.E.ME.MBL.GEN.1240 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Generator Room/ Diesel Tank | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Generator Room/ Diesel Tank | QP.E.ME.MBL.GEN.1250 | Submittal | 14 | 2026-10-05 | 2026-10-20
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | ETS/ CWP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ ETS/ CWP Room | QP.E.ME.MBL.GEN.1170 | Submittal | 14 | 2026-09-01 | 2026-09-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1030 | Submittal | 14 | 2026-09-24 | 2026-10-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B2 SERVICE LEVEL +893.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B2 SERVICE LEVEL +893.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1290 | Submittal | 28 | 2026-09-01 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M | QP.E.ME.MBL.GEN.6560 | Submittal | 14 | 2026-08-18 | 2026-09-02
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Irrigation/ Water Features | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Irrigation/ Water Features | QP.E.ME.MBL.GEN.1020 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Domestic Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Domestic Water | QP.E.ME.MBL.GEN.1010 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | Plant Room - Fire Water | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ Plant Room - Fire Water | QP.E.ME.MBL.GEN.1000 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | B1 SERVICE LEVEL +900.50M | IDF Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ B1 SERVICE LEVEL +900.50M ¦ IDF Room | QP.E.ME.MBL.GEN.1280 | Submittal | 14 | 2026-09-17 | 2026-10-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 LOBBY LEVEL +905.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 LOBBY LEVEL +905.00M | QP.E.ME.MBL.GEN.6640 | Submittal | 21 | 2026-09-03 | 2026-09-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L1 UPEER LOBBY LEVEL MEZZANINE +909M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L1 UPEER LOBBY LEVEL MEZZANINE +909M | QP.E.ME.MBL.GEN.6660 | Submittal | 21 | 2026-09-29 | 2026-10-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L2 THEATRE STALLS +913M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L2 THEATRE STALLS +913M | QP.E.ME.MBL.GEN.6680 | Submittal | 21 | 2026-10-24 | 2026-11-16
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L3 STALL MEZZ AND ADAPTIVE THEATRE +917.50M | QP.E.ME.MBL.GEN.6700 | Submittal | 21 | 2026-11-17 | 2026-12-10
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L4 FIRST CIRCLE AND ADAPTIVE THEATRE +921.00M | QP.E.ME.MBL.GEN.6720 | Submittal | 21 | 2026-12-12 | 2027-01-04
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 SECOND CIRCLE AND LOFT +928.00M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 SECOND CIRCLE AND LOFT +928.00M | QP.E.ME.MBL.GEN.6740 | Submittal | 21 | 2027-01-05 | 2027-01-28
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M | QP.E.ME.MBL.GEN.5540 | Submittal | 21 | 2027-01-30 | 2027-02-23
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - AHU Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - AHU Room | QP.E.ME.MBL.GEN.1180 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Makeup Air Unit and Ecology | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Makeup Air Unit and Ecology | QP.E.ME.MBL.GEN.1190 | Submittal | 14 | 2027-01-06 | 2027-01-21
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L5 LOFT MEP MEZZANINE +931.70M | Plant Room - Sky Garden Irrigation | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L5 LOFT MEP MEZZANINE +931.70M ¦ Plant Room - Sky Garden Irrigation | QP.E.ME.MBL.GEN.1070 | Submittal | 14 | 2027-02-24 | 2027-03-14
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L6 SKY GARDEN +935.85M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L6 SKY GARDEN +935.85M | QP.E.ME.MBL.GEN.6760 | Submittal | 21 | 2027-02-24 | 2027-03-22
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | MEP Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M | QP.E.ME.MBL.GEN.6580 | Submittal | 28 | 2027-03-23 | 2027-04-24
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | MEP Room | L8 ROYAL MAJLIS +948.28M | Plant Room - Fan Room | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ MEP Room ¦ L8 ROYAL MAJLIS +948.28M ¦ Plant Room - Fan Room | QP.E.ME.MBL.GEN.6600 | Submittal | 28 | 2027-04-25 | 2027-05-31
Shop Drawings | MEP | Main Building | MEP 4th Deliverables | Kitchen and Laundry | Kitchen and Laundry | Kitchen and Laundry | Shop Drawings ¦ MEP ¦ Main Building ¦ MEP 4th Deliverables ¦ Kitchen and Laundry | QP.E.ME.MBL.GEN.7400 | Submittal | 14 | 2028-02-01 | 2028-02-16
Shop Drawings | MEP | Panels | Panels | Panels | Panels | Panels | Shop Drawings ¦ MEP ¦ Panels | QP.E.ME.MBL.GEN.6510 | Submittal | 28 | 2027-04-14 | 2027-05-20
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Mechanical | QP.E.ME.BL1.GEN.3720 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +870.6M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical | QP.E.ME.BL1.GEN.3740 | Submittal | 18 | 2026-04-06 | 2026-04-26
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL1.GEN.3760 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL1.GEN.3780 | Submittal | 28 | 2026-11-29 | 2026-12-30
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Mechanical | QP.E.ME.BL1.GEN.3800 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP Early Package and Builder's Work | BL1 - LEVEL +935.85M to +993.11M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP Early Package and Builder's Work ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical | QP.E.ME.BL1.GEN.3820 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1020 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1030 | Submittal | 21 | 2027-02-25 | 2027-03-23
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1040 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1050 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +870.6M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +870.6M to +899.25M ¦ ICT Containment | QP.E.ME.BL1.GEN.1060 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL1.GEN.2940 | Submittal | 21 | 2027-04-11 | 2027-05-04
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.2950 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.2960 | Submittal | 21 | 2027-05-05 | 2027-06-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.2970 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL1.GEN.2980 | Submittal | 21 | 2027-06-03 | 2027-06-27
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Fire Suppression | QP.E.ME.BL1.GEN.1510 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Drainage & Plumbing | QP.E.ME.BL1.GEN.1520 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL1.GEN.1530 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL1.GEN.1540 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 1st Deliverables | BL1 - LEVEL +935.85M to +993.11M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 1st Deliverables ¦ BL1 - LEVEL +935.85M to +993.11M ¦ ICT Containment | QP.E.ME.BL1.GEN.1550 | Submittal | 21 | 2027-07-22 | 2027-08-15
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Passive Ssytem | Passive Ssytem | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Passive Ssytem | QP.E.ME.BL1.GEN.3280 | Submittal | 21 | 2027-08-30 | 2027-09-22
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL1.GEN.3320 | Submittal | 21 | 2027-10-07 | 2027-10-31
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL1.GEN.3340 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL1.GEN.3360 | Submittal | 21 | 2027-10-02 | 2027-10-25
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL1.GEN.3580 | Submittal | 21 | 2027-11-15 | 2027-12-08
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL1.GEN.3600 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL1.GEN.3620 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL1.GEN.3680 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL1.GEN.3640 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL1.GEN.3660 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3480 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL1.GEN.1000 | Submittal | 21 | 2027-11-09 | 2027-12-02
Shop Drawings | MEP | Blades | Blade-1 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-1 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL1.GEN.3700 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3400 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +876.25M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical | QP.E.ME.BL2.GEN.3420 | Submittal | 21 | 2026-04-06 | 2026-04-29
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL2.GEN.3440 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL2.GEN.3460 | Submittal | 28 | 2026-12-31 | 2027-02-01
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Mechanical | QP.E.ME.BL2.GEN.3480 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP Early Package and Builder's Work | BL2 - LEVEL +935.85M to +957.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP Early Package and Builder's Work ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical | QP.E.ME.BL2.GEN.3500 | Submittal | 28 | 2027-02-02 | 2027-03-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1020 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1030 | Submittal | 21 | 2027-03-24 | 2027-04-17
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1040 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1050 | Submittal | 21 | 2027-04-05 | 2027-04-28
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +876.25M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +876.25M to +899.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.1060 | Submittal | 21 | 2027-04-18 | 2027-05-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL2.GEN.1910 | Submittal | 21 | 2027-08-11 | 2027-09-04
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.1920 | Submittal | 21 | 2027-05-02 | 2027-05-30
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.1930 | Submittal | 21 | 2027-05-13 | 2027-06-10
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.1940 | Submittal | 21 | 2027-04-29 | 2027-05-27
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL2.GEN.1950 | Submittal | 21 | 2027-05-12 | 2027-06-09
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Fire Suppression | QP.E.ME.BL2.GEN.2110 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Drainage & Plumbing | QP.E.ME.BL2.GEN.2120 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL2.GEN.2130 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL2.GEN.2140 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 1st Deliverables | BL2 - LEVEL +935.85M to +957.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 1st Deliverables ¦ BL2 - LEVEL +935.85M to +957.25M ¦ ICT Containment | QP.E.ME.BL2.GEN.2150 | Submittal | 21 | 2027-09-05 | 2027-09-29
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL2.GEN.3160 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL2.GEN.3200 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL2.GEN.3220 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL2.GEN.3240 | Submittal | 21 | 2027-10-14 | 2027-11-07
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL2.GEN.3260 | Submittal | 14 | 2027-12-22 | 2028-01-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL2.GEN.3280 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL2.GEN.3300 | Submittal | 21 | 2027-11-22 | 2027-12-15
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL2.GEN.3380 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL2.GEN.3320 | Submittal | 28 | 2027-11-22 | 2027-12-23
Shop Drawings | MEP | Blades | Blade-2 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL2.GEN.3340 | Submittal | 21 | 2027-11-08 | 2027-12-01
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3500 | Submittal | 14 | 2028-02-17 | 2028-03-08
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL2.GEN.1000 | Submittal | 16 | 2028-02-17 | 2028-03-11
Shop Drawings | MEP | Blades | Blade-2 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-2 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL2.GEN.3360 | Submittal | 14 | 2028-04-09 | 2028-04-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Mechanical | QP.E.ME.BL3.GEN.3640 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +847.5M to +899.25M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical | QP.E.ME.BL3.GEN.3660 | Submittal | 28 | 2026-03-04 | 2026-04-07
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical | QP.E.ME.BL3.GEN.3700 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP Early Package and Builder's Work | BL3 - LEVEL +905.00M to +931.1M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP Early Package and Builder's Work ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Mechanical | QP.E.ME.BL3.GEN.3680 | Submittal | 28 | 2026-04-22 | 2026-05-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1020 | Submittal | 21 | 2026-06-17 | 2026-07-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.1030 | Submittal | 21 | 2026-07-12 | 2026-08-04
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1040 | Submittal | 21 | 2026-08-05 | 2026-08-29
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1050 | Submittal | 21 | 2026-08-30 | 2026-09-22
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +847.5M to +899.25M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +847.5M to +899.25M ¦ ICT Containment | QP.E.ME.BL3.GEN.1060 | Submittal | 21 | 2026-10-07 | 2026-10-31
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Fire Suppression | QP.E.ME.BL3.GEN.1790 | Submittal | 21 | 2026-12-31 | 2027-01-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Drainage & Plumbing | QP.E.ME.BL3.GEN.3280 | Submittal | 21 | 2027-01-25 | 2027-02-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL3.GEN.1810 | Submittal | 21 | 2027-02-18 | 2027-03-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL3.GEN.1820 | Submittal | 21 | 2027-03-18 | 2027-04-11
Shop Drawings | MEP | Blades | Blade-3 | MEP 1st Deliverables | BL3 - LEVEL +905.00M to +931.1M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 1st Deliverables ¦ BL3 - LEVEL +905.00M to +931.1M ¦ ICT Containment | QP.E.ME.BL3.GEN.1830 | Submittal | 21 | 2027-04-12 | 2027-05-05
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL3.GEN.3400 | Submittal | 21 | 2027-06-23 | 2027-07-17
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL3.GEN.3440 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL3.GEN.3460 | Submittal | 21 | 2027-08-01 | 2027-08-24
Shop Drawings | MEP | Blades | Blade-3 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL3.GEN.3480 | Submittal | 21 | 2027-09-08 | 2027-10-03
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL3.GEN.3500 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL3.GEN.3540 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL3.GEN.3560 | Submittal | 21 | 2027-10-04 | 2027-10-27
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL3.GEN.3620 | Submittal | 14 | 2028-01-22 | 2028-02-06
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL3.GEN.3600 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL3.GEN.3580 | Submittal | 21 | 2027-10-18 | 2027-11-10
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3520 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL3.GEN.1000 | Submittal | 21 | 2028-02-21 | 2028-03-20
Shop Drawings | MEP | Blades | Blade-3 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-3 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL3.GEN.3520 | Submittal | 14 | 2028-04-04 | 2028-04-19
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Mechanical | QP.E.ME.BL4.GEN.6010 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +863.85M to +899.25 | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical | QP.E.ME.BL4.GEN.6030 | Submittal | 28 | 2026-04-14 | 2026-05-16
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Mechanical | QP.E.ME.BL4.GEN.6050 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +905M to +928M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +905M to +928M ¦ Electrical | QP.E.ME.BL4.GEN.6070 | Submittal | 21 | 2026-08-10 | 2026-09-02
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Mechanical | QP.E.ME.BL4.GEN.6090 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP Early Package and Builder's Work | BL4 - LEVEL +935.85M to +975.82M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP Early Package and Builder's Work ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical | QP.E.ME.BL4.GEN.6110 | Submittal | 21 | 2026-09-17 | 2026-10-12
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Fire Suppression | QP.E.ME.BL4.GEN.2110 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2120 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2130 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2140 | Submittal | 21 | 2026-10-27 | 2026-11-19
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +863.85M to +899.25 | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +863.85M to +899.25 ¦ ICT Containment | QP.E.ME.BL4.GEN.2150 | Submittal | 21 | 2026-11-01 | 2026-11-24
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2910 | Submittal | 21 | 2026-12-05 | 2026-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.5550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2930 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2940 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +905M to +928M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +905M to +928M ¦ ICT Containment | QP.E.ME.BL4.GEN.2950 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Fire Suppression | QP.E.ME.BL4.GEN.2810 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Drainage & Plumbing | QP.E.ME.BL4.GEN.2820 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL4.GEN.2830 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL4.GEN.2840 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 1st Deliverables | BL4 - LEVEL +935.85M to +975.82M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 1st Deliverables ¦ BL4 - LEVEL +935.85M to +975.82M ¦ ICT Containment | QP.E.ME.BL4.GEN.2850 | Submittal | 21 | 2027-06-29 | 2027-07-22
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL4.GEN.5770 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL4.GEN.5810 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL4.GEN.5830 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL4.GEN.5850 | Submittal | 21 | 2027-09-29 | 2027-10-23
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL4.GEN.5870 | Submittal | 24 | 2027-08-31 | 2027-09-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL4.GEN.5930 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL4.GEN.5950 | Submittal | 21 | 2027-12-05 | 2027-12-28
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL4.GEN.5890 | Submittal | 21 | 2028-01-12 | 2028-02-05
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL4.GEN.5970 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL4.GEN.5990 | Submittal | 24 | 2027-11-07 | 2027-12-04
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3540 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL4.GEN.3110 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Blades | Blade-4 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-4 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL4.GEN.5910 | Submittal | 14 | 2028-04-02 | 2028-04-17
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Mechanical | QP.E.ME.BL5.GEN.3040 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +893.5M to +899.5M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical | QP.E.ME.BL5.GEN.3060 | Submittal | 28 | 2026-05-09 | 2026-06-13
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Mechanical | QP.E.ME.BL5.GEN.3080 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +905.00M to +928.00M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical | QP.E.ME.BL5.GEN.3100 | Submittal | 28 | 2026-07-27 | 2026-08-27
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Mechanical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Mechanical | QP.E.ME.BL5.GEN.3120 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP Early Package and Builder's Work | BL5 - LEVEL +935.85M to 969.3M | Electrical | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP Early Package and Builder's Work ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical | QP.E.ME.BL5.GEN.3140 | Submittal | 28 | 2026-09-12 | 2026-10-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1020 | Submittal | 21 | 2026-10-29 | 2026-11-22
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1030 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1040 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1050 | Submittal | 21 | 2026-11-21 | 2026-12-14
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +893.5M to +899.5M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +893.5M to +899.5M ¦ ICT Containment | QP.E.ME.BL5.GEN.1060 | Submittal | 21 | 2026-11-25 | 2026-12-19
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1550 | Submittal | 21 | 2026-12-29 | 2027-01-21
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1560 | Submittal | 21 | 2027-01-23 | 2027-02-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1570 | Submittal | 21 | 2027-02-16 | 2027-03-15
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1580 | Submittal | 21 | 2027-03-16 | 2027-04-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +905.00M to +928.00M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +905.00M to +928.00M ¦ ICT Containment | QP.E.ME.BL5.GEN.1590 | Submittal | 21 | 2027-04-10 | 2027-05-03
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Fire Suppression | QP.E.ME.BL5.GEN.1750 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Drainage & Plumbing | QP.E.ME.BL5.GEN.1760 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.BL5.GEN.1770 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.BL5.GEN.1780 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 1st Deliverables | BL5 - LEVEL +935.85M to 969.3M | ICT Containment | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 1st Deliverables ¦ BL5 - LEVEL +935.85M to 969.3M ¦ ICT Containment | QP.E.ME.BL5.GEN.1790 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.BL5.GEN.2800 | Submittal | 21 | 2027-07-13 | 2027-08-05
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.BL5.GEN.2840 | Submittal | 21 | 2027-08-21 | 2027-09-13
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.BL5.GEN.2860 | Submittal | 21 | 2027-09-14 | 2027-10-09
Shop Drawings | MEP | Blades | Blade-5 | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.BL5.GEN.2880 | Submittal | 21 | 2027-10-24 | 2027-11-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.BL5.GEN.3020 | Submittal | 14 | 2027-10-24 | 2027-11-08
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.BL5.GEN.2900 | Submittal | 14 | 2027-12-01 | 2027-12-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.BL5.GEN.2920 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.BL5.GEN.3000 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.BL5.GEN.2940 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.BL5.GEN.2960 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | MEP Room | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room | QP.E.ME.BL1.GEN.3560 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | MEP Room | Stromwater Tank and Pump | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ MEP Room ¦ Stromwater Tank and Pump | QP.E.ME.BL5.GEN.1000 | Submittal | 21 | 2028-01-24 | 2028-02-16
Shop Drawings | MEP | Blades | Blade-5 | MEP 4th Deliverables | Busway | Busway | Shop Drawings ¦ MEP ¦ Blades ¦ Blade-5 ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.BL5.GEN.2980 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Mechanical | QP.E.ME.PAR.GEN.1459 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone A | Parking Zone A | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone A ¦ Electrical | QP.E.ME.PAR.GEN.1479 | Submittal | 21 | 2027-05-06 | 2027-06-03
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Mechanical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Mechanical | QP.E.ME.PAR.GEN.1499 | Submittal | 21 | 2027-06-19 | 2027-07-12
Shop Drawings | MEP | Parking | MEP Early Package and Builder's Work | Parking Zone B | Parking Zone B | Electrical | Shop Drawings ¦ MEP ¦ Parking ¦ MEP Early Package and Builder's Work ¦ Parking Zone B ¦ Electrical | QP.E.ME.PAR.GEN.1519 | Submittal | 21 | 2027-06-05 | 2027-06-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Fire Suppression | QP.E.ME.PAR.GEN.1000 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1011 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1022 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1033 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone A | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone A ¦ ICT Containment | QP.E.ME.PAR.GEN.1044 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Fire Suppression | QP.E.ME.PAR.GEN.1055 | Submittal | 21 | 2027-08-04 | 2027-08-28
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Drainage & Plumbing | Drainage & Plumbing | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Drainage & Plumbing | QP.E.ME.PAR.GEN.1066 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | HVAC, Chilled Water, Ventilation | HVAC, Chilled Water, Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ HVAC, Chilled Water, Ventilation | QP.E.ME.PAR.GEN.1077 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | Electrical (Electrical Containment, Small Power, Lighting) | Electrical (Electrical Containment, Small Power, Lighting) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ Electrical (Electrical Containment, Small Power, Lighting) | QP.E.ME.PAR.GEN.1088 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 1st Deliverables | Parking Zone B | ICT Containment | ICT Containment | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 1st Deliverables ¦ Parking Zone B ¦ ICT Containment | QP.E.ME.PAR.GEN.1099 | Submittal | 21 | 2027-08-29 | 2027-09-21
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Fire Suppression | QP.E.ME.PAR.GEN.1219 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Smoke Ventilation | Smoke Ventilation | Smoke Ventilation | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Smoke Ventilation | QP.E.ME.PAR.GEN.1259 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | Electrical (Lighting Control) | Electrical (Lighting Control) | Electrical (Lighting Control) | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ Electrical (Lighting Control) | QP.E.ME.PAR.GEN.1279 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 2nd Deliverables | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | ICT Network, Emergency Lighting, Fire Alarm | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 2nd Deliverables ¦ ICT Network, Emergency Lighting, Fire Alarm | QP.E.ME.PAR.GEN.1299 | Submittal | 21 | 2027-10-06 | 2027-10-30
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Mechanical Power | Mechanical Power | Mechanical Power | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Mechanical Power | QP.E.ME.PAR.GEN.1419 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Audio Visual | Audio Visual | Audio Visual | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Audio Visual | QP.E.ME.PAR.GEN.1319 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Background Music | Background Music | Background Music | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Background Music | QP.E.ME.PAR.GEN.1339 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Fire Protection NOVEC System | Fire Protection NOVEC System | Fire Protection NOVEC System | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Fire Protection NOVEC System | QP.E.ME.PAR.GEN.1439 | Submittal | 14 | 2028-02-07 | 2028-02-23
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | BMS | BMS | BMS | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ BMS | QP.E.ME.PAR.GEN.1359 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 3rd Deliverables (MEP Systems by Specialists) | Security | Security | Security | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 3rd Deliverables (MEP Systems by Specialists) ¦ Security | QP.E.ME.PAR.GEN.1379 | Submittal | 21 | 2027-11-14 | 2027-12-07
Shop Drawings | MEP | Parking | MEP 4th Deliverables | Busway | Busway | Busway | Shop Drawings ¦ MEP ¦ Parking ¦ MEP 4th Deliverables ¦ Busway | QP.E.ME.PAR.GEN.1399 | Submittal | 14 | 2028-03-09 | 2028-03-25
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3600 | Submittal | 21 | 2027-08-07 | 2027-08-30
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3610 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 1 - Blade 2 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 1 - Blade 2 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3620 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.4430 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4440 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 2 - Blade 3 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 2 - Blade 3 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.4450 | Submittal | 14 | 2027-12-18 | 2028-01-02
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Fire Suppression | QP.E.ME.MBL.GEN.3960 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3970 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 3 - Blade 4 to Promenade Level | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 3 - Blade 4 to Promenade Level ¦ Electrical | QP.E.ME.MBL.GEN.3980 | Submittal | 14 | 2028-01-01 | 2028-01-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Fire Suppression | QP.E.ME.MBL.GEN.3930 | Submittal | 21 | 2027-08-31 | 2027-09-25
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3940 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 4 - Blade 2 to Plaza | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 4 - Blade 2 to Plaza ¦ Electrical | QP.E.ME.MBL.GEN.3950 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Fire Suppression | QP.E.ME.MBL.GEN.3810 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3820 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 5 - Blade 3 to Lobby | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 5 - Blade 3 to Lobby ¦ Electrical | QP.E.ME.MBL.GEN.3830 | Submittal | 21 | 2027-11-23 | 2027-12-16
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4400 | Submittal | 21 | 2027-10-30 | 2027-11-22
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4410 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 6 - Blade 1 to Adaptable Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 6 - Blade 1 to Adaptable Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4420 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4340 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4350 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 7 - Adaptable Theatre to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 7 - Adaptable Theatre to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4360 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4520 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4530 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 9 - Blade 5 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 9 - Blade 5 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4540 | Submittal | 21 | 2027-12-18 | 2028-01-10
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Fire Suppression | QP.E.ME.MBL.GEN.4640 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4650 | Submittal | 21 | 2027-12-07 | 2027-12-30
Shop Drawings | MEP | Link Bridges | Link Bridge 10 - Blade 3 to Premium Theatre | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 10 - Blade 3 to Premium Theatre ¦ Electrical | QP.E.ME.MBL.GEN.4660 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3870 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3880 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 11 - Blade 1 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 11 - Blade 1 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3890 | Submittal | 14 | 2028-01-17 | 2028-02-01
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.3840 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.3850 | Submittal | 21 | 2028-01-01 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 12 - Blade 4 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 12 - Blade 4 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.3860 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Fire Suppression | Fire Suppression | Fire Suppression | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Fire Suppression | QP.E.ME.MBL.GEN.4550 | Submittal | 21 | 2028-02-08 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.4560 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | MEP | Link Bridges | Link Bridge 13 - Blade 5 to Loft | Electrical | Electrical | Electrical | Shop Drawings ¦ MEP ¦ Link Bridges ¦ Link Bridge 13 - Blade 5 to Loft ¦ Electrical | QP.E.ME.MBL.GEN.4570 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 3, 4 & 5 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 3, 4 & 5 | QP.E.FA.GEN.GEN.1460 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Blades 1 & 2 | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Blades 1 & 2 | QP.E.FA.GEN.GEN.2180 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Loft and Lobby | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Loft and Lobby | QP.E.FA.GEN.GEN.2140 | Submittal | 28 | 2026-02-18 | 2026-03-25
Shop Drawings | Facade | Facade System Drawings | Facade System Drawings | Facade System Drawings | Facade System Drawings | Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | Shop Drawings ¦ Facade ¦ Facade System Drawings ¦ Sky-restaurant / Royal Majlis, bridges, Balustrades and basement | QP.E.FA.GEN.GEN.2160 | Submittal | 28 | 2026-03-26 | 2026-04-27
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Blades | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Blades | QP.E.FA.GEN.GEN.1820 | Submittal | 28 | 2025-11-12 | 2025-12-14
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Lobby and Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Lobby and Loft | QP.E.FA.GEN.GEN.1770 | Submittal | 28 | 2025-12-15 | 2026-01-15
Shop Drawings | Facade | Wire Frame | Wire Frame | Wire Frame | Wire Frame | Above Loft | Shop Drawings ¦ Facade ¦ Wire Frame ¦ Above Loft | QP.E.FA.GEN.GEN.1780 | Submittal | 28 | 2026-01-17 | 2026-02-17
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Blades | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Blades | QP.E.FA.GEN.GEN.1890 | Submittal | 21 | 2026-03-04 | 2026-03-30
Shop Drawings | Facade | Facade | Facade Mockup | Facade Mockup | Facade Mockup | Main Building | Shop Drawings ¦ Facade ¦ Facade Mockup ¦ Main Building | QP.E.FA.GEN.GEN.2230 | Submittal | 28 | 2026-05-12 | 2026-06-16
Shop Drawings | Facade | Facade | Blades | Blade 1 | Blade 1 | Blade 1 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 1 | QP.E.FA.GEN.GEN.1920 | Submittal | 28 | 2026-09-29 | 2026-10-31
Shop Drawings | Facade | Facade | Blades | Blade 2 | Blade 2 | Blade 2 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 2 | QP.E.FA.GEN.GEN.1930 | Submittal | 28 | 2026-08-26 | 2026-09-28
Shop Drawings | Facade | Facade | Blades | Blade 3 | Blade 3 | Blade 3 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 3 | QP.E.FA.GEN.GEN.1940 | Submittal | 28 | 2026-05-17 | 2026-06-21
Shop Drawings | Facade | Facade | Blades | Blade 4 | Blade 4 | Blade 4 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 4 | QP.E.FA.GEN.GEN.1950 | Submittal | 28 | 2026-06-22 | 2026-07-23
Shop Drawings | Facade | Facade | Blades | Blade 5 | Blade 5 | Blade 5 | Shop Drawings ¦ Facade ¦ Blades ¦ Blade 5 | QP.E.FA.GEN.GEN.1960 | Submittal | 28 | 2026-07-25 | 2026-08-25
Shop Drawings | Facade | Facade | Amphitheatre | Amphitheatre | Amphitheatre | Amphitheatre | Shop Drawings ¦ Facade ¦ Amphitheatre | QP.E.FA.GEN.GEN.2240 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Lobby | Lobby | Lobby | Lobby | Shop Drawings ¦ Facade ¦ Lobby | QP.E.FA.GEN.GEN.2090 | Submittal | 28 | 2026-12-03 | 2027-01-04
Shop Drawings | Facade | Facade | Loft | Loft | Loft | Loft | Shop Drawings ¦ Facade ¦ Loft | QP.E.FA.GEN.GEN.2100 | Submittal | 28 | 2027-01-05 | 2027-02-06
Shop Drawings | Facade | Facade | Above Loft | Above Loft | Above Loft | Above Loft | Shop Drawings ¦ Facade ¦ Above Loft | QP.E.FA.GEN.GEN.1910 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | Link Bridges | Link Bridges | Link Bridges | Link Bridges | Shop Drawings ¦ Facade ¦ Link Bridges | QP.E.FA.GEN.GEN.2050 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Facade | Facade | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Facade Lighting Fixtures | Shop Drawings ¦ Facade ¦ Facade Lighting Fixtures | QP.E.FA.GEN.GEN.1450 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | Facade | Facade | GRC Cladding | GRC Cladding | GRC Cladding | GRC Cladding | Shop Drawings ¦ Facade ¦ GRC Cladding | QP.E.FA.GEN.GEN.1390 | Submittal | 28 | 2027-03-29 | 2027-04-29
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 1 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 1 | QP.E.CV.MBL.GEN.3060 | Submittal | 28 | 2026-08-06 | 2026-09-07
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 2 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 2 | QP.E.CV.MBL.GEN.3560 | Submittal | 28 | 2026-10-29 | 2026-11-30
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 3 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 3 | QP.E.CV.MBL.GEN.3580 | Submittal | 28 | 2026-12-01 | 2027-01-02
Shop Drawings | External Works | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Structural - Step Walls / Pony Walls | Batch 4 | Shop Drawings ¦ External Works ¦ Structural - Step Walls / Pony Walls ¦ Batch 4 | QP.E.CV.MBL.GEN.3600 | Submittal | 28 | 2027-01-03 | 2027-02-03
Shop Drawings | External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Waterproofing for External Works | Shop Drawings ¦ External Works ¦ Waterproofing for External Works | QP.E.EX.GEN.GEN.1040 | Submittal | 28 | 2026-06-25 | 2026-07-27
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Excavation | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Excavation | QP.E.CV.MBL.GEN.3320 | Submittal | 28 | 2027-01-06 | 2027-02-07
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Blinding Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Blinding Including Embedded Items | QP.E.CV.MBL.GEN.3500 | Submittal | 28 | 2027-02-23 | 2027-03-29
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Foundation Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Foundation Including Embedded Items | QP.E.CV.MBL.GEN.3480 | Submittal | 28 | 2027-04-13 | 2027-05-19
Shop Drawings | External Works | Access Tunnel | Concrete | Concrete | Concrete | Structural Concrete Works Including Embedded Items | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Concrete ¦ Structural Concrete Works Including Embedded Items | QP.E.CV.MBL.GEN.3520 | Submittal | 28 | 2027-06-03 | 2027-07-05
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Rough Finishing (CMU & GA) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Rough Finishing (CMU & GA) | QP.E.AF.MBL.GEN.4000 | Submittal | 21 | 2027-12-01 | 2027-12-25
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Finishing | Finishing | Finishing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Finishing | QP.E.AF.MBL.GEN.4030 | Submittal | 14 | 2028-01-09 | 2028-01-24
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Non-Structural Metal works | Non-Structural Metal works | Non-Structural Metal works | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Non-Structural Metal works | QP.E.AF.MBL.GEN.4010 | Submittal | 14 | 2028-02-16 | 2028-03-07
Shop Drawings | External Works | Access Tunnel | Architecture and Fitouts | Doors / Openings | Doors / Openings | Doors / Openings | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ Architecture and Fitouts ¦ Doors / Openings | QP.E.AF.MBL.GEN.4020 | Submittal | 14 | 2028-03-02 | 2028-03-18
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Fire Suppression | Fire Suppression | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Fire Suppression | QP.E.ME.MBL.GEN.1690 | Submittal | 28 | 2027-09-12 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Plumbing | Plumbing | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Plumbing | QP.E.ME.MBL.GEN.1700 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Heating, Ventilating, and Air Conditioning (HVAC) | Heating, Ventilating, and Air Conditioning (HVAC) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Heating, Ventilating, and Air Conditioning (HVAC) | QP.E.ME.MBL.GEN.1710 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | Electrical | Electrical | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ Electrical | QP.E.ME.MBL.GEN.1720 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | Access Tunnel | MEP Works | MEP 1st Deliverables | ELV (Low Current System) | ELV (Low Current System) | Shop Drawings ¦ External Works ¦ Access Tunnel ¦ MEP Works ¦ MEP 1st Deliverables ¦ ELV (Low Current System) | QP.E.ME.MBL.GEN.1730 | Submittal | 21 | 2027-09-20 | 2027-10-14
Shop Drawings | External Works | External Utilities | Irrigation Works | Irrigation Works | Irrigation Works | Irrigation Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ Irrigation Works | QP.E.EX.GEN.GEN.1090 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Drainage Works | External Drainage Works | External Drainage Works | External Drainage Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Drainage Works | QP.E.EX.GEN.GEN.1110 | Submittal | 28 | 2026-11-15 | 2026-12-16
Shop Drawings | External Works | External Utilities | External Lighting Works | External Lighting Works | External Lighting Works | External Lighting Works | Shop Drawings ¦ External Works ¦ External Utilities ¦ External Lighting Works | QP.E.EX.GEN.GEN.1170 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | External Utilities | Low Current | Low Current | Low Current | Low Current | Shop Drawings ¦ External Works ¦ External Utilities ¦ Low Current | QP.E.EX.GEN.GEN.1100 | Submittal | 28 | 2027-05-01 | 2027-06-06
Shop Drawings | External Works | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Landscape - Hardscape | Shop Drawings ¦ External Works ¦ Landscape - Hardscape | QP.E.EX.GEN.GEN.1200 | Submittal | 14 | 2027-08-07 | 2027-08-22
Shop Drawings | External Works | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Water and Environment | Shop Drawings ¦ External Works ¦ Water and Environment | QP.E.EX.GEN.GEN.1220 | Submittal | 21 | 2026-11-23 | 2026-12-16
Shop Drawings | External Works | External Fixtures | External Fixtures | External Fixtures | External Fixtures | External Fixtures | Shop Drawings ¦ External Works ¦ External Fixtures | QP.E.EX.GEN.GEN.1260 | Submittal | 21 | 2027-03-23 | 2027-04-15
Shop Drawings | External Works | LPG System | LPG System | LPG System | LPG System | LPG System | Shop Drawings ¦ External Works ¦ LPG System | QP.E.EX.GEN.GEN.1300 | Submittal | 28 | 2027-06-21 | 2027-07-22
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Fit-out | Fit-out | Fit-out | Fit-out | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Fit-out | QP.C.PS.GEN.GEN.2590 | Submittal | 110 | 2026-07-30 | 2026-12-06
Shop Drawings | Provisional Sums | PS1 - Theatre Equipment & Fitout | Stage Engineering | Stage Engineering | Stage Engineering | Stage Engineering | Shop Drawings ¦ Provisional Sums ¦ PS1 - Theatre Equipment & Fitout ¦ Stage Engineering | QP.C.PS.GEN.GEN.2560 | Submittal | 110 | 2026-12-07 | 2027-04-17
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | AV / Broadcast | AV / Broadcast | AV / Broadcast | AV / Broadcast | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ AV / Broadcast | QP.C.PS.GEN.GEN.1200 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS2 - IT/AV and Specialist Media | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS2 - IT/AV and Specialist Media ¦ Technology (ICT) | QP.C.PS.GEN.GEN.1810 | Submittal | 180 | 2026-12-26 | 2027-07-31
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Control Systems | Control Systems | Control Systems | Control Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Control Systems | QP.C.PS.GEN.GEN.1880 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS3 - Specialist Lighting | Lighting Systems | Lighting Systems | Lighting Systems | Lighting Systems | Shop Drawings ¦ Provisional Sums ¦ PS3 - Specialist Lighting ¦ Lighting Systems | QP.C.PS.GEN.GEN.1850 | Submittal | 60 | 2027-09-01 | 2027-11-10
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Conveying System Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Conveying System Finishes | QP.C.PS.GEN.GEN.2120 | Submittal | 150 | 2027-06-07 | 2027-11-29
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | HVAC System | HVAC System | HVAC System | HVAC System | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ HVAC System | QP.C.PS.GEN.GEN.2100 | Submittal | 90 | 2027-11-01 | 2028-02-13
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | ID Finishes | ID Finishes | ID Finishes | ID Finishes | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ ID Finishes | QP.C.PS.GEN.GEN.1930 | Submittal | 90 | 2027-07-18 | 2027-10-31
Shop Drawings | Provisional Sums | PS4 - FOH Fitout | Water Features | Water Features | Water Features | Water Features | Shop Drawings ¦ Provisional Sums ¦ PS4 - FOH Fitout ¦ Water Features | QP.C.PS.GEN.GEN.1960 | Submittal | 120 | 2027-02-16 | 2027-07-13
Shop Drawings | Provisional Sums | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | PS5 - Signage and Wayfinding | Shop Drawings ¦ Provisional Sums ¦ PS5 - Signage and Wayfinding | QP.C.PS.GEN.GEN.2140 | Submittal | 60 | 2028-07-29 | 2028-10-07
Shop Drawings | Provisional Sums | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | PS6 - Soft Landscaping | Shop Drawings ¦ Provisional Sums ¦ PS6 - Soft Landscaping | QP.C.PS.GEN.GEN.2180 | Submittal | 160 | 2027-08-30 | 2028-03-08
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Concrete Superstructure | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Concrete Superstructure | QP.C.PS.GEN.GEN.2360 | Submittal | 30 | 2028-06-08 | 2028-07-12
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Foundation | Foundation | Foundation | Foundation | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Foundation | QP.C.PS.GEN.GEN.2260 | Submittal | 30 | 2028-05-01 | 2028-06-07
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Landscape | Landscape | Landscape | Landscape | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Landscape | QP.C.PS.GEN.GEN.2320 | Submittal | 30 | 2028-07-31 | 2028-09-03
Shop Drawings | Provisional Sums | PS7 - Promenade Bridge | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Promenade Bridge MEP | Shop Drawings ¦ Provisional Sums ¦ PS7 - Promenade Bridge ¦ Promenade Bridge MEP | QP.C.PS.GEN.GEN.2340 | Submittal | 30 | 2028-06-26 | 2028-07-30
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Technology (ICT) | Technology (ICT) | Technology (ICT) | Technology (ICT) | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Technology (ICT) | QP.C.PS.GEN.GEN.2400 | Submittal | 150 | 2027-04-11 | 2027-10-07
Shop Drawings | Provisional Sums | PS8 - Security Equipment | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Traffic & Car Parking | Shop Drawings ¦ Provisional Sums ¦ PS8 - Security Equipment ¦ Traffic & Car Parking | QP.C.PS.GEN.GEN.2500 | Submittal | 150 | 2027-07-12 | 2028-01-03

## Picklists
| #VALUE! |  | Numbering System Document - Metadata Mapping
DOCUMENT NUMBERING DROPDOWN ATTRIBUTES | [18 empty] | QIC GENERAL DROPDOWN ATTRIBUTES
FIELD 01 - PROJECT CODE |  | FIELD 02 - ORIGINATOR |  | FIELD 03 - CONTRACT REFERENCE |  | FIELD 04 - DOCUMENT TYPES |  | FIELD 05 - DISCIPLINE |  | FIELD 06 - AREA/ZONE |  | FIELD 07 - VENUE/BUILDING |  | FIELD 08 - SERIAL NUMBER |  |  |  |  | DOCUMENT DETAILS |  |  | SUITABILITY STATUS |  | NAP GENERAL DROPDOWN ATTRIBUTES
Ab. 01 | 1 - Project Name | Ab. 02 | 2 - Originator Name | Ab. 03 | 3 - Contract Reference | Ab. 04 | 4 - Document Type | Ab. 05 | 5 - Discipline | Ab. 06 | 6 - Area/Zone | Ab. 07 | 7 - Venue/Building | Ab. 08A | 8A - Drawing Type | Ab. 08B | 8B - Level | 8C - Sequence Number | Authoring Software | File/Exchange Format | Scope Area | Code | Status | Scale | Classification ID | Classification | Corporate Discipline | Author
QF01012 | Qiddaya Performing Arts Center | NES | Nesma and Partners | C04518 | Contract Number | AGD | Agenda | ACO | Acoustic | 00 | Overall | Z00000 | Overall | 0 | General (General Notes, Abbreviations, Legends, Single Line Diagrams, General Detail) | 00 | Non-Specific ( For Blade ) | 4 Digit Sequence Number For Drawings/Models | Revit | .rvt | Design Management | S0 (WIP) | Initial status or WIP | NTS | FI_60_25 | Drawing | Architectural | Nesma & Partners
[6 empty] | AVV | Agreed Value of Variation | ADM | Administration | 01 | Zone Sheet 1 | CENT01 | Center Block | 1 | Elevations (Vertical View) | B1 | Basement 1 - Parking A +900.50 | 3 Digit Sequence Number For Documents | Civil3D | .nwc | Architecture / LDC | S1 (Shared) | Suitable for Coordination | AS INDICATED | FI_90_75 | Schedule or table | Electrical | JINGGONG
[6 empty] | ASB | As Built | ARC | Architectural | 02 | Zone Sheet 2 | GARD01 | Guard House | 2 | Plans (Overall, Horizontal View, Floor Plan, Ceiling Plan, Site Plan, Loading Plan) | B2 | Basement 2 - Service +893.50 |  | MicrosoftWord | .nwd | Landscape | S2 (Shared) | Suitable for Information | 1:1 | FI_60_53 | Model | Façade | ALUTEC
[6 empty] | AUR | Audit Report | ADT | Area Development | 03 | Zone Sheet 3 | BLAD01 | Blade 01 | 3 | Sections (Sectional View, Wall Section, Riser) | B3 | Basement 3 - Promenade +887.750 |  | MicrosoftExcel | .ifc | Interior Design | S3 (Shared) | Suitable for Review and Comment | 1:2 | FI_60_15 | Clash Rendition | Fire & Life Safety | AFCO
[6 empty] | BOQ | Bill of Quantities | ASM | Assets Management | 04 | Zone Sheet 4 | BLAD02 | Blade 02 | 4 | Large-scale Views (Enlarged Details) (Plans, Elevations, Stair Sections, etc) | FL | Foundation level |  | Navisworks | .pdf | Signage & Wayfinding | S4 (Shared) | Suitable for Review and Authorisation | 1:5 | FI_40_10 | Calculations | Interior Design | DOKA
[6 empty] | BEP | BIM Execution Plan | AVL | Audio Visual | 05 | Zone Sheet 5 | BLAD03 | Blade 03 | 5 | Details (Any detail view, such as Wall / Floor / Manhole Detail, etc) | L1 | Lobby Level +905.0 |  | inDesign | .jpg | Public Interaction & Activation | S5 (Shared) | Suitable for Review and Acceptance | 1:10 | FI_90_72 | Report | Infrastructure | RAWABI
[6 empty] | BIM | BIM Model | AUV | Audio/Video | 06 | Zone Sheet 6 | BLAD04 | Blade 04 | 6 | Schedules and Diagrams | L2 | Theater Stalls +913.0 |  | Inviso | .xls | Structure | A1 (Published) | Authorised and Accepted-Concept Design | 1:20 | FI_10_90 | Transmittal | Landscape | FALLPROTEC
[6 empty] | BRF | Brief | BRG | Bridges | 07 | Zone Sheet 7 | BLAD05 | Blade 05 | 7 | Combination of different views | L3 | Stalles Mezz & AD Theater +917.5 |  | JPG | .xer | Geotechnical Engineering | A2 (Published) | Authorised and Accepted-Schematic Design 100% | 1:25 | FI_90_47 | Log | Mechanical | TKE
[6 empty] | BUD | Budget | BRC | Broadcast | 08 | Zone Sheet 8 | MBLAD1 | Mini Blade 01 | 8 | User-Defined (For types that do not fall in other categories) | L4 | First Circle & AD Theater +921.0 |  | Recap | .dwf | Civil Engineering | A3 (Published) | Authorised and Accepted-Detailed Design 100% | 1:50 | FI_80_50 | Method statement | Structural | Subcontractor - Unassigned
[6 empty] | CAL | Calculation | BIM | Building Information Modelling | 09 | Zone Sheet 9 | MBLAD4 | Mini Blade 04 | 9 | 3D Representation (Isometric, Perspectives, Photographes) | L5 | Second Circle & Loft |  | Rhino | .dwg | MEP Engineering | A4 (Published) | Authorised and Accepted-Tender | 1:100 | FI_90_64 | Plan |  | Provisional Sum
[6 empty] | CER | Certificate | BMS | Building Management System | 10 | Zone Sheet 10 | SECE01 | SEC Room |  |  | L6 | SKY Garden +935.85 |  | Sketchup | .bcf | Fire & Life Safety | A5 (Published) | Authorised and Accepted-IFC | 1:150 |  |  |  | NAP PMO
[6 empty] | COR | Change Order | CWC | Chilled Water / Cooling | 11 | Zone Sheet 11 | PARK01 | Parking Building |  |  | L8 | Royal Majlis +948.10M |  | Autocad | .3ds | Pitch Design & Sports Playing Surfaces | A6 (Published) | Authorised and Accepted-Construction (Shop Drawing) | 1:200 |  |  |  | Sana Al-Jazerah
[6 empty] | CRA | Change Request Authorization | CIV | Civil | 12 | Zone Sheet 12 |  |  |  |  | M1 | Mez Upper Lobby +909.0 |  | ArcGIS | .skp | Specialist Lighting (Services and Systems) | A7 (Published) | Authorised and Accepted-As Built | 1:250
[6 empty] | CDT | Clash Detection Report | CPM | Contracts & Procurement | 13 | Zone Sheet 13 |  |  |  |  | M2 | Mez Loft MEP +931.10 |  |  | .docx | Acoustics | A8(Published) | Authorised and Accepted-In Use | 1:300
[6 empty] | CLM | Claim | CIN | Controls & Instrumentation | 14 | Zone Sheet 14 |  |  |  |  | RL | Roof Level |  |  | .rvt,.nwd,.ifc | AV / Broadcast |  |  | 1:350
[6 empty] | CIN | Client Instruction | CRE | Creative Designer | 15 | Zone Sheet 15 |  |  |  |  | ZZ | Overall |  |  | .nwc,.nwd,.ifc | Security |  |  | 1:500
[6 empty] | CRS | Comments Resolution Sheet | CDM | Crowd Management | 16 | Zone Sheet 16 | [8 empty] | .dwg,.nwc,.ifc | Vertical Transport
[6 empty] | CON | Contract | CUL | Culvert | 17 | Zone Sheet 17 | [8 empty] | .docx,.pdf | Facade & Roof Envelope
[6 empty] | COS | Cost Estimate | DRN | Drainage | 18 | Zone Sheet 18 | [8 empty] | .xer,.pdf | Crowd Modelling / Pedestrian Flow
[6 empty] | DAB | Dashboard | ELP | Earthing & Lighting Protection | 19 | Zone Sheet 19 | [8 empty] | .xls,.pdf | Sustainability
[6 empty] | DOA | Delegation of Authority | ELE | Electrical | 20 | Zone Sheet 20 | [8 empty] | .msp,.pdf | Accessibility
[6 empty] | DES | Design | ELC | Electrical Containment | 21 | Zone Sheet 21 | [8 empty] | .dwg,.pdf | Architect of Record
[6 empty] | MTX | Distribution Matrix | ENV | Environmental | 22 | Zone Sheet 22 | [8 empty] | .indd | Food & Beverage & Operations
[6 empty] | DSS | Dossier | EQP | Equipment | 23 | Zone Sheet 23 | [8 empty] | .pdf, .indd | Utilities, Roads & Infrastructure
[6 empty] | DRW | Drawing | FAC | Facade | 24 | Zone Sheet 24 | [8 empty] | .rvt,.nwc,.ifc | Traffic & Car Parking
[6 empty] | ENI | Engineer Instruction | FED | Federated | 25 | Zone Sheet 25 | [8 empty] | .gdb | Technology (ICT)
[6 empty] | EXP | Expenses | FIN | Finance | 26 | Zone Sheet 26 | [9 empty] | Sports & Specialist Lighting
[6 empty] | HOC | Handover Certificate | FAE | Fire Alarm & Emergency Lighting | 27 | Zone Sheet 27 | [9 empty] | BMS & Access Control
[6 empty] | IRT | Incident Report | FLS | Fire Life Safety | 28 | Zone Sheet 28 | [9 empty] | Waste Management
[6 empty] | ITP | Inspection & Test Plan | FPR | Fire Protection | [11 empty] | Health & Safety in Design
[6 empty] | INS | Instruction | FFE | Furniture Fixture & Equipment | [11 empty] | Wind
[6 empty] | IAB | Insurance and Bonds | GEN | General
[6 empty] | INV | Invoice | GIS | Geospatial Information System
[6 empty] | LAR | Laydown Area Access Request | GEH | Geotechnical & Hydraulics
[6 empty] | LTR | Letter | GRA | Graphics
[6 empty] | LIC | License | HSE | Health and Safety
[6 empty] | LST | List | EHV | High Voltage
[6 empty] | MAN | Manual | HVC | HVAC
[6 empty] | MPL | Master Plan | ICT | Information & Communication Technology
[6 empty] | MAR | Material Approval Request | INF | Infrastructure
[6 empty] | MIR | Material Inspection Request | INS | Installation
[6 empty] | MST | Method Statement | ITS | Intelligent Transportation System
[6 empty] | MOM | Minutes of Meeting | INT | Interior Design
[6 empty] | MIX | Mix Design | IRR | Irrigation
[6 empty] | MOD | Model | KNL | Kitchen & Laundry
[6 empty] | MRP | Monthly Report | LSE | Landscape
[6 empty] | NOC | No Objection Certificate | ELL | Lighting
[6 empty] | NCR | Non-Conformance Report | LTC | Lighting Control
[6 empty] | NDA | Non-Disclosure Agreement | ELV | Low Voltage
[6 empty] | NTC | Notice | LPG | LPG
[6 empty] | OMM | Operation & Maintenance Manual | MAR | Marine Engineering
[6 empty] | ORC | Organizational Chart | MPL | Master Planning
[6 empty] | OTR | Overtime Request | MEC | Mechanical
[6 empty] | PAP | Payment Application | EMV | Medium Voltage
[6 empty] | PYC | Payment Certificate | MEP | MEPF
[6 empty] | PRM | Permit | NTD | Non-Technical Document
[6 empty] | PAF | Personnel Approval Form | OSE | Operating Supplies and Equipment
[6 empty] | PIV | Photographs, Images & Videos | OTH | Others
[6 empty] | PLN | Plan | PLB | Plumbing
[6 empty] | PLT | Plant | PTW | Potable Water
[6 empty] | PPG | Policy & Procedure | PJC | Project Control
[6 empty] | PQS | Prequalification Submittal | QMS | Quality Management
[6 empty] | PRE | Presentation | RID | Rides
[6 empty] | PRO | Procedure | ERL | Road Lighting
[6 empty] | PEP | Project Execution Plan | RKW | Rockwork
[6 empty] | PRS | Proposal | SEC | Security System
[6 empty] | POR | Purchase Order | SEW | Sewage
[6 empty] | REG | Register | SHW | Show
[6 empty] | REP | Report | SGN | Signage / Wayfinding
[6 empty] | RFC | Request For Change | ESP | Small Power
[6 empty] | RSM | Resume | SSC | Smart City
[6 empty] | SVR | Safety Violation Report | SPL | Specialist Lighting
[6 empty] | SMP | Sample | SWD | Storm Water Drainage
[6 empty] | SCH | Schedule | STR | Structural
[6 empty] | SDW | Shop Drawing | SUR | Surveying / Mapping
[6 empty] | SIN | Site Instruction | SUS | Sustainability
[6 empty] | SOR | Site Observation Report | TEL | Telecommunication
[6 empty] | SPE | Specification | TNC | Testing/Commissioning
[6 empty] | STD | Standard | TFC | Traffic System
[6 empty] | SFA | Statement of Final Account | UTI | Utilities
[6 empty] | STR | Strategy | VNT | Ventilation Ductwork
[6 empty] | TOC | Taking Over Certificate | VTR | Vertical Transportation
[6 empty] | TOR | Task Order | VES | Voice Evacuation
[6 empty] | TEM | Template | WSM | Waste Management
[6 empty] | TDC | Tender Document | WTR | Water
[6 empty] | TRP | Test Report | CTV | CCTV System
[6 empty] | TMS | Time Sheet | ACS | Access Control System
[6 empty] | VOR | Variation Order | EFL | Facade Lighting
[6 empty] | WAR | Warranty / Guarantees | DES | Diesel
[6 empty] | WRP | Weekly Report | SMK | Smoke Ductwork
[6 empty] | WIR | Work Inspection Request | STL | Steel Structure
[6 empty] | RLM | RedLine Mark Drawing | FWR | Formwork
[6 empty] | MDP | Master Information Delivery Plan | ELS | Emergency Lighting system
[6 empty] | TDP | Task Information Delivery Plan | EBW | Electrical Builder Works
[8 empty] | MBW | Mechanical Builder Works
[8 empty] | EBC | Electrical Busway
[8 empty] | WFT | Water Features
[8 empty] | LOG | Logistics